## Schematic
I3 Project List
1. Project ID
2. Project name and description
3. Initial assessed Construction Date , Final assessed date, duration
5. Include/Exclude + Rationale
6. Corridor Type, Designation status
7. Land Cost & % for project from DBC (not used)
8. PW Cost & % for project from DBC OR
9. Generic project requirements
P1 Date Adjustment
Allows project construction year to be overwritten by value in Total project cost for DCs.Col AR
I1 Assumptions
1. Property and construction Cost allowances
2. Contigency rates
3. timing assumptions
I2 Escalation Factors
1. Construction and Land price Escalation Rates
2. Rates Compounded from current year
3.Rates compunded fro prior year to base line input costs
I4 Con PW Unit Rates1.
1. Generic project cost rates per unit
2. Unit
3. Date cost assessed
4. Generic project cost rate escalated to current year
I5 Mitigation
1.% of land and construction costs to be delivered by AT after mitigation/third party works for each project
I6 Land Price Model
1. Average forecast land price(unescalated) by funding area/MSM zone, from LAnd Price Model
I7 Land transaction List
1. Project
2.Property ID, Address, Descr
3. Permanent/Temporary
4. Full/Partial
5.Land area required
I8_PropertyData
1. Property ID, Address, Descr
2. MSM
3. Total Land area
4. Land price basis
5. Dwelling for sec 72 costs
6. CV, LV
7. additional costs
8.IA Risk
9. aqusition date if confirmed
10. ratepayer
I9_AlternativePricing
1. Projects to be priced using alternate methdology
2.% split for pricing
I10_Renewals
1.Project number
2. Renewal %
Lnd1_AquisDate
Maps properties to project construction date
Lnd2_LandPriceForAcq
Calcs escalated land price per sqm from RID, LPM and alternate price and selects alternate price (if provided) or the higher of RID/LPM
Lnd2a_LandCostAqc Calculates the land cost of full and partial acquisitions
Lnd3_LeaseCost Calculates Cost of leasing land using the same land pricing methdology as Lnd2a_LandCostAqc. Land will be leased in the year of construction, so costs are calculated per project property transaction
Lnd4_TransCost Calculates Transaction Costs for Land acquisitions and leases, as well as the cost of improvements for full aqusitions
Lnd5_TotalPropertyCost Adds together land costs from Lnd2a_LandCostAqc Lnd3_LeaseCost and Lnd4_TransCost
Lnd6_Proj_Prop_map Apportions share of land aqusition cost to projects based on the share of land required for the project for each transaction
Lnd7_Total_Proj_Prop_Cost Sums up all the land transaction costs on Lnd7_Total_Proj_Prop_Cost for each project for projects to be included in the DCs,
Lnd8_Mitigation Excludes the share of property costs expected to be delivered by developers as mitigation works under their consent, or by other third parties
Con1_Base_Cost Calculates Base Construction cost from I3 Project list
Con2_CostAllowances Applies Physical Works Cost Allowances
Con3_ClientCosts Applies Client Managed Cost Allowances from I1 Assumptions
Con4_Contigency Applies Contigency and Risk assumptions from I1 Assumptions
Con5_UnescalatedConst Spreads the cost over time based on project construction date on
Con6_EscalatedConst Escalates the costs for land price escalation in I2 Escalation factors
Con7_Renewal Subtracts the share of costs attributable to renewal of existing assets
ProJ1_GrowthLOSCost Calculates the total project cost, exclusive of mitigation, and renewal by summingCon7_Renewal and Lnd8_Mitigation
Total project cost for DCs
reformats ProJ1_GrowthLOSCost for Dc model calc
LTP_for DC_model apportions growth share for the first 10 years (LTP period) of Total Project Costs for Dcs to funding areas
LTP_for DC_model apportions growth share for the 2nd and 3rd decades of Total Project Costs for Dcs to funding areas
DC_growth_AGS
1. Calculates growth share in funding areas from the AGS
Drury_beneficiary_allocation. apportions project benfits between Transport funding areas
DC_growth
Converts AGS household and employment growth to estimated HUEs

## Project_Summary
0
Project ID | Project Number | Project name | Project description | Include in DCs? | Corridor Type | Construction year | Land Aqusition/Lease Cost (incl transaction costs) | Contingency | Land Cost Escalation due to Development Stage | Land Price Escalation | Total Property Cost | Share of Property costs to expected to be provided through Mitigation | Total Property Cost to be funded through NZTA, DCs and rates | Construction Base Cost | Contingency | Escalation | Total Construction Costs | Share of construction costs to expected to be provided through Mitigation | Total Construction Cost to be funded through NZTA, DCs and rates | Total project cost before mitigation (Property and Construction) | Total project cost after mitigation (Property and Construction) | Share of construction costs related to AT asset Renewal (these costs are deducted before loading to DC model) | Project costs loaded to DC model before applying NZTA funding and DC growth percentage | Expected NZTA FAR rate funding | Level of Servce Share (rates funded) | Growth Share to be funded by DCs
Drury_1a | 1a | GSR improvements - Waihoehoe Rd to Drury Interchange | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Exclude | Interim Arterial | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_1b | 1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17505572.1801 | 8752786.09 | 5953088.5369 | 32211446.807 | 0 | 32211446.807 | 32211446.807 | 32211446.807 | -1243497.7603 | 30967949.0467 | -15793654.0138 | 2835831.799 | 12338463.2339
Drury_2a | 2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5192565.2818 | 2596282.6409 | 1478537.4175 | 9267385.3402 | 0 | 9267385.3402 | 9267385.3402 | 9267385.3402 | -692685.1794 | 8574700.1608 | -4373097.082 | 854922.5436 | 3346680.5352
Drury_2b | 2b | GSR improvements - From Drury School to Waihoehoe Rd | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Exclude - NZTA | 4-lane arterial | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_3 | 3 | Intersection upgrade on GSR/Karaka Rd intersection | Intersection upgrades- existing intersection with active modes crossings (TDM) | Exclude - NZTA | 4-lane arterial | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_4a | 4a | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Exclude | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_4b | 4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial | 2029 | 2615580.5958 | 784674.1787 | 9751.56 | 515171.3328 | 3925177.6673 | -1177553.3002 | 2747624.3671 | 21933541.6562 | 10966770.8281 | 5068354.9078 | 37968667.3922 | -30374933.9138 | 7593733.4784 | 41893845.0595 | 10341357.8455 | -524622.8783 | 9816734.7325 | -5006534.8333 | 376427.0711 | 4433772.8282
Drury_4 | 4 | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Construct Ultimate 24m Cross section initially (i.e. no interim stage) | Exclude | 2-lane Arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_5 | 5 | Drury Central Station | Not feasible without access. Refer to item 6 below | Exclude | 0 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_6 | 6 | Drury Station Connection+ intersection | NZUP tbc | Exclude | 0 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_7 | 7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5393233.6861 | 2696616.8431 | 3470645.9657 | 11560496.4949 | -10982471.6702 | 578024.8247 | 11560496.4949 | 578024.8247 | 0 | 578024.8247 | 0 | 25221.6472 | 552803.1775
Drury_8 | 8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5393233.6861 | 2696616.8431 | 3470645.9657 | 11560496.4949 | -10982471.6702 | 578024.8247 | 11560496.4949 | 578024.8247 | 0 | 578024.8247 | 0 | 25341.5691 | 552683.2557
Drury_9a | 9a | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | 2-lane signalised intersection with active mode crossings | Exclude - NZTA | 2-lane Arterial | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_9b | 9b | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | multi-lane signalised intersection with active mode crossings, SGA design | Exclude - NZTA | 4-lane arterial | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_10a | 10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial | 2029 | 580844.6007 | 174253.3802 | 0 | 125440.9923 | 880538.9732 | -880538.9732 | 0 | 4449862.7773 | 2224931.3887 | 1028264.5731 | 7703058.739 | -7703058.739 | 0 | 8583597.7122 | 0 | 0 | 0 | 0 | 0 | 0
Drury_10b | 10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial | 2037 | 772043.5444 | 231613.0633 | 1197751.2601 | 2031661.3474 | 4233069.2151 | 0 | 4233069.2151 | 5734760.6543 | 2867380.3271 | 4071494.4504 | 12673635.4318 | 0 | 12673635.4318 | 16906704.6469 | 16906704.6469 | 0 | 16906704.9908 | -8622419.3699 | 1217642.4075 | 7066643.2134
Drury_11 | 11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial | 2037 | 1707593.9381 | 512278.1814 | 45585.1753 | 953279.4091 | 3218736.704 | -2896863.0336 | 321873.6704 | 5562328.4717 | 2781164.2358 | 3949073.1818 | 12292565.8893 | -11063309.3003 | 1229256.5889 | 15511302.5933 | 1551130.2593 | -79852.508 | 1471277.7447 | -750351.6532 | 56416.8287 | 664509.2628
Drury_12 | 12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13927407.052 | 6963703.526 | 8962544.9056 | 29853655.4835 | 0 | 29853655.4835 | 29853655.4835 | 29853655.4835 | -108023.2203 | 29745632.2632 | 0 | 6077556.8322 | 23668075.431
Drury_13a | 13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial | 2037 | 6635709.0043 | 1990712.7013 | 1451350.3711 | 8161723.5581 | 18239495.6348 | -15503571.2896 | 2735924.3452 | 17967659.8602 | 8983829.9301 | 12756456.9506 | 39707946.7409 | -39707946.7409 | 0 | 57947442.3757 | 2735924.3452 | 0 | 2735924.4426 | -1395321.4161 | 70359.9997 | 1270243.0269
Drury_13b | 13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10568424.0961 | 5284212.0481 | 18881683.3305 | 34734319.4747 | -8683579.8687 | 26050739.606 | 34734319.4747 | 26050739.606 | 0 | 26050739.606 | -13285877.1991 | 2709343.6559 | 10055518.751
Drury_14 | 14 | Upgrade Brookefield Road from Fitzgerald to Quarry Rd+ New connection + Intersections on Quarry & Fitzgerald | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements + new connection to Quarry Rd) | Exclude | Upgrade Collector | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_14a | 14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) | 2037 | 7628619.5795 | 2288585.8739 | 20017920 | 31506776.7609 | 61441902.2143 | 0 | 61441902.2143 | 17326260.2366 | 8663130.1183 | 12301083.9777 | 38290474.3327 | 0 | 38290474.3327 | 99732376.5469 | 99732376.5469 | 0 | 99732376.8908 | 0 | 9178661.4552 | 90553715.4357
Drury_14b | 14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16500894.7049 | 8250447.3524 | 10618631.9695 | 35369974.0268 | -31832976.6241 | 3536997.4027 | 35369974.0268 | 3536997.4027 | -90731.0324 | 3446266.3703 | 0 | 317169.9322 | 3129096.438
Drury_15 | 15 | New Collector road E-W from Fitgerald Rd (collector 1) + Intersections | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_16a | 16a | Replace 2-lane Bremner Road Bridge over State Highway 1 | 2-lane urban with active modes on both sides (replacing existing bridge as part of SH1 P2D NZUP) | Exclude | Upgrade Collector | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_16b | 16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9453733.4704 | 4726866.7352 | 16890162.6255 | 31070762.8312 | 0 | 31070762.8312 | 31070762.8312 | 31070762.8312 | -265959.7791 | 30804803.0521 | -15710449.5565 | 4332503.1003 | 10761850.3952
Drury_17 | 17 | Oira Road to Jesmond Road Collector | New 2-lane urban collector with active modes on both sides | Exclude | Greenfields Collector | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_19-1 | 19-1 | SH1 3-laning and cycleway upgrades from Papakura to Drury Interchange | NZUP tbc | Exclude | State Highway | Under Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_19-2 | 19-2 | SH1 Drury Interchange including ramps | NZUP tbc | Exclude | State Highway | Under Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_19-3 | 19-3 | SH1 3-laning and cycleway upgrades from Drury Interchange To Drury South | NZUP tbc | Exclude | State Highway | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_20a | 20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21566259.9503 | 10783129.9751 | 13878288.509 | 46227678.4344 | -36982142.7475 | 9245535.6869 | 46227678.4344 | 9245535.6869 | 0 | 9245535.6869 | 0 | 405339.6519 | 8840196.035
Drury_21 | 21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3056165.7555 | 1528082.8777 | 1769726.1619 | 6353974.7951 | -6036276.0554 | 317698.7398 | 6353974.7951 | 317698.7398 | 0 | 317698.7398 | 0 | 13928.4408 | 303770.2989
Drury_22 | 22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4449862.7773 | 2224931.3887 | 2863569.2787 | 9538363.4446 | 0 | 9538363.4446 | 9538363.4446 | 9538363.4446 | -912821.3817 | 8625542.063 | 0 | 859662.7332 | 7765879.3298
Drury_23a | 23a | Waihoehoe Rd West upgrades- between GSR & Kath Henry | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Exclude | Interim Arterial | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_23b | 23b | Waihoehoe Rd West upgrades- between GSR & Kath Henry Lane | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Exclude | 4-lane arterial | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_23c | 23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2521820.9188 | 1260910.4594 | 94980.0522 | 3877711.4303 | -3877711.4303 | 0 | 3877711.4303 | 0 | 0 | 0 | 0 | 0 | 0
Drury_23d | 23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial | 2037 | 1394318.3913 | 418295.5174 | 1016069.6609 | 2350957.0858 | 5179640.6553 | -776946.0983 | 4402694.557 | 8271404.9305 | 4135702.4652 | 5872429.7843 | 18279537.18 | -7311814.872 | 10967722.308 | 23459177.8353 | 15370416.865 | -617225.367 | 14753192.0848 | -7524127.664 | 1172961.0863 | 6056103.3346
Drury_23 | 23 | Waihoehoe Rd West upgrades- between GSR & Fitzgerald Rd, including bridge replacement over the rail corridor | 4-lane urban- upgrade 2-lane with active modes on both sides, SGA design | Exclude | 4-lane arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_24 | 24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial | 2038 | 1503622.7052 | 451086.8116 | 791592.6186 | 2263741.4572 | 5010043.5926 | -3256528.3352 | 1753515.2574 | 33587752.9667 | 16793876.4834 | 26147280.7436 | 76528910.1938 | -65049573.6647 | 11479336.5291 | 81538953.7864 | 13232851.7865 | -382662.005 | 12850189.925 | -6553596.7886 | 492746.6966 | 5803846.4398
Drury_25 | 25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8539286.6697 | 4269643.3348 | 7250788.629 | 20059718.6335 | -14041803.0435 | 6017915.5901 | 20059718.6335 | 6017915.5901 | 0 | 6017915.5901 | 0 | 263835.4221 | 5754080.168
Drury_27a | 27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8903062.9517 | 4451531.4759 | 7559674.4917 | 20914268.9192 | -10457134.4596 | 10457134.4596 | 20914268.9192 | 10457134.4596 | 0 | 10457134.4596 | 0 | 458458.1559 | 9998676.3037
Drury_27b | 27b | Upgrade from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | 4-lane urban- upgrade existing road layout with active modes on both sides + intersection upgrades (TDM) | Exclude | 0 | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_28 | 28 | New collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_28a | 28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) | 2035 | 906881.025 | 272064.3075 | 2371200 | 2628863.384 | 6179008.7165 | 0 | 6179008.7165 | 8314065.7823 | 4157032.8911 | 4814405.0108 | 17285503.6842 | 0 | 17285503.6842 | 23464512.4006 | 23464512.4006 | 0 | 23464512.0327 | 0 | 1421069.6964 | 22043442.3363
Drury_29 | 29 | New collector in E-W direction between Flanagan & Fitzgerald Rd (collector 2) | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_30 | 30 | 2-lane internal collector between Fitzgerald & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_30.1 | 30.1 | 2-lane internal collector between Fitzgerald & Fielding Road E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_30.2 | 30.2 | 2-lane internal collector between Fielding Road & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_31 | 31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8359512.2135 | 4179756.1067 | 7098140.4473 | 19637408.7676 | -18655538.3292 | 981870.4384 | 19637408.7676 | 981870.4384 | 0 | 981870.4384 | 0 | 43046.832 | 938823.6064
Drury_32 | 32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial | 2039 | 1744672.579 | 523401.7737 | 4629029.3274 | 9170611.5426 | 16067715.2228 | -14460943.7005 | 1606771.5223 | 5562328.4717 | 2781164.2358 | 4723025.4228 | 13066518.1302 | -11759866.3172 | 1306651.813 | 29134233.353 | 2913423.3353 | -63660.0763 | 2849763.3946 | -1453379.2621 | 109275.6442 | 1287108.4884
Drury_33 | 33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector | 2056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415714.6679 | 1707857.3339 | -3921491.4316 | 1202080.5702 | -1141976.5417 | 60104.0285 | 1202080.5702 | 60104.0285 | 0 | 0 | 0 | 0 | 0
Drury_34 | 34 | New Drury Interchange connection to Kiwi development | 2-lane urban- new road layout with active modes on both sides (TDM) | Exclude | State Highway | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_35a | 35a | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 2-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | Exclude | 4-lane arterial | 2043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_35b | 35b | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 4-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | Exclude | 4-lane arterial | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_36 | 36 | Complete Bremner-Norrie Road connection from SH1 upto GSR (overlap with project 12) | 4-lane urban- upgrade with active modes on both sides (SGA design) | Exclude | 4-lane arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_36a | 36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial | 2039 | 11373124.6523 | 3411937.3957 | 10091362.563 | 27667581.4975 | 52544006.1085 | 0 | 52544006.1085 | 20655192.5533 | 10327596.2767 | 17538518.2731 | 48521307.1031 | 0 | 48521307.1031 | 101065313.2116 | 101065313.2116 | -37503.5165 | 101027812.1297 | -51524182.9445 | 11511817.3843 | 37991811.8009
Drury_36b | 36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial | 2050 | 7866126.9761 | 2359838.0928 | 10596237.8377 | 78502077.8249 | 99324280.7316 | 0 | 99324280.7316 | 20552136.2233 | 10276068.1117 | 36718712.6864 | 67546917.0215 | 0 | 67546917.0215 | 166871197.7531 | 166871197.7531 | -744687.3815 | 166126508.7589 | -84724520.2895 | 18514749.8641 | 62887238.6053
Drury_36c | 36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21626333.0978 | 10813166.5489 | 38637886.7311 | 71077386.3777 | 0 | 71077386.3777 | 71077386.3777 | 71077386.3777 | 0 | 71077386.3777 | -36249467.0527 | 7921554.1304 | 26906365.1947
Drury_37a(i) | 37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | 2044 | 9720610.7509 | 2916183.2253 | 82128729.0405 | 222935138.0056 | 317700661.0223 | -190620396.6134 | 127080264.4089 | 38968686.3899 | 19484343.195 | 48185055.1637 | 106638084.7486 | -63982850.8491 | 42655233.8994 | 424338745.7709 | 169735498.3084 | 0 | 169735497.6088 | -86565104.1373 | 24529119.2392 | 58641274.2323
Drury_37a(ii) | 37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42792479.5016 | 21396239.7508 | 52913202.2759 | 117101921.5283 | 0 | 117101921.5283 | 117101921.5283 | 117101921.5283 | 0 | 117101921.5283 | -59721979.9794 | 16922842.345 | 40457099.2038
Drury_37b(i) | 37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19280113.414 | 9640056.707 | 32540809.8848 | 61460980.0058 | 0 | 61460980.0058 | 61460980.0058 | 61460980.0058 | 0 | 61460980.0058 | -31345099.8029 | 8663216.7543 | 21452663.4486
Drury_37b(ii) | 37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24943646.7293 | 12471823.3647 | 42099672.7885 | 79515142.8824 | 0 | 79515142.8824 | 79515142.8824 | 79515142.8824 | 0 | 79515142.8824 | -40552722.87 | 11208036.6758 | 27754383.3366
Drury_38a | 38a | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | Exclude | 2-lane Arterial | 2046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_38b | 38b | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | Exclude | 4-lane arterial | 2055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_18a | 18a | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | Exclude | 0 | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_18b | 18b | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | Exclude | 0 | 2052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_39a | 39a | New Bremner Rd arterial from SH1 to Auranga development | 2-lane urban- new road layout with active modes on both sides (Under construction) | Exclude | Interim 2-lane Arterial | Under Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_39b | 39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6897287.3048 | 3448643.6524 | 10338847.9308 | 20684778.8881 | 0 | 20684778.8881 | 20684778.8881 | 20684778.8881 | 0 | 20684778.8881 | -10549237.2329 | 3514257.7685 | 6621283.8866
Drury_39c | 39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4805851.7995 | 2402925.8998 | 7203842.4292 | 14412620.1285 | 0 | 14412620.1285 | 14412620.1285 | 14412620.1285 | 0 | 14412620.1285 | -7350436.2655 | 2448644.1226 | 4613539.7404
Drury_40a | 40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial | 2037 | 2989724.811 | 896917.4433 | 3123232.5601 | 6935488.0238 | 13945362.8382 | -8367217.7029 | 5578145.1353 | 9037553.1628 | 4518776.5814 | 6416370.2317 | 19972699.9758 | -3994539.9952 | 15978159.9807 | 33918062.8141 | 21556305.116 | -288317.0201 | 21267988.371 | -10846673.9289 | 3747128.865 | 6674185.5771
Drury_40b | 40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4449862.7773 | 2224931.3887 | 1513256.8543 | 8188051.0203 | 0 | 8188051.0203 | 8188051.0203 | 8188051.0203 | 0 | 8188051.0203 | -4175906.0204 | 1364876.9522 | 2647268.0478
Drury_41a | 41a | Jesmond Rd upgrades from SH22 to Waipupuke development boundary | 2-lane urban- upgrade existing road with active modes on both sides (TDM) | Exclude | Interim Arterial | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_41b | 41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | 2047 | 1193056.23 | 357916.869 | 9722688.3 | 34543380.2177 | 45817041.6166 | -6872556.2425 | 38944485.3741 | 12786680.6906 | 6393340.3453 | 19166890.0188 | 38346911.0548 | -19173455.5274 | 19173455.5274 | 84163952.6714 | 58117940.9015 | 0 | 58117941.8163 | -29640149.8598 | 9687756.6268 | 18790035.3296
Drury_42a | 42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3505601.896 | 1752800.948 | 627600.7202 | 5886003.5641 | -5886003.5641 | 0 | 5886003.5641 | 0 | 0 | 0 | 0 | 0 | 0
Drury_42b | 42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17735480.95 | 8867740.475 | 13806657.4439 | 40409878.8689 | -30307409.1516 | 10102469.7172 | 40409878.8689 | 10102469.7172 | -802697.3737 | 9299772.3435 | -4742883.8952 | 1638492.6807 | 2918395.7676
Drury_42c | 42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | 2047 | 5408984.0464 | 1622695.2139 | 22789158.3999 | 86817733.5846 | 116638571.2449 | -17495785.6867 | 99142785.5581 | 8677232.4158 | 4338616.2079 | 13006937.7194 | 26022786.3431 | -10409114.5372 | 15613671.8058 | 142661357.5879 | 114756457.364 | 0 | 114756463.3098 | -58525793.2556 | 19128910.172 | 37101759.8822
Drury_43a | 43a | Intersection upgrade on Jesmond Rd/SH22 Rd | 2-lane intersection (Intersection upgrade + active mode crossings) | Exclude | State Highway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_43b | 43b | Intersection upgrade on Jesmond Rd/SH22 Rd | Multi-lane signalised intersection (Intersection upgrade + active mode crossings) | Exclude | 4-lane arterial | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_44 | 44 | Intersection at SH22/Burberry Rd (likely to close entirely) | Interim design and likely to close - subject to Auranga assessment | Exclude | 4-lane arterial | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_45 | 45 | Upgrade intersection at SH22/Victoria Rd | subject to Auranga assessment | Exclude | State Highway | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_46 | 46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4449862.7773 | 2224931.3887 | 2576770.7658 | 9251564.9318 | 0 | 9251564.9318 | 9251564.9318 | 9251564.9318 | 0 | 9251564.9318 | -4718298.1152 | 926226.2933 | 3607040.5232
Drury_47 | 47 | Old Bremner Road Upgrade from Jesmond Road to Auranga Precinct | 2-lane urban- new road layout with active modes on both sides (Under construction) | Exclude | 0 | Under Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_48 | 48 | Collector road south of New Bremner/ Old Bremner intersection | 2-lane urban- new road layout with active modes on both sides (Under construction) | Exclude | 0 | Under Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_49 | 49 | SH22 improvements from GSR Intersection to Jesmond Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Exclude | State Highway | 2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_50a | 50a | SH22 improvements from Jesmond Rd to Oira Rd- active mode upgrades on the northern section | 2-lane urban- upgrade existing road layout with active modes on northern side only | Exclude | State Highway | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_50b | 50b | SH22 improvements from Jesmond Rd to Oira Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Exclude | State Highway | 2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_51 | 51 | SH22 improvements from Oira Rd to Oira Creek - subject to design, could be incorporated with project 60 | Upgrade road layout to future urban boundary + active modes on both sides | Exclude | State Highway | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_52 | 52 | Intersection upgrade- on SH22/ McPherson Rd/Karaka Rd (Auranga B1) | Ultimate intersection form | Exclude | 4-lane arterial | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_53 | 53 | New intersection east of Jesmond Rd (Auranga B1 main street) | Ultimate intersection form (left-in left-out) | Exclude | 4-lane arterial upgrade | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_54 | 54 | New N-S collectors internal to Auranga B1 (2 links )+ Intersections | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_55 | 55 | New E-W collector Jesmond Rd to SH22 | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_55a | 55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) | 2037 | 3749834.662 | 1124950.3986 | 1810085.8943 | 6599968.2871 | 13284839.242 | 0 | 13284839.242 | 18819704.5734 | 9409852.2867 | 13361381.1192 | 41590937.9794 | 0 | 41590937.9794 | 54875777.2214 | 54875777.2214 | 0 | 54875777.9091 | 0 | 21399388.6473 | 33476389.2618
Drury_56 | 56 | Burberry Rd north connection to Auranga Precinct | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | Under construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_57 | 57 | New access road to Drury West Station | 2-lane urban- new road layout with active modes on both sides, (TDM) | Exclude | 0 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_58 | 58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40683791.8599 | 20341895.93 | 26180775.0798 | 87206462.8697 | -78485816.5827 | 8720646.287 | 87206462.8697 | 8720646.287 | -230435.36 | 8490210.927 | 0 | 3240592.8393 | 5249618.0877
Drury_59 | 59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5562328.4717 | 2781164.2358 | 4330142.7244 | 12673635.4318 | 0 | 12673635.4318 | 12673635.4318 | 12673635.4318 | -205819.8394 | 12467815.5924 | 0 | 4758788.0063 | 7709027.5861
Drury_60a | 60a | SH22 Intersection upgrade - Oira Rd (3 leg) | Interim Roundabout | Exclude | 2-lane Arterial | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_60b | 60b | SH22 Intersection upgrade - Oira Rd (4 leg) | Ultimate intersection form | Exclude | 4-lane arterial | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_63 | 63 | New collectors internal to Waipupuke PC61 (3 links )+ Intersections | 2-lane urban - new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_65a(i) | 65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | 2036 | 27586284.4599 | 8275885.338 | 10476246.3 | 43521317.0155 | 89859733.1134 | -89859733.1134 | 0 | 16487509.4867 | 8243754.7433 | 10610018.3332 | 35341282.5632 | -35341282.5632 | 0 | 125201015.6766 | 0 | 0 | 0 | 0 | 0 | 0
Drury_65a(ii) | 65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4880278.7079 | 2440139.354 | 3140549.9177 | 10460967.9796 | 0 | 10460967.9796 | 10460967.9796 | 10460967.9796 | 0 | 10460967.9796 | -5335093.6696 | 1819778.5192 | 3306095.7908
Drury_65b(i) | 65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7231027.0131 | 3615513.5066 | 10839114.7662 | 21685655.2859 | 0 | 21685655.2859 | 21685655.2859 | 21685655.2859 | 0 | 21685655.2859 | -11059684.1958 | 3710981.1624 | 6914989.9276
Drury_65b(ii) | 65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802194.4248 | 901097.2124 | 2701440.911 | 5404732.5482 | 0 | 5404732.5482 | 5404732.5482 | 5404732.5482 | 0 | 5404732.5482 | -2756413.5996 | 924890.6897 | 1723428.2589
Drury_66 | 66 | SH22 improvements - west of SH1 interchange to GSR | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Exclude | State Highway | 2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_67 | 67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure | 2037 | 4980291.0749 | 1494087.3225 | 16810185.6 | 24219009.084 | 47503573.0814 | 0 | 47503573.0814 | 24741370.0794 | 12370685.0397 | 17565571.965 | 54677627.0841 | 0 | 54677627.0841 | 102181200.1655 | 102181200.1655 | 0 | 102181201.1971 | -52112412.0844 | 18669655.8503 | 31399133.2624
Drury_68 | 68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure | 2037 | 12860615.1223 | 3858184.5367 | 22777504.4207 | 41031152.6659 | 80527456.7457 | 0 | 80527456.7457 | 15236566.4439 | 7618283.222 | 10817469.0209 | 33672318.6868 | 0 | 33672318.6868 | 114199775.4324 | 114199775.4324 | 0 | 114199776.636 | -58241885.4705 | 22204473.0576 | 33753418.1078
Drury_69 | 69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4222591.7233 | 2111295.8616 | 2445165.4922 | 8779053.0771 | 0 | 8779053.0771 | 8779053.0771 | 8779053.0771 | 0 | 8779053.0771 | 0 | 686765.0339 | 8092288.0432
Drury_70 | 70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure | 2031 | 1236.9628 | 371.0888 | 500.5 | 980.5255 | 3089.0771 | 0 | 3089.0771 | 3825206.5451 | 1912603.2726 | 1300831.1297 | 7038640.9474 | 0 | 7038640.9474 | 7041730.0244 | 7041730.0244 | 0 | 7040479.5617 | -3590644.5765 | 692331.297 | 2757503.6882
[7 empty] | 113219775.7121 | 33965932.7136 | 221856181.3896 | 632482053.6023 | 1001523943.4176 | -352168634.0896 | 649355309.328 | 678113286.8822 | 339056643.4411 | 633634978.2348 | 1650804908.5581 | -574225058.7588 | 1076579849.7993 | 2652328851.9757 | 1725935159.1273 | -7291201.6789 | 1718582614.1798 | -734797398.0848 | 253152998.1784 | 730632217.9166

## I1 Assumptions
Cost Assmptions and Allowances
Date and soure of cost estimates as shown below.
Cost allowances have been prepared in accordance with the requirements of the Cost Estimation Manual (CEM which can be found at https://www.nzta.govt.nz/resources/cost-estimation-manual/) for preparation of a Programme Business Case Estimate (PBE).
The costs reflect the Expected Estimate as defined in the CEM for a programme level Business Case (PBE).
Allowance Category | Allowance | Applies to | Rate | Date Rate Assessed | Rate baselined to current Year for model | Escalation | Source/Description
Current Year for costs |  |  |  |  | 2024
Property Cost Allowances | Lease cost % of land cost | All leases | 7% | 2023-03-10 | 7% | Land Escalation (as part of lease cost) | Estimated leases cost as a % of land cost. Rate based on experience.
Property Cost Allowances | Property contingency factor | All property | 30% | 2023-03-10 | 30% | Land Escalation (as part of property cost) | A contingency is required for cost estimation in accordance with the CEM to provide for uncertainty in relation to the estimate inputs and specific project related threats and opportunities with a cost impact.Transport property cost allowances for Drury include a 15 per cent contingency for the property valuation and an additional 15 per cent for the uncertainty in project scope.
Property Cost Allowances | Property risk factor | N/A | 0% | 2023-03-10 | 0% | Land Escalation (as part of property cost)
Public Works Act (PWA) Transaction Costs | Total | Full Acquisitions | 80000 | 2020 | 102138.5545 | Construction Rate | The PWA entitles owners of land "reasonable" compensation for costs incurred for legal representation, valuations and moving. PWA Transaction Csts inclue allowances for: = legal costs ($50k for full and partial acqusitions; $15k for leases) =section 72 compensation. Section s72 provides additional compensation where a dwelling on the property is used as a primary residence. It allows compenstation of up to $50,000 for full aquisition. For partial aquisition, compensation is assessed as 10% of the land value, up to a maximum of $25,000. PWA compensation limits are reviewed periodically and may increase before the land is aquired. We have therefore assumed (based on experience) a flat $45,000 allowance for all full aquisition. We have assessed s72 costs for partial acquisitions based on the escalated land price. No escalation has been otherwise applied to these transactions
Public Works Act (PWA) Transaction Costs | Total (Excluding s72 compensation below) | Partial Acquisitions | 110000 | 2020 | 140440.5125 | Construction Rate
Public Works Act (PWA) Transaction Costs | Total | Temporary Leases | 22000 | 2020 | 28088.1025 | Construction Rate
Public Works Act (PWA) Transaction Costs | S72 compensation for primary residence | Partial Acquisitions of land used as primary residence with value < $250,000 | 10% | 2020 | 10% | None
Public Works Act (PWA) Transaction Costs | S72 compensation for primary residence | Partial Acquisitions of land used as primary residence with value >= $250,000 | 25000 | 2020 | 25000 | None
Public Works Act (PWA) Transaction Costs | S72 compensation for primary residence | Full Acquisitions | 45000 | 2020 | 45000
PWA Injurious Affection Allowancefor partial acqusition | Injurious Affection Risk level : | High | 30% | 2020 | 30% | Land Escalation (as part of property cost) | In some cases, primarily where we are acquiring part of a property, we may need to pay an additional amount to compensate an owner for negative effects the project will have on their remaining land. This is known as Injurious Affection (IA), and needs to be considered for all partial land acquisitions. The amount is often subjective and often agreement is not reached with the landowner, resulting in matters being determined by the Land Valuation Tribunal (LVT). Project cost estimates for Drury are based on the risk assessment, and do not include any additional factors/costs for LVT hearings The level of allowance applied reflects the relative level of risk of these costs being incurred for specific projects. The table shows the assessed risk profile for Drury based on greenfield developments. Due to the early stage of project planning, it is not possible to assess risks for individual properties. Instead the medium risk profile has been assumed for all permanent partial land aquisitions. It is escalated for land zone and land aquisition price escalation
PWA Injurious Affection Allowancefor partial acqusition | Injurious Affection Risk level : | Medium | 20% | 2020 | 20% | Land Escalation (as part of property cost)
PWA Injurious Affection Allowancefor partial acqusition | Injurious Affection Risk level : | Low | 10% | 2020 | 10% | Land Escalation (as part of property cost)
PWA Injurious Affection Allowancefor partial acqusition | Injurious Affection Risk level : | None | 0% | 2020 | 0% | Land Escalation (as part of property cost)
PWA Injurious Affection Allowancefor partial acqusition | Injurious Affection Risk level : | Default | 20% | 2020 | 20% | Land Escalation (as part of property cost)
Land acquisition timing assumption | Land Acquisition occurs: | 2 |  |  | 2 |  | Construction year is provided on Project List. From experience, permanent land acqusitions occur in the three years leading up to start pf physical works. An average of 2 years before construction has therefore been used as the assumed acqusition date for property in the model. Where a property is required for multiple projects, the aqusition is assumed to occur two years prior to earliest project construction year
Land acquisition timing assumption | project Development and Pre-implentation work occurs: | 1 |  |  | 1 |  | See Client Managed Costs below
Land acquisition timing assumption | Temporary Leases incurred only in construction year | 0 |  |  | 0
Physical Works Cost Allowances | Environmental Compliance allowance | All | 6% | 2024 | 6% | Costruction Escalation as part of PW Costs | Management of environmental compliance requirements, preparation and management of compliance management plans, construction of permanent erosion and sediment control measures, maintenance and monitoring, noise attenuation and earthworks bunds. | % applied to (Base PW cost +Traffic Management & Temporary Works Allowance)
Physical Works Cost Allowances | Traffic Management & Temporary Works | No Traffic Management | 0% | 2024 | 0% | Costruction Escalation as part of PW Costs | Implementation of traffic management plans, public notification, lane changeovers, road diversions, temporary roads, plant, and equipment hire costs, temporary construction. Note that Traffic management rates used are as per the Trafiic Management Coloumn on the Project Inout tab, rather than derived from this table | % applied to Base PW cost
Physical Works Cost Allowances | Traffic Management & Temporary Works | Greenfields | 2% | 2024 | 2% | Costruction Escalation as part of PW Costs
Physical Works Cost Allowances | Traffic Management & Temporary Works | Brownfields | 13% | 2024 | 13% | Costruction Escalation as part of PW Costs
Physical Works Cost Allowances | Traffic Management & Temporary Works | Brownfields intersection | 20% | 2024 | 20% | Costruction Escalation as part of PW Costs
Physical Works Cost Allowances | Preliminary and general (P&G) allowance | All | 25% | 2024 | 25% | Costruction Escalation as part of PW Costs | Site establishment, operation, disestablishment, and clean-up; site management, bonds, and insurances, preparing and maintaining quality, health & safety, security, temporary erosion and sediment control, temporary traffic management plans, programming, and reporting. | % applied to (Base PW cost +Traffic Management & Temporary Works + Environmental Compliance Allowances )
Physical Works Cost Allowances | Contingency rate | All | 50% | 2024 | 50% | Costruction Escalation as part of PW Costs | A contingency is required for cost estimation in accordance with the CEM and is added to the ‘Base Estimate’ to provide for uncertainty in relation to the estimate inputs and specific project related threats and opportunities with a cost impact. For the DIFF programme, the cost estimates have been developed using linear rates and proportional assessment of earlier cost estimates prepared for the Drury Arterial Network DBC. Therefore, they reflect a programme wide approach where the specific scope and extent of works is undefined, resulting in significant uncertainty in quantities. Therefore, the physical works cost allowances for the updated DIFF programme’ include a 40% contingency, reflecting the uncertainty in the final form of the projects. | % applied to (Base PW cost +Traffic Management & Temporary Works + Environmental Compliance + P&G Allowances )
Physical Works Cost Allowances | Funding Risk Contingency | All | 0% | 2024 | 0% | Costruction Escalation as part of PW Costs
Client Managed Costs | [6 empty] | Client managed costs are incurred throughout the project lifecycle and would vary depending on each project. Basic elements that make up Client Managed Costs include: • Reviews: Economics Peer Review, Cost Estimate Peer Review / Parallel Estimate, Technical Peer Reviews, Constructability Review, O&M Review, Road Safety Audit • Investigations: Geotechnical Investigations, Utility Location, Pavement Investigations • Third Party Physical Works: Enabling Works such as utilities • Communications and Engagement: Open Days, Production of Engagement Collateral, Iwi Engagement, Communications Consultant • Third Party Professional Services: Procurement Support, Property acquisition support, Investigation and Design, Specialist Advisors, Legal Review, Engineer to Contract, etc • Consenting: Council lodgement and hearing fees, Environment Court / EPA Costs, Legal Advice, Consent Monitoring by Council, Building Consent • Post Construction Monitoring: Noise Monitoring, Traffic counts, speed surveys, consent conditions • Miscellaneous Costs: Insurances, Procurement Disbursements, Statutory Compliance, Revocation costs
Client Managed Cost allowances | Project Development allowance | Pre-implementation | 2% | 2024 | 2% |  | Preliminary design, Implementation Business case, Investigations, Engagment | Each calc is % applied to (Base PW cost +Traffic Management & Temporary Works + Environmental Compliance + P&G Allowances ). Project Development & Pre-implementation costs are assumed to be incurred in the year before construction. Escalated at Construction rate
Client Managed Cost allowances | Pre-Implementation allowance | Pre-implementation | 9% | 2024 | 9% |  | Speciman/Details Desgn/Investigations,Statutory Applications
Client Managed Cost allowances | Implementation allowance | Construction | 9% | 2024 | 9% |  | Procurment, Construction Monitoring & Supervision
Note on D32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Following review by Gary Forgie, contingency was increased to 50% over Drury allowance to align with AT costing guidelines

## I2 Escalation factors
Date | 2024-05-01 |  | Source: | Chief Economist Unit
Financial year |  | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060 | 2061
Construction escalation rate |  | 0% | 3.1% | 12.7% | 6.8% | 2.884% | 2.764% | 2.872% | 2.984% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1% | 3.1%
Compounded Construction rate from 2024 |  | 1 | 1 | 1 | 1 | 1 | 1.0276 | 1.0572 | 1.0887 | 1.1224 | 1.1572 | 1.1931 | 1.2301 | 1.2682 | 1.3076 | 1.3481 | 1.3899 | 1.433 | 1.4774 | 1.5232 | 1.5704 | 1.6191 | 1.6693 | 1.721 | 1.7744 | 1.8294 | 1.8861 | 1.9446 | 2.0048 | 2.067 | 2.1311 | 2.1971 | 2.2652 | 2.3355 | 2.4079 | 2.4825 | 2.5595 | 2.6388 | 2.7206 | 2.805 | 2.8919 | 2.9816 | 3.074
Land acquisition price escalation rate |  | 0% | 0% | 4.2% | -9.018% | 2.753% | 4.169% | 5.079% | 6.37% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1% | 7.1%
Financial year |  | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060 | 2061
LPR_escalation | Compounded rate from FY24 | 1 | 1 | 1 | 1 | 1 | 1.0417 | 1.0946 | 1.1643 | 1.247 | 1.3355 | 1.4303 | 1.5319 | 1.6407 | 1.7572 | 1.8819 | 2.0155 | 2.1586 | 2.3119 | 2.476 | 2.6518 | 2.8401 | 3.0418 | 3.2577 | 3.489 | 3.7367 | 4.0021 | 4.2862 | 4.5905 | 4.9164 | 5.2655 | 5.6394 | 6.0398 | 6.4686 | 6.9278 | 7.4197 | 7.9465 | 8.5107 | 9.115 | 9.7622 | 10.4553 | 11.1976 | 11.9926
[7 empty] | 1.312 | 1.3497 | 1.39 | 1.4331 | 1.4775 | 1.5233 | 1.5705 | 1.6192 | 1.6694 | 1.7211 | 1.7745 | 1.8295 | 1.8862 | 1.9447 | 2.005
Rates Compounded from Earlier Years to Current Year
| From Year | 2025: Lookup_Variable Name
Compounded Construction rate from 2020 to 2024 | 2020 | 2020: 1; 2021: 1.031; 2022: 1.1619; 2023: 1.2409; 2024: 1.2767; 2025: Con_2020_Escalation
Compounded Construction rate from 2021 to 2024 | 2021 | 2020: 1; 2021: 1; 2022: 1.127; 2023: 1.2036; 2024: 1.2383; 2025: Con_2021_Escalation
Compounded Land Price rate from 2021 to 2024 | 2021 | 2020: 1; 2021: 1; 2022: 1.042; 2023: 0.94803; 2024: 0.97414; 2025: Land_2021_Escalation
HistoricConstructEscalation
Category | 2020 | 2020: 2021; 2021: 2024
Construction | 1.2767 | 2020: 1.2383; 2021: 1
Land_RID_Escalation | 0.97414
Financial year |  | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060 | 2061
Compounded Land Esc rate from FY24 |  | 1 | 1 | 1 | 1 | 1 | 1.0508 | 1.1177 | 1.1971 | 1.2821 | 1.3731 | 1.4706 | 1.575 | 1.6868 | 1.8066 | 1.9349 | 2.0722 | 2.2194 | 2.3769 | 2.5457 | 2.7264 | 2.92 | 3.1273 | 3.3494 | 3.5872 | 3.8419 | 4.1147 | 4.4068 | 4.7197 | 5.0548 | 5.4137 | 5.798 | 6.2097 | 6.6506 | 7.1228 | 7.6285 | 8.1701 | 8.7502 | 9.3715 | 10.0368 | 10.7494 | 11.5127 | 12.3301
Note on A14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use to escalate June 2021 RID Valuations

## I3 Project list
Review Date: | [7 empty] | Data Source: | 2023-03-09 | [5 empty] | 0 | Date DBc Costs assessed: |  |  | 4960373.5025
[8 empty] | Andrew Murray's 2022 assessment | Dury DC Analysis Update_v25.xlsx Tab: Project Schedule Col M DC Timing (2023) |  |  |  |  | No longer used |  | 2020-03-01 | for Diff projects |  | Check against diff report | [14 empty] | Rob Mason
Location | Project number | Project ID | Project name | Project Description | Project Scope | Include in DC model | Reasoning for inclusion/exclusion | Operational Date: Initial Transport Assessment date | Construction Date: Revised Transport Assessment Date Adopted 2023 | Rational for Date- triggers, or supporting document | Corridor Type (determines if WK Funding subsidy applied ) | Current corridor designation status (Designated, NOR, None) | Source of Land/Construction cost estimate | Land Cost Estimate (excl escalation) | % of Land Cost to be included in model | DBC Construction Cost Estimate (excl allowances & escalation) | % DBC Cost Estimate for Council | DBC Cost assessmnt year | Cost estimate inc allowances | Length of Linear Rate 1 | Length of Linear Rate 2 | Length of Linear Rate 3 | Bridge Area (m2) | Roundabout 2-lane | Roundabout 4-lane | New Signals simple | New Signals complex | 2-lane interim | E/O for future 4-lane | Greenfields 4 lane rate 4 | Brownfields 4-lane rate 5 | 2-lane Rate 6 | footpath retrofit | Traffic Mangement Category | Transport corridor/intersection before project: | Scope and assumptions in previous DC assessment | NZUP project engineering/scope assumptions within project extent | Changes to DC assumptions/scope | Revised DC assumptions/scope
Drury | 1a | Drury_1a | GSR improvements - Waihoehoe Rd to Drury Interchange | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) |  | Exclude |  |  | 2024 |  | Interim Arterial |  | Assessed |  |  | 0 | 0% |  | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brownfields | 2-lane urban with kerbline along some of the extents. Crosses Hingaia Stream. | - Linear rate 1 for ‘Roadside Berm Construction’ for the addition of separated footpath and cycleway on each side. This has been applied over a length of 810m to reflect an upgrade to both sides of the road. - New pedestrian bridge added to both sides of the Hingaia Stream Bridge. Each shared path bridge is 40m long and 3m wide. - Signalisation of the Firth St intersection – included as a Simple Signalised intersection. | Overlap with crossing to access train station in Drury Rail Stations Drury Central - VM - Stage 1 design. Partial overlap with Waihoehoe Road Upgrade design on approach to GSR/Waihoehoe Rd intersection. Assume extents of 1a end at the start of LT bay indicated in Waihoehoe Rd Upgrade design. Drury Rail Stations Drury Central - VM - Stage 1: design indicates new kerbline at midblock crossing on both sides to accommodate crossing facilities, bus stops and active mode improvements. Assume 80m linear rate 1 on western side, and 70m linear rate 1 on eastern side. NZUP will provide bi-directional active mode facility on North/West side of Great South Road including parallel bridge at same level as current road one. There will be minimal kerb and channel work and Firth St will not be signalised. Therefore, almost all of previous assumptions superseded by NZUP design besides Firth St signals. | It is accepted that provision of a shared path with kerb and channel on one side of the road will suffice for an interim option. Therefore linear rates for berm upgrades can be removed from the assessment. A Shared path bridge is provided on one side to support the shared path. Therefore no interim bridge works are required. The NZUP project does not include signalisation of the Firth Street intersection, so this is required in the interim option. | Signalisation of the Firth St intersection – included as a ‘Simple Signalised intersection. | no
Drury | 1b | Drury_1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) |  | Include |  | 2036 | 2031 |  | 4-lane arterial |  | Assessed |  |  | 7631343.85 | 100% | 2020 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brownfields | Extents from GSR/Waihoehoe Rd intersection to Drury Interchange. 2-lane urban with kerb and channel with active modes. Crosses Hingaia Stream with active mode bridges alongside road bridge. | Cost based on measure and value of set of prelim design drawings by Te Tupu Ngātahi. Assumes new pavement, berm, bridge across Hingaia Stream, allowance for upgrade up to GSR/Waihoehoe intersection. The length that the cost estimate considered was longer than the actual project length, as some of the extents included within the cost estimate were assumed to be constructed as part of the NZUP SH1 Papakura to Drury project at the SH1 interchange. 60% of cost of full buildout works assumed for full 4-lane to account for reduced length of design relative to cost estimate as well as portion of retained works from interim. | Crossing to rail station from Drury Rail Stations Drury Central - VM - Stage 1 design is likely to be reconstructed, alongside kerblines in design. Waihoehoe Rd Upgrade accounts for 4-lanes at tie-in, although this tapers to 2-lanes. Assume 4-lane extent up to intersection is included within 9a rather than 1b. Kerblines within extents of 1a near this intersection are likely to be reconstructed to accommodate 4-lanes. There will be few components retained from NZUP projects, besides minor length near GSR/Waihoehoe intersection, of which little will be retained as new kerb and channel are likely to be reconstructed on both sides. As the scale of works for 1a is reduced from its previous assumption, it is assumed that additional works at the bridge across Hingaia Stream will be required to reach the ultimate form for 1b. Therefore, higher rate than cost report (65% of cost of full 4-lane buildout works). | Increase from 60% to 65% of measure and value cost for prelim design drawings. | 65% of cost of full buildout works previously assumed for full 4-lane. | no
Drury | 2a | Drury_2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) |  | Include |  | 2030 | 2030 |  | Interim Arterial |  | Assessed |  |  | 0 | 0% |  | No | 1140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | Brownfields | 2-lane urban arterial with kerbline for almost entire extent. | Active mode facilities extend 600m from northern boundary of Drury School site. - Linear rate for ‘Roadside Berm Construction’ for the addition of separated footpath and cycleway on each side. This has been applied over a length of 1200m to reflect an upgrade to both sides of the road. - Signalisation of the Great South Road/ Waihoehoe Road intersection – included as a ‘Simple Signalised intersection | Overlap with Waihoehoe Rd Upgrade Design on northern leg of intersection. Assume extents of 2a extend to start of RT bay in Waihoehoe Rd Upgrade design. Waihoehoe Rd Upgrade western side: design indicates new kerbline, footpath and retaining structure on western side of road, although retaining structure is within the extents of the intersection (9a). 20m linear rate 1 for new kerbline/footpath on western side within extents of 2a. Waihoehoe Rd Upgrade eastern side: design indicates new footpath on eastern side of road, and new kerb and channel where the road transitions from one lane to 2 on approach to intersection. 40m footpath retrofit for new footpath, 40m linear rate 1 for new kerb and channel. Waihoehoe Rd Upgrade design does not indicate any cycle facilities within the extents of 2a. Limited space on western side due to retaining structure, assume no cycle facilities to be implemented on western side near intersection, and these will begin on western side outside of the extents of the Waihoehoe Rd Upgrade design. 80m footpath retrofit rate included in 2a (not NZUP) for cycle facilities on eastern side. | All linear rate 1 that has been assumed for NZUP project design overlaps with the linear rate 1 extents originally assumed in DC model, therefore reduce original assumptions by 20+40 = 60m. Some kerbline in NZUP design does not include cycle facilities, add footpath retrofit rate for 80m. Signalisation of GSR/Waihoehoe Rd intersection is excluded, as the intersection upgrades will be included within the extents of 9a. | - Linear rate 1 for ‘Roadside Berm Construction’ for the addition of separated footpath and cycleway on each side. This has been applied over a length of 1140m to reflect an upgrade to both sides of the road. - Footpath retrofit for 80m for additional cycle facilities | no
Drury | 2b | Drury_2b | GSR improvements - From Drury School to Waihoehoe Rd | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) |  | Exclude - NZTA |  | 2034 | 2040 |  | 4-lane arterial |  | Assessed |  |  | 0 | 0% |  | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brownfields | 2-lane urban with active mode facilities on both sides for almost the entire length, as is outlined in 2a. | Previous DC cost report assumptions: - Linear rate for ‘4-lane transport corridor brownfields’ for the reconstruction of the existing road and provision of a full width 4-lane corridor with active modes on each side. This has been applied over the full length of 600m. - Upgrade of the Great South Road/ Waihoehoe Road intersection which was signalised as part of the interim works – included as a ‘Simple Signalised intersection'. However, this form is superseded by the recent SGA business case that identifies this a a 3-lane corridor with a bus lane in the northbound direction through this section. | Overlap with Waihoehoe Rd Upgrade design on northern leg of intersection. Northern leg design considers road space for future 2-lane northbound exit, so the costs will be minimal to transition this to a 3-lane bus priority corridor. Assume extents continue to start of RT bay at tie in, same as for 2a. As corridor is to be 3-lanes with northbound bus lane only, assume the interim project (2a) provides kerb and channel in the correct location so that implementation of the bus lane is a simple line marking exercise on top of the interim form. Therefore, assume any costs associated with 2b are very minimal and therefore 2b can be excluded from the DC model. | Removal of all previous DC cost assumptions: - Linear rate for ‘4-lane transport corridor brownfields’ for the reconstruction of the existing road and provision of a full width 4-lane corridor with active modes on each side. This has been applied over the full length of 600m. - Upgrade of the Great South Road/ Waihoehoe Road intersection which was signalised as part of the interim works – included as a ‘Simple Signalised intersection'. | No significant works required for 2b, no cost included in DC. | no
Drury | 3 | Drury_3 | Intersection upgrade on GSR/Karaka Rd intersection | Intersection upgrades- existing intersection with active modes crossings (TDM) |  | Exclude - NZTA |  | 2030 | 2026 |  | 4-lane arterial |  | Assessed |  |  | 0 | 0% |  | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brownfields | Rural, unsignalised. | Simple signals rate assumed, includes active mode upgrades at intersection. | SH22 design indicates 4-lane signalised intersection with active mode improvements. Full overlap with SH22 design, assume project is excluded from DC model. | Removal of simple signals rate. | Full overlap with SH22 design, assume no signal rate included for DC. | no
Drury | 4a | Drury_4a | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section |  | Exclude |  | 2031 |  |  | 0 |  | Assessed |  |  | 0 | 0% |  | No | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brownfields | [5 empty] | yes
Drury | 4b | Drury_4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section |  | Include |  | 2032 | 2029 |  | 2-lane Arterial |  | Assessed |  |  | 0 | 0% |  | No | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | 0 | Brownfields | [5 empty] | yes
Drury | 4 | Drury_4 | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Construct Ultimate 24m Cross section initially (i.e. no interim stage) |  | Exclude |  |  |  |  | 2-lane Arterial |  | Assessed |  |  | 39860000 | 45% | 2020 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Traffic Management | [5 empty] | yes
Drury | 5 | Drury_5 | Drury Central Station | Not feasible without access. Refer to item 6 below |  | Exclude |  | 2030 | 2024 |  | 0 |  | Assessed |  |  | 0 | 0% |  | No | [14 empty] | No Traffic Management | [5 empty] | yes
Drury | 6 | Drury_6 | Drury Station Connection+ intersection | NZUP tbc |  | Exclude |  | 2030 | 2024 |  | 0 |  | Assessed |  |  |  | 0% |  | No | [14 empty] | Brownfields | [5 empty] | yes
Drury | 7 | Drury_7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides |  | Include |  | 2033 | 2033 |  | Upgrade Collector |  | Assessed |  |  | 0 | 0% |  | No | 1200 | [13 empty] | Brownfields | [5 empty] | yes
Drury | 8 | Drury_8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides |  | Include |  | 2033 | 2033 |  | Upgrade Collector |  | Assessed |  |  | 0 | 0% |  | No | 1200 | [13 empty] | Brownfields | [5 empty] | yes
Drury | 9a | Drury_9a | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | 2-lane signalised intersection with active mode crossings |  | Exclude - NZTA |  | 2031 | 2026 |  | 2-lane Arterial |  | Assessed |  |  | 0 | 0% |  | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brownfields | Urban roundabout. | Complex signals rate assumed for full reconstruction to new form. | Waihoehoe Road Upgrade includes full signalisation to align with future FTN bus requirements. | NZUP project covers the entire extents of the previous DC assumption, Removal of complex signals rate as it is no longer required. | Full overlap with SH22 design, assume no signal rate included for DC. | no
Drury | 9b | Drury_9b | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | multi-lane signalised intersection with active mode crossings, SGA design |  | Exclude - NZTA |  | 2032 | 2031 |  | 4-lane arterial |  | Assessed |  |  | 6280000 | 0% | 2020 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Traffic Management | Waihoehoe Rd Upgrade design - 2-lane signalised intersection. | 70% of cost from DBC assessment, accounting for retained facilities from interim. | Waihoehoe Road Upgrade includes full signalisation to align with future FTN bus requirements. | No cost associated with this project, reduction of 70% of DBC cost estimate to 0%. | No cost associated with this project as the works to upgrade to 4 lanes are minor. | no
Drury | 10a | Drury_10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings |  | Include |  | 2031 | 2029 | Adjusted to 2029 to push out land acquisition date (this project is 100% mitigation so no impact on on costs) | 2-lane Arterial |  | Assessed |  |  | 0 | 0% |  | No | [6 empty] | 1 | [7 empty] | Brownfields | [5 empty] | yes
Drury | 10b | Drury_10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design |  | Include |  | 2035 | 2031 |  | 4-lane arterial |  | Assessed |  |  | 2500000 | 100% | 2020 | No | [14 empty] | Brownfields | [5 empty] | yes
Drury | 11 | Drury_11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design |  | Include |  | 2032 | 2031 |  | 2-lane Arterial |  | Assessed |  |  | 0 | 0% |  | No |  |  |  |  | 1 | [9 empty] | Brownfields | [5 empty] | yes
Drury | 12 | Drury_12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd |  | Include |  | 2033 | 2033 |  | New Collector (AT) |  | Assessed |  |  | 0 | 0% |  | No | [6 empty] | 3 | [6 empty] | 670 | Brownfields | [5 empty] | yes
Drury | 13a | Drury_13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) |  | Include |  | 2032 | 2029 |  | Interim 2-lane Arterial |  | Assessed |  |  | 0 | 0% |  | No | [6 empty] | 1 |  | 550 | [5 empty] | Greenfields | [5 empty] | yes
Drury | 13b | Drury_13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) |  | Include |  | 2035 | 2050 |  | 4-lane arterial upgrade |  | Assessed |  |  | 0 | 0% |  | No | [6 empty] | 1 |  |  | 550 |  |  |  |  | Brownfields | [5 empty] | yes
Drury | 14 | Drury_14 | Upgrade Brookefield Road from Fitzgerald to Quarry Rd+ New connection + Intersections on Quarry & Fitzgerald | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements + new connection to Quarry Rd) |  | Exclude |  |  |  |  | Upgrade Collector |  | Assessed |  |  | 0 | 0% |  | No |  |  |  | 900 |  |  | 2 | [5 empty] | 700 |  | Brownfields | [5 empty] | yes
Drury | 14a | Drury_14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) |  | Include |  | 2035 | 2035 |  | New Collector (AT) |  | Assessed |  |  | 0 | 0% |  | No |  |  |  | 900 |  |  | 1 | [5 empty] | 170 |  | Brownfields | [5 empty] | yes
Drury | 14b | Drury_14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) |  | Include |  | 2035 | 2033 |  | Upgrade Collector |  | Assessed |  |  | 0 | 0% |  | No |  |  |  | 0 |  |  | 1 | [5 empty] | 530 |  | Brownfields | [5 empty] | yes
Drury | 15 | Drury_15 | New Collector road E-W from Fitgerald Rd (collector 1) + Intersections | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) |  | Exclude |  | 2035 | 2033 |  | Greenfields Collector |  | Assessed |  |  | 0 | 0% |  | No |  |  |  |  | 2 | [7 empty] | 700 |  | Greenfields | [5 empty] | yes
Drury | 16a | Drury_16a | Replace 2-lane Bremner Road Bridge over State Highway 1 | 2-lane urban with active modes on both sides (replacing existing bridge as part of SH1 P2D NZUP) |  | Exclude |  | 2046 | 2033 |  | Upgrade Collector |  | Assessed |  |  | 0 | 0% |  | No |  |  |  | 1080 | [8 empty] | 100 |  | Brownfields | [5 empty] | yes
Drury | 16b | Drury_16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) |  | Include |  | 2046 | 2050 |  | 4-lane arterial |  | Assessed |  |  | 0 | 0% |  | No |  |  |  | 600 | [7 empty] | 100 |  |  | Brownfields | [5 empty] | yes
Drury | 17 | Drury_17 | Oira Road to Jesmond Road Collector | New 2-lane urban collector with active modes on both sides |  | Exclude |  |  | 2036 |  | Greenfields Collector |  | Assessed |  |  | 0 | 0% |  | No | [12 empty] | 615 |  | Brownfields | [5 empty] | yes
Drury | 19-1 | Drury_19-1 | SH1 3-laning and cycleway upgrades from Papakura to Drury Interchange | NZUP tbc |  | Exclude |  |  | Under Construction |  | State Highway |  | Assessed |  |  | 0 | 0% |  | No | [14 empty] | No Traffic Management | [5 empty] | yes
Drury | 19-2 | Drury_19-2 | SH1 Drury Interchange including ramps | NZUP tbc |  | Exclude |  |  | Under Construction |  | State Highway |  | Assessed |  |  | 0 | 0% |  | No | [14 empty] | No Traffic Management | [5 empty] | yes
Drury | 19-3 | Drury_19-3 | SH1 3-laning and cycleway upgrades from Drury Interchange To Drury South | NZUP tbc |  | Exclude |  | 2036 | 2036 |  | State Highway |  | Assessed |  |  | 0 | 0% |  | No | [14 empty] | No Traffic Management | [5 empty] | yes
Drury | 20a | Drury_20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing |  | Include |  | 2035 | 2035 |  | Upgrade Collector |  | Assessed |  |  | 0 | 0% |  | No | 1900 | 300 |  |  | 2 | [9 empty] | Brownfields | [5 empty] | yes
Drury | 21 | Drury_21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing |  | Include |  | 2035 | 2035 |  | Upgrade Collector |  | Assessed |  |  | 0 | 0% |  | No | 680 | [13 empty] | Brownfields | [5 empty] | yes
Drury | 22 | Drury_22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) |  | Include |  | 2033 | 2033 |  | New Collector (AT) |  | Assessed |  |  | 0 | 0% |  | No | [6 empty] | 1 | [7 empty] | Brownfields | [5 empty] | yes
Drury | 23a | Drury_23a | Waihoehoe Rd West upgrades- between GSR & Kath Henry | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section |  | Exclude |  | 2031 | 2025 |  | Interim Arterial |  | Assessed |  |  | 0 | 0% |  | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brownfields | Rural 2-lane corridor, no kerb and channel. | - Active mode facilities on both sides, 520m linear rate 1 assumed. - 2 120m2 active mode bridges alongside existing bridge, 240m2 total 23a and 23c do not account for the Kath Henry Ln intersection as they are active mode upgrades only. Assume the boundary between the two projects is at the centre of the Kath Henry Ln intersection. | Overlap with Waihoehoe Road Upgrade design. Design includes final 4 lanes for future FTN with active mode facilities on both sides. This facility accommodates the full corridor upgrade, therefore the full costs of 23a can be removed from the DC model. | Removal of previous DC assumptions as there is full overlap with the NZUP design: - Active mode facilities on both sides, 520m linear rate 1 assumed. - 2 120m2 active mode bridges alongside existing bridge, 240m2 total | Full overlap with SH22 design, assume no costs included in DC. | no
Drury | 23b | Drury_23b | Waihoehoe Rd West upgrades- between GSR & Kath Henry Lane | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design |  | Exclude |  | 2032 | 2031 |  | 4-lane arterial |  | Assessed |  |  | 16666880 | 0% | 2020 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Traffic Management | 2-lane corridor with active mode facilities on both sides as outlined in 23a. | Measure and value of DBC design. Assumes full reconstruction of western section, over about 220m to allow extra height for electification requirements for the NIMT. Kerb and channel and active modes on southern side remain, although road is reconstructed. Intersection with Kath Henry Ln signalised, full intersection included within scope of 23b. Most interim works redundant (besides southern berm), bridges would also need to be reconstructed. Assumed 100% of measure and value cost of DBC design. | Form of Waihoehoe Rd Upgrade design is realigned, 4 lanes, with Kath Henry Ln signalised. Similar level of works required compared to DBC design. Waihoehoe Rd Upgrade design fully supersedes 23b so no cost associated with 23b. | Full overlap with NZUP design, assume no works required for 23b as they are already completed in NZUP design, Reduction of 100% of DBC cost allowance. | No cost in DC. | no
Drury | 23c | Drury_23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section |  | Include |  | 2032 | 2025 |  | Interim Arterial |  | Assessed |  |  | 0 | 0% |  | No | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | Brownfields | Rural 2-lane corridor, no kerb and channel. | Active modes on both sides of the road. 'Linear rate 1 for ‘Roadside Berm Construction’ for the addition of separated footpath and cycleway on each side. This has been applied over a length of 740m to reflect an upgrade to both sides of the road. The project does not include the Kath Henry Ln intersection as it is an active mode upgrade only. Assume the boundary between the two projects is at the centre of the Kath Henry Ln intersection, so the total project length is 370m, up to the Fitzgerald Rd intersection. | Overlap with Waihoehoe Road Upgrade design near Kath Henry Ln intersection. Design indicates 4 lanes with sufficient active mode facilities from Kath Henry Ln intersection, and taper into 2 lanes. Kerbline for 120m on northern side. 60m of this does not have cycle facility. Kerbline for 80m on southern side. 50m of this does not have active mode facilities. Footpath retrofit for 60m on northern side and 50m on southern side should be included in 23c, as these are not included in NZUP design. | Remove 200m linear rate 1 from previous DC assumptions for new kerbline included in NZUP design. Add 60m + 50m = 110m footpath retrofit to DC project assumptions for active mode facilities along NZUP design extents where these facilities are not present. | - Linear rate 1 for ‘Roadside Berm Construction’ for the addition of separated footpath and cycleway on each side. This has been applied over a length of 540m to reflect an upgrade to both sides of the road. - 110m footpath retrofit along extents of NZUP project where there is insufficient active mode facilities to meet DC proejct requirements. | no
Drury | 23d | Drury_23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design |  | Include |  | 2031 | 2031 |  | 4-lane arterial |  | Assessed |  |  | 0 | 0% |  | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | Brownfields | 2-lane corridor with active mode facilities on both sides as outlined in 23c. | Previous DC assumptions state shift in road to the north, carriageway reconstructed. Kerb and channel on southern side remain. As most interim works redundant, assumed only small section of southern berm area remain, this cost saving is minimal compared to rest of works. Linear rate for ‘4 Lane brownfields upgrade’. This has been applied over a length of 240m. | Waihoehoe Road Upgrade design includes 4-lanes at Kath Henry intersection with 50m tie-in, where it tapers to 2-lanes to the east. The intersection at Kath Henry Ln and tie in in the eastern leg is within the extents of project 23b, and is therefore not included in the extents of 23d. Approximately 350m from Kath Henry Ln to Fitzgerald Rd. 50m is tie-in in 23b so outside of 23d scope, 50m is assumed to be tie-in for project 10 at Fitzgerald Rd so also outside of 23d scope. Therefore, approx 250m included in scope of 23d which is similar to 240m assumed in previous DC assessment. Therefore, minimal overlap with NZUP design as the components included in the taper in NZUP design are likely to be reconstructed. | No change. | Linear rate for ‘4 Lane brownfields upgrade’. This has been applied over a length of 240m. | no
Drury | 23 | Drury_23 | Waihoehoe Rd West upgrades- between GSR & Fitzgerald Rd, including bridge replacement over the rail corridor | 4-lane urban- upgrade 2-lane with active modes on both sides, SGA design |  | Exclude |  |  |  |  | 4-lane arterial |  | Assessed |  |  | 22940000 | 100% | 2020 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Traffic Management | [5 empty] | yes
Drury | 24 | Drury_24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section |  | Include |  | 2032 | 2038 |  | 2-lane Arterial |  | Assessed |  |  | 39860000 | 55% | 2020 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Traffic Management | [5 empty] | yes
Drury | 25 | Drury_25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides |  | Include |  | 2038 | 2039 |  | Upgrade Collector |  | Assessed |  |  | 0 | 0% |  | No | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brownfields | [5 empty] | yes
Drury | 27a | Drury_27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing |  | Include |  | 2038 | 2039 |  | Upgrade Collector |  | Assessed |  |  | 0 | 0% |  | No | 1450 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brownfields | [5 empty] | yes
Drury | 27b | Drury_27b | Upgrade from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | 4-lane urban- upgrade existing road layout with active modes on both sides + intersection upgrades (TDM) |  | Exclude |  | 2036 | 2039 |  | 0 |  | Assessed |  |  | 0 | 0% |  | No | [14 empty] | Brownfields | [5 empty] | yes
Drury | 28 | Drury_28 | New collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) |  | Exclude |  | 2036 | 2035 |  | Greenfields Collector |  | Assessed |  |  | 0 | 0% |  | No |  |  |  | 160 | 1 | [7 empty] | 990 |  | Greenfields | [5 empty] | yes
Drury | 28a | Drury_28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) |  | Include |  | 2036 | 2035 |  | New Collector (AT) |  | Assessed |  |  | 0 | 0% |  | No |  |  |  | 160 | 1 | [7 empty] | 90 |  | Greenfields | [5 empty] | yes
Drury | 29 | Drury_29 | New collector in E-W direction between Flanagan & Fitzgerald Rd (collector 2) | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) |  | Exclude |  | 2036 | 2035 |  | Greenfields Collector |  | Assessed |  |  | 0 | 0% |  | No | [12 empty] | 850 |  | Greenfields | [5 empty] | yes
Drury | 30 | Drury_30 | 2-lane internal collector between Fitzgerald & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) |  | Exclude |  |  |  |  | Greenfields Collector |  | Assessed |  |  | 0 | 0% |  | No | [12 empty] | 2000 |  | Greenfields | [5 empty] | yes
Drury | 30.1 | Drury_30.1 | 2-lane internal collector between Fitzgerald & Fielding Road E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) |  | Exclude |  | 2035 | 2033 |  | Greenfields Collector |  | Assessed |  |  | 0 | 0% |  | No | [12 empty] | 650 |  | Greenfields | [5 empty] | yes
Drury | 30.2 | Drury_30.2 | 2-lane internal collector between Fielding Road & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) |  | Exclude |  | 2038 | 2039 |  | Greenfields Collector |  | Assessed |  |  | 0 | 0% |  | No | [12 empty] | 1350 |  | Greenfields | [5 empty] | yes
Drury | 31 | Drury_31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? |  | Include |  | 2038 | 2039 |  | Upgrade Collector |  | Assessed |  |  | 0 | 0% |  | No | 1860 | [13 empty] | Brownfields | [5 empty] | yes
Drury | 32 | Drury_32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection |  | Include |  | 2038 | 2039 |  | 2-lane Arterial |  | Assessed |  |  | 0 | 0% |  | No |  |  |  |  | 1 | [9 empty] | Brownfields | [5 empty] | yes
Drury | 33 | Drury_33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) |  | Include |  | 2033 | 2033 |  | Upgrade Collector |  | Assessed |  |  | 0 | 0% |  | No | 760 | [13 empty] | Brownfields | [5 empty] | yes
Drury | 34 | Drury_34 | New Drury Interchange connection to Kiwi development | 2-lane urban- new road layout with active modes on both sides (TDM) |  | Exclude |  | 2035 | 2034 |  | State Highway |  | Assessed |  |  | 0 | 0% |  | No | [14 empty] | Brownfields | [5 empty] | yes
Drury | 35a | Drury_35a | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 2-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) |  | Exclude |  | 2038 | 2043 |  | 4-lane arterial |  | Assessed |  |  | 0 | 0% |  | No | [14 empty] | Brownfields | [5 empty] | yes
Drury | 35b | Drury_35b | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 4-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) |  | Exclude |  | 2041 | 2050 |  | 4-lane arterial |  | Assessed |  |  | 0 | 0% |  | No | [14 empty] | Brownfields | [5 empty] | yes
Drury | 36 | Drury_36 | Complete Bremner-Norrie Road connection from SH1 upto GSR (overlap with project 12) | 4-lane urban- upgrade with active modes on both sides (SGA design) |  | Exclude |  |  |  |  | 4-lane arterial |  | Assessed |  |  | 40348997.8097 | 100% | 2020 | Yes | [14 empty] | Brownfields | [5 empty] | yes
Drury | 36a | Drury_36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) |  | Include |  | 2032 | 2033 |  | Interim 2-lane Arterial |  | Assessed |  |  | 0 | 0% |  | No | 200 |  |  | 1120 |  |  | 1 | [5 empty] | 180 |  | Brownfields | 2 lane urban, with kerb and channel. Brownfields where there will be new alignment of road. | Scope from Creek St to Norrie Rd tie-in. Retrofitting active modes to existing corridor, and providing a 2-lane connection from Bremner Rod to the western end of Norrie Rd. - New Bridge of 1120m2 over Hingaia Stream - Linear rate for ‘Roadside Berm Construction’ for the addition of separated footpath and cycleway on each side of the road between Creek Street and Firth Street. This has been applied over a length of 200m to reflect an upgrade to both sides of the road. - Linear rate for a new ‘2-lane Transport Corridor’ for the new section of road between Firth street and Norrie Road tie-in, excluding the bridge. This has been applied over a length of 210m. - Simple signals rate for Bremner/Firth intersection. | NZUP design has 30m overlap with 36a, of which the previous DC assumption was 2 lane transport corridor rate. Alignment of road should follow the existing alignment for this extent, so this 30m on each side (60m total) can be assumed to be linear rate 2 for NZUP extents rather than 2 lane transport corridor rate. Linear rate 2 considers retaining structure required indicated by design. | Assume 36a ends at start of RT bay at the tie in to GSR/Waihoehoe intersection indicated in the Waihoehoe Rd Upgrade design. Tie-ins are included in project 9a. Reduce previous DC assumptions on 2 lane transport corridor rate by 30m. | - New Bridge of 1120m2 over Hingaia Stream - Linear rate for ‘Roadside Berm Construction’ for the addition of separated footpath and cycleway on each side of the road between Creek Street and Firth Street. This has been applied over a length of 200m to reflect an upgrade to both sides of the road. - Linear rate for a new ‘2-lane Transport Corridor’ for the new section of road between Firth street and Norrie Road tie-in, excluding the bridge. This has been applied over a length of 180m. - Simple signals rate for Bremner/Firth intersection. | no
Drury | 36b | Drury_36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) |  | Include |  | 2046 | 2050 |  | 4-lane arterial |  | Assessed |  |  | 0 | 80% |  | No | [6 empty] | 2 |  |  | 180 |  | 280 |  |  | Brownfields | 2 lane urban with kerb and channel and active mode facilities on both sides, as outlined for 36a. | Project extents from western end of Ngakoroa stream bridge to Norrie Rd tie-in. - Widen the new section east of Norrie road to 4 lanes over a length of 180m with extra over, assume interim is future proofed for extra over. - Corridor upgrade from 2 lanes to 4-lanes over a length of 280m for existing section of Bremner Rd - 2 sets of simple signal upgrade for Firth Street and Creek Street | Assume only northern kerbline of 30m from NZUP project as outlined in 36a may be retained, which is minimal relative to remainder of works. Assume no change to DC cost from previous. | No change from previous DC assumptions. | - Widen the new section east of Norrie road to 4 lanes over a length of 180m with extra over, assume interim is future proofed for extra over. - Corridor upgrade from 2 lanes to 4-lanes over a length of 280m for existing section of Bremner Rd - 2 sets of simple signal upgrade for Firth Street and Creek Street | no
Drury | 36c | Drury_36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) |  | Include |  | 2046 | 2050 |  | Major Infrastructure |  | Assessed |  |  | 0 | 80% |  | No |  |  |  | 2160 | [10 empty] | Brownfields | [5 empty] | yes
Drury | 37a(i) | Drury_37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) |  | Include |  | 2042 | 2044 |  | Interim 2-lane Arterial |  | Assessed |  |  | 18819962.326 | 100% | 2020 | No | [14 empty] | Greenfields | [5 empty] | yes
Drury | 37a(ii) | Drury_37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction |  | Include |  | 2041 | 2044 |  | Major Infrastructure |  | Assessed |  |  | 20666666.6667 | 100% | 2020 | No | [14 empty] | Greenfields | [5 empty] | yes
Drury | 37b(i) | Drury_37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) |  | Include |  | 2046 | 2049 |  | 4-lane arterial upgrade |  | Assessed |  |  | 0 | 0% |  | No | [5 empty] | 1 |  |  |  | 1020 |  |  |  |  | Greenfields | [5 empty] | yes
Drury | 37b(ii) | Drury_37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening |  | Include |  | 2046 | 2049 |  | Major Infrastructure |  | Assessed |  |  | 0 | 0% |  | No |  |  |  | 2760 | [10 empty] | Greenfields | [5 empty] | yes
Drury | 38a | Drury_38a | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) |  | Exclude |  |  | 2046 |  | 2-lane Arterial |  | Assessed |  |  | 0 | 0% |  | No | [14 empty] | Brownfields | [5 empty] | yes
Drury | 38b | Drury_38b | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) |  | Exclude |  |  | 2055 |  | 4-lane arterial |  | Assessed |  |  | 0 |  |  | No | [14 empty] | Brownfields | [5 empty] | yes
Drury | 18a | Drury_18a | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) |  | Exclude |  | 2036 | 2036 |  |  |  | Assessed | [5 empty] | No | [14 empty] | No Traffic Management | [5 empty] | yes
Drury | 18b | Drury_18b | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) |  | Exclude |  | 2046 | 2052 |  |  |  | Assessed | [5 empty] | No | [14 empty] | No Traffic Management | [5 empty] | yes
Drury | 39a | Drury_39a | New Bremner Rd arterial from SH1 to Auranga development | 2-lane urban- new road layout with active modes on both sides (Under construction) |  | Exclude |  |  | Under Construction |  | Interim 2-lane Arterial |  | Assessed |  |  | 0 | 0% |  | No | [14 empty] | No Traffic Management | [5 empty] | yes
Drury | 39b | Drury_39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge |  | Include |  | 2046 | 2047 |  | 4-lane arterial upgrade |  | Assessed |  |  | 0 | 0% |  | No | [9 empty] | 620 |  |  |  |  | Brownfields | [5 empty] | yes
Drury | 39c | Drury_39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening |  | Include |  | 2046 | 2047 |  | Major Infrastructure |  | Assessed |  |  | 0 | 0% |  | No |  |  |  | 480 | [10 empty] | Brownfields | [5 empty] | yes
Drury | 40a | Drury_40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) |  | Include |  | 2031 | 2027 |  | 2-lane Arterial |  | Assessed |  |  | 0 | 0% |  | No | [7 empty] | 1 | [6 empty] | Greenfields | [5 empty] | yes
Drury | 40b | Drury_40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) |  | Include |  | 2036 | 2031 |  | 4-lane arterial |  | Assessed |  |  | 0 | 0% |  | No | [6 empty] | 1 | [7 empty] | Brownfields | [5 empty] | yes
Drury | 41a | Drury_41a | Jesmond Rd upgrades from SH22 to Waipupuke development boundary | 2-lane urban- upgrade existing road with active modes on both sides (TDM) |  | Exclude |  | 2030 | 2027 |  | Interim Arterial |  | Assessed |  |  | 0 | 0% |  | No | [12 empty] | 0 |  | Brownfields | 2-lane rural, no kerb and channel. | Full reconstruction of road assumed to achieve 2 lane. Interim active mode facility constructed on western side of road. 520m 2-lane rate. | SH22 design of Jesmond road covers same extents and is the similar form as previous DC assumption (2 lane with active modes on one side). Assume full overlap, so reduction of cost included in DC for 41a removed. | Reduction of 2-lane transport corridor rate from 520m to 0m | Full overlap with NZUP design, assume no works required for 41a as they are already completed in NZUP design. | no
Drury | 41b | Drury_41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) |  | Include |  | 2047 | 2047 |  | 4-lane arterial |  | Assessed |  |  | 0 | 100% |  | No | [9 empty] | 220 |  | 300 |  |  | Brownfields | 2 lane urban with active mode facility on western side, as detailed in 41b. | - 220m extra over for widening on western side of road at northern end - 300m 4 lane brownfields rate on southern side as widening moves to the eastern side of the road to tie into SH22 | SH22 design is 2 lane and matches with interim form. Therefore, it is assumed that the assumptions for previous DC assessment remain, as these have already been reduced to account for retained works, which are now part of the SH22 design. | No change from previous DC assumptions. | - 220m extra over for widening on western side of road at northern end - 300m 4 lane brownfields rate on southern side as widening moves to the eastern side of the road to tie into SH22 | no
Drury | 42a | Drury_42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side |  | Include |  | 2030 | 2028 |  | Interim Arterial |  | Assessed |  |  | 0 | 0% |  | No | 780 | [13 empty] | Brownfields | [5 empty] | yes
Drury | 42b | Drury_42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) |  | Include |  | 2031 | 2031 |  | Interim Arterial |  | Assessed |  |  | 0 | 100% |  | No | [12 empty] | 780 |  | Brownfields | [5 empty] | yes
Drury | 42c | Drury_42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) |  | Include |  | 2047 | 2047 |  | 4-lane arterial |  | Assessed |  |  | 0 | 0% |  | No | [9 empty] | 780 |  |  |  |  | Brownfields | [5 empty] | yes
Drury | 43a | Drury_43a | Intersection upgrade on Jesmond Rd/SH22 Rd | 2-lane intersection (Intersection upgrade + active mode crossings) |  | Exclude |  |  |  |  | State Highway |  | Assessed |  |  | 0 | 0% |  | No | [7 empty] | 1 | [6 empty] | Brownfields | [5 empty] | yes
Drury | 43b | Drury_43b | Intersection upgrade on Jesmond Rd/SH22 Rd | Multi-lane signalised intersection (Intersection upgrade + active mode crossings) |  | Exclude |  | 2033 | 2024 |  | 4-lane arterial |  | Assessed |  |  | 0 | 0% |  | No | [6 empty] | 1 | [7 empty] | Brownfields | [5 empty] | yes
Drury | 44 | Drury_44 | Intersection at SH22/Burberry Rd (likely to close entirely) | Interim design and likely to close - subject to Auranga assessment |  | Exclude |  | 2030 | 2023 |  | 4-lane arterial |  | Assessed |  |  | 0 | 0% |  | No | [6 empty] | 1 | [7 empty] | Brownfields | Existing priority controlled intersection. | Upgrade to simple signalised intersection. | SH22 design does not include intersection, although includes 4 lanes across the location of the intersection. As the pavement and much of kerb and channel will be retained from SH22 design, assume additional works required are limited to traffic signal hardware and localised widening/works on Jesmond Road leg. Therefore assume simple signals rate is included in DC assessment, same as previous DC assumption. | No change from previous DC assumptions. | Upgrade to simple signalised intersection. | no
Drury | 45 | Drury_45 | Upgrade intersection at SH22/Victoria Rd | subject to Auranga assessment |  | Exclude |  | 2030 | 2024 |  | State Highway |  | Assessed |  |  | 0 | 0% |  | No | [6 empty] | 1 | [7 empty] | Brownfields | [5 empty] | yes
Drury | 46 | Drury_46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) |  | Include |  | 2031 | 2031 |  | 4-lane arterial |  | Assessed |  |  | 0 | 0% |  | No | [6 empty] | 1 | [7 empty] | Brownfields | [5 empty] | yes
Drury | 47 | Drury_47 | Old Bremner Road Upgrade from Jesmond Road to Auranga Precinct | 2-lane urban- new road layout with active modes on both sides (Under construction) |  | Exclude |  |  | Under Construction |  |  |  | Assessed | [5 empty] | No | [14 empty] | No Traffic Management | [5 empty] | yes
Drury | 48 | Drury_48 | Collector road south of New Bremner/ Old Bremner intersection | 2-lane urban- new road layout with active modes on both sides (Under construction) |  | Exclude |  |  | Under Construction |  |  |  | Assessed | [5 empty] | No | [14 empty] | No Traffic Management | [5 empty] | yes
Drury | 49 | Drury_49 | SH22 improvements from GSR Intersection to Jesmond Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) |  | Exclude |  | 2032 | 2032 |  | State Highway |  | Assessed |  |  | 20626476.1897 | 100% | 2020 | Yes | [14 empty] | No Traffic Management | [5 empty] | yes
Drury | 50a | Drury_50a | SH22 improvements from Jesmond Rd to Oira Rd- active mode upgrades on the northern section | 2-lane urban- upgrade existing road layout with active modes on northern side only |  | Exclude |  | 2030 | 2026 |  | State Highway |  | Assessed |  |  | 0 | 0% |  | No | [13 empty] | 900 | Brownfields | [5 empty] | yes
Drury | 50b | Drury_50b | SH22 improvements from Jesmond Rd to Oira Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) |  | Exclude |  | 2036 | 2032 |  | State Highway |  | Assessed |  |  | 14910000 | 100% | 2020 | Yes | [14 empty] | Brownfields | [5 empty] | yes
Drury | 51 | Drury_51 | SH22 improvements from Oira Rd to Oira Creek - subject to design, could be incorporated with project 60 | Upgrade road layout to future urban boundary + active modes on both sides |  | Exclude |  | 2036 | 2037 |  | State Highway |  | Assessed |  |  | 12000000 | 100% | 2020 | Yes | [14 empty] | Brownfields | [5 empty] | yes
Drury | 52 | Drury_52 | Intersection upgrade- on SH22/ McPherson Rd/Karaka Rd (Auranga B1) | Ultimate intersection form |  | Exclude |  | 2030 | 2024 |  | 4-lane arterial |  | Assessed |  |  | 0 | 0% |  | No | [6 empty] | 1 | [7 empty] | Brownfields | Existing 2-lane rural corridor. | Upgrade to simple signalised intersection. | SH22 design does not include intersection, although includes 4 lanes across the location of the intersection. As the pavement and much of kerb and channel will be retained from SH22 design, assume additional works required are limited to traffic signal hardware and localised widening/works on Macpherson Road leg. Therefore assume simple signals rate is included in DC assessment, same as previous DC assumption. | No change from previous DC assumptions. | Upgrade to simple signalised intersection. | no
Drury | 53 | Drury_53 | New intersection east of Jesmond Rd (Auranga B1 main street) | Ultimate intersection form (left-in left-out) |  | Exclude |  | 2030 | 2024 |  | 4-lane arterial upgrade |  | Assessed |  |  | 0 | 0% |  | No | [6 empty] | 1 | [7 empty] | Greenfields | Existing 2-lane rural corridor. | Upgrade to simple signalised intersection. | SH22 design does not include intersection, although includes 4 lanes across the location of the intersection. As the pavement and much of kerb and channel will be retained from SH22 design, assume additional works required are limited to traffic signal hardware and localised widening/works on the Auranga Development leg. Therefore assume simple signals rate is included in DC assessment, same as previous DC assumption. | No change from previous DC assumptions. | Upgrade to simple signalised intersection. | no
Drury | 54 | Drury_54 | New N-S collectors internal to Auranga B1 (2 links )+ Intersections | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) |  | Exclude |  | 2035 | 2025 |  | Greenfields Collector |  | Assessed |  |  | 0 | 0% |  | No |  |  |  |  | 1 | [7 empty] | 1200 |  | Greenfields | [5 empty] | yes
Drury | 55 | Drury_55 | New E-W collector Jesmond Rd to SH22 | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) |  | Exclude |  | 2035 |  |  | Greenfields Collector |  | Assessed |  |  | 0 | 0% |  | No |  |  |  |  | 1 | [7 empty] | 870 |  | Greenfields | [5 empty] | yes
Drury | 55a | Drury_55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) |  | Include |  | 2035 | 2034 |  | New Collector (AT) |  | Assessed |  |  | 0 | 0% |  | No |  |  |  |  | 1.5 | [7 empty] | 550 |  | Greenfields | [5 empty] | yes
Drury | 56 | Drury_56 | Burberry Rd north connection to Auranga Precinct | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) |  | Exclude |  |  | Under construction |  | Greenfields Collector |  | Assessed |  |  | 0 | 0% |  | No |  |  |  |  | 1 | [7 empty] | 500 |  | Greenfields | [5 empty] | yes
Drury | 57 | Drury_57 | New access road to Drury West Station | 2-lane urban- new road layout with active modes on both sides, (TDM) |  | Exclude |  | 2030 | 2026 |  | 0 |  | Assessed |  |  | 0 | 0% |  | No | [14 empty] | No Traffic Management | Greenfields. | NZUP project, no rate asusmptions for previous DC assessment. | Access and parking lot included in Drury Rail Stations Drury West - Stage 1. | No change from previous DC assumptions, as whole project is included within NZUP project extents. | No cost included in DC assessment | no
Drury | 58 | Drury_58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) |  | Include |  | 2033 | 2033 |  | Upgrade Collector |  | Assessed |  |  | 0 | 0% |  | No |  |  |  |  | 2 | [7 empty] | 1300 |  | Brownfields | [5 empty] | yes
Drury | 59 | Drury_59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) |  | Include |  | 2033 | 2033 |  | New Collector (AT) |  | Assessed |  |  | 0 | 0% |  | No |  |  |  |  | 1 | [9 empty] | Brownfields | [5 empty] | yes
Drury | 60a | Drury_60a | SH22 Intersection upgrade - Oira Rd (3 leg) | Interim Roundabout |  | Exclude |  | 2033 | 2026 |  | 2-lane Arterial |  | Assessed |  |  | 0 | 0% |  | No |  |  |  |  | 1 | [9 empty] | Brownfields | [5 empty] | yes
Drury | 60b | Drury_60b | SH22 Intersection upgrade - Oira Rd (4 leg) | Ultimate intersection form |  | Exclude |  | 2036 | 2037 |  | 4-lane arterial |  | Assessed |  |  | 0 | 0% |  | No |  |  |  |  | 0.5 | [9 empty] | Brownfields | [5 empty] | yes
Drury | 63 | Drury_63 | New collectors internal to Waipupuke PC61 (3 links )+ Intersections | 2-lane urban - new collector with active mode on both sides + intersection improvements (TDM) |  | Exclude |  | 2036 | 2026 |  | Greenfields Collector |  | Assessed |  |  | 0 | 0% |  | No |  |  |  |  | 2 | [7 empty] | 1800 |  | Greenfields | [5 empty] | yes
Drury | 65a(i) | Drury_65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) |  | Include |  | 2033 | 2036 |  | Interim 2-lane Arterial |  | Assessed |  |  | 0 | 0% |  | No | [8 empty] | 650 | [5 empty] | Greenfields | [5 empty] | yes
Drury | 65a(ii) | Drury_65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) |  | Include |  | 2036 | 2036 |  | Major Infrastructure |  | Assessed |  |  | 0 | 0% |  | No |  |  |  | 540 | [10 empty] | Greenfields | [5 empty] | yes
Drury | 65b(i) | Drury_65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) |  | Include |  | 2046 | 2047 |  | 4-lane arterial upgrade |  | Assessed |  |  | 0 | 0% |  | No | [9 empty] | 650 |  |  |  |  | Brownfields | [5 empty] | yes
Drury | 65b(ii) | Drury_65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) |  | Include |  | 2046 | 2047 |  | Major Infrastructure |  | Assessed |  |  | 0 | 0% |  | No |  |  |  | 180 | [10 empty] | Brownfields | [5 empty] | yes
Drury | 66 | Drury_66 | SH22 improvements - west of SH1 interchange to GSR | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) |  | Exclude |  | 2032 | 2032 |  | State Highway |  | Assessed |  |  | 19599103.786 | 100% | 2020 | Yes | [14 empty] | Brownfields | [5 empty] | yes
Drury | 67 | Drury_67 | Active Mode Corridor Drury Central to GSR |  |  | Include |  | 2032 | 2033 |  | Major Infrastructure |  | Assessed |  |  | 16148893.8182 | 100% | 2020 | Yes | [14 empty] | No Traffic Management | [5 empty] | yes
Drury | 68 | Drury_68 | Active Mode Corridor GSR to Drury West |  |  | Include |  | 2032 | 2037 |  | Major Infrastructure |  | Assessed |  |  | 9945031.0499 | 100% | 2020 | Yes | [14 empty] | No Traffic Management | [5 empty] | yes
Drury | 69 | Drury_69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required |  | Include |  | 2034 | 2035 |  | New Collector (AT) |  | Assessed |  |  | 0 | 0% |  | No |  |  |  | 450 | [9 empty] | 200 | Greenfields | [5 empty] | yes
Drury | 70 | Drury_70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required |  | Include |  | 2032 | 2031 |  | Major Infrastructure |  | Assessed |  |  | 0 | 0% |  | No |  |  |  | 400 | [9 empty] | 270 | Greenfields | [5 empty] | yes
Note on L4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Determines level of WK grant applied: 51% for arterials, 0% for collectors
Note on O4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If project land costs have been assessed through a DBC enter uninflated land cost here and record date costs assessed in L2
Note on Q6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on estimate from Mar 2020 - $14.17M as per summary page less traffic management
Note on Q12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Rob's SS has 28.889m and 45%; Diff report has 39.9m, 45% & a result of 15.2m (though should be 17.955) Reply: Rob had used different calc to achieve same answer. I have updated my ss to match with Diff report, result is unchanged
Note on Q18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on physical works cost of $6.28M as set out in estimate
Note on O63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes project 12 costs
Note on B69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Beth added 10Mar2023 to match Andrew Murray Drury DC Analysis Update_v25
Note on B70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Beth added 10Mar2023 to match Andrew Murray Drury DC Analysis Update_v25
Note on B86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Beth added 10Mar2023 to match Andrew Murray Dury DC Analysis Update_v25
Note on B87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Beth added 10Mar2023 to match Andrew Murray Drury DC Analysis Update_v25

## I4 Con PW Unit Rates
I4 Con Unit Rates
Typical Rates for Construction Physical Works Cost (Base Estimate excluding Env compliance, TM and P&G)
To be applied to
|  |  |  | Date Costs assessed: |  | 2024-03-01
Last Updated | 2024-03-01 |  | Reviewed By: | JL | [13 empty] | Renewal Rates
Rate Category | Length of Linear Rate 1 | Length of Linear Rate 2 | Length of Linear Rate 3 | Bridge Area (m2) | Roundabout 2-lane | Roundabout 4-lane | New Signals simple | New Signals complex | 2-lane interim* | E/O for future 4-lane | Greenfields 4 lane rate 4 | Brownfields 4-lane rate 5 | 2-lane Rate 6 | footpath retrofit | 2-Lane collector | Urban frontage | Footpath only | Rural road reseal (chipseal) | Rural road pavement upgrade
Rate Unit | $/m | $/m | $/m | $/m2 | $ | $ | $ | $ | $/m | $/m | $/m | $/m | $/m | $/m | $/m | $/m | $/m | $/m2 | $/m2
Rate ($) | 2020 | 2850 | 4290 | 4500 | 2500000 | 4500000 | 2000000 | 4500000 | 12630 | 5000 | 15130 | 15490 | 10219.5493 | 480 | 9550 | 4610 | 370 | 56 | 116
Year Rate Assessed: | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024
Rate Adjusted to Current Year: | 2501.4534 | 3529.2784 | 5312.4927 | 5572.5448 | 3095858.2243 | 5572544.8038 | 2476686.5795 | 5572544.8038 | 15640.2757 | 6191.7164 | 18736.134 | 19181.9376 | 12655.3103 | 480 | 9550 | 4610 | 370 | 56 | 116
Position in report: | 5 | 6 | 7 | 12 | 13 | 14 | 15 | 16 | 2 | 3 | 4 |  | 1 | 11 | 8 | 9 | 10 | 17 | 18

## I5 Mitigation
Project number | Project name | % of Property costs to be delivered by AT (through DCs, grants or rates) | % Construction costs to be delivered by AT (through DCs, grants or rates)
1a | GSR improvements - Waihoehoe Rd to Drury Interchange | 0% | 0%
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 100% | 100%
2a | GSR improvements - From Drury School to Waihoehoe Rd | 100% | 100%
2b | GSR improvements - From Drury School to Waihoehoe Rd | 100% | 100%
3 | Intersection upgrade on GSR/Karaka Rd intersection | 0% | 0%
4a | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | 0% | 0%
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | 70% | 20%
4 | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | 0% | 0%
5 | Drury Central Station | 0% | 0%
6 | Drury Station Connection+ intersection | 0% | 0%
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 5% | 5%
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 0% | 5%
9a | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | 0% | 0%
9b | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | 100% | 100%
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 0% | 0%
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 100% | 100%
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | 10% | 10%
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | 100% | 100%
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 15% | 0%
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 0% | 75%
14 | Upgrade Brookefield Road from Fitzgerald to Quarry Rd+ New connection + Intersections on Quarry & Fitzgerald | 0% | 0%
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 100% | 100%
14b | Brookefield Road Upgrade | 0% | 10%
15 | New Collector road E-W from Fitgerald Rd (collector 1) + Intersections | 0% | 0%
16a | Replace 2-lane Bremner Road Bridge over State Highway 1 | 0% | 0%
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 100% | 100%
17 | Oira Road to Jesmond Road Collector | 0% | 10%
19-1 | SH1 3-laning and cycleway upgrades from Papakura to Drury Interchange | 0% | 0%
19-2 | SH1 Drury Interchange including ramps | 0% | 0%
19-3 | SH1 3-laning and cycleway upgrades from Drury Interchange To Drury South | 0% | 0%
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | 0% | 20%
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | 0% | 5%
22 | Upgrade Intersection at Quarry/ GSR | 100% | 100%
23a | Waihoehoe Rd West upgrades- between GSR & Kath Henry | 0% | 0%
23b | Waihoehoe Rd West upgrades- between GSR & Kath Henry Lane | 100% | 100%
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | 0% | 0%
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | 85% | 60%
23 | Waihoehoe Rd West upgrades- between GSR & Fitzgerald Rd, including bridge replacement over the rail corridor | 0% | 0%
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 35% | 15%
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 0% | 30%
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | 0% | 50%
27b | Upgrade from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | 0% | 0%
28 | New collector in N-S direction parallel to Fitzgerald Rd | 0% | 0%
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 100% | 100%
29 | New collector in E-W direction between Flanagan & Fitzgerald Rd (collector 2) | 0% | 0%
30 | 2-lane internal collector between Fitzgerald & Drury Hills E-W direction | 0% | 0%
30.1 | 2-lane internal collector between Fitzgerald & Fielding Road E-W direction | 0% | 0%
30.2 | 2-lane internal collector between Fielding Road & Drury Hills E-W direction | 0% | 0%
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 0% | 5%
32 | New Intersection on Cossey Rd/Waihoehoe Rd | 10% | 10%
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 5% | 5%
34 | New Drury Interchange connection to Kiwi development | 0% | 0%
35a | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 0% | 0%
35b | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 0% | 0%
36 | Complete Bremner-Norrie Road connection from SH1 upto GSR (overlap with project 12) | 0% | 0%
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 100% | 100%
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 100% | 100%
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | 100% | 100%
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 40% | 40%
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 100% | 100%
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 100% | 100%
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 100% | 100%
38a | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 0% | 0%
38b | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 0% | 0%
18a | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment)
18b | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment)
39a | New Bremner Rd arterial from SH1 to Auranga development | 0% | 0%
39b | New Bremner Rd arterial from SH1 to Auranga development | 100% | 100%
39c | New Bremner Rd arterial from SH1 to Auranga development | 100% | 100%
40a | New intersection on Jesmond/Bremner Rd | 40% | 80%
40b | Upgrade intersection on Jesmond/Bremner Rd | 100% | 100%
41a | Jesmond Rd upgrades from SH22 to Waipupuke development boundary | 0% | 25%
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 85% | 50%
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | 0% | 0%
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 0% | 25%
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 85% | 60%
43a | Intersection upgrade on Jesmond Rd/SH22 Rd | 0% | 0%
43b | Intersection upgrade on Jesmond Rd/SH22 Rd | 0% | 0%
44 | Intersection at SH22/Burberry Rd (likely to close entirely) | 0% | 0%
45 | Upgrade intersection at SH22/Victoria Rd | 0% | 0%
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | 100% | 100%
47 | Old Bremner Road Upgrade from Jesmond Road to Auranga Precinct
48 | Collector road south of New Bremner/ Old Bremner intersection
49 | SH22 improvements from GSR Intersection to Jesmond Rd | 0% | 0%
50a | SH22 improvements from Jesmond Rd to Oira Rd- active mode upgrades on the northern section | 0% | 0%
50b | SH22 improvements from Jesmond Rd to Oira Rd | 0% | 0%
51 | SH22 improvements from Oira Rd to Oira Creek - subject to design, could be incorporated with project 60 | 0% | 0%
52 | Intersection upgrade- on SH22/ McPherson Rd/Karaka Rd (Auranga B1) | 0% | 0%
53 | New intersection east of Jesmond Rd (Auranga B1 main street) | 0% | 0%
54 | New N-S collectors internal to Auranga B1 (2 links )+ Intersections | 0% | 5%
55 | New E-W collector Jesmond Rd to SH22 | 0% | 0%
55a | New E-W collector Jesmond Rd to Burberry Rd | 100% | 100%
56 | Burberry Rd north connection to Auranga Precinct | 0% | 0%
57 | New access road to Drury West Station | 0% | 0%
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 0% | 10%
59 | New Intersection on Jesmond Rd/collector (PC61) | 100% | 100%
60a | SH22 Intersection upgrade - Oira Rd (3 leg) | 0% | 0%
60b | SH22 Intersection upgrade - Oira Rd (4 leg) | 0% | 0%
63 | New collectors internal to Waipupuke PC61 (3 links )+ Intersections | 0% | 0%
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 0% | 0%
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 20% | 100%
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 45% | 100%
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 100% | 100%
66 | SH22 improvements - west of SH1 interchange to GSR | 0% | 0%
67 | Active Mode Corridor Drury Central to GSR | 100% | 100%
68 | Active Mode Corridor GSR to Drury West | 100% | 100%
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | 100% | 100%
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | 100% | 100%
Note on A69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Beth added 10Mar2023 to match Andrew Murray Drury DC Analysis Update_v25
Note on A70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Beth added 10Mar2023 to match Andrew Murray Drury DC Analysis Update_v25
Note on A86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Beth added 10Mar2023 to match Andrew Murray Dury DC Analysis Update_v25
Note on A87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Beth added 10Mar2023 to match Andrew Murray Drury DC Analysis Update_v25

## I6 Land price model
For DC modelling | These rates have been developed from the council observations of recent land purchases in Drury, the council valuations, and external advice.
Data from Land escalation and plan zone changes methodologies for reserve, community facilities, and transport land acquistions model, based on 27 Feb 2024 o/s dataset | [9 empty] | Current Year for Unescalated data: |  | 2024 | VlookUp offset | 2019
Unescalated estimated average cost psm by MSM zone based on land development stage
Development area | MSM | DC funding area | CL Price | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060 | 2061 | 2062
Auranga | 561a | Drury West 1 | Auranga Existing Development | 0 | 1000 | 1000 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300
Drury West Step1 | 561 | Drury West 1 | Drury West (Stage 1) (remainder) | 0 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 240 | 240 | 240 | 240 | 335 | 335 | 335 | 335 | 1000 | 1000 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300
Drury West Step1 | 562 | Drury West 1 |  | 0 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 240 | 240 | 240 | 240 | 335 | 335 | 335 | 335 | 1000 | 1000 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300
Drury West Step2 | 557 | Drury West 2 | Drury West (Stage 2) | 0 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 240 | 240 | 240 | 240 | 335 | 335 | 335 | 335 | 1000 | 1000 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300
Drury West Step2 | 558 | Drury West 2 | Drury West (Stage 2) | 0 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 240 | 240 | 240 | 240 | 335 | 335 | 335 | 335 | 1000 | 1000 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300
Drury West Step2 | 559 | Drury West 2 | Drury West (Stage 2) | 0 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 240 | 240 | 240 | 240 | 335 | 335 | 335 | 335 | 1000 | 1000 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300
Drury West Step2 | 560 | Drury West 2 | Drury West (Stage 2) | 0 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 240 | 240 | 240 | 240 | 335 | 335 | 335 | 335 | 1000 | 1000 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300
Drury South | 556 | Drury South | Drury South | 0 | 1000 | 1000 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300
Opaheke | 550 | Opaheke | Opaheke | 0 | 130 | 130 | 130 | 130 | 130 | 240 | 240 | 240 | 240 | 335 | 335 | 335 | 335 | 1000 | 1000 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300
Opaheke | 551 | Opaheke | Opaheke | 0 | 130 | 130 | 130 | 130 | 130 | 240 | 240 | 240 | 240 | 335 | 335 | 335 | 335 | 1000 | 1000 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300
Drury- East PC | 554 | Drury East | Drury East PC | 0 | 240 | 240 | 240 | 240 | 335 | 335 | 335 | 335 | 1000 | 1000 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300
Drury - East | 555 | Drury East |  | 0 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 240 | 240 | 240 | 240 | 335 | 335 | 335 | 335 | 1000 | 1000 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300

## I7 Land transaction List
Land Transaction List Data Review date |  | REDACTED FOR PUBLIC RELEASE Local Government Official Information and Meetings Act 1987 Sec 7(2)(i)
Comment | Transaction Ref | Location | Project Number | Project ID | Property ID | Property Address | Acq is Permanent/Temp | Acq is full/Partial | Land area required | Legal desc | Rate Account | Comment | land status

## I8_PropertyData
REDACTED FOR PUBLIC RELEASE Local Government Official Information and Meetings Act 1987 Sec 7(2)(i)
Property Ref | Property | Legal desc | Rate Account | MSM | Total property Area | Land Price Basis (default, RID,Alternative Pricing) | Dwelling for PWA section 72 | Property_CV | Property_LV | Additional Cost allowance (see comment) | Injurious Affection Risk (only applies to partial acquisitions) | Known Acquisition Date | Acquisition Status | ratepayer_name | Val_REF | Zoning | IA Category | leasehold Unit titles | Comment
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Set to yes if property has one or more dwelling, and is owned (ratepayer) by an individual rather than a company
Note on L4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Supplied by AT, default is 20% on assumptions page, or see RWW model for basis of assessing %s
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Model assumes all acquisitions will be 2 years before project construction. If earlier acquisition required, enter date here to overwrite the model assumption. Otherwise enter "Default"
Note on N4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Identify where designation , NOR (Notice of requirement) in place - not sure if we should do this at property level, or just project level?
Note on R4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: IA category used to assess IA% for RWW. For Drury have used AT supplied %, or default of 20%
Note on S4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Identifies where there are multiple ate accounts on the property

## I9_AlternativePricing
REDACTED FOR PUBLIC RELEASE Local Government Official Information and Meetings Act 1987 Sec 7(2)(i)
Property Ref | Ran | Property | % of Land to be acquired that is within flood plain, to be priced on RID value | % of Developable land to be aquired, to be priced on highest price

## I10_Renewals
Brownfield renewal costs for relevant projects are pro rata calculated from cost and renewal rates of generic project types. This section shows the relevant generic brownfield project type information. |  |  |  |  | Brownfield renewal costs for relevant projects are pro rata calculated on either a per unit or per kilometre cost of the project. |  |  | Resurfacing renewal costs for rural roads on which the projects are located are calculated on a m2 basis. This section shows the area and cost of rural road renewals. |  |  |  | Total renewal costs are calculated as the sum of the brownfield renewal rate and road resurfacing renewal rate.
[10 empty] | Rural local road renewal ($/m2) | Rural collector road renewal ($/m2)
[10 empty] | 56 | 116
Project Number | Generic brownfield project type | Generic brownfield project units | Generic brownfield project renewal rate | Generic brownfield project cost | Project length (km) | PW Cost | PW per unit/km | Rural local road renewal area (m2) | Rural collector road renewal area (m2) | Rural local road renewal cost ($) | Rural collector road renewal cost ($) | Brownfield renewal rate | Resurfacing renewal rate | Total renewal rate | Total renewal cost
Drury_1b | Midblock – Medium | per km | 8.66% | 4200000 | 0.81 | 7631343.85 | 9421412.1605 | 0 | 0 | 0 | 0 | 3.86% | 0% | 3.86% | 294602.0724
Drury_2a | Midblock – Medium | per km | 8.66% | 4200000 | 0.6 | 2919600 | 4866000 | 0 | 0 | 0 | 0 | 7.474% | 0% | 7.474% | 218223.7574
Drury_4b |  |  |  |  | 0.9 | 10578075.52 | 10578075.52 | 0 | 6300 | 0 | 730800 | 0% | 6.909% | 6.909% | 730800
Drury_7 |  |  |  |  | 0.6 | 3134000 | 3134000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_8 |  |  |  |  | 0.6 | 2924000 | 2924000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_10a |  |  |  |  | 0 | 2000000 | 2000000 | 350 | 700 | 19600 | 81200 | 0% | 5.04% | 5.04% | 100800
Drury_10b |  |  |  |  | 0 | 2500000 | 2500000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_11 |  |  |  |  | 0 | 2500000 | 2500000 | 0 | 1400 | 0 | 162400 | 0% | 6.496% | 6.496% | 162400
Drury_12 | Footpath/Cycle path retrofit | per km | 3.737% | 960000 | 0.67 | 6643200 | 9915223.8806 | 0 | 0 | 0 | 0 | 0.3618% | 0% | 0.3618% | 24037.9225
Drury_13a |  |  |  |  | 0.55 | 8946500 | 8946500 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_13b |  |  |  |  | 0.55 | 4750000 | 4750000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_14a |  |  |  |  | 0.52 | 7957323.3867 | 7957323.3867 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_14b |  |  |  |  | 0.52 | 7946361.1467 | 7946361.1467 | 3640 | 0 | 203840 | 0 | 0% | 2.565% | 2.565% | 203840
Drury_16b | Midblock – Medium | per km | 8.66% | 4200000 | 0.1 | 4249000 | 42490000 | 0 | 0 | 0 | 0 | 0.856% | 0% | 0.856% | 36370.6262
Drury_20a |  |  |  |  | 1.1 | 11493000 | 11493000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_21 |  |  |  |  | 0.34 | 1873600 | 1873600 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_22 |  |  |  |  | 0 | 2000000 | 2000000 | 0 | 1650 | 0 | 191400 | 0% | 9.57% | 9.57% | 191400
Drury_23a |  |  |  |  | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_23b |  |  |  |  | 0.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_23c |  |  |  |  | 0.37 | 1566400 | 1566400 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_23d |  |  |  |  | 0.24 | 3957600 | 3957600 | 0 | 1920 | 0 | 222720 | 0% | 5.628% | 5.628% | 222720
Drury_24 |  |  |  |  | 0.9 | 21923000 | 21923000 | 0 | 6300 | 0 | 730800 | 0% | 3.333% | 3.333% | 730800
Drury_25 |  |  |  |  | 0.95 | 5408000 | 5408000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_27a |  |  |  |  | 0.85 | 4001500 | 4001500 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_28a |  |  |  |  | 1 | 4139759.44 | 4139759.44 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_31 |  |  |  |  | 0.93 | 4657200 | 4657200 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_32 |  |  |  |  | 0 | 2500000 | 2500000 | 0 | 1050 | 0 | 121800 | 0% | 4.872% | 4.872% | 121800
Drury_33 |  |  |  |  | 0.38 | 1815200 | 1815200 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_36a | Footpath/Cycle path retrofit | per km | 3.737% | 960000 | 0.2 | 9283518.88 | 46417594.4 | 0 | 0 | 0 | 0 | 0.07729% | 0% | 0.07729% | 7175.4993
Drury_36b | Midblock – Medium | per km | 8.66% | 4200000 | 0.28 | 9237200 | 32990000 | 0 | 0 | 0 | 0 | 1.102% | 0% | 1.102% | 101837.7534
Drury_36c |  |  |  |  | 0.18 | 9720000 | 9720000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_37a(i) |  |  |  |  | 1.02 | 18819962.326 | 18819962.326 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_37a(ii) |  |  |  |  | 0.23 | 20666666.6667 | 20666666.6667 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_37b(i) |  |  |  |  | 1.02 | 9600000 | 9600000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_37b(ii) |  |  |  |  | 0.23 | 12420000 | 12420000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_39b |  |  |  |  | 0.62 | 3100000 | 3100000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_39c |  |  |  |  | 0.04 | 2160000 | 2160000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_40a |  |  |  |  | 0 | 4500000 | 4500000 | 0 | 700 | 0 | 81200 | 0% | 1.804% | 1.804% | 81200
Drury_40b |  |  |  |  | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_41a |  |  |  |  | 0.52 | 5314165.6533 | 5314165.6533 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_41b |  |  |  |  | 0.52 | 5747000 | 5747000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_42a |  |  |  |  | 0.78 | 2275600 | 2275600 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_42b |  |  |  |  | 0.78 | 7971248.48 | 7971248.48 | 0 | 5460 | 0 | 633360 | 0% | 7.946% | 7.946% | 633360
Drury_42c |  |  |  |  | 0.78 | 3900000 | 3900000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_46 |  |  |  |  | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_55a |  |  |  |  | 0.55 | 9370752.1333 | 9370752.1333 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_58 |  |  |  |  | 1.3 | 19285414.1333 | 19285414.1333 | 9100 | 0 | 509600 | 0 | 0% | 2.642% | 2.642% | 509600
Drury_59 |  |  |  |  | 0 | 2500000 | 2500000 | 0 | 350 | 0 | 40600 | 0% | 1.624% | 1.624% | 40600
Drury_65a(i) |  |  |  |  | 0.65 | 8209500 | 8209500 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_65a(ii) |  |  |  |  | 0.3 | 2430000 | 2430000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_65b(i) |  |  |  |  | 0.65 | 3250000 | 3250000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_65b(ii) |  |  |  |  | 0.3 | 810000 | 810000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_67 |  |  |  |  | 1.6 | 16148893.8182 | 16148893.8182 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_68 |  |  |  |  | 1.3 | 9945031.0499 | 9945031.0499 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_69 |  |  |  |  | 0.2 | 2217000 | 2217000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0
Drury_70 |  |  |  |  | 0.27 | 2059200 | 2059200 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0

## P1 Date Adjustment
Date Adjusted
Location | Project number | Project ID | Project name | Project Description | Input Date | Construction Date: Finance Adjusted Modelled Construction year
Drury | 1a | Drury_1a | GSR improvements - Waihoehoe Rd to Drury Interchange | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 2024 | 2024
Drury | 1b | Drury_1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 2031 | 2031
Drury | 2a | Drury_2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 2030 | 2030
Drury | 2b | Drury_2b | GSR improvements - From Drury School to Waihoehoe Rd | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 2040 | 2040
Drury | 3 | Drury_3 | Intersection upgrade on GSR/Karaka Rd intersection | Intersection upgrades- existing intersection with active modes crossings (TDM) | 2026 | 2026
Drury | 4a | Drury_4a | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | 0 | 0
Drury | 4b | Drury_4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | 2029 | 2029
Drury | 4 | Drury_4 | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Construct Ultimate 24m Cross section initially (i.e. no interim stage) | 0 | 0
Drury | 5 | Drury_5 | Drury Central Station | Not feasible without access. Refer to item 6 below | 2024 | 2024
Drury | 6 | Drury_6 | Drury Station Connection+ intersection | NZUP tbc | 2024 | 2024
Drury | 7 | Drury_7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | 2033 | 2036
Drury | 8 | Drury_8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | 2033 | 2036
Drury | 9a | Drury_9a | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | 2-lane signalised intersection with active mode crossings | 2026 | 2026
Drury | 9b | Drury_9b | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | multi-lane signalised intersection with active mode crossings, SGA design | 2031 | 2031
Drury | 10a | Drury_10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | 2029 | 2029
Drury | 10b | Drury_10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | 2031 | 2037
Drury | 11 | Drury_11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | 2031 | 2037
Drury | 12 | Drury_12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | 2033 | 2036
Drury | 13a | Drury_13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | 2029 | 2037
Drury | 13b | Drury_13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | 2050 | 2050
Drury | 14 | Drury_14 | Upgrade Brookefield Road from Fitzgerald to Quarry Rd+ New connection + Intersections on Quarry & Fitzgerald | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements + new connection to Quarry Rd) | 0 | 0
Drury | 14a | Drury_14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | 2035 | 2037
Drury | 14b | Drury_14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | 2033 | 2036
Drury | 15 | Drury_15 | New Collector road E-W from Fitgerald Rd (collector 1) + Intersections | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 2033 | 2033
Drury | 16a | Drury_16a | Replace 2-lane Bremner Road Bridge over State Highway 1 | 2-lane urban with active modes on both sides (replacing existing bridge as part of SH1 P2D NZUP) | 2033 | 2033
Drury | 16b | Drury_16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | 2050 | 2050
Drury | 17 | Drury_17 | Oira Road to Jesmond Road Collector | New 2-lane urban collector with active modes on both sides | 2036 | 2036
Drury | 19-1 | Drury_19-1 | SH1 3-laning and cycleway upgrades from Papakura to Drury Interchange | NZUP tbc | Under Construction | Under Construction
Drury | 19-2 | Drury_19-2 | SH1 Drury Interchange including ramps | NZUP tbc | Under Construction | Under Construction
Drury | 19-3 | Drury_19-3 | SH1 3-laning and cycleway upgrades from Drury Interchange To Drury South | NZUP tbc | 2036 | 2036
Drury | 20a | Drury_20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 2035 | 2036
Drury | 21 | Drury_21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 2035 | 2035
Drury | 22 | Drury_22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | 2033 | 2036
Drury | 23a | Drury_23a | Waihoehoe Rd West upgrades- between GSR & Kath Henry | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | 2025 | 2025
Drury | 23b | Drury_23b | Waihoehoe Rd West upgrades- between GSR & Kath Henry Lane | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | 2031 | 2031
Drury | 23c | Drury_23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | 2025 | 2025
Drury | 23d | Drury_23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | 2031 | 2037
Drury | 23 | Drury_23 | Waihoehoe Rd West upgrades- between GSR & Fitzgerald Rd, including bridge replacement over the rail corridor | 4-lane urban- upgrade 2-lane with active modes on both sides, SGA design | 0 | 0
Drury | 24 | Drury_24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | 2038 | 2038
Drury | 25 | Drury_25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | 2039 | 2039
Drury | 27a | Drury_27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 2039 | 2039
Drury | 27b | Drury_27b | Upgrade from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | 4-lane urban- upgrade existing road layout with active modes on both sides + intersection upgrades (TDM) | 2039 | 2039
Drury | 28 | Drury_28 | New collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 2035 | 2035
Drury | 28a | Drury_28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | 2035 | 2035
Drury | 29 | Drury_29 | New collector in E-W direction between Flanagan & Fitzgerald Rd (collector 2) | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 2035 | 2035
Drury | 30 | Drury_30 | 2-lane internal collector between Fitzgerald & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 0 | 0
Drury | 30.1 | Drury_30.1 | 2-lane internal collector between Fitzgerald & Fielding Road E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 2033 | 2033
Drury | 30.2 | Drury_30.2 | 2-lane internal collector between Fielding Road & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 2039 | 2039
Drury | 31 | Drury_31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | 2039 | 2039
Drury | 32 | Drury_32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | 2039 | 2039
Drury | 33 | Drury_33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | 2033 | 2056
Drury | 34 | Drury_34 | New Drury Interchange connection to Kiwi development | 2-lane urban- new road layout with active modes on both sides (TDM) | 2034 | 2034
Drury | 35a | Drury_35a | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 2-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | 2043 | 2043
Drury | 35b | Drury_35b | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 4-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | 2050 | 2050
Drury | 36 | Drury_36 | Complete Bremner-Norrie Road connection from SH1 upto GSR (overlap with project 12) | 4-lane urban- upgrade with active modes on both sides (SGA design) | 0 | 0
Drury | 36a | Drury_36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | 2033 | 2039
Drury | 36b | Drury_36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | 2050 | 2050
Drury | 36c | Drury_36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | 2050 | 2050
Drury | 37a(i) | Drury_37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | 2044 | 2044
Drury | 37a(ii) | Drury_37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | 2044 | 2044
Drury | 37b(i) | Drury_37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | 2049 | 2049
Drury | 37b(ii) | Drury_37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | 2049 | 2049
Drury | 38a | Drury_38a | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | 2046 | 2046
Drury | 38b | Drury_38b | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | 2055 | 2055
Drury | 18a | Drury_18a | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | 2036 | 2036
Drury | 18b | Drury_18b | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | 2052 | 2052
Drury | 39a | Drury_39a | New Bremner Rd arterial from SH1 to Auranga development | 2-lane urban- new road layout with active modes on both sides (Under construction) | Under Construction | Under Construction
Drury | 39b | Drury_39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | 2047 | 2047
Drury | 39c | Drury_39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | 2047 | 2047
Drury | 40a | Drury_40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | 2027 | 2037
Drury | 40b | Drury_40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | 2031 | 2031
Drury | 41a | Drury_41a | Jesmond Rd upgrades from SH22 to Waipupuke development boundary | 2-lane urban- upgrade existing road with active modes on both sides (TDM) | 2027 | 2027
Drury | 41b | Drury_41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 2047 | 2047
Drury | 42a | Drury_42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | 2028 | 2028
Drury | 42b | Drury_42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | 2031 | 2038
Drury | 42c | Drury_42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 2047 | 2047
Drury | 43a | Drury_43a | Intersection upgrade on Jesmond Rd/SH22 Rd | 2-lane intersection (Intersection upgrade + active mode crossings) | 0 | 0
Drury | 43b | Drury_43b | Intersection upgrade on Jesmond Rd/SH22 Rd | Multi-lane signalised intersection (Intersection upgrade + active mode crossings) | 2024 | 2024
Drury | 44 | Drury_44 | Intersection at SH22/Burberry Rd (likely to close entirely) | Interim design and likely to close - subject to Auranga assessment | 2023 | 2023
Drury | 45 | Drury_45 | Upgrade intersection at SH22/Victoria Rd | subject to Auranga assessment | 2024 | 2024
Drury | 46 | Drury_46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | 2031 | 2035
Drury | 47 | Drury_47 | Old Bremner Road Upgrade from Jesmond Road to Auranga Precinct | 2-lane urban- new road layout with active modes on both sides (Under construction) | Under Construction | Under Construction
Drury | 48 | Drury_48 | Collector road south of New Bremner/ Old Bremner intersection | 2-lane urban- new road layout with active modes on both sides (Under construction) | Under Construction | Under Construction
Drury | 49 | Drury_49 | SH22 improvements from GSR Intersection to Jesmond Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 2032 | 2032
Drury | 50a | Drury_50a | SH22 improvements from Jesmond Rd to Oira Rd- active mode upgrades on the northern section | 2-lane urban- upgrade existing road layout with active modes on northern side only | 2026 | 2026
Drury | 50b | Drury_50b | SH22 improvements from Jesmond Rd to Oira Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 2032 | 2032
Drury | 51 | Drury_51 | SH22 improvements from Oira Rd to Oira Creek - subject to design, could be incorporated with project 60 | Upgrade road layout to future urban boundary + active modes on both sides | 2037 | 2037
Drury | 52 | Drury_52 | Intersection upgrade- on SH22/ McPherson Rd/Karaka Rd (Auranga B1) | Ultimate intersection form | 2024 | 2024
Drury | 53 | Drury_53 | New intersection east of Jesmond Rd (Auranga B1 main street) | Ultimate intersection form (left-in left-out) | 2024 | 2024
Drury | 54 | Drury_54 | New N-S collectors internal to Auranga B1 (2 links )+ Intersections | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 2025 | 2025
Drury | 55 | Drury_55 | New E-W collector Jesmond Rd to SH22 | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 0 | 0
Drury | 55a | Drury_55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 2034 | 2037
Drury | 56 | Drury_56 | Burberry Rd north connection to Auranga Precinct | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Under construction | Under construction
Drury | 57 | Drury_57 | New access road to Drury West Station | 2-lane urban- new road layout with active modes on both sides, (TDM) | 2026 | 2026
Drury | 58 | Drury_58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | 2033 | 2036
Drury | 59 | Drury_59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | 2033 | 2038
Drury | 60a | Drury_60a | SH22 Intersection upgrade - Oira Rd (3 leg) | Interim Roundabout | 2026 | 2026
Drury | 60b | Drury_60b | SH22 Intersection upgrade - Oira Rd (4 leg) | Ultimate intersection form | 2037 | 2037
Drury | 63 | Drury_63 | New collectors internal to Waipupuke PC61 (3 links )+ Intersections | 2-lane urban - new collector with active mode on both sides + intersection improvements (TDM) | 2026 | 2026
Drury | 65a(i) | Drury_65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | 2036 | 2036
Drury | 65a(ii) | Drury_65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | 2036 | 2036
Drury | 65b(i) | Drury_65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 2047 | 2047
Drury | 65b(ii) | Drury_65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 2047 | 2047
Drury | 66 | Drury_66 | SH22 improvements - west of SH1 interchange to GSR | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 2032 | 2032
Drury | 67 | Drury_67 | Active Mode Corridor Drury Central to GSR | 0 | 2033 | 2037
Drury | 68 | Drury_68 | Active Mode Corridor GSR to Drury West | 0 | 2037 | 2037
Drury | 69 | Drury_69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | 2035 | 2035
Drury | 70 | Drury_70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | 2031 | 2031

## Lnd1_AquisDate
Lnd1_AquisDate
Model assumes that where mutliple projects require land from the same property, all of the land will be aquired in a single transaction. This page maps property aqusition to project construction dates, to enable identification of the earliest date land is required
REDACTED FOR PUBLIC RELEASE Local Government Official Information and Meetings Act 1987 Sec 7(2)(i)
Overall project | Property ID | Acq is Perm/Temp | Project is Included in Dcs? | Construction Year

## Lnd2_LandPriceForAcq
Lnd2_LandPriceForAcq
Calcs escalated land price per sqm from RID, LPM and alternate price and selects alternate price (if provided) or the higher of RID/LPM. Costs are split into unescalated, unescalated but adjusted for expected land development stage in year of aqusition and escalated, to show the impact of shifting project dates
REDACTED FOR PUBLIC RELEASE Local Government Official Information and Meetings Act 1987 Sec 7(2)(i)
Property Ref | Property | Legal desc | Rate Account | MSM | Total property Area | Known Acquisition Date | Earliest Construction year | Assumed Acquition Year is 2 years before earliest construction date | Total Land for Partial Aquistion | Total Land for Full Acquistion | Land Price Basis (default, RID,Alternative Pricing) | Land Value from RID | RID LV Escalated to current year | Current Year RID Land Rate $/sqm | Land Price Model price$/psm current year | Land Price Model current year price$/psm for development stage at year of acquisition | Proportion on Alternative pricing % | Alternative pricing standard price % | Unescalated land price used for modelling no development stage adj | Unescalated land price used for modelling with development stage adj | Current Year RID Land Rate $/sqm Escalated | Land Price Model current year price$/psm for development stage at year of acquisition Escalated | Escalated Land Price for modelling

## Lnd2a_LandCostAqc
Lnd2a_LandCostAqc
Calculates the land cost of full and partial acquisitions using the land price from Lnd2_LandPriceForAcq. Assumes where multiple projects require land from the property land will be aquired in one transaction for the earliest project date
REDACTED FOR PUBLIC RELEASE Local Government Official Information and Meetings Act 1987 Sec 7(2)(i)
Property Ref | Property | Legal desc | Rate Account | MSM | Total property Area | Known Acquisition Date | Earliest Construction year | Assumed Acquition Year is 2 years before earliest construction date | Total Land for Partial Aquistion | Total Land for Full Aquistion | Unescalated land price used for modelling no development stage adj | Unescalated land price used for modelling with development stage adj | Escalated Land Price for modelling | Partial Land Acquisition Cost Unescalated, No Dev stage adjustment | Partial Land Aquisition Cost Unescalated, Adjusted for Dev stage | Partial Land Acquisition Cost Escalated in Dev Stage Adjustment | Full Land Acquisition Cost Unescalated, No Dev stage adjustment | Full Land Aquisition Cost Unescalated, Adjusted for Dev stage | Full Land Acquisition Cost Escalated in Dev Stage Adjustment

## Lnd3_LeaseCost
Lnd3_LeaseCost
Calculates Cost of leasing land using the same land pricing methdology as Lnd2a_LandCostAqc. Land will be leased in the year of construction, so costs are calculated per project property transaction
REDACTED FOR PUBLIC RELEASE Local Government Official Information and Meetings Act 1987 Sec 7(2)(i)
Project ID | Property ID | Property Address | MSM Zone | Acq is Permanent/Temp | Acq is full/Partial | Land area required | Total Property Land Area | Land Price basis | Construction Year/Lease Year | Lease Cost as % of Land Cost | Land Value from RID | RID LV Escalated to current year | Current Year RID Land Rate $/sqm | Land Price Model price$/psm current year | Land Price Model current year price$/psm for development stage at year of acquisition | Proportion on Alternative pricing % | Proportion standard price % | Unescalated land price used for modelling no development stage adj | Unescalated land price used for modelling with development stage adj | Current Year RID Land Rate $/sqm Escalated | Land Price Model current year price$/psm for development stage at year of acquisition Escalated | Escalated Land Price for modelling | Land Lease Cost Unescalated, No Dev stage adjustment | Land Lease Cost Unescalated, Adjusted for Dev stage | Land Lease Cost Escalated inc Dev Stage Adjustment

## Lnd4_TransCost
Lnd4_TransCost
Calculates Transaction Costs for Land acquisitions and leases, as well as the cost of improvements for full aqusitions
REDACTED FOR PUBLIC RELEASE Local Government Official Information and Meetings Act 1987 Sec 7(2)(i) | [20 empty] | Transaction Cost Allowances for Partial Acqusitions | [9 empty] | Transaction Cost Allowances for Full Aqusitions |  |  |  |  | Transaction Cost Allowances for Temp Aqusitions
Property Ref | Property | Legal desc | Rate Account | MSM | Total property Area | Total Land for Partial Aquistion | Total Land for Full Acquistion | Total Land for temporary Acquistion | Land Price Basis (default, RID,Alternative Pricing) | Dwelling for PWA section 72 | Property_CV | Property_LV | Additional Cost allowance (see comment) | Injurious Affection Risk (only applies to partial acquisitions) | Earliest Construction Date (for leases) | Assumed Acquisition Date | Earliest Date for Tempoary Lease | Partial Acquisition Unescalated no dev stage adj | Partial Acquisition Unescalated with dev stage adj | Partial Acquisititon Cost Escalated | Partial Acquisition Transaction Cost Unescalated | Partial Acquisition Transaction Cost Escalated | Partial Aquistion Section 72 Not Escalated | Injurious Affection (Unscalated No Dev stage adj) | Injurious Affection (Unscalated with Dev stage adj) | Injurious Affection (Escalated) | Total Partial Transaction Costs Unescalated | Total Partial Transactions Costs Unescalated, adjusted for dev stage | Total Partial Transaction Costs Escalated | Full Acquisition Transaction Cost Unescalated | Full Acquisition Transaction Cost Escalated | Full Aquistion Section 72 Not Escalated | Allowance for Improvements on Land (not escalated) | Total Full Transaction Costs Unescalated | Total Full Transaction Costs Escalated | Temp Acquisition Transaction Cost Unescalated | Temp Acquisition Transaction Cost Escalated
Note on K4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Set to yes if property has one or more dwelling, and is owned (ratepayer) by an individual rather than a company
Note on O4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Supplied by AT, default is 20% on assumptions page, or see RWW model for basis of assessing %s

## Lnd5_TotalPropertyCost
Lnd5_TotalPropertyCost
Adds together land costs from Lnd2a_LandCostAqc Lnd3_LeaseCost Lnd4_TransCost
REDACTED FOR PUBLIC RELEASE Local Government Official Information and Meetings Act 1987 Sec 7(2)(i)
Property Ref | Property | Legal desc | Earliest Construction Year | Contigency | Partial Acquisition Cost Unescalated, Not Adjusted for Dev stage | Partial Acquisition Cost Unescalated, Adjusted for Dev stage | Partial Acquisition Cost Escalated | Full Acquisition Cost Unescalated, Not Adjusted for Dev stage | Full Acquisition Cost Unescalated, Adjusted for Dev stage | Full Acquisition Cost Escalated | Temp Lease Cost Unescalated, Not Adjusted for Dev stage | Temp Lease Cost Unescalated, Adjusted for Dev stage | Temp Lease Cost Escalated | Total Property Cost, Unescalated | Land Development Stage Adjustment | Escalation | Total Property Cost, Escalated

## Lnd6_Proj_Prop_map
Lnd6_Proj_Prop_map
Apportions share of land aqusition cost to projects based on the share of land required for the project for each transaction
REDACTED FOR PUBLIC RELEASE Local Government Official Information and Meetings Act 1987 Sec 7(2)(i)
Project ID | Property ID | Property Address | Acq is Permanent/Temp | Acq is full/Partial | Land area required | Construction Date | Aqusition Date | Share Partial on Property | Share Full acquisition on Property | Share Temp on property | Check Partial total | Check Full total | Check Temp | Contigency | Partial Acquisition Cost Unescalated, Not Adjusted for Dev stage | Partial Acquisition Cost Unescalated, Adjusted for Dev stage | Partial Acquisition Cost Escalated | Full Acquisition Cost Unescalated, Not Adjusted for Dev stage | Full Acquisition Cost Unescalated, Adjusted for Dev stage | Full Acquisition Cost Escalated | Total Full and Partial escalated | Temp Lease Cost Unescalated, Not Adjusted for Dev stage | Temp Lease Cost Unescalated, Adjusted for Dev stage | Temp Lease Cost Escalated | Total Property Cost, Unescalated | Land Development Stage Adjustment | Escalation | Total Property Cost, Escalated | 0

## Lnd7_Total_Proj_Prop_Cost
Lnd7_Total_Proj_Prop_Cost
Sums up all the land transaction costs on Lnd7_Total_Proj_Prop_Cost for each project for projects to be included in the DCs,
Phasing
Project ID | Project name | Project Description | Include in DC model | Construction Date: Finance Adjusted Modelled Construction year | Total Cost | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | Total
Drury_1a | GSR improvements - Waihoehoe Rd to Drury Interchange | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Exclude | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_2b | GSR improvements - From Drury School to Waihoehoe Rd | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Exclude - NZTA | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_3 | Intersection upgrade on GSR/Karaka Rd intersection | Intersection upgrades- existing intersection with active modes crossings (TDM) | Exclude - NZTA | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_4a | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Exclude | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2029 | 3925177.6673 | 0 | 0 | 0 | 0 | 0 | 0 | 3207426.2222 | 0 | 717751.4451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3925177.6673 | 0.33535
Drury_4 | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Construct Ultimate 24m Cross section initially (i.e. no interim stage) | Exclude | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_5 | Drury Central Station | Not feasible without access. Refer to item 6 below | Exclude | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_6 | Drury Station Connection+ intersection | NZUP tbc | Exclude | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_9a | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | 2-lane signalised intersection with active mode crossings | Exclude - NZTA | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_9b | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | multi-lane signalised intersection with active mode crossings, SGA design | Exclude - NZTA | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2029 | 880538.9732 | 0 | 0 | 0 | 0 | 0 | 0 | 880538.9732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880538.9732 | 0.013121
Drury_10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 2037 | 4233069.2151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3863581.1851 | 0 | 369488.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4233069.2151 | -0.34387
Drury_11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2037 | 3218736.704 | 0 | 0 | 0 | 0 | 0 | 0 | 852900.9688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2365835.7352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3218736.704 | 0.065986
Drury_12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | 2037 | 18239495.6348 | 0 | 0 | 0 | 0 | 0 | 0 | 2404271.6418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15835223.993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18239495.6348 | -0.64926
Drury_13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_14 | Upgrade Brookefield Road from Fitzgerald to Quarry Rd+ New connection + Intersections on Quarry & Fitzgerald | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements + new connection to Quarry Rd) | Exclude | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | 2037 | 61441902.2143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61441902.2143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61441902.2143 | -0.34387
Drury_14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_15 | New Collector road E-W from Fitgerald Rd (collector 1) + Intersections | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_16a | Replace 2-lane Bremner Road Bridge over State Highway 1 | 2-lane urban with active modes on both sides (replacing existing bridge as part of SH1 P2D NZUP) | Exclude | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_17 | Oira Road to Jesmond Road Collector | New 2-lane urban collector with active modes on both sides | Exclude | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_19-1 | SH1 3-laning and cycleway upgrades from Papakura to Drury Interchange | NZUP tbc | Exclude | Under Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_19-2 | SH1 Drury Interchange including ramps | NZUP tbc | Exclude | Under Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_19-3 | SH1 3-laning and cycleway upgrades from Drury Interchange To Drury South | NZUP tbc | Exclude | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_23a | Waihoehoe Rd West upgrades- between GSR & Kath Henry | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Exclude | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_23b | Waihoehoe Rd West upgrades- between GSR & Kath Henry Lane | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Exclude | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 2037 | 5179640.6553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4435142.6406 | 0 | 744498.0147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5179640.6553 | -0.69037
Drury_23 | Waihoehoe Rd West upgrades- between GSR & Fitzgerald Rd, including bridge replacement over the rail corridor | 4-lane urban- upgrade 2-lane with active modes on both sides, SGA design | Exclude | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2038 | 5010043.5926 | 0 | 0 | 0 | 0 | 0 | 0 | 431750.0875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4578293.5051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5010043.5926 | -0.40992
Drury_25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_27b | Upgrade from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | 4-lane urban- upgrade existing road layout with active modes on both sides + intersection upgrades (TDM) | Exclude | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_28 | New collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | 2035 | 6179008.7165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6179008.7165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6179008.7165 | 0.36795
Drury_29 | New collector in E-W direction between Flanagan & Fitzgerald Rd (collector 2) | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_30 | 2-lane internal collector between Fitzgerald & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_30.1 | 2-lane internal collector between Fitzgerald & Fielding Road E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_30.2 | 2-lane internal collector between Fielding Road & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2039 | 16067715.2228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2585903.5021 | 9128218.8963 | 0 | 4353592.8244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16067715.2228 | -1.3566
Drury_33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | 2056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_34 | New Drury Interchange connection to Kiwi development | 2-lane urban- new road layout with active modes on both sides (TDM) | Exclude | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_35a | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 2-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | Exclude | 2043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_35b | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 4-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | Exclude | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_36 | Complete Bremner-Norrie Road connection from SH1 upto GSR (overlap with project 12) | 4-lane urban- upgrade with active modes on both sides (SGA design) | Exclude | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | 2039 | 52544006.1085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50286768.5201 | 0 | 2257237.5884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52544006.1085 | -2.4346
Drury_36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 2050 | 99324280.7316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99324280.7316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99324280.7316 | 1.6126
Drury_36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | 2044 | 317700661.0223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 301822758.8126 | 0 | 15877902.2098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317700661.0223 | 1.7489
Drury_37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_38a | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | Exclude | 2046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_38b | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | Exclude | 2055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_18a | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | Exclude | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_18b | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | Exclude | 2052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_39a | New Bremner Rd arterial from SH1 to Auranga development | 2-lane urban- new road layout with active modes on both sides (Under construction) | Exclude | Under Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2037 | 13945362.8382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13466763.1831 | 0 | 478599.6552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13945362.8382 | -0.68773
Drury_40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_41a | Jesmond Rd upgrades from SH22 to Waipupuke development boundary | 2-lane urban- upgrade existing road with active modes on both sides (TDM) | Exclude | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 2047 | 45817041.6166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41779015.0954 | 0 | 4038026.5212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45817041.6166 | -1.0762
Drury_42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 2047 | 116638571.2449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106528910.6882 | 0 | 10109660.5567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116638571.2449 | -6.9951
Drury_43a | Intersection upgrade on Jesmond Rd/SH22 Rd | 2-lane intersection (Intersection upgrade + active mode crossings) | Exclude | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_43b | Intersection upgrade on Jesmond Rd/SH22 Rd | Multi-lane signalised intersection (Intersection upgrade + active mode crossings) | Exclude | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_44 | Intersection at SH22/Burberry Rd (likely to close entirely) | Interim design and likely to close - subject to Auranga assessment | Exclude | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_45 | Upgrade intersection at SH22/Victoria Rd | subject to Auranga assessment | Exclude | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_47 | Old Bremner Road Upgrade from Jesmond Road to Auranga Precinct | 2-lane urban- new road layout with active modes on both sides (Under construction) | Exclude | Under Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_48 | Collector road south of New Bremner/ Old Bremner intersection | 2-lane urban- new road layout with active modes on both sides (Under construction) | Exclude | Under Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_49 | SH22 improvements from GSR Intersection to Jesmond Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Exclude | 2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_50a | SH22 improvements from Jesmond Rd to Oira Rd- active mode upgrades on the northern section | 2-lane urban- upgrade existing road layout with active modes on northern side only | Exclude | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_50b | SH22 improvements from Jesmond Rd to Oira Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Exclude | 2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_51 | SH22 improvements from Oira Rd to Oira Creek - subject to design, could be incorporated with project 60 | Upgrade road layout to future urban boundary + active modes on both sides | Exclude | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_52 | Intersection upgrade- on SH22/ McPherson Rd/Karaka Rd (Auranga B1) | Ultimate intersection form | Exclude | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_53 | New intersection east of Jesmond Rd (Auranga B1 main street) | Ultimate intersection form (left-in left-out) | Exclude | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_54 | New N-S collectors internal to Auranga B1 (2 links )+ Intersections | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_55 | New E-W collector Jesmond Rd to SH22 | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | 2037 | 13284839.242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13284839.242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13284839.242 | -0.68773
Drury_56 | Burberry Rd north connection to Auranga Precinct | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Under construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_57 | New access road to Drury West Station | 2-lane urban- new road layout with active modes on both sides, (TDM) | Exclude | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_60a | SH22 Intersection upgrade - Oira Rd (3 leg) | Interim Roundabout | Exclude | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_60b | SH22 Intersection upgrade - Oira Rd (4 leg) | Ultimate intersection form | Exclude | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_63 | New collectors internal to Waipupuke PC61 (3 links )+ Intersections | 2-lane urban - new collector with active mode on both sides + intersection improvements (TDM) | Exclude | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | 2036 | 89859733.1134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83690277.8626 | 0 | 6169455.2509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89859733.1134 | -1.2017
Drury_65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_66 | SH22 improvements - west of SH1 interchange to GSR | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Exclude | 2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_67 | Active Mode Corridor Drury Central to GSR | 0 | Include | 2037 | 47503573.0814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47503573.0814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47503573.0814 | -1.0316
Drury_68 | Active Mode Corridor GSR to Drury West | 0 | Include | 2037 | 80527456.7457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80527456.7457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80527456.7457 | -1.2035
Drury_69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | 2031 | 3089.0771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3089.0771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3089.0771 | 1250.4627

## Lnd8_Mitigation
Lnd8_Mitigation
Excludes the share of property costs expected to be delivered by developers as mitigation works under their consent, or by other third parties
Phasing
Project ID | Project name | Project Description | Include in DC model | Construction Date: Finance Adjusted Modelled Construction year | Total Property Cost Escalated | % of Property costs to be delivered by AT (through DCs, grants or rates) | Total Property Cost after mitigation excluded | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | Total | mitigation
Drury_1a | GSR improvements - Waihoehoe Rd to Drury Interchange | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Exclude | 2024 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 2031 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 2030 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_2b | GSR improvements - From Drury School to Waihoehoe Rd | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Exclude - NZTA | 2040 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_3 | Intersection upgrade on GSR/Karaka Rd intersection | Intersection upgrades- existing intersection with active modes crossings (TDM) | Exclude - NZTA | 2026 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_4a | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Exclude | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2029 | 3925177.6673 | 70% | 2747624.3671 | 0 | 0 | 0 | 0 | 0 | 0 | 2245198.3556 | 0 | 502426.0115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2747624.3671 | -1177553.3002
Drury_4 | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Construct Ultimate 24m Cross section initially (i.e. no interim stage) | Exclude | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_5 | Drury Central Station | Not feasible without access. Refer to item 6 below | Exclude | 2024 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_6 | Drury Station Connection+ intersection | NZUP tbc | Exclude | 2024 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | 2036 | 0 | 5% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | 2036 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_9a | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | 2-lane signalised intersection with active mode crossings | Exclude - NZTA | 2026 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_9b | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | multi-lane signalised intersection with active mode crossings, SGA design | Exclude - NZTA | 2031 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2029 | 880538.9732 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -880538.9732
Drury_10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 2037 | 4233069.2151 | 100% | 4233069.2151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3863581.1851 | 0 | 369488.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4233069.2151 | 0
Drury_11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2037 | 3218736.704 | 10% | 321873.6704 | 0 | 0 | 0 | 0 | 0 | 0 | 85290.0969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236583.5735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321873.6704 | -2896863.0336
Drury_12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | 2036 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | 2037 | 18239495.6348 | 15% | 2735924.3452 | 0 | 0 | 0 | 0 | 0 | 0 | 360640.7463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2375283.5989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2735924.3452 | -15503571.2896
Drury_13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 2050 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_14 | Upgrade Brookefield Road from Fitzgerald to Quarry Rd+ New connection + Intersections on Quarry & Fitzgerald | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements + new connection to Quarry Rd) | Exclude | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | 2037 | 61441902.2143 | 100% | 61441902.2143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61441902.2143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61441902.2143 | 0
Drury_14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | 2036 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_15 | New Collector road E-W from Fitgerald Rd (collector 1) + Intersections | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | 2033 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_16a | Replace 2-lane Bremner Road Bridge over State Highway 1 | 2-lane urban with active modes on both sides (replacing existing bridge as part of SH1 P2D NZUP) | Exclude | 2033 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 2050 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_17 | Oira Road to Jesmond Road Collector | New 2-lane urban collector with active modes on both sides | Exclude | 2036 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_19-1 | SH1 3-laning and cycleway upgrades from Papakura to Drury Interchange | NZUP tbc | Exclude | Under Construction | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_19-2 | SH1 Drury Interchange including ramps | NZUP tbc | Exclude | Under Construction | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_19-3 | SH1 3-laning and cycleway upgrades from Drury Interchange To Drury South | NZUP tbc | Exclude | 2036 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | 2036 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | 2035 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | 2036 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_23a | Waihoehoe Rd West upgrades- between GSR & Kath Henry | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Exclude | 2025 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_23b | Waihoehoe Rd West upgrades- between GSR & Kath Henry Lane | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Exclude | 2031 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | 2025 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 2037 | 5179640.6553 | 85% | 4402694.557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3769871.2445 | 0 | 632823.3125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4402694.557 | -776946.0983
Drury_23 | Waihoehoe Rd West upgrades- between GSR & Fitzgerald Rd, including bridge replacement over the rail corridor | 4-lane urban- upgrade 2-lane with active modes on both sides, SGA design | Exclude | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2038 | 5010043.5926 | 35% | 1753515.2574 | 0 | 0 | 0 | 0 | 0 | 0 | 151112.5306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1602402.7268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1753515.2574 | -3256528.3352
Drury_25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | 2039 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | 2039 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_27b | Upgrade from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | 4-lane urban- upgrade existing road layout with active modes on both sides + intersection upgrades (TDM) | Exclude | 2039 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_28 | New collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | 2035 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | 2035 | 6179008.7165 | 100% | 6179008.7165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6179008.7165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6179008.7165 | 0
Drury_29 | New collector in E-W direction between Flanagan & Fitzgerald Rd (collector 2) | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | 2035 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_30 | 2-lane internal collector between Fitzgerald & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_30.1 | 2-lane internal collector between Fitzgerald & Fielding Road E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | 2033 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_30.2 | 2-lane internal collector between Fielding Road & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | 2039 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | 2039 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2039 | 16067715.2228 | 10% | 1606771.5223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258590.3502 | 912821.8896 | 0 | 435359.2824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1606771.5223 | -14460943.7005
Drury_33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | 2036 | 0 | 5% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_34 | New Drury Interchange connection to Kiwi development | 2-lane urban- new road layout with active modes on both sides (TDM) | Exclude | 2034 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_35a | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 2-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | Exclude | 2043 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_35b | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 4-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | Exclude | 2050 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_36 | Complete Bremner-Norrie Road connection from SH1 upto GSR (overlap with project 12) | 4-lane urban- upgrade with active modes on both sides (SGA design) | Exclude | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | 2039 | 52544006.1085 | 100% | 52544006.1085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50286768.5201 | 0 | 2257237.5884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52544006.1085 | 0
Drury_36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 2050 | 99324280.7316 | 100% | 99324280.7316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99324280.7316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99324280.7316 | 0
Drury_36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | 2050 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | 2044 | 317700661.0223 | 40% | 127080264.4089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120729103.525 | 0 | 6351160.8839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127080264.4089 | -190620396.6134
Drury_37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | 2044 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 2049 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | 2049 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_38a | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | Exclude | 2046 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_38b | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | Exclude | 2055 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_18a | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | Exclude | 2036 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_18b | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | Exclude | 2052 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_39a | New Bremner Rd arterial from SH1 to Auranga development | 2-lane urban- new road layout with active modes on both sides (Under construction) | Exclude | Under Construction | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 2047 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | 2047 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2037 | 13945362.8382 | 40% | 5578145.1353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5386705.2732 | 0 | 191439.8621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5578145.1353 | -8367217.7029
Drury_40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 2031 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_41a | Jesmond Rd upgrades from SH22 to Waipupuke development boundary | 2-lane urban- upgrade existing road with active modes on both sides (TDM) | Exclude | 2027 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 2047 | 45817041.6166 | 85% | 38944485.3741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35512162.8311 | 0 | 3432322.543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38944485.3741 | -6872556.2425
Drury_42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | 2028 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | 2038 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 2047 | 116638571.2449 | 85% | 99142785.5581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90549574.085 | 0 | 8593211.4732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99142785.5581 | -17495785.6867
Drury_43a | Intersection upgrade on Jesmond Rd/SH22 Rd | 2-lane intersection (Intersection upgrade + active mode crossings) | Exclude | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_43b | Intersection upgrade on Jesmond Rd/SH22 Rd | Multi-lane signalised intersection (Intersection upgrade + active mode crossings) | Exclude | 2024 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_44 | Intersection at SH22/Burberry Rd (likely to close entirely) | Interim design and likely to close - subject to Auranga assessment | Exclude | 2023 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_45 | Upgrade intersection at SH22/Victoria Rd | subject to Auranga assessment | Exclude | 2024 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 2035 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_47 | Old Bremner Road Upgrade from Jesmond Road to Auranga Precinct | 2-lane urban- new road layout with active modes on both sides (Under construction) | Exclude | Under Construction | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_48 | Collector road south of New Bremner/ Old Bremner intersection | 2-lane urban- new road layout with active modes on both sides (Under construction) | Exclude | Under Construction | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_49 | SH22 improvements from GSR Intersection to Jesmond Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Exclude | 2032 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_50a | SH22 improvements from Jesmond Rd to Oira Rd- active mode upgrades on the northern section | 2-lane urban- upgrade existing road layout with active modes on northern side only | Exclude | 2026 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_50b | SH22 improvements from Jesmond Rd to Oira Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Exclude | 2032 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_51 | SH22 improvements from Oira Rd to Oira Creek - subject to design, could be incorporated with project 60 | Upgrade road layout to future urban boundary + active modes on both sides | Exclude | 2037 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_52 | Intersection upgrade- on SH22/ McPherson Rd/Karaka Rd (Auranga B1) | Ultimate intersection form | Exclude | 2024 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_53 | New intersection east of Jesmond Rd (Auranga B1 main street) | Ultimate intersection form (left-in left-out) | Exclude | 2024 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_54 | New N-S collectors internal to Auranga B1 (2 links )+ Intersections | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | 2025 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_55 | New E-W collector Jesmond Rd to SH22 | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | 2037 | 13284839.242 | 100% | 13284839.242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13284839.242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13284839.242 | 0
Drury_56 | Burberry Rd north connection to Auranga Precinct | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Under construction | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_57 | New access road to Drury West Station | 2-lane urban- new road layout with active modes on both sides, (TDM) | Exclude | 2026 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 2036 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | 2038 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_60a | SH22 Intersection upgrade - Oira Rd (3 leg) | Interim Roundabout | Exclude | 2026 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_60b | SH22 Intersection upgrade - Oira Rd (4 leg) | Ultimate intersection form | Exclude | 2037 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_63 | New collectors internal to Waipupuke PC61 (3 links )+ Intersections | 2-lane urban - new collector with active mode on both sides + intersection improvements (TDM) | Exclude | 2026 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | 2036 | 89859733.1134 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -89859733.1134
Drury_65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | 2036 | 0 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 2047 | 0 | 45% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 2047 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_66 | SH22 improvements - west of SH1 interchange to GSR | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Exclude | 2032 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_67 | Active Mode Corridor Drury Central to GSR | 0 | Include | 2037 | 47503573.0814 | 100% | 47503573.0814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47503573.0814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47503573.0814 | 0
Drury_68 | Active Mode Corridor GSR to Drury West | 0 | Include | 2037 | 80527456.7457 | 100% | 80527456.7457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80527456.7457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80527456.7457 | 0
Drury_69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | 2035 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury_70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | 2031 | 3089.0771 | 100% | 3089.0771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3089.0771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3089.0771 | 0

## Con1_Base_Cost
Con1_Base_Cost
Calculates Base Construction cost from I3 Project list
Location | Project number | ProjectID | Project name | Project Description | Non-Generic Base Cost Unescalated | Non-Generic Base Cost Year | Non_Generic Base Cost Escalated to 2024 | Generic Base Cost | Total Construction Base Cost | Allowances Included?
Drury | 1a | Drury_1a | GSR improvements - Waihoehoe Rd to Drury Interchange | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 0 | 0 | 0 | 2476686.5795 | 2476686.5795 | No
Drury | 1b | Drury_1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 7631343.85 | 2020 | 9743180.3752 | 0 | 9743180.3752 | No
Drury | 2a | Drury_2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 0 | 0 | 0 | 2890056.9276 | 2890056.9276 | No
Drury | 2b | Drury_2b | GSR improvements - From Drury School to Waihoehoe Rd | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 0 | 0 | 0 | 0 | 0 | No
Drury | 3 | Drury_3 | Intersection upgrade on GSR/Karaka Rd intersection | Intersection upgrades- existing intersection with active modes crossings (TDM) | 0 | 0 | 0 | 0 | 0 | No
Drury | 4a | Drury_4a | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | 0 | 0 | 0 | 4502616.2015 | 4502616.2015 | No
Drury | 4b | Drury_4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | 0 | 0 | 0 | 12207681.6699 | 12207681.6699 | No
Drury | 4 | Drury_4 | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Construct Ultimate 24m Cross section initially (i.e. no interim stage) | 17937000 | 2020 | 22900740.6591 | 0 | 22900740.6591 | Yes
Drury | 5 | Drury_5 | Drury Central Station | Not feasible without access. Refer to item 6 below | 0 | 0 | 0 | 0 | 0 | No
Drury | 6 | Drury_6 | Drury Station Connection+ intersection | NZUP tbc | 0 | 0 | 0 | 0 | 0 | No
Drury | 7 | Drury_7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | 0 | 0 | 0 | 3001744.1343 | 3001744.1343 | No
Drury | 8 | Drury_8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | 0 | 0 | 0 | 3001744.1343 | 3001744.1343 | No
Drury | 9a | Drury_9a | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | 2-lane signalised intersection with active mode crossings | 0 | 0 | 0 | 0 | 0 | No
Drury | 9b | Drury_9b | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | multi-lane signalised intersection with active mode crossings, SGA design | 0 | 2020 | 0 | 0 | 0 | No
Drury | 10a | Drury_10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | 0 | 0 | 0 | 2476686.5795 | 2476686.5795 | No
Drury | 10b | Drury_10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | 2500000 | 2020 | 3191829.8293 | 0 | 3191829.8293 | No
Drury | 11 | Drury_11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | 0 | 0 | 0 | 3095858.2243 | 3095858.2243 | No
Drury | 12 | Drury_12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | 0 | 0 | 0 | 7751659.7384 | 7751659.7384 | No
Drury | 13a | Drury_13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | 0 | 0 | 0 | 11078838.2416 | 11078838.2416 | No
Drury | 13b | Drury_13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | 0 | 0 | 0 | 5882130.6262 | 5882130.6262 | No
Drury | 14 | Drury_14 | Upgrade Brookefield Road from Fitzgerald to Quarry Rd+ New connection + Intersections on Quarry & Fitzgerald | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements + new connection to Quarry Rd) | 0 | 0 | 0 | 18827380.7211 | 18827380.7211 | No
Drury | 14a | Drury_14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | 0 | 0 | 0 | 9643379.6608 | 9643379.6608 | No
Drury | 14b | Drury_14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | 0 | 0 | 0 | 9184001.0602 | 9184001.0602 | No
Drury | 15 | Drury_15 | New Collector road E-W from Fitgerald Rd (collector 1) + Intersections | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 0 | 0 | 0 | 15050433.6874 | 15050433.6874 | No
Drury | 16a | Drury_16a | Replace 2-lane Bremner Road Bridge over State Highway 1 | 2-lane urban with active modes on both sides (replacing existing bridge as part of SH1 P2D NZUP) | 0 | 0 | 0 | 7283879.4222 | 7283879.4222 | No
Drury | 16b | Drury_16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | 0 | 0 | 0 | 5261720.6381 | 5261720.6381 | No
Drury | 17 | Drury_17 | Oira Road to Jesmond Road Collector | New 2-lane urban collector with active modes on both sides | 0 | 0 | 0 | 7783015.8597 | 7783015.8597 | No
Drury | 19-1 | Drury_19-1 | SH1 3-laning and cycleway upgrades from Papakura to Drury Interchange | NZUP tbc | 0 | 0 | 0 | 0 | 0 | No
Drury | 19-2 | Drury_19-2 | SH1 Drury Interchange including ramps | NZUP tbc | 0 | 0 | 0 | 0 | 0 | No
Drury | 19-3 | Drury_19-3 | SH1 3-laning and cycleway upgrades from Drury Interchange To Drury South | NZUP tbc | 0 | 0 | 0 | 0 | 0 | No
Drury | 20a | Drury_20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 0 | 0 | 0 | 12003261.5074 | 12003261.5074 | No
Drury | 21 | Drury_21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 0 | 0 | 0 | 1700988.3428 | 1700988.3428 | No
Drury | 22 | Drury_22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | 0 | 0 | 0 | 2476686.5795 | 2476686.5795 | No
Drury | 23a | Drury_23a | Waihoehoe Rd West upgrades- between GSR & Kath Henry | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | 0 | 0 | 0 | 0 | 0 | No
Drury | 23b | Drury_23b | Waihoehoe Rd West upgrades- between GSR & Kath Henry Lane | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | 0 | 2020 | 0 | 0 | 0 | No
Drury | 23c | Drury_23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | 0 | 0 | 0 | 1403584.8604 | 1403584.8604 | No
Drury | 23d | Drury_23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | 0 | 0 | 0 | 4603665.0139 | 4603665.0139 | No
Drury | 23 | Drury_23 | Waihoehoe Rd West upgrades- between GSR & Fitzgerald Rd, including bridge replacement over the rail corridor | 4-lane urban- upgrade 2-lane with active modes on both sides, SGA design | 22940000 | 2020 | 29288230.5135 | 0 | 29288230.5135 | Yes
Drury | 24 | Drury_24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | 21923000 | 2020 | 27989794.139 | 0 | 27989794.139 | Yes
Drury | 25 | Drury_25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | 0 | 0 | 0 | 4752761.546 | 4752761.546 | No
Drury | 27a | Drury_27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 0 | 0 | 0 | 4955230.6739 | 4955230.6739 | No
Drury | 27b | Drury_27b | Upgrade from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | 4-lane urban- upgrade existing road layout with active modes on both sides + intersection upgrades (TDM) | 0 | 0 | 0 | 0 | 0 | No
Drury | 28 | Drury_28 | New collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 0 | 0 | 0 | 16516222.6305 | 16516222.6305 | No
Drury | 28a | Drury_28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | 0 | 0 | 0 | 5126443.3236 | 5126443.3236 | No
Drury | 29 | Drury_29 | New collector in E-W direction between Flanagan & Fitzgerald Rd (collector 2) | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 0 | 0 | 0 | 10757013.7899 | 10757013.7899 | No
Drury | 30 | Drury_30 | 2-lane internal collector between Fitzgerald & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 0 | 0 | 0 | 25310620.682 | 25310620.682 | No
Drury | 30.1 | Drury_30.1 | 2-lane internal collector between Fitzgerald & Fielding Road E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 0 | 0 | 0 | 8225951.7217 | 8225951.7217 | No
Drury | 30.2 | Drury_30.2 | 2-lane internal collector between Fielding Road & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 0 | 0 | 0 | 17084668.9604 | 17084668.9604 | No
Drury | 31 | Drury_31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | 0 | 0 | 0 | 4652703.4082 | 4652703.4082 | No
Drury | 32 | Drury_32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | 0 | 0 | 0 | 3095858.2243 | 3095858.2243 | No
Drury | 33 | Drury_33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | 0 | 0 | 0 | 1901104.6184 | 1901104.6184 | No
Drury | 34 | Drury_34 | New Drury Interchange connection to Kiwi development | 2-lane urban- new road layout with active modes on both sides (TDM) | 0 | 0 | 0 | 0 | 0 | No
Drury | 35a | Drury_35a | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 2-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | 0 | 0 | 0 | 0 | 0 | No
Drury | 35b | Drury_35b | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 4-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | 0 | 0 | 0 | 0 | 0 | No
Drury | 36 | Drury_36 | Complete Bremner-Norrie Road connection from SH1 upto GSR (overlap with project 12) | 4-lane urban- upgrade with active modes on both sides (SGA design) | 40348997.8097 | 2020 | 51514853.9163 | 0 | 51514853.9163 | Yes
Drury | 36a | Drury_36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | 0 | 0 | 0 | 11496183.3101 | 11496183.3101 | No
Drury | 36b | Drury_36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | 0 | 0 | 0 | 11438824.6359 | 11438824.6359 | No
Drury | 36c | Drury_36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | 0 | 0 | 0 | 12036696.7762 | 12036696.7762 | No
Drury | 37a(i) | Drury_37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | 18819962.326 | 2020 | 24028046.8553 | 0 | 24028046.8553 | No
Drury | 37a(ii) | Drury_37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | 20666666.6667 | 2020 | 26385793.2554 | 0 | 26385793.2554 | No
Drury | 37b(i) | Drury_37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | 0 | 0 | 0 | 11888095.5814 | 11888095.5814 | No
Drury | 37b(ii) | Drury_37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | 0 | 0 | 0 | 15380223.6585 | 15380223.6585 | No
Drury | 38a | Drury_38a | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | 0 | 0 | 0 | 0 | 0 | No
Drury | 38b | Drury_38b | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | 0 | 0 | 0 | 0 | 0 | No
Drury | 18a | Drury_18a | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | 0 | 0 | 0 | 0 | 0 | No
Drury | 18b | Drury_18b | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | 0 | 0 | 0 | 0 | 0 | No
Drury | 39a | Drury_39a | New Bremner Rd arterial from SH1 to Auranga development | 2-lane urban- new road layout with active modes on both sides (Under construction) | 0 | 0 | 0 | 0 | 0 | No
Drury | 39b | Drury_39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | 0 | 0 | 0 | 3838864.1982 | 3838864.1982 | No
Drury | 39c | Drury_39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | 0 | 0 | 0 | 2674821.5058 | 2674821.5058 | No
Drury | 40a | Drury_40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | 0 | 0 | 0 | 5572544.8038 | 5572544.8038 | No
Drury | 40b | Drury_40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | 0 | 0 | 0 | 2476686.5795 | 2476686.5795 | No
Drury | 41a | Drury_41a | Jesmond Rd upgrades from SH22 to Waipupuke development boundary | 2-lane urban- upgrade existing road with active modes on both sides (TDM) | 0 | 0 | 0 | 0 | 0 | No
Drury | 41b | Drury_41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 0 | 0 | 0 | 7116758.8861 | 7116758.8861 | No
Drury | 42a | Drury_42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | 0 | 0 | 0 | 1951133.6873 | 1951133.6873 | No
Drury | 42b | Drury_42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | 0 | 0 | 0 | 9871142.066 | 9871142.066 | No
Drury | 42c | Drury_42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 0 | 0 | 0 | 4829538.83 | 4829538.83 | No
Drury | 43a | Drury_43a | Intersection upgrade on Jesmond Rd/SH22 Rd | 2-lane intersection (Intersection upgrade + active mode crossings) | 0 | 0 | 0 | 5572544.8038 | 5572544.8038 | No
Drury | 43b | Drury_43b | Intersection upgrade on Jesmond Rd/SH22 Rd | Multi-lane signalised intersection (Intersection upgrade + active mode crossings) | 0 | 0 | 0 | 2476686.5795 | 2476686.5795 | No
Drury | 44 | Drury_44 | Intersection at SH22/Burberry Rd (likely to close entirely) | Interim design and likely to close - subject to Auranga assessment | 0 | 0 | 0 | 2476686.5795 | 2476686.5795 | No
Drury | 45 | Drury_45 | Upgrade intersection at SH22/Victoria Rd | subject to Auranga assessment | 0 | 0 | 0 | 2476686.5795 | 2476686.5795 | No
Drury | 46 | Drury_46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | 0 | 0 | 0 | 2476686.5795 | 2476686.5795 | No
Drury | 47 | Drury_47 | Old Bremner Road Upgrade from Jesmond Road to Auranga Precinct | 2-lane urban- new road layout with active modes on both sides (Under construction) | 0 | 0 | 0 | 0 | 0 | No
Drury | 48 | Drury_48 | Collector road south of New Bremner/ Old Bremner intersection | 2-lane urban- new road layout with active modes on both sides (Under construction) | 0 | 0 | 0 | 0 | 0 | No
Drury | 49 | Drury_49 | SH22 improvements from GSR Intersection to Jesmond Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 20626476.1897 | 2020 | 26334480.7901 | 0 | 26334480.7901 | Yes
Drury | 50a | Drury_50a | SH22 improvements from Jesmond Rd to Oira Rd- active mode upgrades on the northern section | 2-lane urban- upgrade existing road layout with active modes on northern side only | 0 | 0 | 0 | 432000 | 432000 | No
Drury | 50b | Drury_50b | SH22 improvements from Jesmond Rd to Oira Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 14910000 | 2020 | 19036073.1018 | 0 | 19036073.1018 | Yes
Drury | 51 | Drury_51 | SH22 improvements from Oira Rd to Oira Creek - subject to design, could be incorporated with project 60 | Upgrade road layout to future urban boundary + active modes on both sides | 12000000 | 2020 | 15320783.1806 | 0 | 15320783.1806 | Yes
Drury | 52 | Drury_52 | Intersection upgrade- on SH22/ McPherson Rd/Karaka Rd (Auranga B1) | Ultimate intersection form | 0 | 0 | 0 | 2476686.5795 | 2476686.5795 | No
Drury | 53 | Drury_53 | New intersection east of Jesmond Rd (Auranga B1 main street) | Ultimate intersection form (left-in left-out) | 0 | 0 | 0 | 2476686.5795 | 2476686.5795 | No
Drury | 54 | Drury_54 | New N-S collectors internal to Auranga B1 (2 links )+ Intersections | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 0 | 0 | 0 | 18282230.6335 | 18282230.6335 | No
Drury | 55 | Drury_55 | New E-W collector Jesmond Rd to SH22 | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 0 | 0 | 0 | 14105978.221 | 14105978.221 | No
Drury | 55a | Drury_55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 0 | 0 | 0 | 11604208.0241 | 11604208.0241 | No
Drury | 56 | Drury_56 | Burberry Rd north connection to Auranga Precinct | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 0 | 0 | 0 | 9423513.3948 | 9423513.3948 | No
Drury | 57 | Drury_57 | New access road to Drury West Station | 2-lane urban- new road layout with active modes on both sides, (TDM) | 0 | 0 | 0 | 0 | 0 | No
Drury | 58 | Drury_58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | 0 | 0 | 0 | 22643619.892 | 22643619.892 | No
Drury | 59 | Drury_59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | 0 | 0 | 0 | 3095858.2243 | 3095858.2243 | No
Drury | 60a | Drury_60a | SH22 Intersection upgrade - Oira Rd (3 leg) | Interim Roundabout | 0 | 0 | 0 | 3095858.2243 | 3095858.2243 | No
Drury | 60b | Drury_60b | SH22 Intersection upgrade - Oira Rd (4 leg) | Ultimate intersection form | 0 | 0 | 0 | 1547929.1122 | 1547929.1122 | No
Drury | 63 | Drury_63 | New collectors internal to Waipupuke PC61 (3 links )+ Intersections | 2-lane urban - new collector with active mode on both sides + intersection improvements (TDM) | 0 | 0 | 0 | 28971275.0625 | 28971275.0625 | No
Drury | 65a(i) | Drury_65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | 0 | 0 | 0 | 10166179.2371 | 10166179.2371 | No
Drury | 65a(ii) | Drury_65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | 0 | 0 | 0 | 3009174.194 | 3009174.194 | No
Drury | 65b(i) | Drury_65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 0 | 0 | 0 | 4024615.6916 | 4024615.6916 | No
Drury | 65b(ii) | Drury_65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 0 | 0 | 0 | 1003058.0647 | 1003058.0647 | No
Drury | 66 | Drury_66 | SH22 improvements - west of SH1 interchange to GSR | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 19599103.786 | 2020 | 25022801.6365 | 0 | 25022801.6365 | Yes
Drury | 67 | Drury_67 | Active Mode Corridor Drury Central to GSR | 0 | 16148893.8182 | 2020 | 20617808.3995 | 0 | 20617808.3995 | Yes
Drury | 68 | Drury_68 | Active Mode Corridor GSR to Drury West | 0 | 9945031.0499 | 2020 | 12697138.7033 | 0 | 12697138.7033 | Yes
Drury | 69 | Drury_69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | 0 | 0 | 0 | 2603645.1617 | 2603645.1617 | No
Drury | 70 | Drury_70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | 0 | 0 | 0 | 2358617.9215 | 2358617.9215 | No

## Con2_CostAllowances
Con2_CostAllowances |  |  |  | Allowances from I1 Assumptions: | Allowance | Applies to | Allowance rate applied to total cost
Applies Physical Works Cost Allowances |  |  |  |  | Environmental Compliance allowance | All | 6%
[5 empty] | Traffic Management & Temporary Works | No Traffic Management | 0%
[6 empty] | Greenfields | 2%
[6 empty] | Brownfields | 13%
[6 empty] | Brownfields intersection | 20%
[5 empty] | Preliminary and general (P&G) allowance | All | 25%
Location | Project ID | Project number | Project name | Project Description | Total Construction Base Cost | Allowances Included? | Traffic Management Category | Environmental Compliance | Traffic Management Rate | Traffic Management | P&G | Total Construction Base Cost inc of cost Allowances
Drury | Drury_1a | 1a | GSR improvements - Waihoehoe Rd to Drury Interchange | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 2476686.5795 | No | Brownfields | 2625287.7742 | 13% | 2966575.1849 | 3708218.9811 | 3708218.9811
Drury | Drury_1b | 1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 9743180.3752 | No | Brownfields | 10327771.1977 | 13% | 11670381.4534 | 14587976.8167 | 14587976.8167
Drury | Drury_2a | 2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 2890056.9276 | No | Brownfields | 3063460.3432 | 13% | 3461710.1879 | 4327137.7348 | 4327137.7348
Drury | Drury_2b | 2b | GSR improvements - From Drury School to Waihoehoe Rd | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 0 | No | Brownfields | 0 | 13% | 0 | 0 | 0
Drury | Drury_3 | 3 | Intersection upgrade on GSR/Karaka Rd intersection | Intersection upgrades- existing intersection with active modes crossings (TDM) | 0 | No | Brownfields | 0 | 13% | 0 | 0 | 0
Drury | Drury_4a | 4a | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | 4502616.2015 | No | Brownfields | 4772773.1736 | 13% | 5393233.6861 | 6741542.1076 | 6741542.1076
Drury | Drury_4b | 4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | 12207681.6699 | No | Brownfields | 12940142.5701 | 13% | 14622361.1042 | 18277951.3802 | 18277951.3802
Drury | Drury_4 | 4 | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Construct Ultimate 24m Cross section initially (i.e. no interim stage) | 22900740.6591 | Yes | No Traffic Management | 22900740.6591 | 0% | 22900740.6591 | 22900740.6591 | 22900740.6591
Drury | Drury_5 | 5 | Drury Central Station | Not feasible without access. Refer to item 6 below | 0 | No | No Traffic Management | 0 | 0% | 0 | 0 | 0
Drury | Drury_6 | 6 | Drury Station Connection+ intersection | NZUP tbc | 0 | No | Brownfields | 0 | 13% | 0 | 0 | 0
Drury | Drury_7 | 7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | 3001744.1343 | No | Brownfields | 3181848.7824 | 13% | 3595489.1241 | 4494361.4051 | 4494361.4051
Drury | Drury_8 | 8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | 3001744.1343 | No | Brownfields | 3181848.7824 | 13% | 3595489.1241 | 4494361.4051 | 4494361.4051
Drury | Drury_9a | 9a | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | 2-lane signalised intersection with active mode crossings | 0 | No | Brownfields | 0 | 13% | 0 | 0 | 0
Drury | Drury_9b | 9b | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | multi-lane signalised intersection with active mode crossings, SGA design | 0 | No | No Traffic Management | 0 | 0% | 0 | 0 | 0
Drury | Drury_10a | 10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | 2476686.5795 | No | Brownfields | 2625287.7742 | 13% | 2966575.1849 | 3708218.9811 | 3708218.9811
Drury | Drury_10b | 10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | 3191829.8293 | No | Brownfields | 3383339.619 | 13% | 3823173.7695 | 4778967.2119 | 4778967.2119
Drury | Drury_11 | 11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | 3095858.2243 | No | Brownfields | 3281609.7178 | 13% | 3708218.9811 | 4635273.7264 | 4635273.7264
Drury | Drury_12 | 12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | 7751659.7384 | No | Brownfields | 8216759.3227 | 13% | 9284938.0346 | 11606172.5433 | 11606172.5433
Drury | Drury_13a | 13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | 11078838.2416 | No | Greenfields | 11743568.5361 | 2% | 11978439.9068 | 14973049.8835 | 14973049.8835
Drury | Drury_13b | 13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | 5882130.6262 | No | Brownfields | 6235058.4638 | 13% | 7045616.0641 | 8807020.0801 | 8807020.0801
Drury | Drury_14 | 14 | Upgrade Brookefield Road from Fitzgerald to Quarry Rd+ New connection + Intersections on Quarry & Fitzgerald | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements + new connection to Quarry Rd) | 18827380.7211 | No | Brownfields | 19957023.5643 | 13% | 22551436.6277 | 28189295.7846 | 28189295.7846
Drury | Drury_14a | 14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | 9643379.6608 | No | Brownfields | 10221982.4405 | 13% | 11550840.1578 | 14438550.1972 | 14438550.1972
Drury | Drury_14b | 14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | 9184001.0602 | No | Brownfields | 9735041.1238 | 13% | 11000596.4699 | 13750745.5874 | 13750745.5874
Drury | Drury_15 | 15 | New Collector road E-W from Fitgerald Rd (collector 1) + Intersections | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 15050433.6874 | No | Greenfields | 15953459.7086 | 2% | 16272528.9028 | 20340661.1285 | 20340661.1285
Drury | Drury_16a | 16a | Replace 2-lane Bremner Road Bridge over State Highway 1 | 2-lane urban with active modes on both sides (replacing existing bridge as part of SH1 P2D NZUP) | 7283879.4222 | No | Brownfields | 7720912.1875 | 13% | 8724630.7719 | 10905788.4649 | 10905788.4649
Drury | Drury_16b | 16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | 5261720.6381 | No | Brownfields | 5577423.8764 | 13% | 6302488.9803 | 7878111.2254 | 7878111.2254
Drury | Drury_17 | 17 | Oira Road to Jesmond Road Collector | New 2-lane urban collector with active modes on both sides | 7783015.8597 | No | Brownfields | 8249996.8113 | 13% | 9322496.3968 | 11653120.496 | 11653120.496
Drury | Drury_19-1 | 19-1 | SH1 3-laning and cycleway upgrades from Papakura to Drury Interchange | NZUP tbc | 0 | No | No Traffic Management | 0 | 0% | 0 | 0 | 0
Drury | Drury_19-2 | 19-2 | SH1 Drury Interchange including ramps | NZUP tbc | 0 | No | No Traffic Management | 0 | 0% | 0 | 0 | 0
Drury | Drury_19-3 | 19-3 | SH1 3-laning and cycleway upgrades from Drury Interchange To Drury South | NZUP tbc | 0 | No | No Traffic Management | 0 | 0% | 0 | 0 | 0
Drury | Drury_20a | 20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 12003261.5074 | No | Brownfields | 12723457.1978 | 13% | 14377506.6335 | 17971883.2919 | 17971883.2919
Drury | Drury_21 | 21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 1700988.3428 | No | Brownfields | 1803047.6433 | 13% | 2037443.837 | 2546804.7962 | 2546804.7962
Drury | Drury_22 | 22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | 2476686.5795 | No | Brownfields | 2625287.7742 | 13% | 2966575.1849 | 3708218.9811 | 3708218.9811
Drury | Drury_23a | 23a | Waihoehoe Rd West upgrades- between GSR & Kath Henry | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | 0 | No | Brownfields | 0 | 13% | 0 | 0 | 0
Drury | Drury_23b | 23b | Waihoehoe Rd West upgrades- between GSR & Kath Henry Lane | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | 0 | No | No Traffic Management | 0 | 0% | 0 | 0 | 0
Drury | Drury_23c | 23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | 1403584.8604 | No | Brownfields | 1487799.9521 | 13% | 1681213.9458 | 2101517.4323 | 2101517.4323
Drury | Drury_23d | 23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | 4603665.0139 | No | Brownfields | 4879884.9147 | 13% | 5514269.9537 | 6892837.4421 | 6892837.4421
Drury | Drury_23 | 23 | Waihoehoe Rd West upgrades- between GSR & Fitzgerald Rd, including bridge replacement over the rail corridor | 4-lane urban- upgrade 2-lane with active modes on both sides, SGA design | 29288230.5135 | Yes | No Traffic Management | 29288230.5135 | 0% | 29288230.5135 | 29288230.5135 | 29288230.5135
Drury | Drury_24 | 24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | 27989794.139 | Yes | No Traffic Management | 27989794.139 | 0% | 27989794.139 | 27989794.139 | 27989794.139
Drury | Drury_25 | 25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | 4752761.546 | No | Brownfields | 5037927.2387 | 13% | 5692857.7798 | 7116072.2247 | 7116072.2247
Drury | Drury_27a | 27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 4955230.6739 | No | Brownfields | 5252544.5143 | 13% | 5935375.3012 | 7419219.1264 | 7419219.1264
Drury | Drury_27b | 27b | Upgrade from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | 4-lane urban- upgrade existing road layout with active modes on both sides + intersection upgrades (TDM) | 0 | No | Brownfields | 0 | 13% | 0 | 0 | 0
Drury | Drury_28 | 28 | New collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 16516222.6305 | No | Greenfields | 17507195.9884 | 2% | 17857339.9081 | 22321674.8852 | 22321674.8852
Drury | Drury_28a | 28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | 5126443.3236 | No | Greenfields | 5434029.923 | 2% | 5542710.5215 | 6928388.1519 | 6928388.1519
Drury | Drury_29 | 29 | New collector in E-W direction between Flanagan & Fitzgerald Rd (collector 2) | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 10757013.7899 | No | Greenfields | 11402434.6173 | 2% | 11630483.3096 | 14538104.137 | 14538104.137
Drury | Drury_30 | 30 | 2-lane internal collector between Fitzgerald & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 25310620.682 | No | Greenfields | 26829257.923 | 2% | 27365843.0814 | 34207303.8518 | 34207303.8518
Drury | Drury_30.1 | 30.1 | 2-lane internal collector between Fitzgerald & Fielding Road E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 8225951.7217 | No | Greenfields | 8719508.825 | 2% | 8893899.0015 | 11117373.7518 | 11117373.7518
Drury | Drury_30.2 | 30.2 | 2-lane internal collector between Fielding Road & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 17084668.9604 | No | Greenfields | 18109749.098 | 2% | 18471944.08 | 23089930.0999 | 23089930.0999
Drury | Drury_31 | 31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | 4652703.4082 | No | Brownfields | 4931865.6127 | 13% | 5573008.1423 | 6966260.1779 | 6966260.1779
Drury | Drury_32 | 32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | 3095858.2243 | No | Brownfields | 3281609.7178 | 13% | 3708218.9811 | 4635273.7264 | 4635273.7264
Drury | Drury_33 | 33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | 1901104.6184 | No | Brownfields | 2015170.8955 | 13% | 2277143.1119 | 2846428.8899 | 2846428.8899
Drury | Drury_34 | 34 | New Drury Interchange connection to Kiwi development | 2-lane urban- new road layout with active modes on both sides (TDM) | 0 | No | Brownfields | 0 | 13% | 0 | 0 | 0
Drury | Drury_35a | 35a | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 2-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | 0 | No | Brownfields | 0 | 13% | 0 | 0 | 0
Drury | Drury_35b | 35b | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 4-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | 0 | No | Brownfields | 0 | 13% | 0 | 0 | 0
Drury | Drury_36 | 36 | Complete Bremner-Norrie Road connection from SH1 upto GSR (overlap with project 12) | 4-lane urban- upgrade with active modes on both sides (SGA design) | 51514853.9163 | Yes | Brownfields | 51514853.9163 | 13% | 51514853.9163 | 51514853.9163 | 51514853.9163
Drury | Drury_36a | 36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | 11496183.3101 | No | Brownfields | 12185954.3088 | 13% | 13770128.3689 | 17212660.4611 | 17212660.4611
Drury | Drury_36b | 36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | 11438824.6359 | No | Brownfields | 12125154.1141 | 13% | 13701424.1489 | 17126780.1861 | 17126780.1861
Drury | Drury_36c | 36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | 12036696.7762 | No | Brownfields | 12758898.5828 | 13% | 14417555.3985 | 18021944.2482 | 18021944.2482
Drury | Drury_37a(i) | 37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | 24028046.8553 | No | Greenfields | 25469729.6666 | 2% | 25979124.26 | 32473905.3249 | 32473905.3249
Drury | Drury_37a(ii) | 37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | 26385793.2554 | No | Greenfields | 27968940.8507 | 2% | 28528319.6678 | 35660399.5847 | 35660399.5847
Drury | Drury_37b(i) | 37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | 11888095.5814 | No | Greenfields | 12601381.3163 | 2% | 12853408.9426 | 16066761.1783 | 16066761.1783
Drury | Drury_37b(ii) | 37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | 15380223.6585 | No | Greenfields | 16303037.078 | 2% | 16629097.8195 | 20786372.2744 | 20786372.2744
Drury | Drury_38a | 38a | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | 0 | No | Brownfields | 0 | 13% | 0 | 0 | 0
Drury | Drury_38b | 38b | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | 0 | No | Brownfields | 0 | 13% | 0 | 0 | 0
Drury | Drury_18a | 18a | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | 0 | No | No Traffic Management | 0 | 0% | 0 | 0 | 0
Drury | Drury_18b | 18b | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | 0 | No | No Traffic Management | 0 | 0% | 0 | 0 | 0
Drury | Drury_39a | 39a | New Bremner Rd arterial from SH1 to Auranga development | 2-lane urban- new road layout with active modes on both sides (Under construction) | 0 | No | No Traffic Management | 0 | 0% | 0 | 0 | 0
Drury | Drury_39b | 39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | 3838864.1982 | No | Brownfields | 4069196.0501 | 13% | 4598191.5366 | 5747739.4207 | 5747739.4207
Drury | Drury_39c | 39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | 2674821.5058 | No | Brownfields | 2835310.7962 | 13% | 3203901.1997 | 4004876.4996 | 4004876.4996
Drury | Drury_40a | 40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | 5572544.8038 | No | Greenfields | 5906897.492 | 2% | 6025035.4419 | 7531294.3023 | 7531294.3023
Drury | Drury_40b | 40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | 2476686.5795 | No | Brownfields | 2625287.7742 | 13% | 2966575.1849 | 3708218.9811 | 3708218.9811
Drury | Drury_41a | 41a | Jesmond Rd upgrades from SH22 to Waipupuke development boundary | 2-lane urban- upgrade existing road with active modes on both sides (TDM) | 0 | No | Brownfields | 0 | 13% | 0 | 0 | 0
Drury | Drury_41b | 41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 7116758.8861 | No | Brownfields | 7543764.4193 | 13% | 8524453.7938 | 10655567.2422 | 10655567.2422
Drury | Drury_42a | 42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | 1951133.6873 | No | Brownfields | 2068201.7085 | 13% | 2337067.9306 | 2921334.9133 | 2921334.9133
Drury | Drury_42b | 42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | 9871142.066 | No | Brownfields | 10463410.59 | 13% | 11823653.9666 | 14779567.4583 | 14779567.4583
Drury | Drury_42c | 42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 4829538.83 | No | Brownfields | 5119311.1598 | 13% | 5784821.6105 | 7231027.0131 | 7231027.0131
Drury | Drury_43a | 43a | Intersection upgrade on Jesmond Rd/SH22 Rd | 2-lane intersection (Intersection upgrade + active mode crossings) | 5572544.8038 | No | Brownfields | 5906897.492 | 13% | 6674794.166 | 8343492.7075 | 8343492.7075
Drury | Drury_43b | 43b | Intersection upgrade on Jesmond Rd/SH22 Rd | Multi-lane signalised intersection (Intersection upgrade + active mode crossings) | 2476686.5795 | No | Brownfields | 2625287.7742 | 13% | 2966575.1849 | 3708218.9811 | 3708218.9811
Drury | Drury_44 | 44 | Intersection at SH22/Burberry Rd (likely to close entirely) | Interim design and likely to close - subject to Auranga assessment | 2476686.5795 | No | Brownfields | 2625287.7742 | 13% | 2966575.1849 | 3708218.9811 | 3708218.9811
Drury | Drury_45 | 45 | Upgrade intersection at SH22/Victoria Rd | subject to Auranga assessment | 2476686.5795 | No | Brownfields | 2625287.7742 | 13% | 2966575.1849 | 3708218.9811 | 3708218.9811
Drury | Drury_46 | 46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | 2476686.5795 | No | Brownfields | 2625287.7742 | 13% | 2966575.1849 | 3708218.9811 | 3708218.9811
Drury | Drury_47 | 47 | Old Bremner Road Upgrade from Jesmond Road to Auranga Precinct | 2-lane urban- new road layout with active modes on both sides (Under construction) | 0 | No | No Traffic Management | 0 | 0% | 0 | 0 | 0
Drury | Drury_48 | 48 | Collector road south of New Bremner/ Old Bremner intersection | 2-lane urban- new road layout with active modes on both sides (Under construction) | 0 | No | No Traffic Management | 0 | 0% | 0 | 0 | 0
Drury | Drury_49 | 49 | SH22 improvements from GSR Intersection to Jesmond Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 26334480.7901 | Yes | No Traffic Management | 26334480.7901 | 0% | 26334480.7901 | 26334480.7901 | 26334480.7901
Drury | Drury_50a | 50a | SH22 improvements from Jesmond Rd to Oira Rd- active mode upgrades on the northern section | 2-lane urban- upgrade existing road layout with active modes on northern side only | 432000 | No | Brownfields | 457920 | 13% | 517449.6 | 646812 | 646812
Drury | Drury_50b | 50b | SH22 improvements from Jesmond Rd to Oira Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 19036073.1018 | Yes | Brownfields | 19036073.1018 | 13% | 19036073.1018 | 19036073.1018 | 19036073.1018
Drury | Drury_51 | 51 | SH22 improvements from Oira Rd to Oira Creek - subject to design, could be incorporated with project 60 | Upgrade road layout to future urban boundary + active modes on both sides | 15320783.1806 | Yes | Brownfields | 15320783.1806 | 13% | 15320783.1806 | 15320783.1806 | 15320783.1806
Drury | Drury_52 | 52 | Intersection upgrade- on SH22/ McPherson Rd/Karaka Rd (Auranga B1) | Ultimate intersection form | 2476686.5795 | No | Brownfields | 2625287.7742 | 13% | 2966575.1849 | 3708218.9811 | 3708218.9811
Drury | Drury_53 | 53 | New intersection east of Jesmond Rd (Auranga B1 main street) | Ultimate intersection form (left-in left-out) | 2476686.5795 | No | Greenfields | 2625287.7742 | 2% | 2677793.5297 | 3347241.9121 | 3347241.9121
Drury | Drury_54 | 54 | New N-S collectors internal to Auranga B1 (2 links )+ Intersections | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 18282230.6335 | No | Greenfields | 19379164.4716 | 2% | 19766747.761 | 24708434.7012 | 24708434.7012
Drury | Drury_55 | 55 | New E-W collector Jesmond Rd to SH22 | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 14105978.221 | No | Greenfields | 14952336.9143 | 2% | 15251383.6526 | 19064229.5657 | 19064229.5657
Drury | Drury_55a | 55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 11604208.0241 | No | Greenfields | 12300460.5055 | 2% | 12546469.7156 | 15683087.1445 | 15683087.1445
Drury | Drury_56 | 56 | Burberry Rd north connection to Auranga Precinct | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 9423513.3948 | No | Greenfields | 9988924.1985 | 2% | 10188702.6825 | 12735878.3531 | 12735878.3531
Drury | Drury_57 | 57 | New access road to Drury West Station | 2-lane urban- new road layout with active modes on both sides, (TDM) | 0 | No | No Traffic Management | 0 | 0% | 0 | 0 | 0
Drury | Drury_58 | 58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | 22643619.892 | No | Brownfields | 24002237.0855 | 13% | 27122527.9066 | 33903159.8833 | 33903159.8833
Drury | Drury_59 | 59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | 3095858.2243 | No | Brownfields | 3281609.7178 | 13% | 3708218.9811 | 4635273.7264 | 4635273.7264
Drury | Drury_60a | 60a | SH22 Intersection upgrade - Oira Rd (3 leg) | Interim Roundabout | 3095858.2243 | No | Brownfields | 3281609.7178 | 13% | 3708218.9811 | 4635273.7264 | 4635273.7264
Drury | Drury_60b | 60b | SH22 Intersection upgrade - Oira Rd (4 leg) | Ultimate intersection form | 1547929.1122 | No | Brownfields | 1640804.8589 | 13% | 1854109.4906 | 2317636.8632 | 2317636.8632
Drury | Drury_63 | 63 | New collectors internal to Waipupuke PC61 (3 links )+ Intersections | 2-lane urban - new collector with active mode on both sides + intersection improvements (TDM) | 28971275.0625 | No | Greenfields | 30709551.5662 | 2% | 31323742.5976 | 39154678.247 | 39154678.247
Drury | Drury_65a(i) | 65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | 10166179.2371 | No | Greenfields | 10776149.9913 | 2% | 10991672.9911 | 13739591.2389 | 13739591.2389
Drury | Drury_65a(ii) | 65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | 3009174.194 | No | Greenfields | 3189724.6457 | 2% | 3253519.1386 | 4066898.9233 | 4066898.9233
Drury | Drury_65b(i) | 65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 4024615.6916 | No | Brownfields | 4266092.6331 | 13% | 4820684.6754 | 6025855.8443 | 6025855.8443
Drury | Drury_65b(ii) | 65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 1003058.0647 | No | Brownfields | 1063241.5486 | 13% | 1201462.9499 | 1501828.6873 | 1501828.6873
Drury | Drury_66 | 66 | SH22 improvements - west of SH1 interchange to GSR | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 25022801.6365 | Yes | Brownfields | 25022801.6365 | 13% | 25022801.6365 | 25022801.6365 | 25022801.6365
Drury | Drury_67 | 67 | Active Mode Corridor Drury Central to GSR | 0 | 20617808.3995 | Yes | No Traffic Management | 20617808.3995 | 0% | 20617808.3995 | 20617808.3995 | 20617808.3995
Drury | Drury_68 | 68 | Active Mode Corridor GSR to Drury West | 0 | 12697138.7033 | Yes | No Traffic Management | 12697138.7033 | 0% | 12697138.7033 | 12697138.7033 | 12697138.7033
Drury | Drury_69 | 69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | 2603645.1617 | No | Greenfields | 2759863.8714 | 2% | 2815061.1488 | 3518826.436 | 3518826.436
0 | Drury_70 | 70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | 2358617.9215 | No | Greenfields | 2500134.9968 | 2% | 2550137.6967 | 3187672.1209 | 3187672.1209

## Con3_ClientCosts
Con2_ClientCosts |  | Con3_ClientCosts
Applies Client Managed Cost Allowances from I1 Assumptions
Client Managed Cost Allowances
Location | Project ID | Project number | Project name | Project Description | Total Construction Base Cost inc of cost Allowances | Project development % | Project preimplementaion % | Project implementation % | Project Development | Pre-Implementation | Implementation | Total Pre-implementation Costs ($m) | Total PW +Implement Costs $m | Total Physical works unescalated, no contigency
Drury | Drury_1a | 1a | GSR improvements - Waihoehoe Rd to Drury Interchange | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 3708218.9811 | 2% | 9% | 9% | 74164.3796 | 333739.7083 | 333739.7083 | 407904.0879 | 4041958.6894 | 4449862.7773
Drury | Drury_1b | 1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 14587976.8167 | 2% | 9% | 9% | 291759.5363 | 1312917.9135 | 1312917.9135 | 1604677.4498 | 15900894.7302 | 17505572.1801
Drury | Drury_2a | 2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 4327137.7348 | 2% | 9% | 9% | 86542.7547 | 389442.3961 | 389442.3961 | 475985.1508 | 4716580.131 | 5192565.2818
Drury | Drury_2b | 2b | GSR improvements - From Drury School to Waihoehoe Rd | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_3 | 3 | Intersection upgrade on GSR/Karaka Rd intersection | Intersection upgrades- existing intersection with active modes crossings (TDM) | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_4a | 4a | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | 6741542.1076 | 2% | 9% | 9% | 134830.8422 | 606738.7897 | 606738.7897 | 741569.6318 | 7348280.8973 | 8089850.5292
Drury | Drury_4b | 4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | 18277951.3802 | 2% | 9% | 9% | 365559.0276 | 1645015.6242 | 1645015.6242 | 2010574.6518 | 19922967.0044 | 21933541.6562
Drury | Drury_4 | 4 | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Construct Ultimate 24m Cross section initially (i.e. no interim stage) | 22900740.6591 | 2% | 9% | 9% | 458014.8132 | 2061066.6593 | 2061066.6593 | 2519081.4725 | 24961807.3185 | 27480888.791
Drury | Drury_5 | 5 | Drury Central Station | Not feasible without access. Refer to item 6 below | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_6 | 6 | Drury Station Connection+ intersection | NZUP tbc | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_7 | 7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | 4494361.4051 | 2% | 9% | 9% | 89887.2281 | 404492.5265 | 404492.5265 | 494379.7546 | 4898853.9316 | 5393233.6861
Drury | Drury_8 | 8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | 4494361.4051 | 2% | 9% | 9% | 89887.2281 | 404492.5265 | 404492.5265 | 494379.7546 | 4898853.9316 | 5393233.6861
Drury | Drury_9a | 9a | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | 2-lane signalised intersection with active mode crossings | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_9b | 9b | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | multi-lane signalised intersection with active mode crossings, SGA design | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_10a | 10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | 3708218.9811 | 2% | 9% | 9% | 74164.3796 | 333739.7083 | 333739.7083 | 407904.0879 | 4041958.6894 | 4449862.7773
Drury | Drury_10b | 10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | 4778967.2119 | 2% | 9% | 9% | 95579.3442 | 430107.0491 | 430107.0491 | 525686.3933 | 5209074.261 | 5734760.6543
Drury | Drury_11 | 11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | 4635273.7264 | 2% | 9% | 9% | 92705.4745 | 417174.6354 | 417174.6354 | 509880.1099 | 5052448.3618 | 5562328.4717
Drury | Drury_12 | 12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | 11606172.5433 | 2% | 9% | 9% | 232123.4509 | 1044555.5289 | 1044555.5289 | 1276678.9798 | 12650728.0722 | 13927407.052
Drury | Drury_13a | 13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | 14973049.8835 | 2% | 9% | 9% | 299460.9977 | 1347574.4895 | 1347574.4895 | 1647035.4872 | 16320624.373 | 17967659.8602
Drury | Drury_13b | 13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | 8807020.0801 | 2% | 9% | 9% | 176140.4016 | 792631.8072 | 792631.8072 | 968772.2088 | 9599651.8873 | 10568424.0961
Drury | Drury_14 | 14 | Upgrade Brookefield Road from Fitzgerald to Quarry Rd+ New connection + Intersections on Quarry & Fitzgerald | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements + new connection to Quarry Rd) | 28189295.7846 | 2% | 9% | 9% | 563785.9157 | 2537036.6206 | 2537036.6206 | 3100822.5363 | 30726332.4052 | 33827154.9415
Drury | Drury_14a | 14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | 14438550.1972 | 2% | 9% | 9% | 288771.0039 | 1299469.5177 | 1299469.5177 | 1588240.5217 | 15738019.715 | 17326260.2366
Drury | Drury_14b | 14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | 13750745.5874 | 2% | 9% | 9% | 275014.9117 | 1237567.1029 | 1237567.1029 | 1512582.0146 | 14988312.6903 | 16500894.7049
Drury | Drury_15 | 15 | New Collector road E-W from Fitgerald Rd (collector 1) + Intersections | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 20340661.1285 | 2% | 9% | 9% | 406813.2226 | 1830659.5016 | 1830659.5016 | 2237472.7241 | 22171320.63 | 24408793.3542
Drury | Drury_16a | 16a | Replace 2-lane Bremner Road Bridge over State Highway 1 | 2-lane urban with active modes on both sides (replacing existing bridge as part of SH1 P2D NZUP) | 10905788.4649 | 2% | 9% | 9% | 218115.7693 | 981520.9618 | 981520.9618 | 1199636.7311 | 11887309.4267 | 13086946.1579
Drury | Drury_16b | 16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | 7878111.2254 | 2% | 9% | 9% | 157562.2245 | 709030.0103 | 709030.0103 | 866592.2348 | 8587141.2356 | 9453733.4704
Drury | Drury_17 | 17 | Oira Road to Jesmond Road Collector | New 2-lane urban collector with active modes on both sides | 11653120.496 | 2% | 9% | 9% | 233062.4099 | 1048780.8446 | 1048780.8446 | 1281843.2546 | 12701901.3406 | 13983744.5952
Drury | Drury_19-1 | 19-1 | SH1 3-laning and cycleway upgrades from Papakura to Drury Interchange | NZUP tbc | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_19-2 | 19-2 | SH1 Drury Interchange including ramps | NZUP tbc | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_19-3 | 19-3 | SH1 3-laning and cycleway upgrades from Drury Interchange To Drury South | NZUP tbc | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_20a | 20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 17971883.2919 | 2% | 9% | 9% | 359437.6658 | 1617469.4963 | 1617469.4963 | 1976907.1621 | 19589352.7882 | 21566259.9503
Drury | Drury_21 | 21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 2546804.7962 | 2% | 9% | 9% | 50936.0959 | 229212.4317 | 229212.4317 | 280148.5276 | 2776017.2279 | 3056165.7555
Drury | Drury_22 | 22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | 3708218.9811 | 2% | 9% | 9% | 74164.3796 | 333739.7083 | 333739.7083 | 407904.0879 | 4041958.6894 | 4449862.7773
Drury | Drury_23a | 23a | Waihoehoe Rd West upgrades- between GSR & Kath Henry | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_23b | 23b | Waihoehoe Rd West upgrades- between GSR & Kath Henry Lane | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_23c | 23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | 2101517.4323 | 2% | 9% | 9% | 42030.3486 | 189136.5689 | 189136.5689 | 231166.9176 | 2290654.0012 | 2521820.9188
Drury | Drury_23d | 23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | 6892837.4421 | 2% | 9% | 9% | 137856.7488 | 620355.3698 | 620355.3698 | 758212.1186 | 7513192.8119 | 8271404.9305
Drury | Drury_23 | 23 | Waihoehoe Rd West upgrades- between GSR & Fitzgerald Rd, including bridge replacement over the rail corridor | 4-lane urban- upgrade 2-lane with active modes on both sides, SGA design | 29288230.5135 | 2% | 9% | 9% | 585764.6103 | 2635940.7462 | 2635940.7462 | 3221705.3565 | 31924171.2597 | 35145876.6162
Drury | Drury_24 | 24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | 27989794.139 | 2% | 9% | 9% | 559795.8828 | 2519081.4725 | 2519081.4725 | 3078877.3553 | 30508875.6115 | 33587752.9667
Drury | Drury_25 | 25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | 7116072.2247 | 2% | 9% | 9% | 142321.4445 | 640446.5002 | 640446.5002 | 782767.9447 | 7756518.725 | 8539286.6697
Drury | Drury_27a | 27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 7419219.1264 | 2% | 9% | 9% | 148384.3825 | 667729.7214 | 667729.7214 | 816114.1039 | 8086948.8478 | 8903062.9517
Drury | Drury_27b | 27b | Upgrade from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | 4-lane urban- upgrade existing road layout with active modes on both sides + intersection upgrades (TDM) | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_28 | 28 | New collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 22321674.8852 | 2% | 9% | 9% | 446433.4977 | 2008950.7397 | 2008950.7397 | 2455384.2374 | 24330625.6248 | 26786009.8622
Drury | Drury_28a | 28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | 6928388.1519 | 2% | 9% | 9% | 138567.763 | 623554.9337 | 623554.9337 | 762122.6967 | 7551943.0856 | 8314065.7823
Drury | Drury_29 | 29 | New collector in E-W direction between Flanagan & Fitzgerald Rd (collector 2) | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 14538104.137 | 2% | 9% | 9% | 290762.0827 | 1308429.3723 | 1308429.3723 | 1599191.4551 | 15846533.5093 | 17445724.9644
Drury | Drury_30 | 30 | 2-lane internal collector between Fitzgerald & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 34207303.8518 | 2% | 9% | 9% | 684146.077 | 3078657.3467 | 3078657.3467 | 3762803.4237 | 37285961.1984 | 41048764.6221
Drury | Drury_30.1 | 30.1 | 2-lane internal collector between Fitzgerald & Fielding Road E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 11117373.7518 | 2% | 9% | 9% | 222347.475 | 1000563.6377 | 1000563.6377 | 1222911.1127 | 12117937.3895 | 13340848.5022
Drury | Drury_30.2 | 30.2 | 2-lane internal collector between Fielding Road & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 23089930.0999 | 2% | 9% | 9% | 461798.602 | 2078093.709 | 2078093.709 | 2539892.311 | 25168023.8089 | 27707916.1199
Drury | Drury_31 | 31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | 6966260.1779 | 2% | 9% | 9% | 139325.2036 | 626963.416 | 626963.416 | 766288.6196 | 7593223.5939 | 8359512.2135
Drury | Drury_32 | 32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | 4635273.7264 | 2% | 9% | 9% | 92705.4745 | 417174.6354 | 417174.6354 | 509880.1099 | 5052448.3618 | 5562328.4717
Drury | Drury_33 | 33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | 2846428.8899 | 2% | 9% | 9% | 56928.5778 | 256178.6001 | 256178.6001 | 313107.1779 | 3102607.49 | 3415714.6679
Drury | Drury_34 | 34 | New Drury Interchange connection to Kiwi development | 2-lane urban- new road layout with active modes on both sides (TDM) | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_35a | 35a | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 2-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_35b | 35b | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 4-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_36 | 36 | Complete Bremner-Norrie Road connection from SH1 upto GSR (overlap with project 12) | 4-lane urban- upgrade with active modes on both sides (SGA design) | 51514853.9163 | 2% | 9% | 9% | 1030297.0783 | 4636336.8525 | 4636336.8525 | 5666633.9308 | 56151190.7688 | 61817824.6996
Drury | Drury_36a | 36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | 17212660.4611 | 2% | 9% | 9% | 344253.2092 | 1549139.4415 | 1549139.4415 | 1893392.6507 | 18761799.9026 | 20655192.5533
Drury | Drury_36b | 36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | 17126780.1861 | 2% | 9% | 9% | 342535.6037 | 1541410.2168 | 1541410.2168 | 1883945.8205 | 18668190.4029 | 20552136.2233
Drury | Drury_36c | 36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | 18021944.2482 | 2% | 9% | 9% | 360438.885 | 1621974.9823 | 1621974.9823 | 1982413.8673 | 19643919.2305 | 21626333.0978
Drury | Drury_37a(i) | 37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | 32473905.3249 | 2% | 9% | 9% | 649478.1065 | 2922651.4792 | 2922651.4792 | 3572129.5857 | 35396556.8042 | 38968686.3899
Drury | Drury_37a(ii) | 37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | 35660399.5847 | 2% | 9% | 9% | 713207.9917 | 3209435.9626 | 3209435.9626 | 3922643.9543 | 38869835.5473 | 42792479.5016
Drury | Drury_37b(i) | 37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | 16066761.1783 | 2% | 9% | 9% | 321335.2236 | 1446008.506 | 1446008.506 | 1767343.7296 | 17512769.6843 | 19280113.414
Drury | Drury_37b(ii) | 37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | 20786372.2744 | 2% | 9% | 9% | 415727.4455 | 1870773.5047 | 1870773.5047 | 2286500.9502 | 22657145.7791 | 24943646.7293
Drury | Drury_38a | 38a | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_38b | 38b | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_18a | 18a | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_18b | 18b | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_39a | 39a | New Bremner Rd arterial from SH1 to Auranga development | 2-lane urban- new road layout with active modes on both sides (Under construction) | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_39b | 39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | 5747739.4207 | 2% | 9% | 9% | 114954.7884 | 517296.5479 | 517296.5479 | 632251.3363 | 6265035.9686 | 6897287.3048
Drury | Drury_39c | 39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | 4004876.4996 | 2% | 9% | 9% | 80097.53 | 360438.885 | 360438.885 | 440536.415 | 4365315.3846 | 4805851.7995
Drury | Drury_40a | 40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | 7531294.3023 | 2% | 9% | 9% | 150625.886 | 677816.4872 | 677816.4872 | 828442.3733 | 8209110.7895 | 9037553.1628
Drury | Drury_40b | 40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | 3708218.9811 | 2% | 9% | 9% | 74164.3796 | 333739.7083 | 333739.7083 | 407904.0879 | 4041958.6894 | 4449862.7773
Drury | Drury_41a | 41a | Jesmond Rd upgrades from SH22 to Waipupuke development boundary | 2-lane urban- upgrade existing road with active modes on both sides (TDM) | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_41b | 41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 10655567.2422 | 2% | 9% | 9% | 213111.3448 | 959001.0518 | 959001.0518 | 1172112.3966 | 11614568.294 | 12786680.6906
Drury | Drury_42a | 42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | 2921334.9133 | 2% | 9% | 9% | 58426.6983 | 262920.1422 | 262920.1422 | 321346.8405 | 3184255.0555 | 3505601.896
Drury | Drury_42b | 42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | 14779567.4583 | 2% | 9% | 9% | 295591.3492 | 1330161.0712 | 1330161.0712 | 1625752.4204 | 16109728.5296 | 17735480.95
Drury | Drury_42c | 42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 7231027.0131 | 2% | 9% | 9% | 144620.5403 | 650792.4312 | 650792.4312 | 795412.9714 | 7881819.4443 | 8677232.4158
Drury | Drury_43a | 43a | Intersection upgrade on Jesmond Rd/SH22 Rd | 2-lane intersection (Intersection upgrade + active mode crossings) | 8343492.7075 | 2% | 9% | 9% | 166869.8541 | 750914.3437 | 750914.3437 | 917784.1978 | 9094407.0512 | 10012191.249
Drury | Drury_43b | 43b | Intersection upgrade on Jesmond Rd/SH22 Rd | Multi-lane signalised intersection (Intersection upgrade + active mode crossings) | 3708218.9811 | 2% | 9% | 9% | 74164.3796 | 333739.7083 | 333739.7083 | 407904.0879 | 4041958.6894 | 4449862.7773
Drury | Drury_44 | 44 | Intersection at SH22/Burberry Rd (likely to close entirely) | Interim design and likely to close - subject to Auranga assessment | 3708218.9811 | 2% | 9% | 9% | 74164.3796 | 333739.7083 | 333739.7083 | 407904.0879 | 4041958.6894 | 4449862.7773
Drury | Drury_45 | 45 | Upgrade intersection at SH22/Victoria Rd | subject to Auranga assessment | 3708218.9811 | 2% | 9% | 9% | 74164.3796 | 333739.7083 | 333739.7083 | 407904.0879 | 4041958.6894 | 4449862.7773
Drury | Drury_46 | 46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | 3708218.9811 | 2% | 9% | 9% | 74164.3796 | 333739.7083 | 333739.7083 | 407904.0879 | 4041958.6894 | 4449862.7773
Drury | Drury_47 | 47 | Old Bremner Road Upgrade from Jesmond Road to Auranga Precinct | 2-lane urban- new road layout with active modes on both sides (Under construction) | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_48 | 48 | Collector road south of New Bremner/ Old Bremner intersection | 2-lane urban- new road layout with active modes on both sides (Under construction) | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_49 | 49 | SH22 improvements from GSR Intersection to Jesmond Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 26334480.7901 | 2% | 9% | 9% | 526689.6158 | 2370103.2711 | 2370103.2711 | 2896792.8869 | 28704584.0612 | 31601376.9481
Drury | Drury_50a | 50a | SH22 improvements from Jesmond Rd to Oira Rd- active mode upgrades on the northern section | 2-lane urban- upgrade existing road layout with active modes on northern side only | 646812 | 2% | 9% | 9% | 12936.24 | 58213.08 | 58213.08 | 71149.32 | 705025.08 | 776174.4
Drury | Drury_50b | 50b | SH22 improvements from Jesmond Rd to Oira Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 19036073.1018 | 2% | 9% | 9% | 380721.462 | 1713246.5792 | 1713246.5792 | 2093968.0412 | 20749319.681 | 22843287.7222
Drury | Drury_51 | 51 | SH22 improvements from Oira Rd to Oira Creek - subject to design, could be incorporated with project 60 | Upgrade road layout to future urban boundary + active modes on both sides | 15320783.1806 | 2% | 9% | 9% | 306415.6636 | 1378870.4863 | 1378870.4863 | 1685286.1499 | 16699653.6668 | 18384939.8167
Drury | Drury_52 | 52 | Intersection upgrade- on SH22/ McPherson Rd/Karaka Rd (Auranga B1) | Ultimate intersection form | 3708218.9811 | 2% | 9% | 9% | 74164.3796 | 333739.7083 | 333739.7083 | 407904.0879 | 4041958.6894 | 4449862.7773
Drury | Drury_53 | 53 | New intersection east of Jesmond Rd (Auranga B1 main street) | Ultimate intersection form (left-in left-out) | 3347241.9121 | 2% | 9% | 9% | 66944.8382 | 301251.7721 | 301251.7721 | 368196.6103 | 3648493.6842 | 4016690.2946
Drury | Drury_54 | 54 | New N-S collectors internal to Auranga B1 (2 links )+ Intersections | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 24708434.7012 | 2% | 9% | 9% | 494168.694 | 2223759.1231 | 2223759.1231 | 2717927.8171 | 26932193.8244 | 29650121.6415
Drury | Drury_55 | 55 | New E-W collector Jesmond Rd to SH22 | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 19064229.5657 | 2% | 9% | 9% | 381284.5913 | 1715780.6609 | 1715780.6609 | 2097065.2522 | 20780010.2266 | 22877075.4788
Drury | Drury_55a | 55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 15683087.1445 | 2% | 9% | 9% | 313661.7429 | 1411477.843 | 1411477.843 | 1725139.5859 | 17094564.9875 | 18819704.5734
Drury | Drury_56 | 56 | Burberry Rd north connection to Auranga Precinct | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 12735878.3531 | 2% | 9% | 9% | 254717.5671 | 1146229.0518 | 1146229.0518 | 1400946.6188 | 13882107.4049 | 15283054.0237
Drury | Drury_57 | 57 | New access road to Drury West Station | 2-lane urban- new road layout with active modes on both sides, (TDM) | 0 | 2% | 9% | 9% | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_58 | 58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | 33903159.8833 | 2% | 9% | 9% | 678063.1977 | 3051284.3895 | 3051284.3895 | 3729347.5872 | 36954444.2728 | 40683791.8599
Drury | Drury_59 | 59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | 4635273.7264 | 2% | 9% | 9% | 92705.4745 | 417174.6354 | 417174.6354 | 509880.1099 | 5052448.3618 | 5562328.4717
Drury | Drury_60a | 60a | SH22 Intersection upgrade - Oira Rd (3 leg) | Interim Roundabout | 4635273.7264 | 2% | 9% | 9% | 92705.4745 | 417174.6354 | 417174.6354 | 509880.1099 | 5052448.3618 | 5562328.4717
Drury | Drury_60b | 60b | SH22 Intersection upgrade - Oira Rd (4 leg) | Ultimate intersection form | 2317636.8632 | 2% | 9% | 9% | 46352.7373 | 208587.3177 | 208587.3177 | 254940.055 | 2526224.1809 | 2781164.2358
Drury | Drury_63 | 63 | New collectors internal to Waipupuke PC61 (3 links )+ Intersections | 2-lane urban - new collector with active mode on both sides + intersection improvements (TDM) | 39154678.247 | 2% | 9% | 9% | 783093.5649 | 3523921.0422 | 3523921.0422 | 4307014.6072 | 42678599.2892 | 46985613.8963
Drury | Drury_65a(i) | 65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | 13739591.2389 | 2% | 9% | 9% | 274791.8248 | 1236563.2115 | 1236563.2115 | 1511355.0363 | 14976154.4504 | 16487509.4867
Drury | Drury_65a(ii) | 65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | 4066898.9233 | 2% | 9% | 9% | 81337.9785 | 366020.9031 | 366020.9031 | 447358.8816 | 4432919.8263 | 4880278.7079
Drury | Drury_65b(i) | 65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 6025855.8443 | 2% | 9% | 9% | 120517.1169 | 542327.026 | 542327.026 | 662844.1429 | 6568182.8703 | 7231027.0131
Drury | Drury_65b(ii) | 65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 1501828.6873 | 2% | 9% | 9% | 30036.5737 | 135164.5819 | 135164.5819 | 165201.1556 | 1636993.2692 | 1802194.4248
Drury | Drury_66 | 66 | SH22 improvements - west of SH1 interchange to GSR | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 25022801.6365 | 2% | 9% | 9% | 500456.0327 | 2252052.1473 | 2252052.1473 | 2752508.18 | 27274853.7838 | 30027361.9638
Drury | Drury_67 | 67 | Active Mode Corridor Drury Central to GSR | 0 | 20617808.3995 | 2% | 9% | 9% | 412356.168 | 1855602.756 | 1855602.756 | 2267958.9239 | 22473411.1555 | 24741370.0794
Drury | Drury_68 | 68 | Active Mode Corridor GSR to Drury West | 0 | 12697138.7033 | 2% | 9% | 9% | 253942.7741 | 1142742.4833 | 1142742.4833 | 1396685.2574 | 13839881.1865 | 15236566.4439
Drury | Drury_69 | 69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | 3518826.436 | 2% | 9% | 9% | 70376.5287 | 316694.3792 | 316694.3792 | 387070.908 | 3835520.8153 | 4222591.7233
Drury | Drury_70 | 70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | 3187672.1209 | 2% | 9% | 9% | 63753.4424 | 286890.4909 | 286890.4909 | 350643.9333 | 3474562.6118 | 3825206.5451

## Con4_Contigency
Con4_Contigency
Applies Contigency and Risk assumptions from I1 Assumptions
Costs Inclusive of Contigency
Location | Project ID | Project number | Project name | Project Description | Contigency | Funding Risk | Total Contigency to apply | Total Pre-implementation Costs ($m) | Total PW +Implement Costs $m | Total Physical works unescalated
Drury | Drury_1a | 1a | GSR improvements - Waihoehoe Rd to Drury Interchange | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 50% | 0% | 1.5 | 611856.1319 | 6062938.0341 | 6674794.166
Drury | Drury_1b | 1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 50% | 0% | 1.5 | 2407016.1748 | 23851342.0954 | 26258358.2701
Drury | Drury_2a | 2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 50% | 0% | 1.5 | 713977.7262 | 7074870.1965 | 7788847.9227
Drury | Drury_2b | 2b | GSR improvements - From Drury School to Waihoehoe Rd | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_3 | 3 | Intersection upgrade on GSR/Karaka Rd intersection | Intersection upgrades- existing intersection with active modes crossings (TDM) | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_4a | 4a | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | 50% | 0% | 1.5 | 1112354.4478 | 11022421.346 | 12134775.7938
Drury | Drury_4b | 4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | 50% | 0% | 1.5 | 3015861.9777 | 29884450.5066 | 32900312.4844
Drury | Drury_4 | 4 | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Construct Ultimate 24m Cross section initially (i.e. no interim stage) | 50% | 0% | 1.5 | 3778622.2088 | 37442710.9777 | 41221333.1865
Drury | Drury_5 | 5 | Drury Central Station | Not feasible without access. Refer to item 6 below | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_6 | 6 | Drury Station Connection+ intersection | NZUP tbc | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_7 | 7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | 50% | 0% | 1.5 | 741569.6318 | 7348280.8973 | 8089850.5292
Drury | Drury_8 | 8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | 50% | 0% | 1.5 | 741569.6318 | 7348280.8973 | 8089850.5292
Drury | Drury_9a | 9a | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | 2-lane signalised intersection with active mode crossings | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_9b | 9b | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | multi-lane signalised intersection with active mode crossings, SGA design | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_10a | 10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | 50% | 0% | 1.5 | 611856.1319 | 6062938.0341 | 6674794.166
Drury | Drury_10b | 10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | 50% | 0% | 1.5 | 788529.59 | 7813611.3914 | 8602140.9814
Drury | Drury_11 | 11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | 50% | 0% | 1.5 | 764820.1649 | 7578672.5426 | 8343492.7075
Drury | Drury_12 | 12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | 50% | 0% | 1.5 | 1915018.4696 | 18976092.1083 | 20891110.5779
Drury | Drury_13a | 13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | 50% | 0% | 1.5 | 2470553.2308 | 24480936.5595 | 26951489.7903
Drury | Drury_13b | 13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | 50% | 0% | 1.5 | 1453158.3132 | 14399477.831 | 15852636.1442
Drury | Drury_14 | 14 | Upgrade Brookefield Road from Fitzgerald to Quarry Rd+ New connection + Intersections on Quarry & Fitzgerald | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements + new connection to Quarry Rd) | 50% | 0% | 1.5 | 4651233.8045 | 46089498.6078 | 50740732.4123
Drury | Drury_14a | 14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | 50% | 0% | 1.5 | 2382360.7825 | 23607029.5724 | 25989390.355
Drury | Drury_14b | 14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | 50% | 0% | 1.5 | 2268873.0219 | 22482469.0354 | 24751342.0573
Drury | Drury_15 | 15 | New Collector road E-W from Fitgerald Rd (collector 1) + Intersections | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 50% | 0% | 1.5 | 3356209.0862 | 33256980.9451 | 36613190.0313
Drury | Drury_16a | 16a | Replace 2-lane Bremner Road Bridge over State Highway 1 | 2-lane urban with active modes on both sides (replacing existing bridge as part of SH1 P2D NZUP) | 50% | 0% | 1.5 | 1799455.0967 | 17830964.1401 | 19630419.2368
Drury | Drury_16b | 16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | 50% | 0% | 1.5 | 1299888.3522 | 12880711.8534 | 14180600.2056
Drury | Drury_17 | 17 | Oira Road to Jesmond Road Collector | New 2-lane urban collector with active modes on both sides | 50% | 0% | 1.5 | 1922764.8818 | 19052852.0109 | 20975616.8928
Drury | Drury_19-1 | 19-1 | SH1 3-laning and cycleway upgrades from Papakura to Drury Interchange | NZUP tbc | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_19-2 | 19-2 | SH1 Drury Interchange including ramps | NZUP tbc | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_19-3 | 19-3 | SH1 3-laning and cycleway upgrades from Drury Interchange To Drury South | NZUP tbc | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_20a | 20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 50% | 0% | 1.5 | 2965360.7432 | 29384029.1823 | 32349389.9254
Drury | Drury_21 | 21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 50% | 0% | 1.5 | 420222.7914 | 4164025.8418 | 4584248.6332
Drury | Drury_22 | 22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | 50% | 0% | 1.5 | 611856.1319 | 6062938.0341 | 6674794.166
Drury | Drury_23a | 23a | Waihoehoe Rd West upgrades- between GSR & Kath Henry | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_23b | 23b | Waihoehoe Rd West upgrades- between GSR & Kath Henry Lane | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_23c | 23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | 50% | 0% | 1.5 | 346750.3763 | 3435981.0018 | 3782731.3781
Drury | Drury_23d | 23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | 50% | 0% | 1.5 | 1137318.1779 | 11269789.2178 | 12407107.3957
Drury | Drury_23 | 23 | Waihoehoe Rd West upgrades- between GSR & Fitzgerald Rd, including bridge replacement over the rail corridor | 4-lane urban- upgrade 2-lane with active modes on both sides, SGA design | 50% | 0% | 1.5 | 4832558.0347 | 47886256.8896 | 52718814.9243
Drury | Drury_24 | 24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | 50% | 0% | 1.5 | 4618316.0329 | 45763313.4172 | 50381629.4501
Drury | Drury_25 | 25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | 50% | 0% | 1.5 | 1174151.9171 | 11634778.0874 | 12808930.0045
Drury | Drury_27a | 27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 50% | 0% | 1.5 | 1224171.1559 | 12130423.2717 | 13354594.4276
Drury | Drury_27b | 27b | Upgrade from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | 4-lane urban- upgrade existing road layout with active modes on both sides + intersection upgrades (TDM) | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_28 | 28 | New collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 50% | 0% | 1.5 | 3683076.3561 | 36495938.4373 | 40179014.7933
Drury | Drury_28a | 28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | 50% | 0% | 1.5 | 1143184.0451 | 11327914.6283 | 12471098.6734
Drury | Drury_29 | 29 | New collector in E-W direction between Flanagan & Fitzgerald Rd (collector 2) | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 50% | 0% | 1.5 | 2398787.1826 | 23769800.264 | 26168587.4466
Drury | Drury_30 | 30 | 2-lane internal collector between Fitzgerald & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 50% | 0% | 1.5 | 5644205.1355 | 55928941.7976 | 61573146.9332
Drury | Drury_30.1 | 30.1 | 2-lane internal collector between Fitzgerald & Fielding Road E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 50% | 0% | 1.5 | 1834366.6691 | 18176906.0842 | 20011272.7533
Drury | Drury_30.2 | 30.2 | 2-lane internal collector between Fielding Road & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 50% | 0% | 1.5 | 3809838.4665 | 37752035.7134 | 41561874.1799
Drury | Drury_31 | 31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | 50% | 0% | 1.5 | 1149432.9294 | 11389835.3909 | 12539268.3202
Drury | Drury_32 | 32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | 50% | 0% | 1.5 | 764820.1649 | 7578672.5426 | 8343492.7075
Drury | Drury_33 | 33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | 50% | 0% | 1.5 | 469660.7668 | 4653911.235 | 5123572.0018
Drury | Drury_34 | 34 | New Drury Interchange connection to Kiwi development | 2-lane urban- new road layout with active modes on both sides (TDM) | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_35a | 35a | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 2-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_35b | 35b | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 4-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_36 | 36 | Complete Bremner-Norrie Road connection from SH1 upto GSR (overlap with project 12) | 4-lane urban- upgrade with active modes on both sides (SGA design) | 50% | 0% | 1.5 | 8499950.8962 | 84226786.1532 | 92726737.0494
Drury | Drury_36a | 36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | 50% | 0% | 1.5 | 2840088.9761 | 28142699.8539 | 30982788.83
Drury | Drury_36b | 36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | 50% | 0% | 1.5 | 2825918.7307 | 28002285.6043 | 30828204.335
Drury | Drury_36c | 36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | 50% | 0% | 1.5 | 2973620.8009 | 29465878.8457 | 32439499.6467
Drury | Drury_37a(i) | 37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | 50% | 0% | 1.5 | 5358194.3786 | 53094835.2063 | 58453029.5849
Drury | Drury_37a(ii) | 37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | 50% | 0% | 1.5 | 5883965.9315 | 58304753.321 | 64188719.2524
Drury | Drury_37b(i) | 37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | 50% | 0% | 1.5 | 2651015.5944 | 26269154.5265 | 28920170.1209
Drury | Drury_37b(ii) | 37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | 50% | 0% | 1.5 | 3429751.4253 | 33985718.6687 | 37415470.094
Drury | Drury_38a | 38a | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_38b | 38b | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_18a | 18a | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_18b | 18b | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_39a | 39a | New Bremner Rd arterial from SH1 to Auranga development | 2-lane urban- new road layout with active modes on both sides (Under construction) | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_39b | 39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | 50% | 0% | 1.5 | 948377.0044 | 9397553.9529 | 10345930.9573
Drury | Drury_39c | 39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | 50% | 0% | 1.5 | 660804.6224 | 6547973.0768 | 7208777.6993
Drury | Drury_40a | 40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | 50% | 0% | 1.5 | 1242663.5599 | 12313666.1843 | 13556329.7442
Drury | Drury_40b | 40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | 50% | 0% | 1.5 | 611856.1319 | 6062938.0341 | 6674794.166
Drury | Drury_41a | 41a | Jesmond Rd upgrades from SH22 to Waipupuke development boundary | 2-lane urban- upgrade existing road with active modes on both sides (TDM) | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_41b | 41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 50% | 0% | 1.5 | 1758168.595 | 17421852.441 | 19180021.036
Drury | Drury_42a | 42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | 50% | 0% | 1.5 | 482020.2607 | 4776382.5833 | 5258402.844
Drury | Drury_42b | 42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | 50% | 0% | 1.5 | 2438628.6306 | 24164592.7943 | 26603221.425
Drury | Drury_42c | 42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 50% | 0% | 1.5 | 1193119.4572 | 11822729.1665 | 13015848.6237
Drury | Drury_43a | 43a | Intersection upgrade on Jesmond Rd/SH22 Rd | 2-lane intersection (Intersection upgrade + active mode crossings) | 50% | 0% | 1.5 | 1376676.2967 | 13641610.5767 | 15018286.8735
Drury | Drury_43b | 43b | Intersection upgrade on Jesmond Rd/SH22 Rd | Multi-lane signalised intersection (Intersection upgrade + active mode crossings) | 50% | 0% | 1.5 | 611856.1319 | 6062938.0341 | 6674794.166
Drury | Drury_44 | 44 | Intersection at SH22/Burberry Rd (likely to close entirely) | Interim design and likely to close - subject to Auranga assessment | 50% | 0% | 1.5 | 611856.1319 | 6062938.0341 | 6674794.166
Drury | Drury_45 | 45 | Upgrade intersection at SH22/Victoria Rd | subject to Auranga assessment | 50% | 0% | 1.5 | 611856.1319 | 6062938.0341 | 6674794.166
Drury | Drury_46 | 46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | 50% | 0% | 1.5 | 611856.1319 | 6062938.0341 | 6674794.166
Drury | Drury_47 | 47 | Old Bremner Road Upgrade from Jesmond Road to Auranga Precinct | 2-lane urban- new road layout with active modes on both sides (Under construction) | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_48 | 48 | Collector road south of New Bremner/ Old Bremner intersection | 2-lane urban- new road layout with active modes on both sides (Under construction) | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_49 | 49 | SH22 improvements from GSR Intersection to Jesmond Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 50% | 0% | 1.5 | 4345189.3304 | 43056876.0918 | 47402065.4222
Drury | Drury_50a | 50a | SH22 improvements from Jesmond Rd to Oira Rd- active mode upgrades on the northern section | 2-lane urban- upgrade existing road layout with active modes on northern side only | 50% | 0% | 1.5 | 106723.98 | 1057537.62 | 1164261.6
Drury | Drury_50b | 50b | SH22 improvements from Jesmond Rd to Oira Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 50% | 0% | 1.5 | 3140952.0618 | 31123979.5215 | 34264931.5833
Drury | Drury_51 | 51 | SH22 improvements from Oira Rd to Oira Creek - subject to design, could be incorporated with project 60 | Upgrade road layout to future urban boundary + active modes on both sides | 50% | 0% | 1.5 | 2527929.2248 | 25049480.5002 | 27577409.725
Drury | Drury_52 | 52 | Intersection upgrade- on SH22/ McPherson Rd/Karaka Rd (Auranga B1) | Ultimate intersection form | 50% | 0% | 1.5 | 611856.1319 | 6062938.0341 | 6674794.166
Drury | Drury_53 | 53 | New intersection east of Jesmond Rd (Auranga B1 main street) | Ultimate intersection form (left-in left-out) | 50% | 0% | 1.5 | 552294.9155 | 5472740.5264 | 6025035.4419
Drury | Drury_54 | 54 | New N-S collectors internal to Auranga B1 (2 links )+ Intersections | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 50% | 0% | 1.5 | 4076891.7257 | 40398290.7365 | 44475182.4622
Drury | Drury_55 | 55 | New E-W collector Jesmond Rd to SH22 | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 50% | 0% | 1.5 | 3145597.8783 | 31170015.3399 | 34315613.2183
Drury | Drury_55a | 55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 50% | 0% | 1.5 | 2587709.3788 | 25641847.4813 | 28229556.8601
Drury | Drury_56 | 56 | Burberry Rd north connection to Auranga Precinct | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 50% | 0% | 1.5 | 2101419.9283 | 20823161.1074 | 22924581.0356
Drury | Drury_57 | 57 | New access road to Drury West Station | 2-lane urban- new road layout with active modes on both sides, (TDM) | 50% | 0% | 1.5 | 0 | 0 | 0
Drury | Drury_58 | 58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | 50% | 0% | 1.5 | 5594021.3807 | 55431666.4091 | 61025687.7899
Drury | Drury_59 | 59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | 50% | 0% | 1.5 | 764820.1649 | 7578672.5426 | 8343492.7075
Drury | Drury_60a | 60a | SH22 Intersection upgrade - Oira Rd (3 leg) | Interim Roundabout | 50% | 0% | 1.5 | 764820.1649 | 7578672.5426 | 8343492.7075
Drury | Drury_60b | 60b | SH22 Intersection upgrade - Oira Rd (4 leg) | Ultimate intersection form | 50% | 0% | 1.5 | 382410.0824 | 3789336.2713 | 4171746.3537
Drury | Drury_63 | 63 | New collectors internal to Waipupuke PC61 (3 links )+ Intersections | 2-lane urban - new collector with active mode on both sides + intersection improvements (TDM) | 50% | 0% | 1.5 | 6460521.9107 | 64017898.9338 | 70478420.8445
Drury | Drury_65a(i) | 65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | 50% | 0% | 1.5 | 2267032.5544 | 22464231.6756 | 24731264.23
Drury | Drury_65a(ii) | 65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | 50% | 0% | 1.5 | 671038.3223 | 6649379.7395 | 7320418.0619
Drury | Drury_65b(i) | 65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 50% | 0% | 1.5 | 994266.2143 | 9852274.3054 | 10846540.5197
Drury | Drury_65b(ii) | 65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 50% | 0% | 1.5 | 247801.7334 | 2455489.9038 | 2703291.6372
Drury | Drury_66 | 66 | SH22 improvements - west of SH1 interchange to GSR | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 50% | 0% | 1.5 | 4128762.27 | 40912280.6757 | 45041042.9458
Drury | Drury_67 | 67 | Active Mode Corridor Drury Central to GSR | 0 | 50% | 0% | 1.5 | 3401938.3859 | 33710116.7332 | 37112055.1191
Drury | Drury_68 | 68 | Active Mode Corridor GSR to Drury West | 0 | 50% | 0% | 1.5 | 2095027.886 | 20759821.7798 | 22854849.6659
Drury | Drury_69 | 69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | 50% | 0% | 1.5 | 580606.3619 | 5753281.2229 | 6333887.5849
Drury | Drury_70 | 70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | 50% | 0% | 1.5 | 525965.9 | 5211843.9177 | 5737809.8177

## Con5_UnescalatedConst
Con5_UnescalatedConst
Spreads the cost over time based on project construction date on
Location | Project ID | Project number | Project name | Project Description | Preimp_year | Preimp Costs | Construction year | Duration | Construction costs | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | Total project Cost | Total within 30 years
Drury | Drury_1a | 1a | GSR improvements - Waihoehoe Rd to Drury Interchange | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 2023 | 611856.1319 | 2024 |  | 6062938.0341 | 0 | 611856.1319 | 6062938.0341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6674794.166 | 6062938.0341
Drury | Drury_1b | 1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 2030 | 2407016.1748 | 2031 |  | 23851342.0954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2407016.1748 | 23851342.0954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26258358.2701 | 26258358.2701
Drury | Drury_2a | 2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 2029 | 713977.7262 | 2030 |  | 7074870.1965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 713977.7262 | 7074870.1965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7788847.9227 | 7788847.9227
Drury | Drury_2b | 2b | GSR improvements - From Drury School to Waihoehoe Rd | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 2039 | 0 | 2040 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_3 | 3 | Intersection upgrade on GSR/Karaka Rd intersection | Intersection upgrades- existing intersection with active modes crossings (TDM) | 2025 | 0 | 2026 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_4a | 4a | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section |  | 1112354.4478 | 0 |  | 11022421.346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_4b | 4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | 2028 | 3015861.9777 | 2029 |  | 29884450.5066 | 0 | 0 | 0 | 0 | 0 | 0 | 3015861.9777 | 29884450.5066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32900312.4844 | 32900312.4844
Drury | Drury_4 | 4 | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Construct Ultimate 24m Cross section initially (i.e. no interim stage) |  | 3778622.2088 | 0 |  | 37442710.9777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_5 | 5 | Drury Central Station | Not feasible without access. Refer to item 6 below | 2023 | 0 | 2024 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_6 | 6 | Drury Station Connection+ intersection | NZUP tbc | 2023 | 0 | 2024 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_7 | 7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | 2035 | 741569.6318 | 2036 |  | 7348280.8973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 741569.6318 | 7348280.8973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8089850.5292 | 8089850.5292
Drury | Drury_8 | 8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | 2035 | 741569.6318 | 2036 |  | 7348280.8973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 741569.6318 | 7348280.8973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8089850.5292 | 8089850.5292
Drury | Drury_9a | 9a | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | 2-lane signalised intersection with active mode crossings | 2025 | 0 | 2026 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_9b | 9b | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | multi-lane signalised intersection with active mode crossings, SGA design | 2030 | 0 | 2031 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_10a | 10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | 2028 | 611856.1319 | 2029 |  | 6062938.0341 | 0 | 0 | 0 | 0 | 0 | 0 | 611856.1319 | 6062938.0341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6674794.166 | 6674794.166
Drury | Drury_10b | 10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | 2036 | 788529.59 | 2037 |  | 7813611.3914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 788529.59 | 7813611.3914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8602140.9814 | 8602140.9814
Drury | Drury_11 | 11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | 2036 | 764820.1649 | 2037 |  | 7578672.5426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 764820.1649 | 7578672.5426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8343492.7075 | 8343492.7075
Drury | Drury_12 | 12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | 2035 | 1915018.4696 | 2036 |  | 18976092.1083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1915018.4696 | 18976092.1083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20891110.5779 | 20891110.5779
Drury | Drury_13a | 13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | 2036 | 2470553.2308 | 2037 |  | 24480936.5595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2470553.2308 | 24480936.5595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26951489.7903 | 26951489.7903
Drury | Drury_13b | 13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | 2049 | 1453158.3132 | 2050 |  | 14399477.831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1453158.3132 | 14399477.831 | 0 | 0 | 0 | 0 | 0 | 15852636.1442 | 15852636.1442
Drury | Drury_14 | 14 | Upgrade Brookefield Road from Fitzgerald to Quarry Rd+ New connection + Intersections on Quarry & Fitzgerald | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements + new connection to Quarry Rd) |  | 4651233.8045 | 0 |  | 46089498.6078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_14a | 14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | 2036 | 2382360.7825 | 2037 |  | 23607029.5724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2382360.7825 | 23607029.5724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25989390.355 | 25989390.355
Drury | Drury_14b | 14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | 2035 | 2268873.0219 | 2036 |  | 22482469.0354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2268873.0219 | 22482469.0354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24751342.0573 | 24751342.0573
Drury | Drury_15 | 15 | New Collector road E-W from Fitgerald Rd (collector 1) + Intersections | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 2032 | 3356209.0862 | 2033 |  | 33256980.9451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3356209.0862 | 33256980.9451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36613190.0313 | 36613190.0313
Drury | Drury_16a | 16a | Replace 2-lane Bremner Road Bridge over State Highway 1 | 2-lane urban with active modes on both sides (replacing existing bridge as part of SH1 P2D NZUP) | 2032 | 1799455.0967 | 2033 |  | 17830964.1401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1799455.0967 | 17830964.1401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19630419.2368 | 19630419.2368
Drury | Drury_16b | 16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | 2049 | 1299888.3522 | 2050 |  | 12880711.8534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1299888.3522 | 12880711.8534 | 0 | 0 | 0 | 0 | 0 | 14180600.2056 | 14180600.2056
Drury | Drury_17 | 17 | Oira Road to Jesmond Road Collector | New 2-lane urban collector with active modes on both sides | 2035 | 1922764.8818 | 2036 |  | 19052852.0109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1922764.8818 | 19052852.0109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20975616.8928 | 20975616.8928
Drury | Drury_19-1 | 19-1 | SH1 3-laning and cycleway upgrades from Papakura to Drury Interchange | NZUP tbc |  | 0 | Under Construction |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_19-2 | 19-2 | SH1 Drury Interchange including ramps | NZUP tbc |  | 0 | Under Construction |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_19-3 | 19-3 | SH1 3-laning and cycleway upgrades from Drury Interchange To Drury South | NZUP tbc | 2035 | 0 | 2036 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_20a | 20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 2035 | 2965360.7432 | 2036 |  | 29384029.1823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2965360.7432 | 29384029.1823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32349389.9254 | 32349389.9254
Drury | Drury_21 | 21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 2034 | 420222.7914 | 2035 |  | 4164025.8418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420222.7914 | 4164025.8418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4584248.6332 | 4584248.6332
Drury | Drury_22 | 22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | 2035 | 611856.1319 | 2036 |  | 6062938.0341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 611856.1319 | 6062938.0341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6674794.166 | 6674794.166
Drury | Drury_23a | 23a | Waihoehoe Rd West upgrades- between GSR & Kath Henry | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | 2024 | 0 | 2025 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_23b | 23b | Waihoehoe Rd West upgrades- between GSR & Kath Henry Lane | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | 2030 | 0 | 2031 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_23c | 23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | 2024 | 346750.3763 | 2025 |  | 3435981.0018 | 0 | 0 | 346750.3763 | 3435981.0018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3782731.3781 | 3782731.3781
Drury | Drury_23d | 23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | 2036 | 1137318.1779 | 2037 |  | 11269789.2178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1137318.1779 | 11269789.2178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12407107.3957 | 12407107.3957
Drury | Drury_23 | 23 | Waihoehoe Rd West upgrades- between GSR & Fitzgerald Rd, including bridge replacement over the rail corridor | 4-lane urban- upgrade 2-lane with active modes on both sides, SGA design |  | 4832558.0347 | 0 |  | 47886256.8896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_24 | 24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | 2037 | 4618316.0329 | 2038 |  | 45763313.4172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4618316.0329 | 45763313.4172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50381629.4501 | 50381629.4501
Drury | Drury_25 | 25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | 2038 | 1174151.9171 | 2039 |  | 11634778.0874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174151.9171 | 11634778.0874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12808930.0045 | 12808930.0045
Drury | Drury_27a | 27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 2038 | 1224171.1559 | 2039 |  | 12130423.2717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1224171.1559 | 12130423.2717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13354594.4276 | 13354594.4276
Drury | Drury_27b | 27b | Upgrade from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | 4-lane urban- upgrade existing road layout with active modes on both sides + intersection upgrades (TDM) | 2038 | 0 | 2039 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_28 | 28 | New collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 2034 | 3683076.3561 | 2035 |  | 36495938.4373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3683076.3561 | 36495938.4373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40179014.7933 | 40179014.7933
Drury | Drury_28a | 28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | 2034 | 1143184.0451 | 2035 |  | 11327914.6283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1143184.0451 | 11327914.6283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12471098.6734 | 12471098.6734
Drury | Drury_29 | 29 | New collector in E-W direction between Flanagan & Fitzgerald Rd (collector 2) | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 2034 | 2398787.1826 | 2035 |  | 23769800.264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2398787.1826 | 23769800.264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26168587.4466 | 26168587.4466
Drury | Drury_30 | 30 | 2-lane internal collector between Fitzgerald & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) |  | 5644205.1355 | 0 |  | 55928941.7976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_30.1 | 30.1 | 2-lane internal collector between Fitzgerald & Fielding Road E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 2032 | 1834366.6691 | 2033 |  | 18176906.0842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1834366.6691 | 18176906.0842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20011272.7533 | 20011272.7533
Drury | Drury_30.2 | 30.2 | 2-lane internal collector between Fielding Road & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 2038 | 3809838.4665 | 2039 |  | 37752035.7134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3809838.4665 | 37752035.7134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41561874.1799 | 41561874.1799
Drury | Drury_31 | 31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | 2038 | 1149432.9294 | 2039 |  | 11389835.3909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149432.9294 | 11389835.3909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12539268.3202 | 12539268.3202
Drury | Drury_32 | 32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | 2038 | 764820.1649 | 2039 |  | 7578672.5426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 764820.1649 | 7578672.5426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8343492.7075 | 8343492.7075
Drury | Drury_33 | 33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | 2055 | 469660.7668 | 2056 |  | 4653911.235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469660.7668 | 469660.7668 | 0
Drury | Drury_34 | 34 | New Drury Interchange connection to Kiwi development | 2-lane urban- new road layout with active modes on both sides (TDM) | 2033 | 0 | 2034 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_35a | 35a | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 2-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | 2042 | 0 | 2043 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_35b | 35b | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 4-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | 2049 | 0 | 2050 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_36 | 36 | Complete Bremner-Norrie Road connection from SH1 upto GSR (overlap with project 12) | 4-lane urban- upgrade with active modes on both sides (SGA design) |  | 8499950.8962 | 0 |  | 84226786.1532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_36a | 36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | 2038 | 2840088.9761 | 2039 |  | 28142699.8539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2840088.9761 | 28142699.8539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30982788.83 | 30982788.83
Drury | Drury_36b | 36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | 2049 | 2825918.7307 | 2050 |  | 28002285.6043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2825918.7307 | 28002285.6043 | 0 | 0 | 0 | 0 | 0 | 30828204.335 | 30828204.335
Drury | Drury_36c | 36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | 2049 | 2973620.8009 | 2050 |  | 29465878.8457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2973620.8009 | 29465878.8457 | 0 | 0 | 0 | 0 | 0 | 32439499.6467 | 32439499.6467
Drury | Drury_37a(i) | 37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | 2043 | 5358194.3786 | 2044 |  | 53094835.2063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5358194.3786 | 53094835.2063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58453029.5849 | 58453029.5849
Drury | Drury_37a(ii) | 37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | 2043 | 5883965.9315 | 2044 |  | 58304753.321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5883965.9315 | 58304753.321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64188719.2524 | 64188719.2524
Drury | Drury_37b(i) | 37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | 2048 | 2651015.5944 | 2049 |  | 26269154.5265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2651015.5944 | 26269154.5265 | 0 | 0 | 0 | 0 | 0 | 0 | 28920170.1209 | 28920170.1209
Drury | Drury_37b(ii) | 37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | 2048 | 3429751.4253 | 2049 |  | 33985718.6687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3429751.4253 | 33985718.6687 | 0 | 0 | 0 | 0 | 0 | 0 | 37415470.094 | 37415470.094
Drury | Drury_38a | 38a | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | 2045 | 0 | 2046 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_38b | 38b | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | 2054 | 0 | 2055 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_18a | 18a | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | 2035 | 0 | 2036 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_18b | 18b | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | 2051 | 0 | 2052 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_39a | 39a | New Bremner Rd arterial from SH1 to Auranga development | 2-lane urban- new road layout with active modes on both sides (Under construction) |  | 0 | Under Construction |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_39b | 39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | 2046 | 948377.0044 | 2047 |  | 9397553.9529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948377.0044 | 9397553.9529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10345930.9573 | 10345930.9573
Drury | Drury_39c | 39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | 2046 | 660804.6224 | 2047 |  | 6547973.0768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660804.6224 | 6547973.0768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7208777.6993 | 7208777.6993
Drury | Drury_40a | 40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | 2036 | 1242663.5599 | 2037 |  | 12313666.1843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1242663.5599 | 12313666.1843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13556329.7442 | 13556329.7442
Drury | Drury_40b | 40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | 2030 | 611856.1319 | 2031 |  | 6062938.0341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 611856.1319 | 6062938.0341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6674794.166 | 6674794.166
Drury | Drury_41a | 41a | Jesmond Rd upgrades from SH22 to Waipupuke development boundary | 2-lane urban- upgrade existing road with active modes on both sides (TDM) | 2026 | 0 | 2027 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_41b | 41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 2046 | 1758168.595 | 2047 |  | 17421852.441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1758168.595 | 17421852.441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19180021.036 | 19180021.036
Drury | Drury_42a | 42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | 2027 | 482020.2607 | 2028 |  | 4776382.5833 | 0 | 0 | 0 | 0 | 0 | 482020.2607 | 4776382.5833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5258402.844 | 5258402.844
Drury | Drury_42b | 42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | 2037 | 2438628.6306 | 2038 |  | 24164592.7943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2438628.6306 | 24164592.7943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26603221.425 | 26603221.425
Drury | Drury_42c | 42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 2046 | 1193119.4572 | 2047 |  | 11822729.1665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1193119.4572 | 11822729.1665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13015848.6237 | 13015848.6237
Drury | Drury_43a | 43a | Intersection upgrade on Jesmond Rd/SH22 Rd | 2-lane intersection (Intersection upgrade + active mode crossings) |  | 1376676.2967 | 0 |  | 13641610.5767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_43b | 43b | Intersection upgrade on Jesmond Rd/SH22 Rd | Multi-lane signalised intersection (Intersection upgrade + active mode crossings) | 2023 | 611856.1319 | 2024 |  | 6062938.0341 | 0 | 611856.1319 | 6062938.0341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6674794.166 | 6062938.0341
Drury | Drury_44 | 44 | Intersection at SH22/Burberry Rd (likely to close entirely) | Interim design and likely to close - subject to Auranga assessment | 2022 | 611856.1319 | 2023 |  | 6062938.0341 | 611856.1319 | 6062938.0341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6062938.0341 | 0
Drury | Drury_45 | 45 | Upgrade intersection at SH22/Victoria Rd | subject to Auranga assessment | 2023 | 611856.1319 | 2024 |  | 6062938.0341 | 0 | 611856.1319 | 6062938.0341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6674794.166 | 6062938.0341
Drury | Drury_46 | 46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | 2034 | 611856.1319 | 2035 |  | 6062938.0341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 611856.1319 | 6062938.0341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6674794.166 | 6674794.166
Drury | Drury_47 | 47 | Old Bremner Road Upgrade from Jesmond Road to Auranga Precinct | 2-lane urban- new road layout with active modes on both sides (Under construction) |  | 0 | Under Construction |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_48 | 48 | Collector road south of New Bremner/ Old Bremner intersection | 2-lane urban- new road layout with active modes on both sides (Under construction) |  | 0 | Under Construction |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_49 | 49 | SH22 improvements from GSR Intersection to Jesmond Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 2031 | 4345189.3304 | 2032 |  | 43056876.0918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4345189.3304 | 43056876.0918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47402065.4222 | 47402065.4222
Drury | Drury_50a | 50a | SH22 improvements from Jesmond Rd to Oira Rd- active mode upgrades on the northern section | 2-lane urban- upgrade existing road layout with active modes on northern side only | 2025 | 106723.98 | 2026 |  | 1057537.62 | 0 | 0 | 0 | 106723.98 | 1057537.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1164261.6 | 1164261.6
Drury | Drury_50b | 50b | SH22 improvements from Jesmond Rd to Oira Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 2031 | 3140952.0618 | 2032 |  | 31123979.5215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3140952.0618 | 31123979.5215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34264931.5833 | 34264931.5833
Drury | Drury_51 | 51 | SH22 improvements from Oira Rd to Oira Creek - subject to design, could be incorporated with project 60 | Upgrade road layout to future urban boundary + active modes on both sides | 2036 | 2527929.2248 | 2037 |  | 25049480.5002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2527929.2248 | 25049480.5002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27577409.725 | 27577409.725
Drury | Drury_52 | 52 | Intersection upgrade- on SH22/ McPherson Rd/Karaka Rd (Auranga B1) | Ultimate intersection form | 2023 | 611856.1319 | 2024 |  | 6062938.0341 | 0 | 611856.1319 | 6062938.0341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6674794.166 | 6062938.0341
Drury | Drury_53 | 53 | New intersection east of Jesmond Rd (Auranga B1 main street) | Ultimate intersection form (left-in left-out) | 2023 | 552294.9155 | 2024 |  | 5472740.5264 | 0 | 552294.9155 | 5472740.5264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6025035.4419 | 5472740.5264
Drury | Drury_54 | 54 | New N-S collectors internal to Auranga B1 (2 links )+ Intersections | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 2024 | 4076891.7257 | 2025 |  | 40398290.7365 | 0 | 0 | 4076891.7257 | 40398290.7365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44475182.4622 | 44475182.4622
Drury | Drury_55 | 55 | New E-W collector Jesmond Rd to SH22 | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) |  | 3145597.8783 | 0 |  | 31170015.3399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_55a | 55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 2036 | 2587709.3788 | 2037 |  | 25641847.4813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2587709.3788 | 25641847.4813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28229556.8601 | 28229556.8601
Drury | Drury_56 | 56 | Burberry Rd north connection to Auranga Precinct | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) |  | 0 | Under construction |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_57 | 57 | New access road to Drury West Station | 2-lane urban- new road layout with active modes on both sides, (TDM) | 2025 | 0 | 2026 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_58 | 58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | 2035 | 5594021.3807 | 2036 |  | 55431666.4091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5594021.3807 | 55431666.4091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61025687.7899 | 61025687.7899
Drury | Drury_59 | 59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | 2037 | 764820.1649 | 2038 |  | 7578672.5426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 764820.1649 | 7578672.5426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8343492.7075 | 8343492.7075
Drury | Drury_60a | 60a | SH22 Intersection upgrade - Oira Rd (3 leg) | Interim Roundabout | 2025 | 764820.1649 | 2026 |  | 7578672.5426 | 0 | 0 | 0 | 764820.1649 | 7578672.5426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8343492.7075 | 8343492.7075
Drury | Drury_60b | 60b | SH22 Intersection upgrade - Oira Rd (4 leg) | Ultimate intersection form | 2036 | 382410.0824 | 2037 |  | 3789336.2713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 382410.0824 | 3789336.2713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4171746.3537 | 4171746.3537
Drury | Drury_63 | 63 | New collectors internal to Waipupuke PC61 (3 links )+ Intersections | 2-lane urban - new collector with active mode on both sides + intersection improvements (TDM) | 2025 | 6460521.9107 | 2026 |  | 64017898.9338 | 0 | 0 | 0 | 6460521.9107 | 64017898.9338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70478420.8445 | 70478420.8445
Drury | Drury_65a(i) | 65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | 2035 | 2267032.5544 | 2036 |  | 22464231.6756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2267032.5544 | 22464231.6756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24731264.23 | 24731264.23
Drury | Drury_65a(ii) | 65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | 2035 | 671038.3223 | 2036 |  | 6649379.7395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671038.3223 | 6649379.7395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7320418.0619 | 7320418.0619
Drury | Drury_65b(i) | 65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 2046 | 994266.2143 | 2047 |  | 9852274.3054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 994266.2143 | 9852274.3054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10846540.5197 | 10846540.5197
Drury | Drury_65b(ii) | 65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 2046 | 247801.7334 | 2047 |  | 2455489.9038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247801.7334 | 2455489.9038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2703291.6372 | 2703291.6372
Drury | Drury_66 | 66 | SH22 improvements - west of SH1 interchange to GSR | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 2031 | 4128762.27 | 2032 |  | 40912280.6757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4128762.27 | 40912280.6757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45041042.9458 | 45041042.9458
Drury | Drury_67 | 67 | Active Mode Corridor Drury Central to GSR | 0 | 2036 | 3401938.3859 | 2037 |  | 33710116.7332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3401938.3859 | 33710116.7332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37112055.1191 | 37112055.1191
Drury | Drury_68 | 68 | Active Mode Corridor GSR to Drury West | 0 | 2036 | 2095027.886 | 2037 |  | 20759821.7798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2095027.886 | 20759821.7798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22854849.6659 | 22854849.6659
Drury | Drury_69 | 69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | 2034 | 580606.3619 | 2035 |  | 5753281.2229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580606.3619 | 5753281.2229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6333887.5849 | 6333887.5849
Drury | Drury_70 | 70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | 2030 | 525965.9 | 2031 |  | 5211843.9177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525965.9 | 5211843.9177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5737809.8177 | 5737809.8177

## Con6_EscalatedConst
Con6_EscalatedConst
Escalates the costs for land price escalation in I2 Escalation factors
|  |  |  | Compunded Construction Escalation Rate from I2 Escalation factors |  |  | 1 | 1 | 1 | 1.0276 | 1.0572 | 1.0887 | 1.1224 | 1.1572 | 1.1931 | 1.2301 | 1.2682 | 1.3076 | 1.3481 | 1.3899 | 1.433 | 1.4774 | 1.5232 | 1.5704 | 1.6191 | 1.6693 | 1.721 | 1.7744 | 1.8294 | 1.8861 | 1.9446 | 2.0048 | 2.067 | 2.1311 | 2.1971 | 2.2652 | 2.3355 | 2.4079 | 2.4825 | 2.5595
Location | Project ID | Project number | Project name | Project Description | Preimp_year | Construction year | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | Total project Cost | Total within 30 years
Drury | Drury_1a | 1a | GSR improvements - Waihoehoe Rd to Drury Interchange | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 2023 | 2024 | 0 | 611856.1319 | 6062938.0341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6674794.166 | 6062938.0341
Drury | Drury_1b | 1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 2030 | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2871849.4628 | 29339597.3441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32211446.807 | 32211446.807
Drury | Drury_2a | 2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 2029 | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 826244.6506 | 8441140.6897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9267385.3402 | 9267385.3402
Drury | Drury_2b | 2b | GSR improvements - From Drury School to Waihoehoe Rd | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 2039 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_3 | 3 | Intersection upgrade on GSR/Karaka Rd intersection | Intersection upgrades- existing intersection with active modes crossings (TDM) | 2025 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_4a | 4a | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_4b | 4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | 2028 | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 3385141.2421 | 34583526.1501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37968667.3922 | 37968667.3922
Drury | Drury_4 | 4 | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Construct Ultimate 24m Cross section initially (i.e. no interim stage) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_5 | 5 | Drury Central Station | Not feasible without access. Refer to item 6 below | 2023 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_6 | 6 | Drury Station Connection+ intersection | NZUP tbc | 2023 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_7 | 7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | 2035 | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1030689.6753 | 10529806.8196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560496.4949 | 11560496.4949
Drury | Drury_8 | 8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | 2035 | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1030689.6753 | 10529806.8196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560496.4949 | 11560496.4949
Drury | Drury_9a | 9a | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | 2-lane signalised intersection with active mode crossings | 2025 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_9b | 9b | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | multi-lane signalised intersection with active mode crossings, SGA design | 2030 | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_10a | 10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | 2028 | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 686775.2707 | 7016283.4683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7703058.739 | 7703058.739
Drury | Drury_10b | 10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | 2036 | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1129932.8877 | 11543702.5442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12673635.4318 | 12673635.4318
Drury | Drury_11 | 11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | 2036 | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1095958.184 | 11196607.7053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12292565.8893 | 12292565.8893
Drury | Drury_12 | 12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | 2035 | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2661637.8016 | 27192017.6819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29853655.4835 | 29853655.4835
Drury | Drury_13a | 13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | 2036 | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3540208.7401 | 36167738.0007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39707946.7409 | 39707946.7409
Drury | Drury_13b | 13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | 2049 | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3096779.1457 | 31637540.329 | 0 | 0 | 0 | 0 | 0 | 34734319.4747 | 34734319.4747
Drury | Drury_14 | 14 | Upgrade Brookefield Road from Fitzgerald to Quarry Rd+ New connection + Intersections on Quarry & Fitzgerald | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements + new connection to Quarry Rd) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_14a | 14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | 2036 | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3413832.3188 | 34876642.0139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38290474.3327 | 38290474.3327
Drury | Drury_14b | 14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | 2035 | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3153451.6757 | 32216522.3511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35369974.0268 | 35369974.0268
Drury | Drury_15 | 15 | New Collector road E-W from Fitgerald Rd (collector 1) + Intersections | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 2032 | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4256464.366 | 43485200.8172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47741665.1833 | 47741665.1833
Drury | Drury_16a | 16a | Replace 2-lane Bremner Road Bridge over State Highway 1 | 2-lane urban with active modes on both sides (replacing existing bridge as part of SH1 P2D NZUP) | 2032 | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2282133.294 | 23314896.132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25597029.426 | 25597029.426
Drury | Drury_16b | 16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | 2049 | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2770150.4401 | 28300612.3911 | 0 | 0 | 0 | 0 | 0 | 31070762.8312 | 31070762.8312
Drury | Drury_17 | 17 | Oira Road to Jesmond Road Collector | New 2-lane urban collector with active modes on both sides | 2035 | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2672404.3523 | 27302011.7006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29974416.0529 | 29974416.0529
Drury | Drury_19-1 | 19-1 | SH1 3-laning and cycleway upgrades from Papakura to Drury Interchange | NZUP tbc |  | Under Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_19-2 | 19-2 | SH1 Drury Interchange including ramps | NZUP tbc |  | Under Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_19-3 | 19-3 | SH1 3-laning and cycleway upgrades from Drury Interchange To Drury South | NZUP tbc | 2035 | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_20a | 20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 2035 | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4121483.095 | 42106195.3394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46227678.4344 | 46227678.4344
Drury | Drury_21 | 21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 2034 | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 566496.1034 | 5787478.6917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6353974.7951 | 6353974.7951
Drury | Drury_22 | 22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | 2035 | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850404.0225 | 8687959.4221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9538363.4446 | 9538363.4446
Drury | Drury_23a | 23a | Waihoehoe Rd West upgrades- between GSR & Kath Henry | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | 2024 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_23b | 23b | Waihoehoe Rd West upgrades- between GSR & Kath Henry Lane | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | 2030 | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_23c | 23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | 2024 | 2025 | 0 | 0 | 346750.3763 | 3530961.054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3877711.4303 | 3877711.4303
Drury | Drury_23d | 23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | 2036 | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629733.6579 | 16649803.5221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18279537.18 | 18279537.18
Drury | Drury_23 | 23 | Waihoehoe Rd West upgrades- between GSR & Fitzgerald Rd, including bridge replacement over the rail corridor | 4-lane urban- upgrade 2-lane with active modes on both sides, SGA design |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_24 | 24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | 2037 | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6823025.0864 | 69705885.1074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76528910.1938 | 76528910.1938
Drury | Drury_25 | 25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | 2038 | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1788447.8312 | 18271270.8023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20059718.6335 | 20059718.6335
Drury | Drury_27a | 27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 2038 | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1864636.268 | 19049632.6512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20914268.9192 | 20914268.9192
Drury | Drury_27b | 27b | Upgrade from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | 4-lane urban- upgrade existing road layout with active modes on both sides + intersection upgrades (TDM) | 2038 | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_28 | 28 | New collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 2034 | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4965100.5305 | 50724821.1376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55689921.6681 | 55689921.6681
Drury | Drury_28a | 28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | 2034 | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1541109.4313 | 15744394.2529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17285503.6842 | 17285503.6842
Drury | Drury_29 | 29 | New collector in E-W direction between Flanagan & Fitzgerald Rd (collector 2) | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 2034 | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3233769.3714 | 33037069.8356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36270839.207 | 36270839.207
Drury | Drury_30 | 30 | 2-lane internal collector between Fitzgerald & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_30.1 | 30.1 | 2-lane internal collector between Fitzgerald & Fielding Road E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 2032 | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2326409.3984 | 23767232.8891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26093642.2874 | 26093642.2874
Drury | Drury_30.2 | 30.2 | 2-lane internal collector between Fielding Road & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 2038 | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5803079.8601 | 59285846.509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65088926.3691 | 65088926.3691
Drury | Drury_31 | 31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | 2038 | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750796.2979 | 17886612.4696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19637408.7676 | 19637408.7676
Drury | Drury_32 | 32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | 2038 | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1164960.8072 | 11901557.323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13066518.1302 | 13066518.1302
Drury | Drury_33 | 33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | 2055 | 2056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1202080.5702 | 1202080.5702 | 0
Drury | Drury_34 | 34 | New Drury Interchange connection to Kiwi development | 2-lane urban- new road layout with active modes on both sides (TDM) | 2033 | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_35a | 35a | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 2-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | 2042 | 2043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_35b | 35b | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 4-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | 2049 | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_36 | 36 | Complete Bremner-Norrie Road connection from SH1 upto GSR (overlap with project 12) | 4-lane urban- upgrade with active modes on both sides (SGA design) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_36a | 36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | 2038 | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4325974.2593 | 44195332.8439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48521307.1031 | 48521307.1031
Drury | Drury_36b | 36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | 2049 | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6022224.9105 | 61524692.1109 | 0 | 0 | 0 | 0 | 0 | 67546917.0215 | 67546917.0215
Drury | Drury_36c | 36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | 2049 | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6336988.0624 | 64740398.3153 | 0 | 0 | 0 | 0 | 0 | 71077386.3777 | 71077386.3777
Drury | Drury_37a(i) | 37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | 2043 | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9507443.9916 | 97130640.757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106638084.7486 | 106638084.7486
Drury | Drury_37a(ii) | 37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | 2043 | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10440359.6788 | 106661561.8495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117101921.5283 | 117101921.5283
Drury | Drury_37b(i) | 37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | 2048 | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5479626.0309 | 55981353.9749 | 0 | 0 | 0 | 0 | 0 | 0 | 61460980.0058 | 61460980.0058
Drury | Drury_37b(ii) | 37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | 2048 | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7089266.1774 | 72425876.705 | 0 | 0 | 0 | 0 | 0 | 0 | 79515142.8824 | 79515142.8824
Drury | Drury_38a | 38a | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | 2045 | 2046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_38b | 38b | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | 2054 | 2055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_18a | 18a | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | 2035 | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_18b | 18b | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | 2051 | 2052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_39a | 39a | New Bremner Rd arterial from SH1 to Auranga development | 2-lane urban- new road layout with active modes on both sides (Under construction) |  | Under Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_39b | 39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | 2046 | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1844175.8141 | 18840603.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20684778.8881 | 20684778.8881
Drury | Drury_39c | 39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | 2046 | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284974.1156 | 13127646.0128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14412620.1285 | 14412620.1285
Drury | Drury_40a | 40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | 2036 | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1780689.5804 | 18192010.3955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19972699.9758 | 19972699.9758
Drury | Drury_40b | 40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | 2030 | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730015.3286 | 7458035.6917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8188051.0203 | 8188051.0203
Drury | Drury_41a | 41a | Jesmond Rd upgrades from SH22 to Waipupuke development boundary | 2-lane urban- upgrade existing road with active modes on both sides (TDM) | 2026 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_41b | 41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 2046 | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3418864.0012 | 34928047.0536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38346911.0548 | 38346911.0548
Drury | Drury_42a | 42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | 2027 | 2028 | 0 | 0 | 0 | 0 | 0 | 524773.5774 | 5361229.9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5886003.5641 | 5886003.5641
Drury | Drury_42b | 42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | 2037 | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3602790.3254 | 36807088.5435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40409878.8689 | 40409878.8689
Drury | Drury_42c | 42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 2046 | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2320092.1532 | 23702694.1898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26022786.3431 | 26022786.3431
Drury | Drury_43a | 43a | Intersection upgrade on Jesmond Rd/SH22 Rd | 2-lane intersection (Intersection upgrade + active mode crossings) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_43b | 43b | Intersection upgrade on Jesmond Rd/SH22 Rd | Multi-lane signalised intersection (Intersection upgrade + active mode crossings) | 2023 | 2024 | 0 | 611856.1319 | 6062938.0341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6674794.166 | 6062938.0341
Drury | Drury_44 | 44 | Intersection at SH22/Burberry Rd (likely to close entirely) | Interim design and likely to close - subject to Auranga assessment | 2022 | 2023 | 611856.1319 | 6062938.0341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6674794.166 | 0
Drury | Drury_45 | 45 | Upgrade intersection at SH22/Victoria Rd | subject to Auranga assessment | 2023 | 2024 | 0 | 611856.1319 | 6062938.0341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6674794.166 | 6062938.0341
Drury | Drury_46 | 46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | 2034 | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824834.1634 | 8426730.7683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9251564.9318 | 9251564.9318
Drury | Drury_47 | 47 | Old Bremner Road Upgrade from Jesmond Road to Auranga Precinct | 2-lane urban- new road layout with active modes on both sides (Under construction) |  | Under Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_48 | 48 | Collector road south of New Bremner/ Old Bremner intersection | 2-lane urban- new road layout with active modes on both sides (Under construction) |  | Under Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_49 | 49 | SH22 improvements from GSR Intersection to Jesmond Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 2031 | 2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5345028.587 | 54606269.7794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59951298.3664 | 59951298.3664
Drury | Drury_50a | 50a | SH22 improvements from Jesmond Rd to Oira Rd- active mode upgrades on the northern section | 2-lane urban- upgrade existing road layout with active modes on northern side only | 2025 | 2026 | 0 | 0 | 0 | 109674.127 | 1117981.189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1227655.3161 | 1227655.3161
Drury | Drury_50b | 50b | SH22 improvements from Jesmond Rd to Oira Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 2031 | 2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3863693.2212 | 39472543.6824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43336236.9036 | 43336236.9036
Drury | Drury_51 | 51 | SH22 improvements from Oira Rd to Oira Creek - subject to design, could be incorporated with project 60 | Upgrade road layout to future urban boundary + active modes on both sides | 2036 | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3622426.3556 | 37007695.5832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40630121.9388 | 40630121.9388
Drury | Drury_52 | 52 | Intersection upgrade- on SH22/ McPherson Rd/Karaka Rd (Auranga B1) | Ultimate intersection form | 2023 | 2024 | 0 | 611856.1319 | 6062938.0341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6674794.166 | 6062938.0341
Drury | Drury_53 | 53 | New intersection east of Jesmond Rd (Auranga B1 main street) | Ultimate intersection form (left-in left-out) | 2023 | 2024 | 0 | 552294.9155 | 5472740.5264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6025035.4419 | 5472740.5264
Drury | Drury_54 | 54 | New N-S collectors internal to Auranga B1 (2 links )+ Intersections | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 2024 | 2025 | 0 | 0 | 4076891.7257 | 41515011.6264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45591903.3522 | 45591903.3522
Drury | Drury_55 | 55 | New E-W collector Jesmond Rd to SH22 | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_55a | 55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 2036 | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3708089.0409 | 37882848.9385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41590937.9794 | 41590937.9794
Drury | Drury_56 | 56 | Burberry Rd north connection to Auranga Precinct | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) |  | Under construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_57 | 57 | New access road to Drury West Station | 2-lane urban- new road layout with active modes on both sides, (TDM) | 2025 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_58 | 58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | 2035 | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7774994.866 | 79431468.0038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87206462.8697 | 87206462.8697
Drury | Drury_59 | 59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | 2037 | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1129932.8877 | 11543702.5442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12673635.4318 | 12673635.4318
Drury | Drury_60a | 60a | SH22 Intersection upgrade - Oira Rd (3 leg) | Interim Roundabout | 2025 | 2026 | 0 | 0 | 0 | 785961.9171 | 8011831.6175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8797793.5346 | 8797793.5346
Drury | Drury_60b | 60b | SH22 Intersection upgrade - Oira Rd (4 leg) | Ultimate intersection form | 2036 | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 547979.092 | 5598303.8526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6146282.9446 | 6146282.9446
Drury | Drury_63 | 63 | New collectors internal to Waipupuke PC61 (3 links )+ Intersections | 2-lane urban - new collector with active mode on both sides + intersection improvements (TDM) | 2025 | 2026 | 0 | 0 | 0 | 6639108.6689 | 67676842.3332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74315951.0021 | 74315951.0021
Drury | Drury_65a(i) | 65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | 2035 | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3150893.6545 | 32190388.9087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35341282.5632 | 35341282.5632
Drury | Drury_65a(ii) | 65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | 2035 | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932659.916 | 9528308.0636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10460967.9796 | 10460967.9796
Drury | Drury_65b(i) | 65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 2046 | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1933410.1277 | 19752245.1582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21685655.2859 | 21685655.2859
Drury | Drury_65b(ii) | 65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 2046 | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 481865.2934 | 4922867.2548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5404732.5482 | 5404732.5482
Drury | Drury_66 | 66 | SH22 improvements - west of SH1 interchange to GSR | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 2031 | 2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5078801.1026 | 51886417.1917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56965218.2943 | 56965218.2943
Drury | Drury_67 | 67 | Active Mode Corridor Drury Central to GSR | 0 | 2036 | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4874848.2151 | 49802778.869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54677627.0841 | 54677627.0841
Drury | Drury_68 | 68 | Active Mode Corridor GSR to Drury West | 0 | 2036 | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3002095.2152 | 30670223.4716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33672318.6868 | 33672318.6868
Drury | Drury_69 | 69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | 2034 | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 782706.8127 | 7996346.2644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8779053.0771 | 8779053.0771
Drury | Drury_70 | 70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | 2030 | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627538.3203 | 6411102.6271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7038640.9474 | 7038640.9474

## Con6_Mitigation
Con6_Mitigation
Subtracts the share of costs to be delivered by developers as mitigation works, or by other third parties
Location | Project ID | Project name | Project Description | % Construction costs to be delivered by AT (through DCs, grants or rates) | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | Total project Cost after mitigation | Total project Cost after mitigation within 30 years | Total Mitigation
Drury | Drury_1a | GSR improvements - Waihoehoe Rd to Drury Interchange | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2871849.4628 | 29339597.3441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32211446.807 | 32211446.807
Drury | Drury_2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 826244.6506 | 8441140.6897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9267385.3402 | 9267385.3402
Drury | Drury_2b | GSR improvements - From Drury School to Waihoehoe Rd | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_3 | Intersection upgrade on GSR/Karaka Rd intersection | Intersection upgrades- existing intersection with active modes crossings (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_4a | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 677028.2484 | 6916705.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7593733.4784 | 7593733.4784
Drury | Drury_4 | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Construct Ultimate 24m Cross section initially (i.e. no interim stage) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_5 | Drury Central Station | Not feasible without access. Refer to item 6 below | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_6 | Drury Station Connection+ intersection | NZUP tbc | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | 5% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51534.4838 | 526490.341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578024.8247 | 578024.8247
Drury | Drury_8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | 5% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51534.4838 | 526490.341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578024.8247 | 578024.8247
Drury | Drury_9a | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | 2-lane signalised intersection with active mode crossings | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_9b | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | multi-lane signalised intersection with active mode crossings, SGA design | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1129932.8877 | 11543702.5442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12673635.4318 | 12673635.4318
Drury | Drury_11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | 10% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109595.8184 | 1119660.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1229256.5889 | 1229256.5889
Drury | Drury_12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2661637.8016 | 27192017.6819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29853655.4835 | 29853655.4835
Drury | Drury_13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | 75% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2322584.3593 | 23728155.2467 | 0 | 0 | 0 | 0 | 0 | 26050739.606 | 26050739.606
Drury | Drury_14 | Upgrade Brookefield Road from Fitzgerald to Quarry Rd+ New connection + Intersections on Quarry & Fitzgerald | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements + new connection to Quarry Rd) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3413832.3188 | 34876642.0139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38290474.3327 | 38290474.3327
Drury | Drury_14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | 10% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315345.1676 | 3221652.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3536997.4027 | 3536997.4027
Drury | Drury_15 | New Collector road E-W from Fitgerald Rd (collector 1) + Intersections | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_16a | Replace 2-lane Bremner Road Bridge over State Highway 1 | 2-lane urban with active modes on both sides (replacing existing bridge as part of SH1 P2D NZUP) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2770150.4401 | 28300612.3911 | 0 | 0 | 0 | 0 | 0 | 31070762.8312 | 31070762.8312
Drury | Drury_17 | Oira Road to Jesmond Road Collector | New 2-lane urban collector with active modes on both sides | 10% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267240.4352 | 2730201.1701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997441.6053 | 2997441.6053
Drury | Drury_19-1 | SH1 3-laning and cycleway upgrades from Papakura to Drury Interchange | NZUP tbc | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_19-2 | SH1 Drury Interchange including ramps | NZUP tbc | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_19-3 | SH1 3-laning and cycleway upgrades from Drury Interchange To Drury South | NZUP tbc | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824296.619 | 8421239.0679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9245535.6869 | 9245535.6869
Drury | Drury_21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 5% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28324.8052 | 289373.9346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317698.7398 | 317698.7398
Drury | Drury_22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850404.0225 | 8687959.4221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9538363.4446 | 9538363.4446
Drury | Drury_23a | Waihoehoe Rd West upgrades- between GSR & Kath Henry | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_23b | Waihoehoe Rd West upgrades- between GSR & Kath Henry Lane | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | 60% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 977840.1947 | 9989882.1132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10967722.308 | 10967722.308
Drury | Drury_23 | Waihoehoe Rd West upgrades- between GSR & Fitzgerald Rd, including bridge replacement over the rail corridor | 4-lane urban- upgrade 2-lane with active modes on both sides, SGA design | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | 15% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1023453.763 | 10455882.7661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11479336.5291 | 11479336.5291
Drury | Drury_25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | 30% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 536534.3494 | 5481381.2407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6017915.5901 | 6017915.5901
Drury | Drury_27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 50% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932318.134 | 9524816.3256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10457134.4596 | 10457134.4596
Drury | Drury_27b | Upgrade from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | 4-lane urban- upgrade existing road layout with active modes on both sides + intersection upgrades (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_28 | New collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1541109.4313 | 15744394.2529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17285503.6842 | 17285503.6842
Drury | Drury_29 | New collector in E-W direction between Flanagan & Fitzgerald Rd (collector 2) | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_30 | 2-lane internal collector between Fitzgerald & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_30.1 | 2-lane internal collector between Fitzgerald & Fielding Road E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_30.2 | 2-lane internal collector between Fielding Road & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | 5% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87539.8149 | 894330.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981870.4384 | 981870.4384
Drury | Drury_32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | 10% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116496.0807 | 1190155.7323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1306651.813 | 1306651.813
Drury | Drury_33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | 5% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60104.0285 | 60104.0285 | 0
Drury | Drury_34 | New Drury Interchange connection to Kiwi development | 2-lane urban- new road layout with active modes on both sides (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_35a | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 2-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_35b | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 4-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_36 | Complete Bremner-Norrie Road connection from SH1 upto GSR (overlap with project 12) | 4-lane urban- upgrade with active modes on both sides (SGA design) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4325974.2593 | 44195332.8439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48521307.1031 | 48521307.1031
Drury | Drury_36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6022224.9105 | 61524692.1109 | 0 | 0 | 0 | 0 | 0 | 67546917.0215 | 67546917.0215
Drury | Drury_36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6336988.0624 | 64740398.3153 | 0 | 0 | 0 | 0 | 0 | 71077386.3777 | 71077386.3777
Drury | Drury_37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | 40% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3802977.5966 | 38852256.3028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42655233.8994 | 42655233.8994
Drury | Drury_37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10440359.6788 | 106661561.8495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117101921.5283 | 117101921.5283
Drury | Drury_37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5479626.0309 | 55981353.9749 | 0 | 0 | 0 | 0 | 0 | 0 | 61460980.0058 | 61460980.0058
Drury | Drury_37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7089266.1774 | 72425876.705 | 0 | 0 | 0 | 0 | 0 | 0 | 79515142.8824 | 79515142.8824
Drury | Drury_38a | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_38b | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_18a | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_18b | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_39a | New Bremner Rd arterial from SH1 to Auranga development | 2-lane urban- new road layout with active modes on both sides (Under construction) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1844175.8141 | 18840603.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20684778.8881 | 20684778.8881
Drury | Drury_39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284974.1156 | 13127646.0128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14412620.1285 | 14412620.1285
Drury | Drury_40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1424551.6643 | 14553608.3164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15978159.9807 | 15978159.9807
Drury | Drury_40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730015.3286 | 7458035.6917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8188051.0203 | 8188051.0203
Drury | Drury_41a | Jesmond Rd upgrades from SH22 to Waipupuke development boundary | 2-lane urban- upgrade existing road with active modes on both sides (TDM) | 25% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 50% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1709432.0006 | 17464023.5268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19173455.5274 | 19173455.5274
Drury | Drury_42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | 25% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900697.5813 | 9201772.1359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10102469.7172 | 10102469.7172
Drury | Drury_42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 60% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1392055.2919 | 14221616.5139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15613671.8058 | 15613671.8058
Drury | Drury_43a | Intersection upgrade on Jesmond Rd/SH22 Rd | 2-lane intersection (Intersection upgrade + active mode crossings) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_43b | Intersection upgrade on Jesmond Rd/SH22 Rd | Multi-lane signalised intersection (Intersection upgrade + active mode crossings) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_44 | Intersection at SH22/Burberry Rd (likely to close entirely) | Interim design and likely to close - subject to Auranga assessment | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_45 | Upgrade intersection at SH22/Victoria Rd | subject to Auranga assessment | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824834.1634 | 8426730.7683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9251564.9318 | 9251564.9318
Drury | Drury_47 | Old Bremner Road Upgrade from Jesmond Road to Auranga Precinct | 2-lane urban- new road layout with active modes on both sides (Under construction) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_48 | Collector road south of New Bremner/ Old Bremner intersection | 2-lane urban- new road layout with active modes on both sides (Under construction) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_49 | SH22 improvements from GSR Intersection to Jesmond Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_50a | SH22 improvements from Jesmond Rd to Oira Rd- active mode upgrades on the northern section | 2-lane urban- upgrade existing road layout with active modes on northern side only | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_50b | SH22 improvements from Jesmond Rd to Oira Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_51 | SH22 improvements from Oira Rd to Oira Creek - subject to design, could be incorporated with project 60 | Upgrade road layout to future urban boundary + active modes on both sides | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_52 | Intersection upgrade- on SH22/ McPherson Rd/Karaka Rd (Auranga B1) | Ultimate intersection form | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_53 | New intersection east of Jesmond Rd (Auranga B1 main street) | Ultimate intersection form (left-in left-out) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_54 | New N-S collectors internal to Auranga B1 (2 links )+ Intersections | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 5% | 0 | 0 | 203844.5863 | 2075750.5813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2279595.1676 | 2279595.1676
Drury | Drury_55 | New E-W collector Jesmond Rd to SH22 | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3708089.0409 | 37882848.9385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41590937.9794 | 41590937.9794
Drury | Drury_56 | Burberry Rd north connection to Auranga Precinct | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_57 | New access road to Drury West Station | 2-lane urban- new road layout with active modes on both sides, (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | 10% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 777499.4866 | 7943146.8004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8720646.287 | 8720646.287
Drury | Drury_59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1129932.8877 | 11543702.5442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12673635.4318 | 12673635.4318
Drury | Drury_60a | SH22 Intersection upgrade - Oira Rd (3 leg) | Interim Roundabout | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_60b | SH22 Intersection upgrade - Oira Rd (4 leg) | Ultimate intersection form | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_63 | New collectors internal to Waipupuke PC61 (3 links )+ Intersections | 2-lane urban - new collector with active mode on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932659.916 | 9528308.0636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10460967.9796 | 10460967.9796
Drury | Drury_65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1933410.1277 | 19752245.1582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21685655.2859 | 21685655.2859
Drury | Drury_65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 481865.2934 | 4922867.2548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5404732.5482 | 5404732.5482
Drury | Drury_66 | SH22 improvements - west of SH1 interchange to GSR | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_67 | Active Mode Corridor Drury Central to GSR | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4874848.2151 | 49802778.869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54677627.0841 | 54677627.0841
Drury | Drury_68 | Active Mode Corridor GSR to Drury West | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3002095.2152 | 30670223.4716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33672318.6868 | 33672318.6868
Drury | Drury_69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 782706.8127 | 7996346.2644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8779053.0771 | 8779053.0771
Drury | Drury_70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627538.3203 | 6411102.6271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7038640.9474 | 7038640.9474

## Con7_Renewal
Con7_Renewal
Subtracts the share of costs attributable to renewal of existing assets
Location | Project ID | Project name | Project Description | Renewal Share of Project % | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | Total project Cost after mitigation | Total project Cost after mitigation within 30 years | Total Mitigation
Drury | Drury_1a | GSR improvements - Waihoehoe Rd to Drury Interchange | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 3.86% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760983.9561 | 28206965.0907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30967949.0467 | 30967949.0467
Drury | Drury_2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 7.474% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 764487.4879 | 7810212.6729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8574700.1608 | 8574700.1608
Drury | Drury_2b | GSR improvements - From Drury School to Waihoehoe Rd | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_3 | Intersection upgrade on GSR/Karaka Rd intersection | Intersection upgrades- existing intersection with active modes crossings (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_4a | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | 6.909% | 0 | 0 | 0 | 0 | 0 | 0 | 630254.8781 | 6438855.7221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7069110.6002 | 7069110.6002
Drury | Drury_4 | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Construct Ultimate 24m Cross section initially (i.e. no interim stage) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_5 | Drury Central Station | Not feasible without access. Refer to item 6 below | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_6 | Drury Station Connection+ intersection | NZUP tbc | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51534.4838 | 526490.341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578024.8247 | 578024.8247
Drury | Drury_8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51534.4838 | 526490.341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578024.8247 | 578024.8247
Drury | Drury_9a | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | 2-lane signalised intersection with active mode crossings | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_9b | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | multi-lane signalised intersection with active mode crossings, SGA design | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | 5.04% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1129932.8877 | 11543702.5442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12673635.4318 | 12673635.4318
Drury | Drury_11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | 6.496% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102476.474 | 1046927.6069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149404.0809 | 1149404.0809
Drury | Drury_12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | 0.3618% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2652006.8642 | 27093625.399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29745632.2632 | 29745632.2632
Drury | Drury_13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2322584.3593 | 23728155.2467 | 0 | 0 | 0 | 0 | 0 | 26050739.606 | 26050739.606
Drury | Drury_14 | Upgrade Brookefield Road from Fitzgerald to Quarry Rd+ New connection + Intersections on Quarry & Fitzgerald | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements + new connection to Quarry Rd) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3413832.3188 | 34876642.0139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38290474.3327 | 38290474.3327
Drury | Drury_14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | 2.565% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307255.9356 | 3139010.4347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3446266.3703 | 3446266.3703
Drury | Drury_15 | New Collector road E-W from Fitgerald Rd (collector 1) + Intersections | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_16a | Replace 2-lane Bremner Road Bridge over State Highway 1 | 2-lane urban with active modes on both sides (replacing existing bridge as part of SH1 P2D NZUP) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | 0.856% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2746438.4828 | 28058364.5692 | 0 | 0 | 0 | 0 | 0 | 30804803.0521 | 30804803.0521
Drury | Drury_17 | Oira Road to Jesmond Road Collector | New 2-lane urban collector with active modes on both sides | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267240.4352 | 2730201.1701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997441.6053 | 2997441.6053
Drury | Drury_19-1 | SH1 3-laning and cycleway upgrades from Papakura to Drury Interchange | NZUP tbc | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_19-2 | SH1 Drury Interchange including ramps | NZUP tbc | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_19-3 | SH1 3-laning and cycleway upgrades from Drury Interchange To Drury South | NZUP tbc | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824296.619 | 8421239.0679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9245535.6869 | 9245535.6869
Drury | Drury_21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28324.8052 | 289373.9346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317698.7398 | 317698.7398
Drury | Drury_22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | 9.57% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 769020.3575 | 7856521.7054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8625542.063 | 8625542.063
Drury | Drury_23a | Waihoehoe Rd West upgrades- between GSR & Kath Henry | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_23b | Waihoehoe Rd West upgrades- between GSR & Kath Henry Lane | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | 5.628% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 922810.7405 | 9427686.2005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10350496.941 | 10350496.941
Drury | Drury_23 | Waihoehoe Rd West upgrades- between GSR & Fitzgerald Rd, including bridge replacement over the rail corridor | 4-lane urban- upgrade 2-lane with active modes on both sides, SGA design | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | 3.333% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 989337.0814 | 10107337.4427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11096674.5241 | 11096674.5241
Drury | Drury_25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 536534.3494 | 5481381.2407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6017915.5901 | 6017915.5901
Drury | Drury_27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932318.134 | 9524816.3256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10457134.4596 | 10457134.4596
Drury | Drury_27b | Upgrade from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | 4-lane urban- upgrade existing road layout with active modes on both sides + intersection upgrades (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_28 | New collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1541109.4313 | 15744394.2529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17285503.6842 | 17285503.6842
Drury | Drury_29 | New collector in E-W direction between Flanagan & Fitzgerald Rd (collector 2) | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_30 | 2-lane internal collector between Fitzgerald & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_30.1 | 2-lane internal collector between Fitzgerald & Fielding Road E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_30.2 | 2-lane internal collector between Fielding Road & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87539.8149 | 894330.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981870.4384 | 981870.4384
Drury | Drury_32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | 4.872% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110820.3917 | 1132171.345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1242991.7367 | 1242991.7367
Drury | Drury_33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60104.0285 | 60104.0285 | 0
Drury | Drury_34 | New Drury Interchange connection to Kiwi development | 2-lane urban- new road layout with active modes on both sides (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_35a | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 2-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_35b | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 4-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_36 | Complete Bremner-Norrie Road connection from SH1 upto GSR (overlap with project 12) | 4-lane urban- upgrade with active modes on both sides (SGA design) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | 0.07729% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4322630.5891 | 44161172.9976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48483803.5867 | 48483803.5867
Drury | Drury_36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | 1.102% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5955831.4303 | 60846398.2096 | 0 | 0 | 0 | 0 | 0 | 66802229.6399 | 66802229.6399
Drury | Drury_36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6336988.0624 | 64740398.3153 | 0 | 0 | 0 | 0 | 0 | 71077386.3777 | 71077386.3777
Drury | Drury_37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3802977.5966 | 38852256.3028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42655233.8994 | 42655233.8994
Drury | Drury_37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10440359.6788 | 106661561.8495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117101921.5283 | 117101921.5283
Drury | Drury_37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5479626.0309 | 55981353.9749 | 0 | 0 | 0 | 0 | 0 | 0 | 61460980.0058 | 61460980.0058
Drury | Drury_37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7089266.1774 | 72425876.705 | 0 | 0 | 0 | 0 | 0 | 0 | 79515142.8824 | 79515142.8824
Drury | Drury_38a | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_38b | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_18a | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_18b | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_39a | New Bremner Rd arterial from SH1 to Auranga development | 2-lane urban- new road layout with active modes on both sides (Under construction) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1844175.8141 | 18840603.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20684778.8881 | 20684778.8881
Drury | Drury_39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284974.1156 | 13127646.0128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14412620.1285 | 14412620.1285
Drury | Drury_40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | 1.804% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1398846.4209 | 14290996.5397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15689842.9606 | 15689842.9606
Drury | Drury_40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730015.3286 | 7458035.6917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8188051.0203 | 8188051.0203
Drury | Drury_41a | Jesmond Rd upgrades from SH22 to Waipupuke development boundary | 2-lane urban- upgrade existing road with active modes on both sides (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1709432.0006 | 17464023.5268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19173455.5274 | 19173455.5274
Drury | Drury_42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | 7.946% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 829132.152 | 8470640.1915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9299772.3435 | 9299772.3435
Drury | Drury_42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1392055.2919 | 14221616.5139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15613671.8058 | 15613671.8058
Drury | Drury_43a | Intersection upgrade on Jesmond Rd/SH22 Rd | 2-lane intersection (Intersection upgrade + active mode crossings) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_43b | Intersection upgrade on Jesmond Rd/SH22 Rd | Multi-lane signalised intersection (Intersection upgrade + active mode crossings) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_44 | Intersection at SH22/Burberry Rd (likely to close entirely) | Interim design and likely to close - subject to Auranga assessment | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_45 | Upgrade intersection at SH22/Victoria Rd | subject to Auranga assessment | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824834.1634 | 8426730.7683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9251564.9318 | 9251564.9318
Drury | Drury_47 | Old Bremner Road Upgrade from Jesmond Road to Auranga Precinct | 2-lane urban- new road layout with active modes on both sides (Under construction) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_48 | Collector road south of New Bremner/ Old Bremner intersection | 2-lane urban- new road layout with active modes on both sides (Under construction) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_49 | SH22 improvements from GSR Intersection to Jesmond Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_50a | SH22 improvements from Jesmond Rd to Oira Rd- active mode upgrades on the northern section | 2-lane urban- upgrade existing road layout with active modes on northern side only | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_50b | SH22 improvements from Jesmond Rd to Oira Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_51 | SH22 improvements from Oira Rd to Oira Creek - subject to design, could be incorporated with project 60 | Upgrade road layout to future urban boundary + active modes on both sides | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_52 | Intersection upgrade- on SH22/ McPherson Rd/Karaka Rd (Auranga B1) | Ultimate intersection form | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_53 | New intersection east of Jesmond Rd (Auranga B1 main street) | Ultimate intersection form (left-in left-out) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_54 | New N-S collectors internal to Auranga B1 (2 links )+ Intersections | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 203844.5863 | 2075750.5813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2279595.1676 | 2279595.1676
Drury | Drury_55 | New E-W collector Jesmond Rd to SH22 | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3708089.0409 | 37882848.9385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41590937.9794 | 41590937.9794
Drury | Drury_56 | Burberry Rd north connection to Auranga Precinct | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_57 | New access road to Drury West Station | 2-lane urban- new road layout with active modes on both sides, (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | 2.642% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 756954.7508 | 7733256.1762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8490210.927 | 8490210.927
Drury | Drury_59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | 1.624% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1111582.7776 | 11356232.8148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12467815.5924 | 12467815.5924
Drury | Drury_60a | SH22 Intersection upgrade - Oira Rd (3 leg) | Interim Roundabout | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_60b | SH22 Intersection upgrade - Oira Rd (4 leg) | Ultimate intersection form | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_63 | New collectors internal to Waipupuke PC61 (3 links )+ Intersections | 2-lane urban - new collector with active mode on both sides + intersection improvements (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932659.916 | 9528308.0636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10460967.9796 | 10460967.9796
Drury | Drury_65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1933410.1277 | 19752245.1582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21685655.2859 | 21685655.2859
Drury | Drury_65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 481865.2934 | 4922867.2548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5404732.5482 | 5404732.5482
Drury | Drury_66 | SH22 improvements - west of SH1 interchange to GSR | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drury | Drury_67 | Active Mode Corridor Drury Central to GSR | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4874848.2151 | 49802778.869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54677627.0841 | 54677627.0841
Drury | Drury_68 | Active Mode Corridor GSR to Drury West | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3002095.2152 | 30670223.4716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33672318.6868 | 33672318.6868
Drury | Drury_69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 782706.8127 | 7996346.2644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8779053.0771 | 8779053.0771
Drury | Drury_70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627538.3203 | 6411102.6271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7038640.9474 | 7038640.9474

## Prj1_GrowthLOSCost
ProJ1_GrowthLOSCost
Calculates the total project cost, exclusive of mitigation, and renewal
51%
Project ID | Project Number | Project name | Project Description | Included in DCs | Corridor Type | Total Property Cost after mitigation | Total Construction Cost after mitigation | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | Total | Total 2025 to 2054 | Total in LTP (2025 to 2034) | Total beyond 2034 | adjusted year to meet financial constraints | Collector road indicator | WK funding within the LTP (51% for non-collectors) | WK funding beyond 2031 (51% for non-collectors) | Construction year prior to adjustment
Drury_1a | 1a | GSR improvements - Waihoehoe Rd to Drury Interchange | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Exclude | Interim Arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2024
Drury_1b | 1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial | 0 | 30967949.0467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760983.9561 | 28206965.0907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30967949.0467 | 30967949.0467 | 30967949.0467 | 0 |  | Arterial | 15793654.0138 | 0 | 2031
Drury_2a | 2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial | 0 | 8574700.1608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 764487.4879 | 7810212.6729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8574700.1608 | 8574700.1608 | 8574700.1608 | 0 |  | Arterial | 4373097.082 | 0 | 2030
Drury_2b | 2b | GSR improvements - From Drury School to Waihoehoe Rd | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Exclude - NZTA | 4-lane arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2040
Drury_3 | 3 | Intersection upgrade on GSR/Karaka Rd intersection | Intersection upgrades- existing intersection with active modes crossings (TDM) | Exclude - NZTA | 4-lane arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2026
Drury_4a | 4a | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Exclude | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0
Drury_4b | 4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial | 2747624.3671 | 7069110.6002 | 0 | 0 | 0 | 0 | 0 | 2245198.3556 | 630254.8781 | 6941281.7336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9816734.9673 | 9816734.7325 | 9816734.7325 | 0 |  | Arterial | 5006534.7136 | 0 | 2029
Drury_4 | 4 | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Construct Ultimate 24m Cross section initially (i.e. no interim stage) | Exclude | 2-lane Arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0
Drury_5 | 5 | Drury Central Station | Not feasible without access. Refer to item 6 below | Exclude | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2024
Drury_6 | 6 | Drury Station Connection+ intersection | NZUP tbc | Exclude | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2024
Drury_7 | 7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | 0 | 578024.8247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51534.4838 | 526490.341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578024.8247 | 578024.8247 | 0 | 578024.8247 | 2036 | Collector | 0 | 0 | 2033
Drury_8 | 8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | 0 | 578024.8247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51534.4838 | 526490.341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578024.8247 | 578024.8247 | 0 | 578024.8247 | 2036 | Collector | 0 | 0 | 2033
Drury_9a | 9a | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | 2-lane signalised intersection with active mode crossings | Exclude - NZTA | 2-lane Arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2026
Drury_9b | 9b | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | multi-lane signalised intersection with active mode crossings, SGA design | Exclude - NZTA | 4-lane arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2031
Drury_10a | 10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2029
Drury_10b | 10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial | 4233069.2151 | 12673635.4318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3863581.1851 | 1129932.8877 | 11913190.5742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16906704.6469 | 16906704.9908 | 0 | 16906704.9908 | 2037 | Arterial | 0 | 8622419.5453 | 2031
Drury_11 | 11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial | 321873.6704 | 1149404.0809 | 0 | 0 | 0 | 0 | 0 | 85290.0969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236583.5735 | 102476.474 | 1046927.6069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1471277.7513 | 1471277.7447 | 85290.0903 | 1385987.6544 | 2037 | Arterial | 43497.946 | 706853.7038 | 2031
Drury_12 | 12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) | 0 | 29745632.2632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2652006.8642 | 27093625.399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29745632.2632 | 29745632.2632 | 0 | 29745632.2632 | 2036 | Collector | 0 | 0 | 2033
Drury_13a | 13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial | 2735924.3452 | 0 | 0 | 0 | 0 | 0 | 0 | 360640.7463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2375283.5989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2735924.3452 | 2735924.4426 | 360640.7409 | 2375283.7017 | 2037 | Arterial | 183926.7779 | 1211394.6879 | 2029
Drury_13b | 13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade | 0 | 26050739.606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2322584.3593 | 23728155.2467 | 0 | 0 | 0 | 0 | 0 | 26050739.606 | 26050739.606 | 0 | 26050739.606 | 0 | Arterial | 0 | 13285877.1991 | 2050
Drury_14 | 14 | Upgrade Brookefield Road from Fitzgerald to Quarry Rd+ New connection + Intersections on Quarry & Fitzgerald | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements + new connection to Quarry Rd) | Exclude | Upgrade Collector | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Collector | 0 | 0
Drury_14a | 14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) | 61441902.2143 | 38290474.3327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61441902.2143 | 3413832.3188 | 34876642.0139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99732376.5469 | 99732376.8908 | 0 | 99732376.8908 | 2037 | Collector | 0 | 0 | 2035
Drury_14b | 14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector | 0 | 3446266.3703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307255.9356 | 3139010.4347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3446266.3703 | 3446266.3703 | 0 | 3446266.3703 | 2036 | Collector | 0 | 0 | 2033
Drury_15 | 15 | New Collector road E-W from Fitgerald Rd (collector 1) + Intersections | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Collector | 0 | 0 | 2033
Drury_16a | 16a | Replace 2-lane Bremner Road Bridge over State Highway 1 | 2-lane urban with active modes on both sides (replacing existing bridge as part of SH1 P2D NZUP) | Exclude | Upgrade Collector | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Collector | 0 | 0 | 2033
Drury_16b | 16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial | 0 | 30804803.0521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2746438.4828 | 28058364.5692 | 0 | 0 | 0 | 0 | 0 | 30804803.0521 | 30804803.0521 | 0 | 30804803.0521 | 0 | Arterial | 0 | 15710449.5565 | 2050
Drury_17 | 17 | Oira Road to Jesmond Road Collector | New 2-lane urban collector with active modes on both sides | Exclude | Greenfields Collector | 0 | 2997441.6053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267240.4352 | 2730201.1701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997441.6053 | 2997441.6053 | 0 | 2997441.6053 | 0 | Collector | 0 | 0 | 2036
Drury_19-1 | 19-1 | SH1 3-laning and cycleway upgrades from Papakura to Drury Interchange | NZUP tbc | Exclude | State Highway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | Under Construction
Drury_19-2 | 19-2 | SH1 Drury Interchange including ramps | NZUP tbc | Exclude | State Highway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | Under Construction
Drury_19-3 | 19-3 | SH1 3-laning and cycleway upgrades from Drury Interchange To Drury South | NZUP tbc | Exclude | State Highway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2036
Drury_20a | 20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | 0 | 9245535.6869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824296.619 | 8421239.0679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9245535.6869 | 9245535.6869 | 0 | 9245535.6869 | 2036 | Collector | 0 | 0 | 2035
Drury_21 | 21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | 0 | 317698.7398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28324.8052 | 289373.9346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317698.7398 | 317698.7398 | 28324.8052 | 289373.9346 | 0 | Collector | 0 | 0 | 2035
Drury_22 | 22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) | 0 | 8625542.063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 769020.3575 | 7856521.7054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8625542.063 | 8625542.063 | 0 | 8625542.063 | 2036 | Collector | 0 | 0 | 2033
Drury_23a | 23a | Waihoehoe Rd West upgrades- between GSR & Kath Henry | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Exclude | Interim Arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2025
Drury_23b | 23b | Waihoehoe Rd West upgrades- between GSR & Kath Henry Lane | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Exclude | 4-lane arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2031
Drury_23c | 23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2025
Drury_23d | 23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial | 4402694.557 | 10350496.941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3769871.2445 | 922810.7405 | 10060509.513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14753191.498 | 14753192.0848 | 0 | 14753192.0848 | 2037 | Arterial | 0 | 7524127.9633 | 2031
Drury_23 | 23 | Waihoehoe Rd West upgrades- between GSR & Fitzgerald Rd, including bridge replacement over the rail corridor | 4-lane urban- upgrade 2-lane with active modes on both sides, SGA design | Exclude | 4-lane arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0
Drury_24 | 24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial | 1753515.2574 | 11096674.5241 | 0 | 0 | 0 | 0 | 0 | 151112.5306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1602402.7268 | 989337.0814 | 10107337.4427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12850189.7815 | 12850189.925 | 151112.515 | 12699077.4099 | 0 | Arterial | 77067.3827 | 6476529.4791 | 2038
Drury_25 | 25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector | 0 | 6017915.5901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 536534.3494 | 5481381.2407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6017915.5901 | 6017915.5901 | 0 | 6017915.5901 | 0 | Collector | 0 | 0 | 2039
Drury_27a | 27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | 0 | 10457134.4596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932318.134 | 9524816.3256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10457134.4596 | 10457134.4596 | 0 | 10457134.4596 | 0 | Collector | 0 | 0 | 2039
Drury_27b | 27b | Upgrade from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | 4-lane urban- upgrade existing road layout with active modes on both sides + intersection upgrades (TDM) | Exclude | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2039
Drury_28 | 28 | New collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Collector | 0 | 0 | 2035
Drury_28a | 28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) | 6179008.7165 | 17285503.6842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6179008.7165 | 1541109.4313 | 15744394.2529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23464512.4006 | 23464512.0327 | 7720117.7798 | 15744394.2529 | 0 | Collector | 0 | 0 | 2035
Drury_29 | 29 | New collector in E-W direction between Flanagan & Fitzgerald Rd (collector 2) | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Collector | 0 | 0 | 2035
Drury_30 | 30 | 2-lane internal collector between Fitzgerald & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Collector | 0 | 0
Drury_30.1 | 30.1 | 2-lane internal collector between Fitzgerald & Fielding Road E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Collector | 0 | 0 | 2033
Drury_30.2 | 30.2 | 2-lane internal collector between Fielding Road & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Collector | 0 | 0 | 2039
Drury_31 | 31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector | 0 | 981870.4384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87539.8149 | 894330.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981870.4384 | 981870.4384 | 0 | 981870.4384 | 0 | Collector | 0 | 0 | 2039
Drury_32 | 32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial | 1606771.5223 | 1242991.7367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258590.3502 | 912821.8896 | 110820.3917 | 1567530.6275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2849763.259 | 2849763.3946 | 0 | 2849763.3946 | 0 | Arterial | 0 | 1453379.3313 | 2039
Drury_33 | 33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector | 0 | 60104.0285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60104.0285 | 60104.0285 | 0 | 0 | 0 | 3036 | Collector | 0 | 0 | 2033
Drury_34 | 34 | New Drury Interchange connection to Kiwi development | 2-lane urban- new road layout with active modes on both sides (TDM) | Exclude | State Highway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2034
Drury_35a | 35a | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 2-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | Exclude | 4-lane arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2043
Drury_35b | 35b | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 4-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | Exclude | 4-lane arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2050
Drury_36 | 36 | Complete Bremner-Norrie Road connection from SH1 upto GSR (overlap with project 12) | 4-lane urban- upgrade with active modes on both sides (SGA design) | Exclude | 4-lane arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0
Drury_36a | 36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial | 52544006.1085 | 48483803.5867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50286768.5201 | 4322630.5891 | 46418410.5859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101027809.6951 | 101027812.1297 | 0 | 101027812.1297 | 2039 | Arterial | 0 | 51524184.1862 | 2033
Drury_36b | 36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial | 99324280.7316 | 66802229.6399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99324280.7316 | 5955831.4303 | 60846398.2096 | 0 | 0 | 0 | 0 | 0 | 166126510.3715 | 166126508.7589 | 0 | 166126508.7589 | 0 | Arterial | 0 | 84724519.467 | 2050
Drury_36c | 36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure | 0 | 71077386.3777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6336988.0624 | 64740398.3153 | 0 | 0 | 0 | 0 | 0 | 71077386.3777 | 71077386.3777 | 0 | 71077386.3777 | 0 | Arterial | 0 | 36249467.0527 | 2050
Drury_37a(i) | 37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | 127080264.4089 | 42655233.8994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120729103.525 | 3802977.5966 | 45203417.1867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169735498.3084 | 169735497.6088 | 0 | 169735497.6088 | 0 | Arterial | 0 | 86565103.7805 | 2044
Drury_37a(ii) | 37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure | 0 | 117101921.5283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10440359.6788 | 106661561.8495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117101921.5283 | 117101921.5283 | 0 | 117101921.5283 | 0 | Arterial | 0 | 59721979.9794 | 2044
Drury_37b(i) | 37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade | 0 | 61460980.0058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5479626.0309 | 55981353.9749 | 0 | 0 | 0 | 0 | 0 | 0 | 61460980.0058 | 61460980.0058 | 0 | 61460980.0058 | 0 | Arterial | 0 | 31345099.8029 | 2049
Drury_37b(ii) | 37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure | 0 | 79515142.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7089266.1774 | 72425876.705 | 0 | 0 | 0 | 0 | 0 | 0 | 79515142.8824 | 79515142.8824 | 0 | 79515142.8824 | 0 | Arterial | 0 | 40552722.87 | 2049
Drury_38a | 38a | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | Exclude | 2-lane Arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2046
Drury_38b | 38b | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | Exclude | 4-lane arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2055
Drury_18a | 18a | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | Exclude | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2036
Drury_18b | 18b | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | Exclude | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2052
Drury_39a | 39a | New Bremner Rd arterial from SH1 to Auranga development | 2-lane urban- new road layout with active modes on both sides (Under construction) | Exclude | Interim 2-lane Arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | Under Construction
Drury_39b | 39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade | 0 | 20684778.8881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1844175.8141 | 18840603.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20684778.8881 | 20684778.8881 | 0 | 20684778.8881 | 0 | Arterial | 0 | 10549237.2329 | 2047
Drury_39c | 39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure | 0 | 14412620.1285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284974.1156 | 13127646.0128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14412620.1285 | 14412620.1285 | 0 | 14412620.1285 | 0 | Arterial | 0 | 7350436.2655 | 2047
Drury_40a | 40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial | 5578145.1353 | 15689842.9606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5386705.2732 | 1398846.4209 | 14482436.4017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21267988.0959 | 21267988.371 | 0 | 21267988.371 | 2037 | Arterial | 0 | 10846674.0692 | 2027
Drury_40b | 40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial | 0 | 8188051.0203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730015.3286 | 7458035.6917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8188051.0203 | 8188051.0203 | 8188051.0203 | 0 | 0 | Arterial | 4175906.0204 | 0 | 2031
Drury_41a | 41a | Jesmond Rd upgrades from SH22 to Waipupuke development boundary | 2-lane urban- upgrade existing road with active modes on both sides (TDM) | Exclude | Interim Arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2027
Drury_41b | 41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | 38944485.3741 | 19173455.5274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35512162.8311 | 1709432.0006 | 20896346.0698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58117940.9015 | 58117941.8163 | 0 | 58117941.8163 | 0 | Arterial | 0 | 29640150.3263 | 2047
Drury_42a | 42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2028
Drury_42b | 42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial | 0 | 9299772.3435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 829132.152 | 8470640.1915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9299772.3435 | 9299772.3435 | 0 | 9299772.3435 | 2038 | Arterial | 0 | 4742883.8952 | 2031
Drury_42c | 42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | 99142785.5581 | 15613671.8058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90549574.085 | 1392055.2919 | 22814827.9871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114756457.364 | 114756463.3098 | 0 | 114756463.3098 | 0 | Arterial | 0 | 58525796.288 | 2047
Drury_43a | 43a | Intersection upgrade on Jesmond Rd/SH22 Rd | 2-lane intersection (Intersection upgrade + active mode crossings) | Exclude | State Highway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0
Drury_43b | 43b | Intersection upgrade on Jesmond Rd/SH22 Rd | Multi-lane signalised intersection (Intersection upgrade + active mode crossings) | Exclude | 4-lane arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2024
Drury_44 | 44 | Intersection at SH22/Burberry Rd (likely to close entirely) | Interim design and likely to close - subject to Auranga assessment | Exclude | 4-lane arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2023
Drury_45 | 45 | Upgrade intersection at SH22/Victoria Rd | subject to Auranga assessment | Exclude | State Highway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2024
Drury_46 | 46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial | 0 | 9251564.9318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824834.1634 | 8426730.7683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9251564.9318 | 9251564.9318 | 824834.1634 | 8426730.7683 | 2035 | Arterial | 420665.4233 | 4297632.6918 | 2031
Drury_47 | 47 | Old Bremner Road Upgrade from Jesmond Road to Auranga Precinct | 2-lane urban- new road layout with active modes on both sides (Under construction) | Exclude | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | Under Construction
Drury_48 | 48 | Collector road south of New Bremner/ Old Bremner intersection | 2-lane urban- new road layout with active modes on both sides (Under construction) | Exclude | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | Under Construction
Drury_49 | 49 | SH22 improvements from GSR Intersection to Jesmond Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Exclude | State Highway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2032
Drury_50a | 50a | SH22 improvements from Jesmond Rd to Oira Rd- active mode upgrades on the northern section | 2-lane urban- upgrade existing road layout with active modes on northern side only | Exclude | State Highway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2026
Drury_50b | 50b | SH22 improvements from Jesmond Rd to Oira Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Exclude | State Highway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2032
Drury_51 | 51 | SH22 improvements from Oira Rd to Oira Creek - subject to design, could be incorporated with project 60 | Upgrade road layout to future urban boundary + active modes on both sides | Exclude | State Highway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2037
Drury_52 | 52 | Intersection upgrade- on SH22/ McPherson Rd/Karaka Rd (Auranga B1) | Ultimate intersection form | Exclude | 4-lane arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2024
Drury_53 | 53 | New intersection east of Jesmond Rd (Auranga B1 main street) | Ultimate intersection form (left-in left-out) | Exclude | 4-lane arterial upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2024
Drury_54 | 54 | New N-S collectors internal to Auranga B1 (2 links )+ Intersections | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 0 | 2279595.1676 | 0 | 0 | 203844.5863 | 2075750.5813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2279595.1676 | 2075750.5813 | 2075750.5813 | 0 | 0 | Collector | 0 | 0 | 2025
Drury_55 | 55 | New E-W collector Jesmond Rd to SH22 | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Collector | 0 | 0
Drury_55a | 55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) | 13284839.242 | 41590937.9794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13284839.242 | 3708089.0409 | 37882848.9385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54875777.2214 | 54875777.9091 | 0 | 54875777.9091 | 2037 | Collector | 0 | 0 | 2034
Drury_56 | 56 | Burberry Rd north connection to Auranga Precinct | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Collector | 0 | 0 | Under construction
Drury_57 | 57 | New access road to Drury West Station | 2-lane urban- new road layout with active modes on both sides, (TDM) | Exclude | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2026
Drury_58 | 58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector | 0 | 8490210.927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 756954.7508 | 7733256.1762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8490210.927 | 8490210.927 | 0 | 8490210.927 | 2036 | Collector | 0 | 0 | 2033
Drury_59 | 59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) | 0 | 12467815.5924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1111582.7776 | 11356232.8148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12467815.5924 | 12467815.5924 | 0 | 12467815.5924 | 2038 | Collector | 0 | 0 | 2033
Drury_60a | 60a | SH22 Intersection upgrade - Oira Rd (3 leg) | Interim Roundabout | Exclude | 2-lane Arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2026
Drury_60b | 60b | SH22 Intersection upgrade - Oira Rd (4 leg) | Ultimate intersection form | Exclude | 4-lane arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2037
Drury_63 | 63 | New collectors internal to Waipupuke PC61 (3 links )+ Intersections | 2-lane urban - new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Collector | 0 | 0 | 2026
Drury_65a(i) | 65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2036
Drury_65a(ii) | 65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure | 0 | 10460967.9796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932659.916 | 9528308.0636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10460967.9796 | 10460967.9796 | 0 | 10460967.9796 | 0 | Arterial | 0 | 5335093.6696 | 2036
Drury_65b(i) | 65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade | 0 | 21685655.2859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1933410.1277 | 19752245.1582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21685655.2859 | 21685655.2859 | 0 | 21685655.2859 | 0 | Arterial | 0 | 11059684.1958 | 2047
Drury_65b(ii) | 65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure | 0 | 5404732.5482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 481865.2934 | 4922867.2548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5404732.5482 | 5404732.5482 | 0 | 5404732.5482 | 0 | Arterial | 0 | 2756413.5996 | 2047
Drury_66 | 66 | SH22 improvements - west of SH1 interchange to GSR | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Exclude | State Highway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2032
Drury_67 | 67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure | 47503573.0814 | 54677627.0841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47503573.0814 | 4874848.2151 | 49802778.869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102181200.1655 | 102181201.1971 | 0 | 102181201.1971 | 2037 | Arterial | 0 | 52112412.6105 | 2033
Drury_68 | 68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure | 80527456.7457 | 33672318.6868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80527456.7457 | 3002095.2152 | 30670223.4716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114199775.4324 | 114199776.636 | 0 | 114199776.636 | 0 | Arterial | 0 | 58241886.0843 | 2037
Drury_69 | 69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) | 0 | 8779053.0771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 782706.8127 | 7996346.2644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8779053.0771 | 8779053.0771 | 782706.8127 | 7996346.2644 |  | Collector | 0 | 0 | 2035
Drury_70 | 70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure | 3089.0771 | 7038640.9474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627538.3203 | 6414191.7041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7041730.0244 | 7040479.5617 | 7040479.5617 | 0 | 0 | Arterial | 3590644.5765 | 0 | 2031

## Total project cost for DCs
| 1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
[45 empty] | 51% | WK/NZTA funding rate
Project number | Project name | Project description | Include in DCs? | Corridor Type | Construction year | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | Total | Total in LTP (2025 to 2034) | Total beyond 2034 | adjusted year to meet financial constraints | Collector road indicator | WK funding within the LTP (51% for non-collectors) | WK funding beyond 2031 (51% for non-collectors) | Construction year prior to adjustment | Total cost less NZTA/WK funding
1a | GSR improvements - Waihoehoe Rd to Drury Interchange | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Exclude | Interim Arterial | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial |  |  | 2024 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760983.9561 | 28206965.0907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30967949.0467 | 30967949.0467 | 0 | 0 | Arterial | 15793654.0138 | 0 | 2031 | 15174295.0329 |  | 2036
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 764487.4879 | 7810212.6729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8574700.1608 | 8574700.1608 | 0 | 0 | Arterial | 4373097.082 | 0 | 2030 | 4201603.0788 |  | 2038
2b | GSR improvements - From Drury School to Waihoehoe Rd | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Exclude - NZTA | 4-lane arterial | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2040 | 0 |  | 0
3 | Intersection upgrade on GSR/Karaka Rd intersection | Intersection upgrades- existing intersection with active modes crossings (TDM) | Exclude - NZTA | 4-lane arterial | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2026 | 0 |  | 0
4a | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Exclude | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 |  | 0 |  | 0
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 2245198.3556 | 630254.8781 | 6941281.7336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9816734.9673 | 9816734.9673 | 0 | 0 | Arterial | 5006534.8333 | 0 | 2029 | 4810200.134 |  | 2037
4 | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Construct Ultimate 24m Cross section initially (i.e. no interim stage) | Exclude | 2-lane Arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 |  | 0 |  | 0
5 | Drury Central Station | Not feasible without access. Refer to item 6 below | Exclude | 0 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2024 | 0 |  | 0
6 | Drury Station Connection+ intersection | NZUP tbc | Exclude | 0 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2024 | 0 |  | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51534.4838 | 526490.341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578024.8247 | 0 | 578024.8247 | 2036 | Collector | 0 | 0 | 2033 | 578024.8247 |  | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51534.4838 | 526490.341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578024.8247 | 0 | 578024.8247 | 2036 | Collector | 0 | 0 | 2033 | 578024.8247 |  | 0
9a | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | 2-lane signalised intersection with active mode crossings | Exclude - NZTA | 2-lane Arterial | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2026 | 0 |  | 0
9b | Upgrade in Norrie Rd/GSR/Waihoehoe intersection | multi-lane signalised intersection with active mode crossings, SGA design | Exclude - NZTA | 4-lane arterial | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2031 | 0 |  | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2029 | 0 |  | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3863581.1851 | 1129932.8877 | 11913190.5742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16906704.6469 | 0 | 16906704.6469 | 2037 | Arterial | 0 | 8622419.3699 | 2031 | 8284285.277 |  | 2037
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 85290.0969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236583.5735 | 102476.474 | 1046927.6069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1471277.7513 | 85290.0969 | 1385987.6544 | 2037 | Arterial | 43497.9494 | 706853.7038 | 2031 | 720926.0981 |  | 0
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2652006.8642 | 27093625.399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29745632.2632 | 0 | 29745632.2632 | 2036 | Collector | 0 | 0 | 2033 | 29745632.2632 |  | 2036
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 360640.7463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2375283.5989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2735924.3452 | 360640.7463 | 2375283.5989 | 2037 | Arterial | 183926.7806 | 1211394.6355 | 2029 | 1340602.9292 |  | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2322584.3593 | 23728155.2467 | 0 | 0 | 0 | 0 | 26050739.606 | 0 | 26050739.606 | 0 | Arterial | 0 | 13285877.1991 | 2050 | 12764862.407 |  | 0
14 | Upgrade Brookefield Road from Fitzgerald to Quarry Rd+ New connection + Intersections on Quarry & Fitzgerald | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements + new connection to Quarry Rd) | Exclude | Upgrade Collector | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Collector | 0 | 0 |  | 0 |  | 0
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61441902.2143 | 3413832.3188 | 34876642.0139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99732376.5469 | 0 | 99732376.5469 | 2037 | Collector | 0 | 0 | 2035 | 99732376.5469 |  | 2037
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307255.9356 | 3139010.4347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3446266.3703 | 0 | 3446266.3703 | 2036 | Collector | 0 | 0 | 2033 | 3446266.3703 |  | 0
15 | New Collector road E-W from Fitgerald Rd (collector 1) + Intersections | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Collector | 0 | 0 | 2033 | 0 |  | 0
16a | Replace 2-lane Bremner Road Bridge over State Highway 1 | 2-lane urban with active modes on both sides (replacing existing bridge as part of SH1 P2D NZUP) | Exclude | Upgrade Collector | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Collector | 0 | 0 | 2033 | 0 |  | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2746438.4828 | 28058364.5692 | 0 | 0 | 0 | 0 | 30804803.0521 | 0 | 30804803.0521 | 0 | Arterial | 0 | 15710449.5565 | 2050 | 15094353.4955 |  | 0
17 | Oira Road to Jesmond Road Collector | New 2-lane urban collector with active modes on both sides | Exclude | Greenfields Collector | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267240.4352 | 2730201.1701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997441.6053 | 0 | 2997441.6053 | 0 | Collector | 0 | 0 | 2036 | 2997441.6053 |  | 0
19-1 | SH1 3-laning and cycleway upgrades from Papakura to Drury Interchange | NZUP tbc | Exclude | State Highway | Under Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | Under Construction | 0 |  | 0
19-2 | SH1 Drury Interchange including ramps | NZUP tbc | Exclude | State Highway | Under Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | Under Construction | 0 |  | 0
19-3 | SH1 3-laning and cycleway upgrades from Drury Interchange To Drury South | NZUP tbc | Exclude | State Highway | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2036 | 0 |  | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824296.619 | 8421239.0679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9245535.6869 | 0 | 9245535.6869 | 2036 | Collector | 0 | 0 | 2035 | 9245535.6869 |  | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28324.8052 | 289373.9346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317698.7398 | 28324.8052 | 289373.9346 | 0 | Collector | 0 | 0 | 2035 | 317698.7398 |  | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 769020.3575 | 7856521.7054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8625542.063 | 0 | 8625542.063 | 2036 | Collector | 0 | 0 | 2033 | 8625542.063 |  | 2036
23a | Waihoehoe Rd West upgrades- between GSR & Kath Henry | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Exclude | Interim Arterial | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2025 | 0 |  | 0
23b | Waihoehoe Rd West upgrades- between GSR & Kath Henry Lane | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Exclude | 4-lane arterial | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2031 | 0 |  | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2025 | 0 |  | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3769871.2445 | 922810.7405 | 10060509.513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14753191.498 | 0 | 14753191.498 | 2037 | Arterial | 0 | 7524127.664 | 2031 | 7229063.834 |  | 2037
23 | Waihoehoe Rd West upgrades- between GSR & Fitzgerald Rd, including bridge replacement over the rail corridor | 4-lane urban- upgrade 2-lane with active modes on both sides, SGA design | Exclude | 4-lane arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 |  | 0 |  | 0
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 151112.5306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1602402.7268 | 989337.0814 | 10107337.4427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12850189.7815 | 151112.5306 | 12699077.2509 | 0 | Arterial | 77067.3906 | 6476529.3979 | 2038 | 6296592.9929 |  | 0
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 536534.3494 | 5481381.2407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6017915.5901 | 0 | 6017915.5901 | 0 | Collector | 0 | 0 | 2039 | 6017915.5901 |  | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932318.134 | 9524816.3256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10457134.4596 | 0 | 10457134.4596 | 0 | Collector | 0 | 0 | 2039 | 10457134.4596 |  | 0
27b | Upgrade from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | 4-lane urban- upgrade existing road layout with active modes on both sides + intersection upgrades (TDM) | Exclude | 0 | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2039 | 0 |  | 0
28 | New collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Collector | 0 | 0 | 2035 | 0 |  | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6179008.7165 | 1541109.4313 | 15744394.2529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23464512.4006 | 7720118.1478 | 15744394.2529 | 0 | Collector | 0 | 0 | 2035 | 23464512.4006 |  | 0
29 | New collector in E-W direction between Flanagan & Fitzgerald Rd (collector 2) | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Collector | 0 | 0 | 2035 | 0 |  | 0
30 | 2-lane internal collector between Fitzgerald & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Collector | 0 | 0 |  | 0 |  | 0
30.1 | 2-lane internal collector between Fitzgerald & Fielding Road E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Collector | 0 | 0 | 2033 | 0 |  | 0
30.2 | 2-lane internal collector between Fielding Road & Drury Hills E-W direction | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Collector | 0 | 0 | 2039 | 0 |  | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87539.8149 | 894330.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981870.4384 | 0 | 981870.4384 | 0 | Collector | 0 | 0 | 2039 | 981870.4384 |  | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258590.3502 | 912821.8896 | 110820.3917 | 1567530.6275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2849763.259 | 0 | 2849763.259 | 0 | Arterial | 0 | 1453379.2621 | 2039 | 1396383.9969 |  | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector | 2056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2056 | Collector | 0 | 0 | 2033 | 0 |  | 2034
34 | New Drury Interchange connection to Kiwi development | 2-lane urban- new road layout with active modes on both sides (TDM) | Exclude | State Highway | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2034 | 0 |  | 0
35a | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 2-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | Exclude | 4-lane arterial | 2043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2043 | 0 |  | 0
35b | Mill Road : Drury South connection from Fitzgerald/Cossey intersection to SH1 + Interchange | 4-lane- new road layout with active modes on both sides (depends on Mill Road design and sequencing) | Exclude | 4-lane arterial | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2050 | 0 |  | 0
36 | Complete Bremner-Norrie Road connection from SH1 upto GSR (overlap with project 12) | 4-lane urban- upgrade with active modes on both sides (SGA design) | Exclude | 4-lane arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 |  | 0 |  | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50286768.5201 | 4322630.5891 | 46418410.5859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101027809.6951 | 0 | 101027809.6951 | 2039 | Arterial | 0 | 51524182.9445 | 2033 | 49503626.7506 |  | 2039
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99324280.7316 | 5955831.4303 | 60846398.2096 | 0 | 0 | 0 | 0 | 166126510.3715 | 0 | 166126510.3715 | 0 | Arterial | 0 | 84724520.2895 | 2050 | 81401990.0821 |  | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6336988.0624 | 64740398.3153 | 0 | 0 | 0 | 0 | 71077386.3777 | 0 | 71077386.3777 | 0 | Arterial | 0 | 36249467.0527 | 2050 | 34827919.3251 |  | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120729103.525 | 3802977.5966 | 45203417.1867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169735498.3084 | 0 | 169735498.3084 | 0 | Arterial | 0 | 86565104.1373 | 2044 | 83170394.1711 |  | 0
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10440359.6788 | 106661561.8495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117101921.5283 | 0 | 117101921.5283 | 0 | Arterial | 0 | 59721979.9794 | 2044 | 57379941.5489 |  | 0
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5479626.0309 | 55981353.9749 | 0 | 0 | 0 | 0 | 0 | 61460980.0058 | 0 | 61460980.0058 | 0 | Arterial | 0 | 31345099.8029 | 2049 | 30115880.2028 |  | 0
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7089266.1774 | 72425876.705 | 0 | 0 | 0 | 0 | 0 | 79515142.8824 | 0 | 79515142.8824 | 0 | Arterial | 0 | 40552722.87 | 2049 | 38962420.0124 |  | 0
38a | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | Exclude | 2-lane Arterial | 2046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2046 | 0 |  | 0
38b | Mill Road: From Waihoehoe Rd to Papakura (alternative project 37) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | Exclude | 4-lane arterial | 2055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2055 | 0 |  | 0
18a | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 2-lane urban- new road layout with active modes on both sides, TDM , (depends on Mill Rd) | Exclude | 0 | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2036 | 0 |  | 0
18b | Mill Road: From Waihoehoe Rd to Fitzgerald Road (depends on Mill Road alignment) | 4-lane urban- with active modes on both sides, TDM , (depends on Mill Rd) | Exclude | 0 | 2052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2052 | 0 |  | 0
39a | New Bremner Rd arterial from SH1 to Auranga development | 2-lane urban- new road layout with active modes on both sides (Under construction) | Exclude | Interim 2-lane Arterial | Under Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | Under Construction | 0 |  | 0
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1844175.8141 | 18840603.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20684778.8881 | 0 | 20684778.8881 | 0 | Arterial | 0 | 10549237.2329 | 2047 | 10135541.6552 |  | 0
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284974.1156 | 13127646.0128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14412620.1285 | 0 | 14412620.1285 | 0 | Arterial | 0 | 7350436.2655 | 2047 | 7062183.8629 |  | 0
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5386705.2732 | 1398846.4209 | 14482436.4017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21267988.0959 | 0 | 21267988.0959 | 2037 | Arterial | 0 | 10846673.9289 | 2027 | 10421314.167 |  | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730015.3286 | 7458035.6917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8188051.0203 | 8188051.0203 | 0 | 0 | Arterial | 4175906.0204 | 0 | 2031 | 4012144.9999 |  | 0
41a | Jesmond Rd upgrades from SH22 to Waipupuke development boundary | 2-lane urban- upgrade existing road with active modes on both sides (TDM) | Exclude | Interim Arterial | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2027 | 0 |  | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35512162.8311 | 1709432.0006 | 20896346.0698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58117940.9015 | 0 | 58117940.9015 | 0 | Arterial | 0 | 29640149.8598 | 2047 | 28477791.0417 |  | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2028 | 0 |  | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 829132.152 | 8470640.1915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9299772.3435 | 0 | 9299772.3435 | 2038 | Arterial | 0 | 4742883.8952 | 2031 | 4556888.4483 |  | 2038
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90549574.085 | 1392055.2919 | 22814827.9871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114756457.364 | 0 | 114756457.364 | 0 | Arterial | 0 | 58525793.2556 | 2047 | 56230664.1084 |  | 0
43a | Intersection upgrade on Jesmond Rd/SH22 Rd | 2-lane intersection (Intersection upgrade + active mode crossings) | Exclude | State Highway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 |  | 0 |  | 0
43b | Intersection upgrade on Jesmond Rd/SH22 Rd | Multi-lane signalised intersection (Intersection upgrade + active mode crossings) | Exclude | 4-lane arterial | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2024 | 0 |  | 0
44 | Intersection at SH22/Burberry Rd (likely to close entirely) | Interim design and likely to close - subject to Auranga assessment | Exclude | 4-lane arterial | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2023 | 0 |  | 0
45 | Upgrade intersection at SH22/Victoria Rd | subject to Auranga assessment | Exclude | State Highway | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2024 | 0 |  | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824834.1634 | 8426730.7683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9251564.9318 | 824834.1634 | 8426730.7683 | 2035 | Arterial | 420665.4233 | 4297632.6918 | 2031 | 4533266.8166 |  | 2035
47 | Old Bremner Road Upgrade from Jesmond Road to Auranga Precinct | 2-lane urban- new road layout with active modes on both sides (Under construction) | Exclude | 0 | Under Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | Under Construction | 0 |  | 0
48 | Collector road south of New Bremner/ Old Bremner intersection | 2-lane urban- new road layout with active modes on both sides (Under construction) | Exclude | 0 | Under Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | Under Construction | 0 |  | 0
49 | SH22 improvements from GSR Intersection to Jesmond Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Exclude | State Highway | 2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2032 | 0 |  | 0
50a | SH22 improvements from Jesmond Rd to Oira Rd- active mode upgrades on the northern section | 2-lane urban- upgrade existing road layout with active modes on northern side only | Exclude | State Highway | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2026 | 0 |  | 0
50b | SH22 improvements from Jesmond Rd to Oira Rd | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Exclude | State Highway | 2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2032 | 0 |  | 0
51 | SH22 improvements from Oira Rd to Oira Creek - subject to design, could be incorporated with project 60 | Upgrade road layout to future urban boundary + active modes on both sides | Exclude | State Highway | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2037 | 0 |  | 0
52 | Intersection upgrade- on SH22/ McPherson Rd/Karaka Rd (Auranga B1) | Ultimate intersection form | Exclude | 4-lane arterial | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2024 | 0 |  | 0
53 | New intersection east of Jesmond Rd (Auranga B1 main street) | Ultimate intersection form (left-in left-out) | Exclude | 4-lane arterial upgrade | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2024 | 0 |  | 0
54 | New N-S collectors internal to Auranga B1 (2 links )+ Intersections | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 2025 | 0 | 0 | 0 | 203844.5863 | 2075750.5813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2075750.5813 | 2075750.5813 | 0 | 0 | Collector | 0 | 0 | 2025 | 2075750.5813 |  | 0
55 | New E-W collector Jesmond Rd to SH22 | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Collector | 0 | 0 |  | 0 |  | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13284839.242 | 3708089.0409 | 37882848.9385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54875777.2214 | 0 | 54875777.2214 | 2037 | Collector | 0 | 0 | 2034 | 54875777.2214 |  | 0
56 | Burberry Rd north connection to Auranga Precinct | 2-lane collector- new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | Under construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Collector | 0 | 0 | Under construction | 0 |  | 0
57 | New access road to Drury West Station | 2-lane urban- new road layout with active modes on both sides, (TDM) | Exclude | 0 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2026 | 0 |  | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 756954.7508 | 7733256.1762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8490210.927 | 0 | 8490210.927 | 2036 | Collector | 0 | 0 | 2033 | 8490210.927 |  | 2035
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1111582.7776 | 11356232.8148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12467815.5924 | 0 | 12467815.5924 | 2038 | Collector | 0 | 0 | 2033 | 12467815.5924 |  | 2038
60a | SH22 Intersection upgrade - Oira Rd (3 leg) | Interim Roundabout | Exclude | 2-lane Arterial | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2026 | 0 |  | 0
60b | SH22 Intersection upgrade - Oira Rd (4 leg) | Ultimate intersection form | Exclude | 4-lane arterial | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2037 | 0 |  | 0
63 | New collectors internal to Waipupuke PC61 (3 links )+ Intersections | 2-lane urban - new collector with active mode on both sides + intersection improvements (TDM) | Exclude | Greenfields Collector | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Collector | 0 | 0 | 2026 | 0 |  | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2036 | 0 |  | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932659.916 | 9528308.0636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10460967.9796 | 0 | 10460967.9796 | 0 | Arterial | 0 | 5335093.6696 | 2036 | 5125874.31 |  | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1933410.1277 | 19752245.1582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21685655.2859 | 0 | 21685655.2859 | 0 | Arterial | 0 | 11059684.1958 | 2047 | 10625971.0901 |  | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 481865.2934 | 4922867.2548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5404732.5482 | 0 | 5404732.5482 | 0 | Arterial | 0 | 2756413.5996 | 2047 | 2648318.9486 |  | 0
66 | SH22 improvements - west of SH1 interchange to GSR | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Exclude | State Highway | 2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Arterial | 0 | 0 | 2032 | 0 |  | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47503573.0814 | 4874848.2151 | 49802778.869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102181200.1655 | 0 | 102181200.1655 | 2037 | Arterial | 0 | 52112412.0844 | 2033 | 50068788.0811 |  | 2037
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80527456.7457 | 3002095.2152 | 30670223.4716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114199775.4324 | 0 | 114199775.4324 | 0 | Arterial | 0 | 58241885.4705 | 2037 | 55957889.9619 |  | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 782706.8127 | 7996346.2644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8779053.0771 | 782706.8127 | 7996346.2644 |  | Collector | 0 | 0 | 2035 | 8779053.0771 |  | 2035
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627538.3203 | 6412941.2414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7040479.5617 | 7040479.5617 | 0 | 0 | Arterial | 3590644.5765 | 0 | 2031 | 3449834.9852 |  | 0
0
[5 empty] | Filter total | 0 | 0 | 0 | 203844.5863 | 2075750.5813 | 0 | 2842241.7294 | 630254.8781 | 7705769.2215 | 11928750.2779 | 42077942.0238 | 0 | 6179008.7165 | 3176975.2126 | 257459145.2246 | 87969067.0889 | 244865199.8095 | 35924053.7281 | 63886469.4032 | 0 | 0 | 120729103.525 | 14243337.2754 | 151864979.0362 | 126061736.9161 | 8645912.6433 | 100354535.5567 | 111893172.9399 | 145769073.0147 | 177373316.3409 | 0 | 0 | 0 | 0 | 1723655795.1437 | 76616692.641 | 1647039102.5027 |  | 0 | 33664994.07 | 701132404.0148 |  | 988858397.0589
[5 empty] | Grand total | 0 | 0 | 0 | 203844.5863 | 2075750.5813 | 0 | 2842241.7294 | 630254.8781 | 7705769.2215 | 11928750.2779 | 42077942.0238 | 0 | 6179008.7165 | 3176975.2126 | 257459145.2246 | 87969067.0889 | 244865199.8095 | 35924053.7281 | 63886469.4032 | 0 | 0 | 120729103.525 | 14243337.2754 | 151864979.0362 | 126061736.9161 | 8645912.6433 | 100354535.5567 | 111893172.9399 | 145769073.0147 | 177373316.3409 | 0 | 0 | 0 | 0 | 1723655795.1437 | 76616692.641 | 1647039102.5027 |  | 0 | 33664994.07 | 701132404.0148 |  | 988858397.0589
[5 empty] | Total of includes | 0 | 0 | 0 | 0 | 0 | 0 | 2842241.7294 | 630254.8781 | 7705769.2215 | 11928750.2779 | 42077942.0238 | 0 | 6179008.7165 | 3176975.2126 | 257191904.7894 | 85238865.9189 | 244865199.8095 | 35924053.7281 | 63886469.4032 | 0 | 0 | 120729103.525 | 14243337.2754 | 151864979.0362 | 126061736.9161 | 8645912.6433 | 100354535.5567 | 111893172.9399 | 145769073.0147 | 177373316.3409 | 0 | 0 | 0 | 0 | 1718582602.9571 | 74540942.0597 | 1644041660.8974 |  | 0 | 33664994.07 | 701132404.0148 |  | 983785204.8723

## LTP_for DC_model
1 | 2 |  | 3 | 4 |  |  |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
[28 empty] | 51% | WK/NZTA funding rate
Project number | Project name | Project description | Include in DCs? | Corrider Type |  | Funding area | DC growth percentage | Construction year | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | Total | Total in LTP (2025 to 2034) | Total beyond 2034 | Greg's adjusted year to meet financial constraints | Collector road indicator | WK funding within the LTP (51% for non-collectors) | WK funding beyond 2031 (51% for non-collectors) | Construction year prior to adjustment | Growth share of Cost
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial |  | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1587565.7747 | 16219004.9271 | 0 | 0 | 0 | 17806570.7019 | 17806570.7019 |  | 0 | Arterial |  |  | 2031 | 17025901.0453
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial |  | Transport - Drury East IPA | 95.62% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439580.3055 | 4490872.2869 | 0 | 0 | 0 | 0 | 4930452.5925 | 4930452.5925 |  | 0 | Arterial |  |  | 2030 | 4714293.3557
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial |  | Transport - Drury East IPA | 95.62% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 2020678.52 | 567229.3903 | 6247153.5603 | 0 | 0 | 0 | 0 | 0 | 8835061.4705 | 8835061.4705 |  | 0 | Arterial |  |  | 2029 | 8447717.6906
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial |  | Transport - Drury East IPA | 95.62% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial |  | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial |  | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 76761.0872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76761.0872 | 76761.0872 |  | 0 | Arterial |  |  | 2031 | 73395.7535
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial |  | Transport - Drury East IPA | 95.62% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 351624.7276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 351624.7276 | 351624.7276 |  | 0 | Arterial |  |  | 2029 | 336208.9151
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade |  | Transport - Drury East IPA | 95.62% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) |  | Transport - Drury East IPA | 95.62% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial |  | Transport - Drury East IPA | 95.62% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Drury East IPA | 95.62% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Drury East IPA | 95.62% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28324.8052 | 28324.8052 | 28324.8052 |  | 0 | Collector |  |  | 2035 | 27082.9986
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial |  | Transport - Drury East IPA | 95.62% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial |  | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial |  | Transport - Drury East IPA | 95.62% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 136001.2776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136001.2776 | 136001.2776 |  | 0 | Arterial |  |  | 2038 | 130038.7555
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector |  | Transport - Drury East IPA | 95.62% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Drury East IPA | 95.62% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) |  | Transport - Drury East IPA | 95.62% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6024533.4986 | 1502581.6955 | 7527115.1941 | 7527115.1941 |  | 0 | Collector |  |  | 2035 | 7197113.9529
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector |  | Transport - Drury East IPA | 95.62% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial |  | Transport - Drury East IPA | 95.62% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial |  | Transport - Drury East IPA | 95.62% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure |  | Transport - Drury East IPA | 95.62% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  | Transport - Drury East IPA | 95.62% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure |  | Transport - Drury East IPA | 95.62% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade |  | Transport - Drury East IPA | 95.62% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure |  | Transport - Drury East IPA | 95.62% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade |  | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure |  | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial |  | Transport - Drury East IPA | 95.62% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial |  | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial |  | Transport - Drury East IPA | 95.62% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial |  | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial |  | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 433037.9358 | 433037.9358 | 433037.9358 |  | 0 | Arterial |  |  | 2031 | 414052.8329
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) |  | Transport - Drury East IPA | 95.62% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  | Transport - Drury East IPA | 95.62% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure |  | Transport - Drury East IPA | 95.62% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade |  | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure |  | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure |  | Transport - Drury East IPA | 95.62% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) |  | Transport - Drury East IPA | 95.62% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626165.4502 | 626165.4502 | 626165.4502 |  | 0 | Collector |  |  | 2035 | 598713.3161
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure |  | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94130.748 | 961941.1862 | 0 | 0 | 0 | 1056071.9343 | 1056071.9343 |  | 0 | Arterial |  |  | 2031 | 1009771.9853 | Arterial
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial | WK DE | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -809658.5451 | -8271692.5128 | 0 | 0 | 0 | -9081351.058 | -9081351.058 |  | 0 | Arterial |  |  | 2031 | -8683209.5331
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial | WK DE | Transport - Drury East IPA | 95.62% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -224185.9558 | -2290344.8663 | 0 | 0 | 0 | 0 | -2514530.8222 | -2514530.8222 |  | 0 | Arterial |  |  | 2030 | -2404289.6114
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial | WK DE | Transport - Drury East IPA | 95.62% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | -1030546.0452 | -289286.989 | -3186048.3157 | 0 | 0 | 0 | 0 | 0 | -4505881.35 | -4505881.35 |  | 0 | Arterial |  |  | 2029 | -4308336.0222
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial | WK DE | Transport - Drury East IPA | 95.62% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial | WK DE | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial | WK DE | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | -39148.1545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -39148.1545 | -39148.1545 |  | 0 | Arterial |  |  | 2031 | -37431.8343
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) | WK DE | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Drury East IPA | 95.62% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | -179328.6111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -179328.6111 | -179328.6111 |  | 0 | Arterial |  |  | 2029 | -171466.5467
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade | WK DE | Transport - Drury East IPA | 95.62% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) | WK DE | Transport - Drury East IPA | 95.62% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector | WK DE | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE | Transport - Drury East IPA | 95.62% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Drury East IPA | 95.62% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Drury East IPA | 95.62% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) | WK DE | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial | WK DE | Transport - Drury East IPA | 95.62% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial | WK DE | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial | WK DE | Transport - Drury East IPA | 95.62% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | -69360.6516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -69360.6516 | -69360.6516 |  | 0 | Arterial |  |  | 2038 | -66319.7653
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Drury East IPA | 95.62% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Drury East IPA | 95.62% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) | WK DE | Transport - Drury East IPA | 95.62% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector | WK DE | Transport - Drury East IPA | 95.62% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial | WK DE | Transport - Drury East IPA | 95.62% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector | WK DE | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial | WK DE | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE | Transport - Drury East IPA | 95.62% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure | WK DE | Transport - Drury East IPA | 95.62% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Drury East IPA | 95.62% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure | WK DE | Transport - Drury East IPA | 95.62% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade | WK DE | Transport - Drury East IPA | 95.62% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure | WK DE | Transport - Drury East IPA | 95.62% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade | WK DE | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure | WK DE | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial | WK DE | Transport - Drury East IPA | 95.62% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial | WK DE | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial | WK DE | Transport - Drury East IPA | 95.62% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial | WK DE | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial | WK DE | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -220849.3473 | -220849.3473 | -220849.3473 |  | 0 | Arterial |  |  | 2031 | -211166.9448
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) | WK DE | Transport - Drury East IPA | 95.62% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector | WK DE | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) | WK DE | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Drury East IPA | 95.62% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure | WK DE | Transport - Drury East IPA | 95.62% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade | WK DE | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure | WK DE | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure | WK DE | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure | WK DE | Transport - Drury East IPA | 95.62% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) | WK DE | Transport - Drury East IPA | 95.62% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure | WK DE | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -48006.6815 | -490590.005 | 0 | 0 | 0 | -538596.6865 | -538596.6865 |  | 0 | Arterial |  |  | 2031 | -514983.7125
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial |  | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207073.7967 | 2115522.3818 | 0 | 0 | 0 | 2322596.1785 | 2322596.1785 |  | 0 | Arterial |  |  | 2031 | 1436094.2283
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial |  | Transport - Drury West 1 IPA | 61.83% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114673.1232 | 1171531.9009 | 0 | 0 | 0 | 0 | 1286205.0241 | 1286205.0241 |  | 0 | Arterial |  |  | 2030 | 795278.8473
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial |  | Transport - Drury West 1 IPA | 61.83% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial |  | Transport - Drury West 1 IPA | 61.83% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial |  | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial |  | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial |  | Transport - Drury West 1 IPA | 61.83% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade |  | Transport - Drury West 1 IPA | 61.83% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) |  | Transport - Drury West 1 IPA | 61.83% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial |  | Transport - Drury West 1 IPA | 61.83% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Drury West 1 IPA | 61.83% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Drury West 1 IPA | 61.83% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial |  | Transport - Drury West 1 IPA | 61.83% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial |  | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial |  | Transport - Drury West 1 IPA | 61.83% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2038 | 0
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector |  | Transport - Drury West 1 IPA | 61.83% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Drury West 1 IPA | 61.83% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) |  | Transport - Drury West 1 IPA | 61.83% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector |  | Transport - Drury West 1 IPA | 61.83% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial |  | Transport - Drury West 1 IPA | 61.83% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial |  | Transport - Drury West 1 IPA | 61.83% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure |  | Transport - Drury West 1 IPA | 61.83% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  | Transport - Drury West 1 IPA | 61.83% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure |  | Transport - Drury West 1 IPA | 61.83% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade |  | Transport - Drury West 1 IPA | 61.83% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure |  | Transport - Drury West 1 IPA | 61.83% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade |  | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure |  | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial |  | Transport - Drury West 1 IPA | 61.83% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial |  | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 547511.4964 | 5593526.7688 | 0 | 0 | 0 | 6141038.2652 | 6141038.2652 |  | 0 | Arterial |  |  | 2031 | 3797091.2421
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial |  | Transport - Drury West 1 IPA | 61.83% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial |  | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial |  | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391796.2276 | 391796.2276 | 391796.2276 |  | 0 | Arterial |  |  | 2031 | 242253.1761
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) |  | Transport - Drury West 1 IPA | 61.83% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  | Transport - Drury West 1 IPA | 61.83% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure |  | Transport - Drury West 1 IPA | 61.83% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade |  | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure |  | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure |  | Transport - Drury West 1 IPA | 61.83% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) |  | Transport - Drury West 1 IPA | 61.83% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39135.3406 | 39135.3406 | 39135.3406 |  | 0 | Collector |  |  | 2035 | 24197.9373
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure |  | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172573.0381 | 1763558.8414 | 0 | 0 | 0 | 1936131.8795 | 1936131.8795 |  | 0 | Arterial |  |  | 2031 | 1197137.8593
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -105607.6363 | -1078916.4147 | 0 | 0 | 0 | -1184524.051 | -1184524.051 |  | 0 | Arterial |  |  | 2031 | -732408.0564
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -58483.2928 | -597481.2695 | 0 | 0 | 0 | 0 | -655964.5623 | -655964.5623 |  | 0 | Arterial |  |  | 2030 | -405592.2121
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) | WK DE | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade | WK DE | Transport - Drury West 1 IPA | 61.83% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) | WK DE | Transport - Drury West 1 IPA | 61.83% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector | WK DE | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Drury West 1 IPA | 61.83% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Drury West 1 IPA | 61.83% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) | WK DE | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2038 | 0
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Drury West 1 IPA | 61.83% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Drury West 1 IPA | 61.83% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) | WK DE | Transport - Drury West 1 IPA | 61.83% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector | WK DE | Transport - Drury West 1 IPA | 61.83% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector | WK DE | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure | WK DE | Transport - Drury West 1 IPA | 61.83% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure | WK DE | Transport - Drury West 1 IPA | 61.83% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade | WK DE | Transport - Drury West 1 IPA | 61.83% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure | WK DE | Transport - Drury West 1 IPA | 61.83% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade | WK DE | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure | WK DE | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -279230.8632 | -2852698.6521 | 0 | 0 | 0 | -3131929.5153 | -3131929.5153 |  | 0 | Arterial |  |  | 2031 | -1936516.5335
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -199816.0761 | -199816.0761 | -199816.0761 |  | 0 | Arterial |  |  | 2031 | -123549.1198
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) | WK DE | Transport - Drury West 1 IPA | 61.83% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector | WK DE | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) | WK DE | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Drury West 1 IPA | 61.83% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure | WK DE | Transport - Drury West 1 IPA | 61.83% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade | WK DE | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure | WK DE | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure | WK DE | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure | WK DE | Transport - Drury West 1 IPA | 61.83% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) | WK DE | Transport - Drury West 1 IPA | 61.83% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure | WK DE | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -88012.2494 | -899415.0091 | 0 | 0 | 0 | -987427.2585 | -987427.2585 |  | 0 | Arterial |  |  | 2031 | -610540.3083
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207073.7967 | 2115522.3818 | 0 | 0 | 0 | 2322596.1785 | 2322596.1785 |  | 0 | Arterial |  |  | 2031 | 1949895.8287
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial |  | Transport - Drury West 2 IPA | 83.95% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2030 | 0
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial |  | Transport - Drury West 2 IPA | 83.95% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial |  | Transport - Drury West 2 IPA | 83.95% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial |  | Transport - Drury West 2 IPA | 83.95% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade |  | Transport - Drury West 2 IPA | 83.95% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) |  | Transport - Drury West 2 IPA | 83.95% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial |  | Transport - Drury West 2 IPA | 83.95% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Drury West 2 IPA | 83.95% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Drury West 2 IPA | 83.95% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial |  | Transport - Drury West 2 IPA | 83.95% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial |  | Transport - Drury West 2 IPA | 83.95% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2038 | 0
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector |  | Transport - Drury West 2 IPA | 83.95% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Drury West 2 IPA | 83.95% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) |  | Transport - Drury West 2 IPA | 83.95% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector |  | Transport - Drury West 2 IPA | 83.95% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial |  | Transport - Drury West 2 IPA | 83.95% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial |  | Transport - Drury West 2 IPA | 83.95% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure |  | Transport - Drury West 2 IPA | 83.95% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  | Transport - Drury West 2 IPA | 83.95% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure |  | Transport - Drury West 2 IPA | 83.95% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade |  | Transport - Drury West 2 IPA | 83.95% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure |  | Transport - Drury West 2 IPA | 83.95% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade |  | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure |  | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial |  | Transport - Drury West 2 IPA | 83.95% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164253.4489 | 1678058.0306 | 0 | 0 | 0 | 1842311.4796 | 1842311.4796 |  | 0 | Arterial |  |  | 2031 | 1546681.0384
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial |  | Transport - Drury West 2 IPA | 83.95% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) |  | Transport - Drury West 2 IPA | 83.95% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  | Transport - Drury West 2 IPA | 83.95% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure |  | Transport - Drury West 2 IPA | 83.95% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade |  | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure |  | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure |  | Transport - Drury West 2 IPA | 83.95% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) |  | Transport - Drury West 2 IPA | 83.95% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117406.0219 | 117406.0219 | 117406.0219 |  | 0 | Collector |  |  | 2035 | 98566.2142
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345146.0762 | 3527117.6828 | 0 | 0 | 0 | 3872263.7589 | 3872263.7589 |  | 0 | Arterial |  |  | 2031 | 3250892.6954
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -105607.6363 | -1078916.4147 | 0 | 0 | 0 | -1184524.051 | -1184524.051 |  | 0 | Arterial |  |  | 2031 | -994446.8726
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2030 | 0
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) | WK DE | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade | WK DE | Transport - Drury West 2 IPA | 83.95% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) | WK DE | Transport - Drury West 2 IPA | 83.95% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector | WK DE | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Drury West 2 IPA | 83.95% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Drury West 2 IPA | 83.95% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) | WK DE | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2038 | 0
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Drury West 2 IPA | 83.95% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Drury West 2 IPA | 83.95% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) | WK DE | Transport - Drury West 2 IPA | 83.95% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector | WK DE | Transport - Drury West 2 IPA | 83.95% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector | WK DE | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure | WK DE | Transport - Drury West 2 IPA | 83.95% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure | WK DE | Transport - Drury West 2 IPA | 83.95% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade | WK DE | Transport - Drury West 2 IPA | 83.95% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure | WK DE | Transport - Drury West 2 IPA | 83.95% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade | WK DE | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure | WK DE | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -83769.259 | -855809.5956 | 0 | 0 | 0 | -939578.8546 | -939578.8546 |  | 0 | Arterial |  |  | 2031 | -788807.3296
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) | WK DE | Transport - Drury West 2 IPA | 83.95% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector | WK DE | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) | WK DE | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Drury West 2 IPA | 83.95% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure | WK DE | Transport - Drury West 2 IPA | 83.95% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade | WK DE | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure | WK DE | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure | WK DE | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure | WK DE | Transport - Drury West 2 IPA | 83.95% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) | WK DE | Transport - Drury West 2 IPA | 83.95% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure | WK DE | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -176024.4988 | -1798830.0182 | 0 | 0 | 0 | -1974854.5171 | -1974854.5171 |  | 0 | Arterial |  |  | 2031 | -1657955.2747
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial |  | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 483172.1923 | 4936218.8909 | 0 | 0 | 0 | 5419391.0832 | 5419391.0832 |  | 0 | Arterial |  |  | 2031 | 3319528.1405
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial |  | Transport - Opaheke IPA | 61.25% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133785.3104 | 1366787.2178 | 0 | 0 | 0 | 0 | 1500572.5281 | 1500572.5281 |  | 0 | Arterial |  |  | 2030 | 919142.5121
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial |  | Transport - Opaheke IPA | 61.25% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 168389.8767 | 47269.1159 | 520596.13 | 0 | 0 | 0 | 0 | 0 | 736255.1225 | 736255.1225 |  | 0 | Arterial |  |  | 2029 | 450976.7906
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial |  | Transport - Opaheke IPA | 61.25% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial |  | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial |  | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 6396.7573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6396.7573 | 6396.7573 |  | 0 | Arterial |  |  | 2031 | 3918.1922
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial |  | Transport - Opaheke IPA | 61.25% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade |  | Transport - Opaheke IPA | 61.25% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) |  | Transport - Opaheke IPA | 61.25% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial |  | Transport - Opaheke IPA | 61.25% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Opaheke IPA | 61.25% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Opaheke IPA | 61.25% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial |  | Transport - Opaheke IPA | 61.25% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial |  | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial |  | Transport - Opaheke IPA | 61.25% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 11333.4398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11333.4398 | 11333.4398 |  | 0 | Arterial |  |  | 2038 | 6942.0479
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector |  | Transport - Opaheke IPA | 61.25% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Opaheke IPA | 61.25% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) |  | Transport - Opaheke IPA | 61.25% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector |  | Transport - Opaheke IPA | 61.25% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial |  | Transport - Opaheke IPA | 61.25% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial |  | Transport - Opaheke IPA | 61.25% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure |  | Transport - Opaheke IPA | 61.25% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  | Transport - Opaheke IPA | 61.25% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure |  | Transport - Opaheke IPA | 61.25% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade |  | Transport - Opaheke IPA | 61.25% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure |  | Transport - Opaheke IPA | 61.25% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade |  | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure |  | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial |  | Transport - Opaheke IPA | 61.25% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial |  | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial |  | Transport - Opaheke IPA | 61.25% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial |  | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial |  | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) |  | Transport - Opaheke IPA | 61.25% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  | Transport - Opaheke IPA | 61.25% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure |  | Transport - Opaheke IPA | 61.25% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade |  | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure |  | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure |  | Transport - Opaheke IPA | 61.25% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) |  | Transport - Opaheke IPA | 61.25% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure |  | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -246417.8181 | -2517471.6343 | 0 | 0 | 0 | -2763889.4524 | -2763889.4524 |  | 0 | Arterial |  |  | 2031 | -1692959.3517
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68230.5083 | -697061.4811 | 0 | 0 | 0 | 0 | -765291.9894 | -765291.9894 |  | 0 | Arterial |  |  | 2030 | -468762.6812
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | -85878.8371 | -24107.2491 | -265504.0263 | 0 | 0 | 0 | 0 | 0 | -375490.1125 | -375490.1125 |  | 0 | Arterial |  |  | 2029 | -229998.1632
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | -3262.3462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3262.3462 | -3262.3462 |  | 0 | Arterial |  |  | 2031 | -1998.278
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) | WK DE | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade | WK DE | Transport - Opaheke IPA | 61.25% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) | WK DE | Transport - Opaheke IPA | 61.25% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector | WK DE | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Opaheke IPA | 61.25% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Opaheke IPA | 61.25% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) | WK DE | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | -5780.0543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5780.0543 | -5780.0543 |  | 0 | Arterial |  |  | 2038 | -3540.4444
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Opaheke IPA | 61.25% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Opaheke IPA | 61.25% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) | WK DE | Transport - Opaheke IPA | 61.25% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector | WK DE | Transport - Opaheke IPA | 61.25% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector | WK DE | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure | WK DE | Transport - Opaheke IPA | 61.25% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure | WK DE | Transport - Opaheke IPA | 61.25% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade | WK DE | Transport - Opaheke IPA | 61.25% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure | WK DE | Transport - Opaheke IPA | 61.25% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade | WK DE | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure | WK DE | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) | WK DE | Transport - Opaheke IPA | 61.25% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector | WK DE | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) | WK DE | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Opaheke IPA | 61.25% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure | WK DE | Transport - Opaheke IPA | 61.25% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade | WK DE | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure | WK DE | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure | WK DE | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure | WK DE | Transport - Opaheke IPA | 61.25% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) | WK DE | Transport - Opaheke IPA | 61.25% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure | WK DE | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2030 | 0
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade |  | Transport - Southern Growth Area 3 | 96.45% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) |  | Transport - Southern Growth Area 3 | 96.45% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Southern Growth Area 3 | 96.45% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Southern Growth Area 3 | 96.45% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2038 | 0
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector |  | Transport - Southern Growth Area 3 | 96.45% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Southern Growth Area 3 | 96.45% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) |  | Transport - Southern Growth Area 3 | 96.45% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector |  | Transport - Southern Growth Area 3 | 96.45% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure |  | Transport - Southern Growth Area 3 | 96.45% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure |  | Transport - Southern Growth Area 3 | 96.45% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade |  | Transport - Southern Growth Area 3 | 96.45% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure |  | Transport - Southern Growth Area 3 | 96.45% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade |  | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure |  | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) |  | Transport - Southern Growth Area 3 | 96.45% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  | Transport - Southern Growth Area 3 | 96.45% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure |  | Transport - Southern Growth Area 3 | 96.45% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade |  | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure |  | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure |  | Transport - Southern Growth Area 3 | 96.45% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) |  | Transport - Southern Growth Area 3 | 96.45% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15688.458 | 160323.531 | 0 | 0 | 0 | 176011.989 | 176011.989 |  | 0 | Arterial |  |  | 2031 | 169756.0073
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2030 | 0
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2038 | 0
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8001.1136 | -81765.0008 | 0 | 0 | 0 | -89766.1144 | -89766.1144 |  | 0 | Arterial |  |  | 2031 | -86575.5637
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69024.5989 | 705174.1273 | 0 | 0 | 0 | 774198.7262 | 774198.7262 |  | 0 | Arterial |  |  | 2031 | 281416.0374
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19112.1872 | 195255.3168 | 0 | 0 | 0 | 0 | 214367.504 | 214367.504 |  | 0 | Arterial |  |  | 2030 | 77921.148
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade |  | Transport - Southern Growth Area 2 | 36.35% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) |  | Transport - Southern Growth Area 2 | 36.35% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Southern Growth Area 2 | 36.35% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Southern Growth Area 2 | 36.35% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2038 | 0
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector |  | Transport - Southern Growth Area 2 | 36.35% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Southern Growth Area 2 | 36.35% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) |  | Transport - Southern Growth Area 2 | 36.35% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector |  | Transport - Southern Growth Area 2 | 36.35% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure |  | Transport - Southern Growth Area 2 | 36.35% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure |  | Transport - Southern Growth Area 2 | 36.35% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade |  | Transport - Southern Growth Area 2 | 36.35% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure |  | Transport - Southern Growth Area 2 | 36.35% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade |  | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure |  | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) |  | Transport - Southern Growth Area 2 | 36.35% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  | Transport - Southern Growth Area 2 | 36.35% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure |  | Transport - Southern Growth Area 2 | 36.35% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade |  | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure |  | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure |  | Transport - Southern Growth Area 2 | 36.35% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) |  | Transport - Southern Growth Area 2 | 36.35% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35202.5454 | -359638.8049 | 0 | 0 | 0 | -394841.3503 | -394841.3503 |  | 0 | Arterial |  |  | 2031 | -143522.179
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9747.2155 | -99580.2116 | 0 | 0 | 0 | 0 | -109327.4271 | -109327.4271 |  | 0 | Arterial |  |  | 2030 | -39739.7855
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2038 | 0
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138049.1978 | 1410348.2545 | 0 | 0 | 0 | 1548397.4523 | 1548397.4523 |  | 0 | Arterial |  |  | 2031 | 945256.1218
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38224.3744 | 390510.6336 | 0 | 0 | 0 | 0 | 428735.008 | 428735.008 |  | 0 | Arterial |  |  | 2030 | 261731.5021
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 56129.9589 | 15756.372 | 173532.0433 | 0 | 0 | 0 | 0 | 0 | 245418.3742 | 245418.3742 |  | 0 | Arterial |  |  | 2029 | 149821.4946
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 2132.2524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2132.2524 | 2132.2524 |  | 0 | Arterial |  |  | 2031 | 1301.6843
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 9016.0187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9016.0187 | 9016.0187 |  | 0 | Arterial |  |  | 2029 | 5504.0434
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade |  | Transport - Southern Growth Area 1 | 61.05% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) |  | Transport - Southern Growth Area 1 | 61.05% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Southern Growth Area 1 | 61.05% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Southern Growth Area 1 | 61.05% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 3777.8133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3777.8133 | 3777.8133 |  | 0 | Arterial |  |  | 2038 | 2306.2561
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector |  | Transport - Southern Growth Area 1 | 61.05% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Southern Growth Area 1 | 61.05% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) |  | Transport - Southern Growth Area 1 | 61.05% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector |  | Transport - Southern Growth Area 1 | 61.05% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure |  | Transport - Southern Growth Area 1 | 61.05% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure |  | Transport - Southern Growth Area 1 | 61.05% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade |  | Transport - Southern Growth Area 1 | 61.05% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure |  | Transport - Southern Growth Area 1 | 61.05% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade |  | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure |  | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) |  | Transport - Southern Growth Area 1 | 61.05% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  | Transport - Southern Growth Area 1 | 61.05% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure |  | Transport - Southern Growth Area 1 | 61.05% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade |  | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure |  | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure |  | Transport - Southern Growth Area 1 | 61.05% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) |  | Transport - Southern Growth Area 1 | 61.05% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -70405.0909 | -719277.6098 | 0 | 0 | 0 | -789682.7007 | -789682.7007 |  | 0 | Arterial |  |  | 2031 | -482080.6221
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19494.4309 | -199160.4232 | 0 | 0 | 0 | 0 | -218654.8541 | -218654.8541 |  | 0 | Arterial |  |  | 2030 | -133483.0661
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | -28626.279 | -8035.7497 | -88501.3421 | 0 | 0 | 0 | 0 | 0 | -125163.3708 | -125163.3708 |  | 0 | Arterial |  |  | 2029 | -76408.9623
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | -1087.4487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1087.4487 | -1087.4487 |  | 0 | Arterial |  |  | 2031 | -663.859
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | -4598.1695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4598.1695 | -4598.1695 |  | 0 | Arterial |  |  | 2029 | -2807.0622
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | -1926.6848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1926.6848 | -1926.6848 |  | 0 | Arterial |  |  | 2038 | -1176.1906
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure | WK DE | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69024.5989 | 705174.1273 | 0 | 0 | 0 | 774198.7262 | 774198.7262 |  | 0 | Arterial |  |  | 2031 | 222445.81
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial |  | Transport - Auckland wide | 28.73% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19112.1872 | 195255.3168 | 0 | 0 | 0 | 0 | 214367.504 | 214367.504 |  | 0 | Arterial |  |  | 2030 | 61592.9108
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial |  | Transport - Auckland wide | 28.73% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial |  | Transport - Auckland wide | 28.73% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial |  | Transport - Auckland wide | 28.73% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade |  | Transport - Auckland wide | 28.73% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) |  | Transport - Auckland wide | 28.73% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial |  | Transport - Auckland wide | 28.73% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Auckland wide | 28.73% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Auckland wide | 28.73% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial |  | Transport - Auckland wide | 28.73% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial |  | Transport - Auckland wide | 28.73% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2038 | 0
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector |  | Transport - Auckland wide | 28.73% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  | Transport - Auckland wide | 28.73% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) |  | Transport - Auckland wide | 28.73% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154475.2179 | 38527.7358 | 193002.9537 | 193002.9537 |  | 0 | Collector |  |  | 2035 | 55454.3645
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector |  | Transport - Auckland wide | 28.73% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial |  | Transport - Auckland wide | 28.73% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial |  | Transport - Auckland wide | 28.73% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure |  | Transport - Auckland wide | 28.73% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  | Transport - Auckland wide | 28.73% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure |  | Transport - Auckland wide | 28.73% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade |  | Transport - Auckland wide | 28.73% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure |  | Transport - Auckland wide | 28.73% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade |  | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure |  | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial |  | Transport - Auckland wide | 28.73% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18250.3832 | 186450.8923 | 0 | 0 | 0 | 204701.2755 | 204701.2755 |  | 0 | Arterial |  |  | 2031 | 58815.5722
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial |  | Transport - Auckland wide | 28.73% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) |  | Transport - Auckland wide | 28.73% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  | Transport - Auckland wide | 28.73% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure |  | Transport - Auckland wide | 28.73% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade |  | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure |  | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure |  | Transport - Auckland wide | 28.73% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) |  | Transport - Auckland wide | 28.73% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial | WK DE | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35202.5454 | -359638.8049 | 0 | 0 | 0 | -394841.3503 | -394841.3503 |  | 0 | Arterial |  |  | 2031 | -113447.3631
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial | WK DE | Transport - Auckland wide | 28.73% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9747.2155 | -99580.2116 | 0 | 0 | 0 | 0 | -109327.4271 | -109327.4271 |  | 0 | Arterial |  |  | 2030 | -31412.3845
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial | WK DE | Transport - Auckland wide | 28.73% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial | WK DE | Transport - Auckland wide | 28.73% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial | WK DE | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial | WK DE | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) | WK DE | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Auckland wide | 28.73% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade | WK DE | Transport - Auckland wide | 28.73% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) | WK DE | Transport - Auckland wide | 28.73% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector | WK DE | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE | Transport - Auckland wide | 28.73% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Auckland wide | 28.73% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Auckland wide | 28.73% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) | WK DE | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial | WK DE | Transport - Auckland wide | 28.73% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial | WK DE | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial | WK DE | Transport - Auckland wide | 28.73% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2038 | 0
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector | WK DE | Transport - Auckland wide | 28.73% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE | Transport - Auckland wide | 28.73% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) | WK DE | Transport - Auckland wide | 28.73% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector | WK DE | Transport - Auckland wide | 28.73% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial | WK DE | Transport - Auckland wide | 28.73% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector | WK DE | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial | WK DE | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE | Transport - Auckland wide | 28.73% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure | WK DE | Transport - Auckland wide | 28.73% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2050 | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Auckland wide | 28.73% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure | WK DE | Transport - Auckland wide | 28.73% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2044 | 0
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade | WK DE | Transport - Auckland wide | 28.73% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure | WK DE | Transport - Auckland wide | 28.73% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2049 | 0
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade | WK DE | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure | WK DE | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial | WK DE | Transport - Auckland wide | 28.73% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial | WK DE | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9307.6954 | -95089.9551 | 0 | 0 | 0 | -104397.6505 | -104397.6505 |  | 0 | Arterial |  |  | 2031 | -29995.9418
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial | WK DE | Transport - Auckland wide | 28.73% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial | WK DE | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial | WK DE | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) | WK DE | Transport - Auckland wide | 28.73% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector | WK DE | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) | WK DE | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE | Transport - Auckland wide | 28.73% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure | WK DE | Transport - Auckland wide | 28.73% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade | WK DE | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure | WK DE | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2047 | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure | WK DE | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure | WK DE | Transport - Auckland wide | 28.73% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) | WK DE | Transport - Auckland wide | 28.73% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure | WK DE | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Arterial |  |  | 2031 | 0
#NAME?
[6 empty] | Transport - Drury East IPA |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2585065.6124 | 567229.3903 | 6686733.8658 | 6172568.8097 | 17180946.1133 | 0 | 6024533.4986 | 2590109.8867 | 41807187.1768 | 41807187.1768 | 0
[6 empty] | Transport - Drury West 1 IPA |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114673.1232 | 2098690.2322 | 9472607.992 | 0 | 0 | 430931.5683 | 12116902.9156 | 12116902.9156 | 0
[6 empty] | Transport - Drury West 2 IPA |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 716473.3218 | 7320698.0952 | 0 | 0 | 117406.0219 | 8154577.4389 | 8154577.4389 | 0
[6 empty] | Transport - Opaheke IPA |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 186120.0737 | 47269.1159 | 654381.4404 | 1849959.4101 | 4936218.8909 | 0 | 0 | 0 | 7673948.9309 | 7673948.9309 | 0
[6 empty] | Transport - Southern Growth Area 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15688.458 | 160323.531 | 0 | 0 | 0 | 176011.989 | 176011.989 | 0
[6 empty] | Transport - Southern Growth Area 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 71056.0432 | 15756.372 | 211756.4177 | 528559.8314 | 1410348.2545 | 0 | 0 | 0 | 2237476.9189 | 2237476.9189 | 0
[6 empty] | Transport - Southern Growth Area 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19112.1872 | 264279.9157 | 705174.1273 | 0 | 0 | 0 | 988566.2302 | 988566.2302 | 0
[6 empty] | Transport - Auckland Wide |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19112.1872 | 282530.2989 | 891625.0196 | 0 | 154475.2179 | 38527.7358 | 1386270.4594 | 1386270.4594 | 0
[6 empty] | Transport - Drury IPA |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2842241.7294 | 630254.8781 | 7705769.2215 | 11928750.2779 | 42077942.0238 | 0 | 6179008.7165 | 3176975.2126 | 74540942.0597 | 74540942.0597 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0

## Beyond_LTP_for_DC_model
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
[35 empty] | 51% | WK/NZTA funding rate
Project number | Project name | Project description | Include in DCs? | Corrider Type |  |  | Funding area | DC growth percentage | Construction year | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | Total | Total in LTP (2025 to 2034) | Total beyond 2034 | Adjusted year to meet financial constraints | Collector road indicator | WK funding within the LTP (51% for non-collectors) | WK funding beyond 2031 (51% for non-collectors) | Construction year prior to adjustment | Growth share of Cost
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial |  |  | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial |  |  | Transport - Drury East IPA | 95.62% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2030 | 0
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial |  |  | Transport - Drury East IPA | 95.62% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Drury East IPA | 95.62% | 2033 | 50246.1217 | 513328.0825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 563574.2041 |  | 563574.2041 | 0 | Collector |  |  | 2033 | 538866.1743
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Drury East IPA | 95.62% | 2033 | 51534.4838 | 526490.341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578024.8247 |  | 578024.8247 | 0 | Collector |  |  | 2033 | 552683.2557
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial |  |  | Transport - Drury East IPA | 95.62% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial |  |  | Transport - Drury East IPA | 95.62% | 2031 | 2704506.8296 | 790953.0214 | 8339233.4019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11834693.2528 |  | 11834693.2528 | 0 | Arterial |  |  | 2031 | 11315840.6297
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial |  |  | Transport - Drury East IPA | 95.62% | 2031 | 212925.2162 | 92228.8266 | 942234.8462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1247388.889 |  | 1247388.889 | 0 | Arterial |  |  | 2031 | 1192701.2868
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) |  |  | Transport - Drury East IPA | 95.62% | 2033 | 1392303.6037 | 14224153.3345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15616456.9382 |  | 15616456.9382 | 0 | Collector |  |  | 2033 | 14931805.5093
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Drury East IPA | 95.62% | 2029 | 2315901.509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2315901.509 |  | 2315901.509 | 0 | Arterial |  |  | 2029 | 2214368.5375
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade |  |  | Transport - Drury East IPA | 95.62% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1161292.1797 | 11864077.6234 | 0 | 0 | 0 | 0 | 13025369.803 |  | 13025369.803 | 0 | Arterial |  |  | 2050 | 12454315.9409
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) |  |  | Transport - Drury East IPA | 95.62% | 2035 | 49153521.7714 | 2731065.855 | 27901313.6111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79785901.2375 |  | 79785901.2375 | 0 | Collector |  |  | 2035 | 76287954.7121
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector |  |  | Transport - Drury East IPA | 95.62% | 2033 | 245804.7484 | 2511208.3478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2757013.0962 |  | 2757013.0962 | 0 | Collector |  |  | 2033 | 2636141.0596
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial |  |  | Transport - Drury East IPA | 95.62% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480626.7345 | 4910213.7996 | 0 | 0 | 0 | 0 | 5390840.5341 |  | 5390840.5341 | 0 | Arterial |  |  | 2050 | 5154497.1248
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Drury East IPA | 95.62% | 2035 | 824296.619 | 8421239.0679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9245535.6869 |  | 9245535.6869 | 0 | Collector |  |  | 2035 | 8840196.035
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Drury East IPA | 95.62% | 2035 | 289373.9346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289373.9346 |  | 289373.9346 | 0 | Collector |  |  | 2035 | 276687.3003
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) |  |  | Transport - Drury East IPA | 95.62% | 2033 | 153804.0715 | 1571304.3411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1725108.4126 |  | 1725108.4126 | 0 | Collector |  |  | 2033 | 1649476.7924
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial |  |  | Transport - Drury East IPA | 95.62% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial |  |  | Transport - Drury East IPA | 95.62% | 2031 | 2544663.09 | 622897.2498 | 6790843.9213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9958404.2612 |  | 9958404.2612 | 0 | Arterial |  |  | 2031 | 9521811.2661
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial |  |  | Transport - Drury East IPA | 95.62% | 2038 | 0 | 1442162.4541 | 890403.3733 | 9096603.6984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11429169.5258 |  | 11429169.5258 | 0 | Arterial |  |  | 2038 | 10928095.7369
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Drury East IPA | 95.62% | 2039 | 0 | 0 | 0 | 536534.3494 | 5481381.2407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6017915.5901 |  | 6017915.5901 | 0 | Collector |  |  | 2039 | 5754080.168
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Drury East IPA | 95.62% | 2039 | 0 | 0 | 0 | 932318.134 | 9524816.3256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10457134.4596 |  | 10457134.4596 | 0 | Collector |  |  | 2039 | 9998676.3037
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) |  |  | Transport - Drury East IPA | 95.62% | 2035 | 15350784.3965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15350784.3965 |  | 15350784.3965 | 0 | Collector |  |  | 2035 | 14677780.4935
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector |  |  | Transport - Drury East IPA | 95.62% | 2039 | 0 | 0 | 0 | 87539.8149 | 894330.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981870.4384 |  | 981870.4384 | 0 | Collector |  |  | 2039 | 938823.6064
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial |  |  | Transport - Drury East IPA | 95.62% | 2039 | 0 | 232731.3152 | 821539.7007 | 99738.3525 | 1410777.5647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2564786.9331 |  | 2564786.9331 | 0 | Arterial |  |  | 2039 | 2452342.4109
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector |  |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial |  |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 22629045.834 | 1945183.7651 | 20888284.7637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45462514.3628 |  | 45462514.3628 | 0 | Arterial |  |  | 2033 | 43469362.1681
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial |  |  | Transport - Drury East IPA | 95.62% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44695926.3292 | 2680124.1436 | 27380879.1943 | 0 | 0 | 0 | 0 | 74756929.6672 |  | 74756929.6672 | 0 | Arterial |  |  | 2050 | 71479461.6142
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure |  |  | Transport - Drury East IPA | 95.62% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2851644.6281 | 29133179.2419 | 0 | 0 | 0 | 0 | 31984823.87 |  | 31984823.87 | 0 | Arterial |  |  | 2050 | 30582556.0283
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Drury East IPA | 95.62% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36218731.0575 | 1140893.279 | 13561025.156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50920649.4925 |  | 50920649.4925 | 0 | Arterial |  |  | 2044 | 48688203.5816
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure |  |  | Transport - Drury East IPA | 95.62% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3132107.9036 | 31998468.5549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35130576.4585 |  | 35130576.4585 | 0 | Arterial |  |  | 2044 | 33590393.5947
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade |  |  | Transport - Drury East IPA | 95.62% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1506897.1585 | 15394872.3431 | 0 | 0 | 0 | 0 | 0 | 16901769.5016 |  | 16901769.5016 | 0 | Arterial |  |  | 2049 | 16160767.8335
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure |  |  | Transport - Drury East IPA | 95.62% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1949548.1988 | 19917116.0939 | 0 | 0 | 0 | 0 | 0 | 21866664.2927 |  | 21866664.2927 | 0 | Arterial |  |  | 2049 | 20907993.3847
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade |  |  | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46104.3954 | 471015.0768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517119.4722 |  | 517119.4722 | 0 | Arterial |  |  | 2047 | 494448.095
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure |  |  | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32124.3529 | 328191.1503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360315.5032 |  | 360315.5032 | 0 | Arterial |  |  | 2047 | 344518.6727
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial |  |  | Transport - Drury East IPA | 95.62% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial |  |  | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  |  | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial |  |  | Transport - Drury East IPA | 95.62% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial |  |  | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  |  | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial |  |  | Transport - Drury East IPA | 95.62% | 2031 | 4424033.6534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4424033.6534 |  | 4424033.6534 | 0 | Arterial |  |  | 2031 | 4230076.6647
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) |  |  | Transport - Drury East IPA | 95.62% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector |  |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) |  |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Drury East IPA | 95.62% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure |  |  | Transport - Drury East IPA | 95.62% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade |  |  | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48335.2532 | 493806.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542141.3821 |  | 542141.3821 | 0 | Arterial |  |  | 2047 | 518373.0028
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure |  |  | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12046.6323 | 123071.6814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135118.3137 |  | 135118.3137 | 0 | Arterial |  |  | 2047 | 129194.5022
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure |  |  | Transport - Drury East IPA | 95.62% | 2033 | 14251071.9244 | 1462454.4645 | 14940833.6607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30654360.0497 |  | 30654360.0497 | 0 | Arterial |  |  | 2033 | 29310421.9533
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure |  |  | Transport - Drury East IPA | 95.62% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) |  |  | Transport - Drury East IPA | 95.62% | 2035 | 6397077.0115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6397077.0115 |  | 6397077.0115 | 0 | Collector |  |  | 2035 | 6116618.5225
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure |  |  | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2030 | 0
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2031 | -1379298.4831 | -403386.0409 | -4253009.035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6035693.559 |  | -6035693.559 | 0 | Arterial |  |  | 2031 | -5771078.7212
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2031 | -108591.8602 | -47036.7016 | -480539.7716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -636168.3334 |  | -636168.3334 | 0 | Arterial |  |  | 2031 | -608277.6562
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) | WK DE |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2029 | -1181109.7696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1181109.7696 |  | -1181109.7696 | 0 | Arterial |  |  | 2029 | -1129327.9541
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Drury East IPA | 95.62% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -592259.0116 | -6050679.5879 | 0 | 0 | 0 | 0 | -6642938.5995 |  | -6642938.5995 | 0 | Arterial |  |  | 2050 | -6351701.1299
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) | WK DE |  | Transport - Drury East IPA | 95.62% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector | WK DE |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -245119.6346 | -2504209.0378 | 0 | 0 | 0 | 0 | -2749328.6724 |  | -2749328.6724 | 0 | Arterial |  |  | 2050 | -2628793.5336
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Drury East IPA | 95.62% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Drury East IPA | 95.62% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) | WK DE |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2031 | -1297778.1759 | -317677.5974 | -3463330.3999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5078786.1732 |  | -5078786.1732 | 0 | Arterial |  |  | 2031 | -4856123.7457
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2038 | 0 | -735502.8516 | -454105.7204 | -4639267.8862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5828876.4581 |  | -5828876.4581 | 0 | Arterial |  |  | 2038 | -5573328.8258
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Drury East IPA | 95.62% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Drury East IPA | 95.62% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) | WK DE |  | Transport - Drury East IPA | 95.62% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector | WK DE |  | Transport - Drury East IPA | 95.62% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2039 | 0 | -118692.9707 | -418985.2473 | -50866.5598 | -719496.558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1308041.3359 |  | -1308041.3359 | 0 | Arterial |  |  | 2039 | -1250694.6296
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector | WK DE |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | -11540813.3754 | -992043.7202 | -10653025.2295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -23185882.325 |  | -23185882.325 | 0 | Arterial |  |  | 2033 | -22169374.7058
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22794922.4279 | -1366863.3133 | -13964248.3891 | 0 | 0 | 0 | 0 | -38126034.1303 |  | -38126034.1303 | 0 | Arterial |  |  | 2050 | -36454525.4232
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure | WK DE |  | Transport - Drury East IPA | 95.62% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1454338.7603 | -14857921.4134 | 0 | 0 | 0 | 0 | -16312260.1737 |  | -16312260.1737 | 0 | Arterial |  |  | 2050 | -15597103.5744
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18471552.8393 | -581855.5723 | -6916122.8296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25969531.2412 |  | -25969531.2412 | 0 | Arterial |  |  | 2044 | -24830983.8266
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure | WK DE |  | Transport - Drury East IPA | 95.62% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1597375.0309 | -16319218.963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17916593.9938 |  | -17916593.9938 | 0 | Arterial |  |  | 2044 | -17131100.7333
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Drury East IPA | 95.62% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -768517.5508 | -7851384.895 | 0 | 0 | 0 | 0 | 0 | -8619902.4458 |  | -8619902.4458 | 0 | Arterial |  |  | 2049 | -8241991.5951
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure | WK DE |  | Transport - Drury East IPA | 95.62% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -994269.5814 | -10157729.2079 | 0 | 0 | 0 | 0 | 0 | -11151998.7893 |  | -11151998.7893 | 0 | Arterial |  |  | 2049 | -10663076.6262
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade | WK DE |  | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -23513.2416 | -240217.6892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -263730.9308 |  | -263730.9308 | 0 | Arterial |  |  | 2047 | -252168.5285
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure | WK DE |  | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16383.42 | -167377.4867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -183760.9066 |  | -183760.9066 | 0 | Arterial |  |  | 2047 | -175704.5231
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2031 | -2256257.1632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2256257.1632 |  | -2256257.1632 | 0 | Arterial |  |  | 2031 | -2157339.099
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) | WK DE |  | Transport - Drury East IPA | 95.62% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector | WK DE |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) | WK DE |  | Transport - Drury East IPA | 95.62% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Drury East IPA | 95.62% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure | WK DE |  | Transport - Drury East IPA | 95.62% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24650.9791 | -251841.1258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -276492.1049 |  | -276492.1049 | 0 | Arterial |  |  | 2047 | -264370.2314
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure | WK DE |  | Transport - Drury East IPA | 95.62% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6143.7825 | -62766.5575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68910.34 |  | -68910.34 | 0 | Arterial |  |  | 2047 | -65889.1961
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure | WK DE |  | Transport - Drury East IPA | 95.62% | 2033 | -7268046.6815 | -745851.7769 | -7619825.167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15633723.6253 |  | -15633723.6253 | 0 | Arterial |  |  | 2033 | -14948315.1962
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure | WK DE |  | Transport - Drury East IPA | 95.62% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) | WK DE |  | Transport - Drury East IPA | 95.62% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure | WK DE |  | Transport - Drury East IPA | 95.62% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2030 | 0
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) |  |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 1259703.2605 | 12869472.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14129175.325 |  | 14129175.325 | 0 | Collector |  |  | 2033 | 8736269.9217
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade |  |  | Transport - Drury West 1 IPA | 61.83% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116129.218 | 1186407.7623 | 0 | 0 | 0 | 0 | 1302536.9803 |  | 1302536.9803 | 0 | Arterial |  |  | 2050 | 805377.1279
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) |  |  | Transport - Drury West 1 IPA | 61.83% | 2035 | 3072095.1107 | 170691.6159 | 1743832.1007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4986618.8273 |  | 4986618.8273 | 0 | Collector |  |  | 2035 | 3083297.2959
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector |  |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 15362.7968 | 156950.5217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172313.3185 |  | 172313.3185 | 0 | Collector |  |  | 2033 | 106543.7739
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1441880.2035 | 14730641.3988 | 0 | 0 | 0 | 0 | 16172521.6023 |  | 16172521.6023 | 0 | Arterial |  |  | 2050 | 9999699.9671
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Drury West 1 IPA | 61.83% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Drury West 1 IPA | 61.83% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) |  |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2031 | 94246.7811 | 23070.2685 | 251512.7378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368829.7875 |  | 368829.7875 | 0 | Arterial |  |  | 2031 | 228052.6998
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2038 | 0
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Drury West 1 IPA | 61.83% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Drury West 1 IPA | 61.83% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) |  |  | Transport - Drury West 1 IPA | 61.83% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector |  |  | Transport - Drury West 1 IPA | 61.83% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector |  |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 23886215.047 | 2053249.5298 | 22048745.0283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47988209.6052 |  | 47988209.6052 | 0 | Arterial |  |  | 2033 | 29671792.0562
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37246605.2744 | 2233436.7864 | 22817399.3286 | 0 | 0 | 0 | 0 | 62297441.3893 |  | 62297441.3893 | 0 | Arterial |  |  | 2050 | 38519393.4457
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure |  |  | Transport - Drury West 1 IPA | 61.83% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2376370.5234 | 24277649.3682 | 0 | 0 | 0 | 0 | 26654019.8917 |  | 26654019.8917 | 0 | Arterial |  |  | 2050 | 16480559.3331
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3018227.5881 | 95074.4399 | 1130085.4297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4243387.4577 |  | 4243387.4577 | 0 | Arterial |  |  | 2044 | 2623746.7764
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure |  |  | Transport - Drury West 1 IPA | 61.83% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261008.992 | 2666539.0462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2927548.0382 |  | 2927548.0382 | 0 | Arterial |  |  | 2044 | 1810144.5613
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade |  |  | Transport - Drury West 1 IPA | 61.83% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273981.3015 | 2799067.6987 | 0 | 0 | 0 | 0 | 0 | 3073049.0003 |  | 3073049.0003 | 0 | Arterial |  |  | 2049 | 1900109.8742
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure |  |  | Transport - Drury West 1 IPA | 61.83% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354463.3089 | 3621293.8352 | 0 | 0 | 0 | 0 | 0 | 3975757.1441 |  | 3975757.1441 | 0 | Arterial |  |  | 2049 | 2458267.1497
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade |  |  | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1152609.8838 | 11775376.9212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12927986.805 |  | 12927986.805 | 0 | Arterial |  |  | 2047 | 7993557.9873
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure |  |  | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 803108.8223 | 8204778.758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9007887.5803 |  | 9007887.5803 | 0 | Arterial |  |  | 2047 | 5569704.9202
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2027 | 4848034.7459 | 1258961.7788 | 13034192.7616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19141189.2863 |  | 19141189.2863 | 0 | Arterial |  |  | 2027 | 11835269.3898
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26634122.1233 | 1282074.0004 | 15672259.5523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43588455.6761 |  | 43588455.6761 | 0 | Arterial |  |  | 2047 | 26951361.668
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 746218.9368 | 7623576.1724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8369795.1092 |  | 8369795.1092 | 0 | Arterial |  |  | 2031 | 5175163.276
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67912180.5637 | 1044041.469 | 17111120.9903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86067343.023 |  | 86067343.023 | 0 | Arterial |  |  | 2047 | 53216661.4678
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2031 | 4002697.115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4002697.115 |  | 4002697.115 | 0 | Arterial |  |  | 2031 | 2474924.5166
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) |  |  | Transport - Drury West 1 IPA | 61.83% | 2034 | 12952718.261 | 3615386.8148 | 36935777.715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53503882.7908 |  | 53503882.7908 | 0 | Collector |  |  | 2034 | 33082211.1812
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector |  |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 756954.7508 | 7733256.1762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8490210.927 |  | 8490210.927 | 0 | Collector |  |  | 2033 | 5249618.0877
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) |  |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 1111582.7776 | 11356232.8148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12467815.5924 |  | 12467815.5924 | 0 | Collector |  |  | 2033 | 7709027.5861
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Drury West 1 IPA | 61.83% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure |  |  | Transport - Drury West 1 IPA | 61.83% | 2036 | 746127.9328 | 7622646.4509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8368774.3837 |  | 8368774.3837 | 0 | Arterial |  |  | 2036 | 5174532.147
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade |  |  | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1160046.0766 | 11851347.0949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13011393.1715 |  | 13011393.1715 | 0 | Arterial |  |  | 2047 | 8045129.3291
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure |  |  | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289119.176 | 2953720.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3242839.5289 |  | 3242839.5289 | 0 | Arterial |  |  | 2047 | 2005093.7713
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure |  |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 7125535.9622 | 731227.2323 | 7470416.8304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15327180.0248 |  | 15327180.0248 | 0 | Arterial |  |  | 2033 | 9477013.2548
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure |  |  | Transport - Drury West 1 IPA | 61.83% | 2037 | 8052745.6746 | 300209.5215 | 3067022.3472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11419977.5432 |  | 11419977.5432 | 0 | Arterial |  |  | 2037 | 7061134.4273
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) |  |  | Transport - Drury West 1 IPA | 61.83% | 2035 | 399817.3132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 399817.3132 |  | 399817.3132 | 0 | Collector |  |  | 2035 | 247212.7274
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure |  |  | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2030 | 0
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -59225.9012 | -605067.9588 | 0 | 0 | 0 | 0 | -664293.86 |  | -664293.86 | 0 | Arterial |  |  | 2050 | -410742.3352
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -735358.9038 | -7512627.1134 | 0 | 0 | 0 | 0 | -8247986.0172 |  | -8247986.0172 | 0 | Arterial |  |  | 2050 | -5099846.9832
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2031 | -48065.8584 | -11765.8369 | -128271.4963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -188103.1916 |  | -188103.1916 | 0 | Arterial |  |  | 2031 | -116306.8769
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2038 | 0
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | -12181969.674 | -1047157.2602 | -11244859.9644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24473986.8986 |  | -24473986.8986 | 0 | Arterial |  |  | 2033 | -15132613.9486
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18995768.6899 | -1139052.761 | -11636873.6576 | 0 | 0 | 0 | 0 | -31771695.1086 |  | -31771695.1086 | 0 | Arterial |  |  | 2050 | -19644890.6573
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1211948.9669 | -12381601.1778 | 0 | 0 | 0 | 0 | -13593550.1447 |  | -13593550.1447 | 0 | Arterial |  |  | 2050 | -8405085.2599
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1539296.0699 | -48487.9644 | -576343.5691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2164127.6034 |  | -2164127.6034 | 0 | Arterial |  |  | 2044 | -1338110.856
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -133114.5859 | -1359934.9136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1493049.4995 |  | -1493049.4995 | 0 | Arterial |  |  | 2044 | -923173.7263
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -139730.4638 | -1427524.5264 | 0 | 0 | 0 | 0 | 0 | -1567254.9901 |  | -1567254.9901 | 0 | Arterial |  |  | 2049 | -969056.0358
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -180776.2875 | -1846859.856 | 0 | 0 | 0 | 0 | 0 | -2027636.1435 |  | -2027636.1435 | 0 | Arterial |  |  | 2049 | -1253716.2464
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -587831.0407 | -6005442.2298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6593273.2706 |  | -6593273.2706 | 0 | Arterial |  |  | 2047 | -4076714.5735
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -409585.4994 | -4184437.1666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4594022.6659 |  | -4594022.6659 | 0 | Arterial |  |  | 2047 | -2840549.5093
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2027 | -2472497.7204 | -642070.5072 | -6647438.3084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9762006.536 |  | -9762006.536 | 0 | Arterial |  |  | 2027 | -6035987.3888
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13583402.2829 | -653857.7402 | -7992852.3717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22230112.3948 |  | -22230112.3948 | 0 | Arterial |  |  | 2047 | -13745194.4507
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | -380571.6578 | -3888023.8479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4268595.5057 |  | -4268595.5057 | 0 | Arterial |  |  | 2031 | -2639333.2708
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34635212.0875 | -532461.1492 | -8726671.7051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -43894344.9417 |  | -43894344.9417 | 0 | Arterial |  |  | 2047 | -27140497.3486
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2031 | -2041375.5286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2041375.5286 |  | -2041375.5286 | 0 | Arterial |  |  | 2031 | -1262211.5035
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2036 | -380525.2457 | -3887549.6899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4268074.9357 |  | -4268074.9357 | 0 | Arterial |  |  | 2036 | -2639011.395
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -591623.4991 | -6044187.0184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6635810.5175 |  | -6635810.5175 | 0 | Arterial |  |  | 2047 | -4103015.9579
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -147450.7798 | -1506397.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1653848.1597 |  | -1653848.1597 | 0 | Arterial |  |  | 2047 | -1022597.8233
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2033 | -3634023.3407 | -372925.8885 | -3809912.5835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7816861.8127 |  | -7816861.8127 | 0 | Arterial |  |  | 2033 | -4833276.76
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2037 | -4106900.294 | -153106.856 | -1564181.3971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5824188.5471 |  | -5824188.5471 | 0 | Arterial |  |  | 2037 | -3601178.5579
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure | WK DE |  | Transport - Drury West 1 IPA | 61.83% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2030 | 0
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) |  |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade |  |  | Transport - Drury West 2 IPA | 83.95% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116129.218 | 1186407.7623 | 0 | 0 | 0 | 0 | 1302536.9803 |  | 1302536.9803 | 0 | Arterial |  |  | 2050 | 1093522.6055
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) |  |  | Transport - Drury West 2 IPA | 83.95% | 2035 | 7680237.7768 | 426729.0398 | 4359580.2517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12466547.0684 |  | 12466547.0684 | 0 | Collector |  |  | 2035 | 10466076.0023
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector |  |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 38406.9919 | 392376.3043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430783.2963 |  | 430783.2963 | 0 | Collector |  |  | 2033 | 361656.7358
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 549287.6966 | 5611672.9138 | 0 | 0 | 0 | 0 | 6160960.6104 |  | 6160960.6104 | 0 | Arterial |  |  | 2050 | 5172328.9249
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Drury West 2 IPA | 83.95% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Drury West 2 IPA | 83.95% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) |  |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 384510.1788 | 3928260.8527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4312771.0315 |  | 4312771.0315 | 0 | Collector |  |  | 2033 | 3620713.0289
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 94246.7811 | 23070.2685 | 251512.7378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368829.7875 |  | 368829.7875 | 0 | Arterial |  |  | 2031 | 309644.7289
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2038 | 0
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Drury West 2 IPA | 83.95% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Drury West 2 IPA | 83.95% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) |  |  | Transport - Drury West 2 IPA | 83.95% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector |  |  | Transport - Drury West 2 IPA | 83.95% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector |  |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 1257169.213 | 108065.7647 | 1160460.2646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2525695.2424 |  | 2525695.2424 | 0 | Arterial |  |  | 2033 | 2120404.1681
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4966214.0366 | 297791.5715 | 3042319.9105 | 0 | 0 | 0 | 0 | 8306325.5186 |  | 8306325.5186 | 0 | Arterial |  |  | 2050 | 6973433.2771
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure |  |  | Transport - Drury West 2 IPA | 83.95% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316849.4031 | 3237019.9158 | 0 | 0 | 0 | 0 | 3553869.3189 |  | 3553869.3189 | 0 | Arterial |  |  | 2050 | 2983590.0984
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3018227.5881 | 95074.4399 | 1130085.4297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4243387.4577 |  | 4243387.4577 | 0 | Arterial |  |  | 2044 | 3562463.2383
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure |  |  | Transport - Drury West 2 IPA | 83.95% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261008.992 | 2666539.0462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2927548.0382 |  | 2927548.0382 | 0 | Arterial |  |  | 2044 | 2457772.7979
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade |  |  | Transport - Drury West 2 IPA | 83.95% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273981.3015 | 2799067.6987 | 0 | 0 | 0 | 0 | 0 | 3073049.0003 |  | 3073049.0003 | 0 | Arterial |  |  | 2049 | 2579925.6378
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure |  |  | Transport - Drury West 2 IPA | 83.95% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354463.3089 | 3621293.8352 | 0 | 0 | 0 | 0 | 0 | 3975757.1441 |  | 3975757.1441 | 0 | Arterial |  |  | 2049 | 3337778.7938
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade |  |  | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414939.5582 | 4239135.6916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4654075.2498 |  | 4654075.2498 | 0 | Arterial |  |  | 2047 | 3907249.1379
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure |  |  | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289119.176 | 2953720.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3242839.5289 |  | 3242839.5289 | 0 | Arterial |  |  | 2047 | 2722470.367
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2027 | 538670.5273 | 139884.6421 | 1448243.6402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2126798.8096 |  | 2126798.8096 | 0 | Arterial |  |  | 2027 | 1785517.5022
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7990236.637 | 384622.2001 | 4701677.8657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13076536.7028 |  | 13076536.7028 | 0 | Arterial |  |  | 2047 | 10978182.349
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 82913.2152 | 847064.0192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 929977.2344 |  | 929977.2344 | 0 | Arterial |  |  | 2031 | 780746.4538
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20373654.1691 | 313212.4407 | 5133336.2971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25820202.9069 |  | 25820202.9069 | 0 | Arterial |  |  | 2047 | 21676908.9738
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) |  |  | Transport - Drury West 2 IPA | 83.95% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector |  |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) |  |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Drury West 2 IPA | 83.95% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure |  |  | Transport - Drury West 2 IPA | 83.95% | 2036 | 139898.9874 | 1429246.2095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1569145.1969 |  | 1569145.1969 | 0 | Arterial |  |  | 2036 | 1317348.966
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade |  |  | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 435017.2787 | 4444255.1606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4879272.4393 |  | 4879272.4393 | 0 | Arterial |  |  | 2047 | 4096309.58
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure |  |  | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108419.691 | 1107645.1323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1216064.8233 |  | 1216064.8233 | 0 | Arterial |  |  | 2047 | 1020926.3876
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure |  |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 4750357.3081 | 487484.8215 | 4980277.8869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10218120.0166 |  | 10218120.0166 | 0 | Arterial |  |  | 2033 | 8578447.5932
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure |  |  | Transport - Drury West 2 IPA | 83.95% | 2037 | 36237355.5355 | 1350942.8468 | 13801600.5622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51389898.9446 |  | 51389898.9446 | 0 | Arterial |  |  | 2037 | 43143509.1976
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) |  |  | Transport - Drury West 2 IPA | 83.95% | 2035 | 1199451.9397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199451.9397 |  | 1199451.9397 | 0 | Collector |  |  | 2035 | 1006979.3258
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure |  |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2030 | 0
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -59225.9012 | -605067.9588 | 0 | 0 | 0 | 0 | -664293.86 |  | -664293.86 | 0 | Arterial |  |  | 2050 | -557696.5288
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -280136.7252 | -2861953.1861 | 0 | 0 | 0 | 0 | -3142089.9113 |  | -3142089.9113 | 0 | Arterial |  |  | 2050 | -2637887.7517
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2031 | -48065.8584 | -11765.8369 | -128271.4963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -188103.1916 |  | -188103.1916 | 0 | Arterial |  |  | 2031 | -157918.8117
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2038 | 0
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | -641156.2986 | -55113.54 | -591834.735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1288104.5736 |  | -1288104.5736 | 0 | Arterial |  |  | 2033 | -1081406.1257
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2532769.1587 | -151873.7015 | -1551583.1543 | 0 | 0 | 0 | 0 | -4236226.0145 |  | -4236226.0145 | 0 | Arterial |  |  | 2050 | -3556450.9713
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -161593.1956 | -1650880.157 | 0 | 0 | 0 | 0 | -1812473.3526 |  | -1812473.3526 | 0 | Arterial |  |  | 2050 | -1521630.9502
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1539296.0699 | -48487.9644 | -576343.5691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2164127.6034 |  | -2164127.6034 | 0 | Arterial |  |  | 2044 | -1816856.2515
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -133114.5859 | -1359934.9136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1493049.4995 |  | -1493049.4995 | 0 | Arterial |  |  | 2044 | -1253464.1269
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -139730.4638 | -1427524.5264 | 0 | 0 | 0 | 0 | 0 | -1567254.9901 |  | -1567254.9901 | 0 | Arterial |  |  | 2049 | -1315762.0753
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -180776.2875 | -1846859.856 | 0 | 0 | 0 | 0 | 0 | -2027636.1435 |  | -2027636.1435 | 0 | Arterial |  |  | 2049 | -1702267.1849
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -211619.1747 | -2161959.2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2373578.3774 |  | -2373578.3774 | 0 | Arterial |  |  | 2047 | -1992697.0603
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -147450.7798 | -1506397.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1653848.1597 |  | -1653848.1597 | 0 | Arterial |  |  | 2047 | -1388459.8872
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2027 | -274721.9689 | -71341.1675 | -738604.2565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1084667.3929 |  | -1084667.3929 | 0 | Arterial |  |  | 2027 | -910613.9261
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4075020.6849 | -196157.3221 | -2397855.7115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6669033.7184 |  | -6669033.7184 | 0 | Arterial |  |  | 2047 | -5598872.998
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | -42285.7398 | -432002.6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -474288.3895 |  | -474288.3895 | 0 | Arterial |  |  | 2031 | -398180.6915
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10390563.6262 | -159738.3448 | -2618001.5115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13168303.4825 |  | -13168303.4825 | 0 | Arterial |  |  | 2047 | -11055223.5767
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2036 | -71348.4836 | -728915.5669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -800264.0504 |  | -800264.0504 | 0 | Arterial |  |  | 2036 | -671847.9726
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -221858.8122 | -2266570.1319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2488428.9441 |  | -2488428.9441 | 0 | Arterial |  |  | 2047 | -2089117.8858
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -55294.0424 | -564899.0175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -620193.0599 |  | -620193.0599 | 0 | Arterial |  |  | 2047 | -520672.4577
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2033 | -2422682.2272 | -248617.259 | -2539941.7223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5211241.2084 |  | -5211241.2084 | 0 | Arterial |  |  | 2033 | -4375008.2725
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2037 | -18481051.3231 | -688980.8519 | -7038816.2867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26208848.4617 |  | -26208848.4617 | 0 | Arterial |  |  | 2037 | -22003189.6908
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure | WK DE |  | Transport - Drury West 2 IPA | 83.95% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial |  |  | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial |  |  | Transport - Opaheke IPA | 61.25% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2030 | 0
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial |  |  | Transport - Opaheke IPA | 61.25% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial |  |  | Transport - Opaheke IPA | 61.25% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial |  |  | Transport - Opaheke IPA | 61.25% | 2031 | 1062484.8259 | 310731.5441 | 3276127.4079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4649343.7779 |  | 4649343.7779 | 0 | Arterial |  |  | 2031 | 2847852.6958
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial |  |  | Transport - Opaheke IPA | 61.25% | 2031 | 17743.768 | 7685.7356 | 78519.5705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103949.0741 |  | 103949.0741 | 0 | Arterial |  |  | 2031 | 63671.7062
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) |  |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Opaheke IPA | 61.25% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade |  |  | Transport - Opaheke IPA | 61.25% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 754839.9168 | 7711650.4552 | 0 | 0 | 0 | 0 | 8466490.372 |  | 8466490.372 | 0 | Arterial |  |  | 2050 | 5185961.4134
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) |  |  | Transport - Opaheke IPA | 61.25% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector |  |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial |  |  | Transport - Opaheke IPA | 61.25% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205982.8862 | 2104377.3427 | 0 | 0 | 0 | 0 | 2310360.2289 |  | 2310360.2289 | 0 | Arterial |  |  | 2050 | 1415160.0571
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Opaheke IPA | 61.25% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Opaheke IPA | 61.25% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) |  |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial |  |  | Transport - Opaheke IPA | 61.25% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial |  |  | Transport - Opaheke IPA | 61.25% | 2031 | 659727.4678 | 161491.8796 | 1760589.1648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2581808.5122 |  | 2581808.5122 | 0 | Arterial |  |  | 2031 | 1581429.699
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial |  |  | Transport - Opaheke IPA | 61.25% | 2038 | 0 | 120180.2045 | 74200.2811 | 758050.3082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 952430.7938 |  | 952430.7938 | 0 | Arterial |  |  | 2038 | 583390.4166
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Opaheke IPA | 61.25% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Opaheke IPA | 61.25% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) |  |  | Transport - Opaheke IPA | 61.25% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector |  |  | Transport - Opaheke IPA | 61.25% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial |  |  | Transport - Opaheke IPA | 61.25% | 2039 | 0 | 19394.2763 | 68461.6417 | 8311.5294 | 117564.7971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213732.2444 |  | 213732.2444 | 0 | Arterial |  |  | 2039 | 130916.9589
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector |  |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial |  |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 1257169.213 | 108065.7647 | 1160460.2646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2525695.2424 |  | 2525695.2424 | 0 | Arterial |  |  | 2033 | 1547058.7568
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial |  |  | Transport - Opaheke IPA | 61.25% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9932428.0732 | 595583.143 | 6084639.821 | 0 | 0 | 0 | 0 | 16612651.0372 |  | 16612651.0372 | 0 | Arterial |  |  | 2050 | 10175711.95
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure |  |  | Transport - Opaheke IPA | 61.25% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 633698.8062 | 6474039.8315 | 0 | 0 | 0 | 0 | 7107738.6378 |  | 7107738.6378 | 0 | Arterial |  |  | 2050 | 4353688.0918
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Opaheke IPA | 61.25% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66401006.9388 | 2091637.6781 | 24861879.4527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93354524.0696 |  | 93354524.0696 | 0 | Arterial |  |  | 2044 | 57182248.8798
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure |  |  | Transport - Opaheke IPA | 61.25% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5742197.8233 | 58663859.0172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64406056.8406 |  | 64406056.8406 | 0 | Arterial |  |  | 2044 | 39450505.5682
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade |  |  | Transport - Opaheke IPA | 61.25% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3013794.317 | 30789744.6862 | 0 | 0 | 0 | 0 | 0 | 33803539.0032 |  | 33803539.0032 | 0 | Arterial |  |  | 2049 | 20705610.1411
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure |  |  | Transport - Opaheke IPA | 61.25% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3899096.3976 | 39834232.1877 | 0 | 0 | 0 | 0 | 0 | 43733328.5853 |  | 43733328.5853 | 0 | Arterial |  |  | 2049 | 26787883.1201
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade |  |  | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46104.3954 | 471015.0768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517119.4722 |  | 517119.4722 | 0 | Arterial |  |  | 2047 | 316750.0949
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure |  |  | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32124.3529 | 328191.1503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360315.5032 |  | 360315.5032 | 0 | Arterial |  |  | 2047 | 220703.2919
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial |  |  | Transport - Opaheke IPA | 61.25% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial |  |  | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  |  | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial |  |  | Transport - Opaheke IPA | 61.25% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial |  |  | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  |  | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial |  |  | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) |  |  | Transport - Opaheke IPA | 61.25% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector |  |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) |  |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Opaheke IPA | 61.25% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure |  |  | Transport - Opaheke IPA | 61.25% | 2036 | 23316.4979 | 238207.7016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261524.1995 |  | 261524.1995 | 0 | Arterial |  |  | 2036 | 160190.8639
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade |  |  | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96670.5064 | 987612.2579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1084282.7643 |  | 1084282.7643 | 0 | Arterial |  |  | 2047 | 664153.4248
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure |  |  | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24093.2647 | 246143.3627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270236.6274 |  | 270236.6274 | 0 | Arterial |  |  | 2047 | 165527.469
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure |  |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure |  |  | Transport - Opaheke IPA | 61.25% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) |  |  | Transport - Opaheke IPA | 61.25% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure |  |  | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2030 | 0
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2031 | -541867.2612 | -158473.0875 | -1670824.978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2371165.3267 |  | -2371165.3267 | 0 | Arterial |  |  | 2031 | -1452404.8749
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2031 | -9049.3217 | -3919.7251 | -40044.981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -53014.0278 |  | -53014.0278 | 0 | Arterial |  |  | 2031 | -32472.5701
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) | WK DE |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Opaheke IPA | 61.25% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -384968.3576 | -3932941.7321 | 0 | 0 | 0 | 0 | -4317910.0897 |  | -4317910.0897 | 0 | Arterial |  |  | 2050 | -2644840.3208
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) | WK DE |  | Transport - Opaheke IPA | 61.25% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector | WK DE |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -105051.272 | -1073232.4448 | 0 | 0 | 0 | 0 | -1178283.7167 |  | -1178283.7167 | 0 | Arterial |  |  | 2050 | -721731.6291
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Opaheke IPA | 61.25% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Opaheke IPA | 61.25% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) | WK DE |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2031 | -336461.0086 | -82360.8586 | -897900.474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1316722.3412 |  | -1316722.3412 | 0 | Arterial |  |  | 2031 | -806529.1465
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2038 | 0 | -61291.9043 | -37842.1434 | -386605.6572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -485739.7048 |  | -485739.7048 | 0 | Arterial |  |  | 2038 | -297529.1125
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Opaheke IPA | 61.25% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Opaheke IPA | 61.25% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) | WK DE |  | Transport - Opaheke IPA | 61.25% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector | WK DE |  | Transport - Opaheke IPA | 61.25% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2039 | 0 | -9891.0809 | -34915.4373 | -4238.88 | -59958.0465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -109003.4447 |  | -109003.4447 | 0 | Arterial |  |  | 2039 | -66767.6491
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector | WK DE |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | -641156.2986 | -55113.54 | -591834.735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1288104.5736 |  | -1288104.5736 | 0 | Arterial |  |  | 2033 | -788999.9659
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5065538.3173 | -303747.4029 | -3103166.3087 | 0 | 0 | 0 | 0 | -8472452.0289 |  | -8472452.0289 | 0 | Arterial |  |  | 2050 | -5189613.0945
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure | WK DE |  | Transport - Opaheke IPA | 61.25% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -323186.3912 | -3301760.3141 | 0 | 0 | 0 | 0 | -3624946.7053 |  | -3624946.7053 | 0 | Arterial |  |  | 2050 | -2220380.9268
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -33864513.5388 | -1066735.2159 | -12679558.5209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -47610807.2755 |  | -47610807.2755 | 0 | Arterial |  |  | 2044 | -29162946.9287
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure | WK DE |  | Transport - Opaheke IPA | 61.25% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2928520.8899 | -29918568.0988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -32847088.9887 |  | -32847088.9887 | 0 | Arterial |  |  | 2044 | -20119757.8398
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Opaheke IPA | 61.25% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1537035.1017 | -15702769.79 | 0 | 0 | 0 | 0 | 0 | -17239804.8916 |  | -17239804.8916 | 0 | Arterial |  |  | 2049 | -10559861.172
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure | WK DE |  | Transport - Opaheke IPA | 61.25% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1988539.1628 | -20315458.4158 | 0 | 0 | 0 | 0 | 0 | -22303997.5785 |  | -22303997.5785 | 0 | Arterial |  |  | 2049 | -13661820.3912
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade | WK DE |  | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -23513.2416 | -240217.6892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -263730.9308 |  | -263730.9308 | 0 | Arterial |  |  | 2047 | -161542.5484
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure | WK DE |  | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16383.42 | -167377.4867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -183760.9066 |  | -183760.9066 | 0 | Arterial |  |  | 2047 | -112558.6789
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) | WK DE |  | Transport - Opaheke IPA | 61.25% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector | WK DE |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) | WK DE |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Opaheke IPA | 61.25% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure | WK DE |  | Transport - Opaheke IPA | 61.25% | 2036 | -11891.4139 | -121485.9278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -133377.3417 |  | -133377.3417 | 0 | Arterial |  |  | 2036 | -81697.3406
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -49301.9583 | -503682.2515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -552984.2098 |  | -552984.2098 | 0 | Arterial |  |  | 2047 | -338718.2467
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure | WK DE |  | Transport - Opaheke IPA | 61.25% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12287.565 | -125533.115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -137820.68 |  | -137820.68 | 0 | Arterial |  |  | 2047 | -84419.0092
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure | WK DE |  | Transport - Opaheke IPA | 61.25% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure | WK DE |  | Transport - Opaheke IPA | 61.25% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) | WK DE |  | Transport - Opaheke IPA | 61.25% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure | WK DE |  | Transport - Opaheke IPA | 61.25% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2030 | 0
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 1288.3621 | 13162.2585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14450.6206 |  | 14450.6206 | 0 | Collector |  |  | 2033 | 13937.0032
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) |  |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade |  |  | Transport - Southern Growth Area 3 | 96.45% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2050 | 0
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) |  |  | Transport - Southern Growth Area 3 | 96.45% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2050 | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 3 | 96.45% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 3 | 96.45% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) |  |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 230706.1073 | 2356956.5116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2587662.6189 |  | 2587662.6189 | 0 | Collector |  |  | 2033 | 2495689.5085
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2038 | 0
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 3 | 96.45% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 3 | 96.45% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) |  |  | Transport - Southern Growth Area 3 | 96.45% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 3 | 96.45% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2033 | 0
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2050 | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 3 | 96.45% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2050 | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2044 | 0
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 3 | 96.45% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2044 | 0
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade |  |  | Transport - Southern Growth Area 3 | 96.45% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2049 | 0
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 3 | 96.45% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2049 | 0
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade |  |  | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) |  |  | Transport - Southern Growth Area 3 | 96.45% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) |  |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Southern Growth Area 3 | 96.45% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 3 | 96.45% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade |  |  | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 3 | 96.45% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) |  |  | Transport - Southern Growth Area 3 | 96.45% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2030 | 0
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2050 | 0
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2050 | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2038 | 0
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2033 | 0
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2050 | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2050 | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2044 | 0
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2044 | 0
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2049 | 0
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2049 | 0
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 3 | 96.45% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2030 | 0
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) |  |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade |  |  | Transport - Southern Growth Area 2 | 36.35% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2050 | 0
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) |  |  | Transport - Southern Growth Area 2 | 36.35% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2050 | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 2 | 36.35% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 2 | 36.35% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) |  |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 188493.5622 | 46140.537 | 503025.4757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 737659.5749 |  | 737659.5749 | 0 | Arterial |  |  | 2031 | 268134.3013
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2038 | 0
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 2 | 36.35% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 2 | 36.35% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) |  |  | Transport - Southern Growth Area 2 | 36.35% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 2 | 36.35% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2033 | 0
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2050 | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 2 | 36.35% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2050 | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2044 | 0
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 2 | 36.35% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2044 | 0
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade |  |  | Transport - Southern Growth Area 2 | 36.35% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136990.6508 | 1399533.8494 | 0 | 0 | 0 | 0 | 0 | 1536524.5001 |  | 1536524.5001 | 0 | Arterial |  |  | 2049 | 558516.3363
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 2 | 36.35% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177231.6544 | 1810646.9176 | 0 | 0 | 0 | 0 | 0 | 1987878.5721 |  | 1987878.5721 | 0 | Arterial |  |  | 2049 | 722580.5101
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade |  |  | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46104.3954 | 471015.0768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517119.4722 |  | 517119.4722 | 0 | Arterial |  |  | 2047 | 187969.4551
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32124.3529 | 328191.1503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360315.5032 |  | 360315.5032 | 0 | Arterial |  |  | 2047 | 130972.2655
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) |  |  | Transport - Southern Growth Area 2 | 36.35% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) |  |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Southern Growth Area 2 | 36.35% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 2 | 36.35% | 2036 | 23316.4979 | 238207.7016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261524.1995 |  | 261524.1995 | 0 | Arterial |  |  | 2036 | 95062.2901
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade |  |  | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193341.0128 | 1975224.5158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2168565.5286 |  | 2168565.5286 | 0 | Arterial |  |  | 2047 | 788259.0053
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48186.5293 | 492286.7255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540473.2548 |  | 540473.2548 | 0 | Arterial |  |  | 2047 | 196458.3982
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 21376607.8866 | 2193681.6968 | 22411250.4911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45981540.0745 |  | 45981540.0745 | 0 | Arterial |  |  | 2033 | 16713980.9996
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 2 | 36.35% | 2037 | 36237355.5355 | 1350942.8468 | 13801600.5622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51389898.9446 |  | 51389898.9446 | 0 | Arterial |  |  | 2037 | 18679883.1257
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) |  |  | Transport - Southern Growth Area 2 | 36.35% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2030 | 0
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2050 | 0
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2050 | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | -96131.7167 | -23531.6739 | -256542.9926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -376206.3832 |  | -376206.3832 | 0 | Arterial |  |  | 2031 | -136748.4936
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2038 | 0
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2033 | 0
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2050 | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2050 | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2044 | 0
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2044 | 0
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -69865.2319 | -713762.2632 | 0 | 0 | 0 | 0 | 0 | -783627.4951 |  | -783627.4951 | 0 | Arterial |  |  | 2049 | -284843.3315
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -90388.1438 | -923429.928 | 0 | 0 | 0 | 0 | 0 | -1013818.0718 |  | -1013818.0718 | 0 | Arterial |  |  | 2049 | -368516.0602
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -23513.2416 | -240217.6892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -263730.9308 |  | -263730.9308 | 0 | Arterial |  |  | 2047 | -95864.4221
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16383.42 | -167377.4867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -183760.9066 |  | -183760.9066 | 0 | Arterial |  |  | 2047 | -66795.8554
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2036 | -11891.4139 | -121485.9278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -133377.3417 |  | -133377.3417 | 0 | Arterial |  |  | 2036 | -48481.7679
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -98603.9165 | -1007364.5031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1105968.4196 |  | -1105968.4196 | 0 | Arterial |  |  | 2047 | -402012.0927
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24575.13 | -251066.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -275641.36 |  | -275641.36 | 0 | Arterial |  |  | 2047 | -100193.7831
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2033 | -10902070.0222 | -1118777.6654 | -11429737.7504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -23450585.438 |  | -23450585.438 | 0 | Arterial |  |  | 2033 | -8524130.3098
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2037 | -18481051.3231 | -688980.8519 | -7038816.2867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26208848.4617 |  | -26208848.4617 | 0 | Arterial |  |  | 2037 | -9526740.3941
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 2 | 36.35% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2030 | 0
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | 96589.5296 | 28248.3222 | 297829.7644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 422667.6162 |  | 422667.6162 | 0 | Arterial |  |  | 2031 | 258027.5181
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | 5914.5893 | 2561.9119 | 26173.1902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34649.6914 |  | 34649.6914 | 0 | Arterial |  |  | 2031 | 21152.7298
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) |  |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2029 | 59382.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59382.09 |  | 59382.09 | 0 | Arterial |  |  | 2029 | 36251.2119
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade |  |  | Transport - Southern Growth Area 1 | 61.05% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116129.218 | 1186407.7623 | 0 | 0 | 0 | 0 | 1302536.9803 |  | 1302536.9803 | 0 | Arterial |  |  | 2050 | 795164.738
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) |  |  | Transport - Southern Growth Area 1 | 61.05% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2050 | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 1 | 61.05% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 1 | 61.05% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) |  |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | 188493.5622 | 46140.537 | 503025.4757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 737659.5749 |  | 737659.5749 | 0 | Arterial |  |  | 2031 | 450321.8653
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2038 | 0 | 40060.0682 | 24733.427 | 252683.4361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317476.9313 |  | 317476.9313 | 0 | Arterial |  |  | 2038 | 193811.3579
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 1 | 61.05% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 1 | 61.05% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) |  |  | Transport - Southern Growth Area 1 | 61.05% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 1 | 61.05% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2039 | 0 | 6464.7588 | 22820.5472 | 2770.5098 | 39188.2657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71244.0815 |  | 71244.0815 | 0 | Arterial |  |  | 2039 | 43492.6472
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2033 | 0
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2050 | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 1 | 61.05% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2050 | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6036455.1763 | 190148.8798 | 2260170.8593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8486774.9154 |  | 8486774.9154 | 0 | Arterial |  |  | 2044 | 5180953.98
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 1 | 61.05% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522017.9839 | 5333078.0925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5855096.0764 |  | 5855096.0764 | 0 | Arterial |  |  | 2044 | 3574382.922
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade |  |  | Transport - Southern Growth Area 1 | 61.05% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273981.3015 | 2799067.6987 | 0 | 0 | 0 | 0 | 0 | 3073049.0003 |  | 3073049.0003 | 0 | Arterial |  |  | 2049 | 1876015.9904
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 1 | 61.05% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354463.3089 | 3621293.8352 | 0 | 0 | 0 | 0 | 0 | 3975757.1441 |  | 3975757.1441 | 0 | Arterial |  |  | 2049 | 2427095.6876
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade |  |  | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46104.3954 | 471015.0768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517119.4722 |  | 517119.4722 | 0 | Arterial |  |  | 2047 | 315687.9043
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32124.3529 | 328191.1503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360315.5032 |  | 360315.5032 | 0 | Arterial |  |  | 2047 | 219963.185
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) |  |  | Transport - Southern Growth Area 1 | 61.05% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector |  |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) |  |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Southern Growth Area 1 | 61.05% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 1 | 61.05% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade |  |  | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 1 | 61.05% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) |  |  | Transport - Southern Growth Area 1 | 61.05% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure |  |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2030 | 0
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | -49260.6601 | -14406.6443 | -151893.1798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -215560.4842 |  | -215560.4842 | 0 | Arterial |  |  | 2031 | -131594.0342
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | -3016.4406 | -1306.575 | -13348.327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17671.3426 |  | -17671.3426 | 0 | Arterial |  |  | 2031 | -10787.8922
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2029 | -30284.8659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30284.8659 |  | -30284.8659 | 0 | Arterial |  |  | 2029 | -18488.118
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -59225.9012 | -605067.9588 | 0 | 0 | 0 | 0 | -664293.86 |  | -664293.86 | 0 | Arterial |  |  | 2050 | -405534.0164
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2050 | 0
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | -96131.7167 | -23531.6739 | -256542.9926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -376206.3832 |  | -376206.3832 | 0 | Arterial |  |  | 2031 | -229664.1513
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2038 | 0 | -20430.6348 | -12614.0478 | -128868.5524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -161913.2349 |  | -161913.2349 | 0 | Arterial |  |  | 2038 | -98843.7925
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2039 | 0 | -3297.027 | -11638.4791 | -1412.96 | -19986.0155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36334.4816 |  | -36334.4816 | 0 | Arterial |  |  | 2039 | -22181.2501
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2033 | 0
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2050 | 0
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2050 | 0
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3078592.1399 | -96975.9287 | -1152687.1383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4328255.2069 |  | -4328255.2069 | 0 | Arterial |  |  | 2044 | -2642286.5298
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -266229.1718 | -2719869.8272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2986098.999 |  | -2986098.999 | 0 | Arterial |  |  | 2044 | -1822935.2902
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -139730.4638 | -1427524.5264 | 0 | 0 | 0 | 0 | 0 | -1567254.9901 |  | -1567254.9901 | 0 | Arterial |  |  | 2049 | -956768.1551
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -180776.2875 | -1846859.856 | 0 | 0 | 0 | 0 | 0 | -2027636.1435 |  | -2027636.1435 | 0 | Arterial |  |  | 2049 | -1237818.8007
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -23513.2416 | -240217.6892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -263730.9308 |  | -263730.9308 | 0 | Arterial |  |  | 2047 | -161000.8312
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16383.42 | -167377.4867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -183760.9066 |  | -183760.9066 | 0 | Arterial |  |  | 2047 | -112181.2243
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure | WK DE |  | Transport - Southern Growth Area 1 | 61.05% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial |  |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial |  |  | Transport - Auckland wide | 28.73% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2030 | 0
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial |  |  | Transport - Auckland wide | 28.73% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial |  |  | Transport - Auckland wide | 28.73% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial |  |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial |  |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) |  |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Auckland wide | 28.73% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade |  |  | Transport - Auckland wide | 28.73% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58064.609 | 593203.8812 | 0 | 0 | 0 | 0 | 651268.4902 |  | 651268.4902 | 0 | Arterial |  |  | 2050 | 187125.0132
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) |  |  | Transport - Auckland wide | 28.73% | 2035 | 1536047.5554 | 85345.808 | 871916.0503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2493309.4137 |  | 2493309.4137 | 0 | Collector |  |  | 2035 | 716387.4254
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector |  |  | Transport - Auckland wide | 28.73% | 2033 | 7681.3984 | 78475.2609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86156.6593 |  | 86156.6593 | 0 | Collector |  |  | 2033 | 24754.8688
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial |  |  | Transport - Auckland wide | 28.73% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68660.9621 | 701459.1142 | 0 | 0 | 0 | 0 | 770120.0763 |  | 770120.0763 | 0 | Arterial |  |  | 2050 | 221273.9164
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Auckland wide | 28.73% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Auckland wide | 28.73% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) |  |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial |  |  | Transport - Auckland wide | 28.73% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial |  |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial |  |  | Transport - Auckland wide | 28.73% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2038 | 0
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector |  |  | Transport - Auckland wide | 28.73% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector |  |  | Transport - Auckland wide | 28.73% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) |  |  | Transport - Auckland wide | 28.73% | 2035 | 393609.8563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 393609.8563 |  | 393609.8563 | 0 | Collector |  |  | 2035 | 113093.5254
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector |  |  | Transport - Auckland wide | 28.73% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial |  |  | Transport - Auckland wide | 28.73% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector |  |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial |  |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 1257169.213 | 108065.7647 | 1160460.2646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2525695.2424 |  | 2525695.2424 | 0 | Arterial |  |  | 2033 | 725692.6485
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial |  |  | Transport - Auckland wide | 28.73% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2483107.0183 | 148895.7858 | 1521159.9552 | 0 | 0 | 0 | 0 | 4153162.7593 |  | 4153162.7593 | 0 | Arterial |  |  | 2050 | 1193302.9892
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure |  |  | Transport - Auckland wide | 28.73% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158424.7016 | 1618509.9579 | 0 | 0 | 0 | 0 | 1776934.6594 |  | 1776934.6594 | 0 | Arterial |  |  | 2050 | 510555.8254
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Auckland wide | 28.73% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6036455.1763 | 190148.8798 | 2260170.8593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8486774.9154 |  | 8486774.9154 | 0 | Arterial |  |  | 2044 | 2438453.4059
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure |  |  | Transport - Auckland wide | 28.73% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522017.9839 | 5333078.0925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5855096.0764 |  | 5855096.0764 | 0 | Arterial |  |  | 2044 | 1682309.1353
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade |  |  | Transport - Auckland wide | 28.73% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2049 | 0
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure |  |  | Transport - Auckland wide | 28.73% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2049 | 0
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade |  |  | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92208.7907 | 942030.1537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1034238.9444 |  | 1034238.9444 | 0 | Arterial |  |  | 2047 | 297161.5839
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure |  |  | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64248.7058 | 656382.3006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720631.0064 |  | 720631.0064 | 0 | Arterial |  |  | 2047 | 207054.523
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial |  |  | Transport - Auckland wide | 28.73% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial |  |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  |  | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 887804.0708 | 42735.8 | 522408.6517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1452948.5225 |  | 1452948.5225 | 0 | Arterial |  |  | 2047 | 417466.8597
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial |  |  | Transport - Auckland wide | 28.73% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial |  |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial |  |  | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2263739.3521 | 34801.3823 | 570370.6997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2868911.4341 |  | 2868911.4341 | 0 | Arterial |  |  | 2047 | 824306.8689
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial |  |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) |  |  | Transport - Auckland wide | 28.73% | 2034 | 332120.9811 | 92702.226 | 947071.2235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1371894.4305 |  | 1371894.4305 | 0 | Collector |  |  | 2034 | 394178.0806
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector |  |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) |  |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial |  |  | Transport - Auckland wide | 28.73% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure |  |  | Transport - Auckland wide | 28.73% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade |  |  | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure |  |  | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure |  |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure |  |  | Transport - Auckland wide | 28.73% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) |  |  | Transport - Auckland wide | 28.73% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure |  |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
1b | GSR improvements - Waihoehoe Rd to Drury Interchange | 4-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
2a | GSR improvements - From Drury School to Waihoehoe Rd | 2-lane urban- existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Interim Arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2030 | 0
4b | Waihoehoe Rd East upgrades- from Fitzgerald Rd to before Cossey Rd (development boundary) | Expand to 24m cross section | Include | 2-lane Arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
7 | Fitzgerald Rd upgrades (from Waihoehoe Rd to development boundary) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
8 | Fielding Rd upgrades ( from Waihoehoe Rd to development boundary ) | 2-lane urban - upgrade existing road layout with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
10a | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | 2-lane signalised intersection with active mode crossings | Include | 2-lane Arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
10b | New intersection on Waihoehoe Rd/Fitzgerald Rd( including approach cross-sections) | multi-lane roundabout with active mode crossings, SGA design | Include | 4-lane arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
11 | Intersection upgrade Waihoehoe Rd/Fielding Rd/Appleby Rd | Roundabout as per SGA design | Include | 2-lane Arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
12 | Interim walking, cycling and bus connections within Drury Centre (includes Bremner/Norrie/Firth Intersection upgrades, active mode on Norrie) -overlap with project 36 and 46 | Intersection improvements on Bremner-Firth Rd, Norrie-Firth Rd, GSR-Firth Rd, Active mode facilities on both sides of Firth & Norrie Rd | Include | New Collector (AT) | WK DE |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
13a | N-S Opaheke Arterial across development (upto Waihoehoe Stream) | 2-lane urban- new 2-lane arterial with active modes on both sides + intersection improvements (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2029 | 0
13b | N-S Opaheke Arterial across development (upto Waihoihoi Stream) | 4-lane urban- upgrade 2-lane arterial with SGA design + intersection improvements (TDM) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Auckland wide | 28.73% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -29612.9506 | -302533.9794 | 0 | 0 | 0 | 0 | -332146.93 |  | -332146.93 | 0 | Arterial |  |  | 2050 | -95433.7567
14a | Western end of Brookefield Road Extension tie in with Quarry Rd | 2-lane urban (New Road connection to Quarry Road with active modes on both sides + intersection improvements) | Include | New Collector (AT) | WK DE |  | Transport - Auckland wide | 28.73% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
14b | Brookefield Road Upgrade | 2-lane urban (upgrade existing road layout with active modes on both sides + intersection improvements) | Include | Upgrade Collector | WK DE |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
16b | Widen Bremner Road Bridge ove SH1 to 4-lanes | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35017.0907 | -357744.1483 | 0 | 0 | 0 | 0 | -392761.2389 |  | -392761.2389 | 0 | Arterial |  |  | 2050 | -112849.6974
20a | Upgrade Fitzgerald Rd from Brookefield to Cossey Rd for active modes | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Auckland wide | 28.73% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
21 | Fielding Rd upgrades for active modes ( from Fitzgerald Rd to development boundary ) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Auckland wide | 28.73% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
22 | Upgrade Intersection at Quarry/ GSR | Upgrade intersection with active modes facilities(TDM) | Include | New Collector (AT) | WK DE |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
23c | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Interim 2-lane – install kerb and channel within existing road corridor with provision of active modes on both sides, 20m cross-section | Include | Interim Arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2025 | 0
23d | Waihoehoe Rd West upgrades- between Kath Henry Lane and Fitzgerald Rd | Final 4-lane - following interim option, upgrade Road corridor to provide four lanes with additional turning lanes at intersections where required (as indicated in SGA Design | Include | 4-lane arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
24 | Upgrades on Waihoehoe Rd east- from project 4 to Drury Hills + Drury Hills Intersection | 2-lane urban - upgrade existing road layout with active modes on both sides, 20m cross-section | Include | 2-lane Arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2038 | 0
25 | Upgrades on Drury Hills from Waihoehoe Rd to Macwhinney Dr | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides | Include | Upgrade Collector | WK DE |  | Transport - Auckland wide | 28.73% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
27a | Active mode facilities from Drury hills and Fitzgerald to Quarry Rd (2 links and intersections) | Active mode upgrades- existing road layout with active modes on both sides + intersection upgrades for active mode crossing | Include | Upgrade Collector | WK DE |  | Transport - Auckland wide | 28.73% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
28a | Northern Section of new collector in N-S direction parallel to Fitzgerald Rd | 2-lane collector to connect with Drury Central Station, including bridge over streamM) | Include | New Collector (AT) | WK DE |  | Transport - Auckland wide | 28.73% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
31 | Upgrades on Cossey Rd between Fitzgerald & Waihoehoe Rd | 2-lane urban - upgrade existing roadwith active modes on both sides / Mill Road design ? | Include | Upgrade Collector | WK DE |  | Transport - Auckland wide | 28.73% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2039 | 0
32 | New Intersection on Cossey Rd/Waihoehoe Rd | Assume 1 simple roundabout intesection | Include | 2-lane Arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2039 | 0
33 | Upgrade Fitzgerald Rd from project 7 to Brookefield Rd | 2-lane urban- upgrade existing road layout to 2-lane urban with active modes on both sides (TDM ) | Include | Upgrade Collector | WK DE |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
36a | Bremner-Norrie Road east of SH1 up to GSR (overlap with project 12) | 2-lane urban- upgrade existing road layout with active modes on both sides (Under construction) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | -641156.2986 | -55113.54 | -591834.735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1288104.5736 |  | -1288104.5736 | 0 | Arterial |  |  | 2033 | -370103.2508
36b | Complete Bremner-Norrie Road connection from SH1 up to GSR excluding Bridge (overlap with project 12) | 4-lane urban- upgrade interim 2-lane urban corridor to a 4-lane corridor with active modes on both sides (SGA design) | Include | 4-lane arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1266384.5793 | -75936.8507 | -775791.5772 | 0 | 0 | 0 | 0 | -2118113.0072 |  | -2118113.0072 | 0 | Arterial |  |  | 2050 | -608584.5245
36c | Complete Bremner-Norrie Road connection from SH1 up to GSR - Bridge structure (overlap with project 12) | Upgrade interim 2-lane bridges (3No. to 4 lane bridges with active modes on both sides (SGA design) | Include | Major Infrastructure | WK DE |  | Transport - Auckland wide | 28.73% | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -80796.5978 | -825440.0785 | 0 | 0 | 0 | 0 | -906236.6763 |  | -906236.6763 | 0 | Arterial |  |  | 2050 | -260383.471
37a(i) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3078592.1399 | -96975.9287 | -1152687.1383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4328255.2069 |  | -4328255.2069 | 0 | Arterial |  |  | 2044 | -1243611.237
37a(ii) | N-S Opaheke Arterial from development to Ponga Rd | 2-lane urban- bridge construction | Include | Major Infrastructure | WK DE |  | Transport - Auckland wide | 28.73% | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -266229.1718 | -2719869.8272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2986098.999 |  | -2986098.999 | 0 | Arterial |  |  | 2044 | -857977.659
37b(i) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- upgrade 2-lane urban with active modes on both sides (SGA design) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Auckland wide | 28.73% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2049 | 0
37b(ii) | N-S Opaheke Arterial from development to Ponga Rd | 4-lane urban- Bridge Widening | Include | Major Infrastructure | WK DE |  | Transport - Auckland wide | 28.73% | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2049 | 0
39b | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane urban excl bridge | Include | 4-lane arterial upgrade | WK DE |  | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -47026.4833 | -480435.3784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -527461.8616 |  | -527461.8616 | 0 | Arterial |  |  | 2047 | -151552.4078
39c | New Bremner Rd arterial from SH1 to Auranga development | 4-lane urban- upgrade 2-lane bridge widening | Include | Major Infrastructure | WK DE |  | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -32766.8399 | -334754.9733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -367521.8133 |  | -367521.8133 | 0 | Arterial |  |  | 2047 | -105597.8067
40a | New intersection on Jesmond/Bremner Rd | 2-lane signalised intersection (new intersection with active mode crossings) | Include | 2-lane Arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2027 | 0
40b | Upgrade intersection on Jesmond/Bremner Rd | Multi-lane signalised intersection (upgrade intersection with active mode crossings) | Include | 4-lane arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
41b | Jesmond Rd from SH22 to Waipupuke development boundary | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -452780.0761 | -21795.258 | -266428.4124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -741003.7465 |  | -741003.7465 | 0 | Arterial |  |  | 2047 | -212908.0985
42a | Jesmond Rd upgrades from project 41 to New Bremner Rd | Interim active modes e.g. shared path on one side | Include | Interim Arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2028 | 0
42b | Jesmond Rd upgrades from project 41 to New Bremner Rd | 2-lane urban- upgrade existing road with active mode facility on both sides (TDM) | Include | Interim Arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
42c | Jesmond Rd upgrades from project 41 to New Bremner Rd | 4-lane urban FTN- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1154507.0696 | -17748.705 | -290889.0568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1463144.8314 |  | -1463144.8314 | 0 | Arterial |  |  | 2047 | -420396.5031
46 | Upgrades in GSR/Firth St intersection (overlap with project12) | Possible signals(subject to Auranga assessment) | Include | 4-lane arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
55a | New E-W collector Jesmond Rd to Burberry Rd | 2-lane urban- new collector with active mode on both sides + intersection improvements (TDM) | Include | New Collector (AT) | WK DE |  | Transport - Auckland wide | 28.73% | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2034 | 0
58 | Oira Rd upgrades from SH22 to proposed east-west collector | 2-lane urban- upgrade existing road layout with active modes on both sides + intersection improvements (TDM) | Include | Upgrade Collector | WK DE |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
59 | New Intersection on Jesmond Rd/collector (PC61) | 2-lane intersection (new intersection + active mode crossings) | Include | New Collector (AT) | WK DE |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2033 | 0
65a(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Interim 2-lane Arterial | WK DE |  | Transport - Auckland wide | 28.73% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65a(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge only) | 2-lane urban- new road layout with active modes on both sides (TDM) | Include | Major Infrastructure | WK DE |  | Transport - Auckland wide | 28.73% | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2036 | 0
65b(i) | New Bremner Rd arterial from Auranga development to Jesmond Rd (excl bridge) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | 4-lane arterial upgrade | WK DE |  | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
65b(ii) | New Bremner Rd arterial from Auranga development to Jesmond Rd (bridge widening) | 4-lane urban- upgrade 2-lane urban to 4-lane with active modes on both sides, (TDM) | Include | Major Infrastructure | WK DE |  | Transport - Auckland wide | 28.73% | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2047 | 0
67 | Active Mode Corridor Drury Central to GSR | 0 | Include | Major Infrastructure | WK DE |  | Transport - Auckland wide | 28.73% | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2033 | 0
68 | Active Mode Corridor GSR to Drury West | 0 | Include | Major Infrastructure | WK DE |  | Transport - Auckland wide | 28.73% | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2037 | 0
69 | walk/cycle bridges on Quarry Road bridge (oiver SH1) | New cycle bridge 5m wide, 90m long, approach lengths 200m total for both sides. No property required | Include | New Collector (AT) | WK DE |  | Transport - Auckland wide | 28.73% | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Collector |  |  | 2035 | 0
70 | walk/cycle bridges on GSR Road bridge over the rail corridor | New cycle bridge 5m wide, 80m long, approach lengths 270m total for both sides. No property required | Include | Major Infrastructure | WK DE |  | Transport - Auckland wide | 28.73% | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Arterial |  |  | 2031 | 0
[7 empty] | Transport - Drury East IPA |  |  | 100361848.9846 | 35142216.7014 | 83255448.3492 | 12697918.1143 | 38199590.5182 | 0 | 0 | 36218731.0575 | 4273001.1826 | 45559493.7109 | 0 | 138610.6338 | 1416084.0375 | 48152371.6865 | 42485676.1228 | 73288349.8592 | 0 | 0 | 0 | 0 | 521189340.9585 | 0 | 521189340.9585
[7 empty] | Transport - Drury West 1 IPA |  |  | 43326039.7045 | 34481872.4453 | 88246771.254 | 21033058.517 | 22048745.0283 | 0 | 0 | 3018227.5881 | 356083.4319 | 3796624.4759 | 94546302.6871 | 5730999.4281 | 67568603.6697 | 37875049.8848 | 12588178.2652 | 63012097.858 | 0 | 0 | 0 | 0 | 497628654.238 | 0 | 497628654.238
[7 empty] | Transport - Drury West 2 IPA |  |  | 51063136.0267 | 8177994.9854 | 26181297.5071 | 955129.7839 | 1160460.2646 | 0 | 0 | 3018227.5881 | 356083.4319 | 3796624.4759 | 28363890.8061 | 1945330.3448 | 22579770.5003 | 5594658.647 | 7700419.4232 | 13077420.5024 | 0 | 0 | 0 | 0 | 173970444.2873 | 0 | 173970444.2873
[7 empty] | Transport - Opaheke IPA |  |  | 1763272.5596 | 857691.3416 | 6515067.279 | 874427.6023 | 1278025.0617 | 0 | 0 | 66401006.9388 | 7833835.5015 | 83525738.4699 | 0 | 198992.5193 | 2032961.8478 | 16845318.7877 | 72814081.6262 | 22374707.4504 | 0 | 0 | 0 | 0 | 283315126.9858 | 0 | 283315126.9858
[7 empty] | Transport - Southern Growth Area 3 |  |  | 231994.4694 | 2370118.7702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602113.2395 | 0 | 2602113.2395
[7 empty] | Transport - Southern Growth Area 1 |  |  | 350379.7712 | 123475.598 | 874582.4045 | 255453.9459 | 39188.2657 | 0 | 0 | 6036455.1763 | 712166.8638 | 7593248.9518 | 0 | 78228.7482 | 799206.2272 | 628444.6104 | 6536490.752 | 1186407.7623 | 0 | 0 | 0 | 0 | 25213729.0771 | 0 | 25213729.0771
[7 empty] | Transport - Southern Growth Area 2 |  |  | 57825773.4823 | 3828972.7822 | 36715876.5289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319756.2903 | 3266717.4685 | 314222.3052 | 3210180.767 | 0 | 0 | 0 | 0 | 0 | 105481499.6245 | 0 | 105481499.6245
[7 empty] | Transport - Auckland Wide |  |  | 2269459.7911 | 256523.2949 | 3076156.4868 | 108065.7647 | 1160460.2646 | 0 | 0 | 6036455.1763 | 712166.8638 | 7593248.9518 | 3151543.4229 | 233994.6788 | 2691191.8058 | 2483107.0183 | 434046.0584 | 4434332.9085 | 0 | 0 | 0 | 0 | 34640752.4866 | 0 | 34640752.4866
[7 empty] | Transport - Drury IPA |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Total |  |  | 257191904.7894 | 85238865.9189 | 244865199.8095 | 35924053.7281 | 63886469.4032 | 0 | 0 | 120729103.525 | 14243337.2754 | 151864979.0362 | 126061736.9161 | 8645912.6433 | 100354535.5567 | 111893172.9399 | 145769073.0147 | 177373316.3409 | 0 | 0 | 0 | 0 | 1644041660.8974 | 0 | 1644041660.8974
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## DC_growth_AGS
AGS extended to full build out year (FBO) for the investment priority areas (IPA)
Growth scenario - Extending AGSv1 from 2052 to full build out year |  |  |  |  | HOUSEHOLD FORECASTS | [63 empty] | POPULATION FORECASTS | [68 empty] | EMPLOYMENT FORECASTS | [64 empty] | HOUSEHOLD OCCUPANCY LEVELS (population divided by households)
MSM zone | Local Board | IPA area | IPA sub area | FBO Year (assume 2052 for non-IPAs) | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060 | 2061 | 2062 | 2063 | 2064 | 2065 | 2066 | 2067 | 2068 | 2069 | 2070 | 2071 | 2072 | 2073 | 2074 | 2075 | 2076 | 2077 | 2078 | 2079 | 2080 |  | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060 | 2061 | 2062 | 2063 | 2064 | 2065 | 2066 | 2067 | 2068 | 2069 | 2070 | 2071 | 2072 | 2073 | 2074 | 2075 | 2076 | 2077 | 2078 | 2079 | 2080 | LTP growth (2025-2034) | Total growth 2023-2052 |  |  |  |  | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060 | 2061 | 2062 | 2063 | 2064 | 2065 | 2066 | 2067 | 2068 | 2069 | 2070 | 2071 | 2072 | 2073 | 2074 | 2075 | 2076 | 2077 | 2078 | 2079 | 2080 | LTP growth (2025-2034) | Total growth 2023-2052 |  |  |  |  | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060 | 2061 | 2062 | 2063 | 2064 | 2065 | 2066 | 2067 | 2068 | 2069 | 2070 | 2071 | 2072 | 2073 | 2074 | 2075 | 2076 | 2077 | 2078 | 2079 | 2080
1 | Rodney |  |  | 2052 | 1224.6698 | 1259.9517 | 1296.25 | 1333.5941 | 1372.014 | 1373.0125 | 1374.0118 | 1375.0118 | 1376.0125 | 1377.014 | 1378.0125 | 1379.0118 | 1380.0118 | 1381.0125 | 1382.014 | 1383.0125 | 1384.0118 | 1385.0118 | 1386.0125 | 1387.014 | 1388.0126 | 1389.0118 | 1390.0118 | 1391.0126 | 1392.014 | 1393.0126 | 1394.0118 | 1395.0118 | 1396.0126 | 1397.014 | 1398.0126 | 1399.0118 | 1400.0118 | 1401.0126 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 | 1402.014 |  | 3180 | 3271.0173 | 3364.6397 | 3460.9417 | 3560 | 3549.0839 | 3538.2014 | 3527.3522 | 3516.5362 | 3505.7534 | 3494.7375 | 3483.7561 | 3472.8093 | 3461.8968 | 3451.0187 | 3441.8773 | 3432.7602 | 3423.6672 | 3414.5982 | 3405.5534 | 3396.533 | 3387.5365 | 3378.5638 | 3369.6149 | 3360.6897 | 3351.241 | 3341.8189 | 3332.4233 | 3323.054 | 3313.7112 | 3316.0798 | 3318.4501 | 3320.8221 | 3323.1957 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 3325.5711 | 26.8366 | 46.1796 | 166.1796 | -15.8% | 0 | 2065 | 1005 | 1005 | 1005 | 1005 | 1004.2 | 1013 | 1022 | 1031 | 1040 | 1049 | 1056.5 | 1050 | 1044 | 1038 | 1032 | 1026 | 1020 | 1014 | 1008 | 1002 | 996 | 990 | 984 | 978 | 972 | 966 | 960 | 954 | 948 | 942 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 935.1 | 18 | 54.8 | 212.8 | -8.461% | 0 | 2065 | 2.5966 | 2.5961 | 2.5957 | 2.5952 | 2.5947 | 2.5849 | 2.5751 | 2.5653 | 2.5556 | 2.5459 | 2.5361 | 2.5263 | 2.5165 | 2.5068 | 2.4971 | 2.4887 | 2.4803 | 2.4719 | 2.4636 | 2.4553 | 2.447 | 2.4388 | 2.4306 | 2.4224 | 2.4143 | 2.4058 | 2.3973 | 2.3888 | 2.3804 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372 | 2.372
2 | Rodney |  |  | 2052 | 428.7142 | 443.3407 | 458.4662 | 474.1078 | 490.283 | 494.0051 | 497.7555 | 501.5343 | 505.3418 | 509.1782 | 512.974 | 516.798 | 520.6506 | 524.5319 | 528.4421 | 530.7495 | 533.0669 | 535.3944 | 537.7321 | 540.08 | 541.4692 | 542.862 | 544.2583 | 545.6583 | 547.0618 | 548.9298 | 550.8041 | 552.6849 | 554.572 | 556.4656 | 558.218 | 559.976 | 561.7394 | 563.5084 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 | 565.283 |  | 1230 | 1268.1848 | 1307.555 | 1348.1474 | 1390 | 1393.5025 | 1397.0138 | 1400.5339 | 1404.0629 | 1407.6008 | 1410.8211 | 1414.0488 | 1417.2838 | 1420.5263 | 1423.7762 | 1424.1212 | 1424.4663 | 1424.8115 | 1425.1568 | 1425.5022 | 1423.4931 | 1421.4869 | 1419.4835 | 1417.4829 | 1415.4851 | 1414.3061 | 1413.1282 | 1411.9512 | 1410.7752 | 1409.6001 | 1413.6763 | 1417.7643 | 1421.8641 | 1425.9757 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 1430.0993 | 5674.7005 | 6146.2486 | 7592 | 2.531% | 0 | 2065 | 660 | 663 | 666 | 669 | 672.9 | 680 | 687 | 694 | 701 | 708 | 712.6 | 707 | 702 | 697 | 692 | 687 | 682 | 677 | 672 | 667 | 662 | 657 | 652 | 647 | 642 | 637 | 632 | 627 | 622 | 617 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 0 | -1.1 | 664 | 62% | 0 | 2065 | 2.869 | 2.8605 | 2.852 | 2.8435 | 2.8351 | 2.8208 | 2.8066 | 2.7925 | 2.7784 | 2.7645 | 2.7503 | 2.7362 | 2.7221 | 2.7082 | 2.6943 | 2.6832 | 2.6722 | 2.6612 | 2.6503 | 2.6394 | 2.6289 | 2.6185 | 2.6081 | 2.5977 | 2.5874 | 2.5765 | 2.5656 | 2.5547 | 2.5439 | 2.5331 | 2.5325 | 2.5318 | 2.5312 | 2.5305 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299 | 2.5299
3 | Rodney |  |  | 2052 | 290.4509 | 296.8294 | 303.3478 | 310.0095 | 316.8174 | 332.0717 | 348.0606 | 364.8192 | 382.3848 | 400.7961 | 416.6198 | 433.0683 | 450.1661 | 467.939 | 486.4136 | 492.3478 | 498.3544 | 504.4342 | 510.5883 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 | 516.8174 |  | 760 | 776.9261 | 794.2292 | 811.9176 | 830 | 865.9971 | 903.5553 | 942.7425 | 983.6292 | 1026.2892 | 1061.6208 | 1098.1688 | 1135.975 | 1175.0828 | 1215.5369 | 1225.2045 | 1234.9491 | 1244.7712 | 1254.6714 | 1264.6503 | 1259.188 | 1253.7493 | 1248.3341 | 1242.9422 | 1237.5737 | 1231.9464 | 1226.3448 | 1220.7686 | 1215.2178 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 1209.6922 | 10198.3202 | 9934.8801 | 10987 | 1.077% | 0 | 2065 | 73 | 73 | 73 | 73 | 72.3 | 73 | 74 | 75 | 76 | 77 | 77.6 | 77 | 76 | 75 | 74 | 73 | 72 | 71 | 70 | 69 | 68 | 67 | 66 | 65 | 64 | 63 | 62 | 61 | 60 | 59 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 64.5 | 78 | 391.3 | 968 | 11.82% | 0 | 2065 | 2.6166 | 2.6174 | 2.6182 | 2.619 | 2.6198 | 2.6079 | 2.596 | 2.5841 | 2.5724 | 2.5606 | 2.5482 | 2.5358 | 2.5235 | 2.5112 | 2.499 | 2.4885 | 2.4781 | 2.4677 | 2.4573 | 2.447 | 2.4364 | 2.4259 | 2.4154 | 2.405 | 2.3946 | 2.3837 | 2.3729 | 2.3621 | 2.3513 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407 | 2.3407
4 | Rodney |  |  | 2052 | 111.1948 | 113.253 | 115.3492 | 117.4843 | 119.6588 | 123.5907 | 127.6518 | 131.8464 | 136.1788 | 140.6535 | 144.6953 | 148.8533 | 153.1307 | 157.5311 | 162.0579 | 163.5503 | 165.0565 | 166.5766 | 168.1106 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 | 169.6588 |  | 300 | 304.8796 | 309.8387 | 314.8783 | 320 | 329.6068 | 339.502 | 349.6943 | 360.1926 | 371.0061 | 380.9396 | 391.139 | 401.6116 | 412.3645 | 423.4054 | 426.8476 | 430.3178 | 433.8163 | 437.3432 | 440.8988 | 440.7772 | 440.6557 | 440.5342 | 440.4128 | 440.2914 | 440.1662 | 440.0411 | 439.916 | 439.7909 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 439.6659 | 2218.7301 | 3157.8085 | 3367.8085 | -2.221% | 0 | 2065 | 422 | 425 | 428 | 431 | 432.6 | 437 | 441 | 445 | 449 | 453 | 459 | 456 | 453 | 450 | 447 | 444 | 441 | 438 | 435 | 432 | 429 | 426 | 423 | 420 | 417 | 414 | 411 | 408 | 405 | 402 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 399 | 18 | 48.8 | 317 | 6.262% | 0 | 2065 | 2.698 | 2.692 | 2.6861 | 2.6802 | 2.6743 | 2.6669 | 2.6596 | 2.6523 | 2.645 | 2.6377 | 2.6327 | 2.6277 | 2.6227 | 2.6177 | 2.6127 | 2.6099 | 2.6071 | 2.6043 | 2.6015 | 2.5987 | 2.598 | 2.5973 | 2.5966 | 2.5959 | 2.5952 | 2.5944 | 2.5937 | 2.5929 | 2.5922 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915 | 2.5915
5 | Rodney |  |  | 2052 | 1653.5698 | 1689.2812 | 1725.7639 | 1763.0344 | 1801.1099 | 1801.6135 | 1802.1172 | 1802.6211 | 1803.1251 | 1803.6293 | 1804.1427 | 1804.6562 | 1805.1699 | 1805.6838 | 1806.1978 | 1806.6358 | 1807.074 | 1807.5123 | 1807.9506 | 1808.3891 | 1808.7613 | 1809.1336 | 1809.506 | 1809.8784 | 1810.2509 | 1810.5875 | 1810.9241 | 1811.2607 | 1811.5975 | 1811.9343 | 1812.1693 | 1812.4044 | 1812.6395 | 1812.8747 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 | 1813.1099 |  | 4450 | 4546.7957 | 4645.6969 | 4746.7494 | 4850 | 4826.6409 | 4803.3944 | 4780.2598 | 4757.2367 | 4734.3244 | 4710.9158 | 4687.6229 | 4664.4453 | 4641.3822 | 4618.4331 | 4599.7194 | 4581.0815 | 4562.5191 | 4544.0319 | 4525.6197 | 4507.0403 | 4488.5372 | 4470.1101 | 4451.7586 | 4433.4825 | 4414.1857 | 4394.9729 | 4375.8437 | 4356.7978 | 4337.8347 | 4338.4018 | 4338.9689 | 4339.5361 | 4340.1034 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4340.6707 | 4230.5922 | 4868.2068 | 5828.2068 | -0.1319% | 0 | 2065 | 1089 | 1111 | 1133 | 1155 | 1176.2 | 1207 | 1238 | 1269 | 1300 | 1331 | 1361.8 | 1372 | 1382 | 1392 | 1402 | 1412 | 1422 | 1432 | 1442 | 1452 | 1462 | 1472 | 1482 | 1492 | 1502 | 1512 | 1522 | 1532 | 1542 | 1552 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 1568.9 | 13 | 46.2 | 538 | 22.66% | 0 | 2065 | 2.6911 | 2.6916 | 2.692 | 2.6924 | 2.6928 | 2.6791 | 2.6654 | 2.6518 | 2.6383 | 2.6249 | 2.6112 | 2.5975 | 2.5839 | 2.5704 | 2.557 | 2.546 | 2.5351 | 2.5242 | 2.5134 | 2.5026 | 2.4918 | 2.481 | 2.4703 | 2.4597 | 2.4491 | 2.438 | 2.4269 | 2.4159 | 2.4049 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394
6 | Rodney |  |  | 2052 | 1680.0459 | 1721.5745 | 1764.1296 | 1807.7366 | 1852.4215 | 1861.8976 | 1871.4222 | 1880.9956 | 1890.6178 | 1900.2894 | 1909.951 | 1919.6618 | 1929.4219 | 1939.2317 | 1949.0913 | 1957.9138 | 1966.7762 | 1975.6787 | 1984.6215 | 1993.6047 | 2001.4553 | 2009.3368 | 2017.2493 | 2025.193 | 2033.168 | 2043.7157 | 2054.3181 | 2064.9755 | 2075.6882 | 2086.4565 | 2096.3551 | 2106.3007 | 2116.2935 | 2126.3337 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 | 2136.4215 |  | 3940 | 4036.4037 | 4135.1663 | 4236.3453 | 4340 | 4342.9138 | 4345.8296 | 4348.7474 | 4351.6671 | 4354.5888 | 4356.9463 | 4359.3051 | 4361.6652 | 4364.0265 | 4366.3892 | 4369.2048 | 4372.0223 | 4374.8415 | 4377.6626 | 4380.4855 | 4380.7569 | 4381.0282 | 4381.2996 | 4381.5709 | 4381.8423 | 4386.6441 | 4391.4512 | 4396.2635 | 4401.0811 | 4405.904 | 4426.6119 | 4447.4172 | 4468.3202 | 4489.3215 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | 4510.4214 | -4.5163 | 5190.2057 | 8774 | 5.915% | 0 | 2065 | 1528 | 1533 | 1538 | 1543 | 1547.8 | 1560 | 1572 | 1584 | 1596 | 1608 | 1622.4 | 1611 | 1599 | 1587 | 1575 | 1563 | 1551 | 1539 | 1527 | 1515 | 1503 | 1491 | 1479 | 1467 | 1455 | 1443 | 1431 | 1419 | 1407 | 1395 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | 1388.8 | -103 | 100 | 1699 | -7.405% | 0 | 2065 | 2.3452 | 2.3446 | 2.344 | 2.3435 | 2.3429 | 2.3325 | 2.3222 | 2.3119 | 2.3017 | 2.2915 | 2.2812 | 2.2709 | 2.2606 | 2.2504 | 2.2402 | 2.2316 | 2.2229 | 2.2143 | 2.2058 | 2.1973 | 2.1888 | 2.1803 | 2.1719 | 2.1635 | 2.1552 | 2.1464 | 2.1377 | 2.129 | 2.1203 | 2.1117 | 2.1116 | 2.1115 | 2.1114 | 2.1113 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112 | 2.1112
7 | Rodney |  |  | 2052 | 2395.824 | 2438.4524 | 2481.8392 | 2525.9981 | 2570.9427 | 2611.1507 | 2651.9875 | 2693.463 | 2735.5871 | 2778.3701 | 2819.4332 | 2861.1033 | 2903.3892 | 2946.3001 | 2989.8453 | 3004.7161 | 3019.6609 | 3034.68 | 3049.7738 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 | 3064.9427 |  | 5370 | 5464.9518 | 5561.5825 | 5659.9218 | 5760 | 5837.1976 | 5915.4299 | 5994.7106 | 6075.0539 | 6156.474 | 6233.6203 | 6311.7334 | 6390.8252 | 6470.9082 | 6551.9947 | 6570.3671 | 6588.7909 | 6607.2664 | 6625.7938 | 6644.373 | 6630.4225 | 6616.5012 | 6602.6091 | 6588.7462 | 6574.9124 | 6560.359 | 6545.8377 | 6531.3486 | 6516.8916 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 6502.4666 | 843.4096 | 4707.4428 | 7158 | 5.295% | 0 | 2060 | 1062 | 1068 | 1074 | 1080 | 1087.7 | 1098 | 1108 | 1118 | 1128 | 1138 | 1147.1 | 1140 | 1133 | 1126 | 1119 | 1112 | 1105 | 1098 | 1091 | 1084 | 1077 | 1070 | 1063 | 1056 | 1049 | 1042 | 1035 | 1028 | 1021 | 1014 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 1003.4 | 310 | 853.4 | 10680 | 15.11% | 0 | 2060 | 2.2414 | 2.2412 | 2.2409 | 2.2407 | 2.2404 | 2.2355 | 2.2306 | 2.2257 | 2.2207 | 2.2159 | 2.2109 | 2.206 | 2.2012 | 2.1963 | 2.1914 | 2.1867 | 2.182 | 2.1773 | 2.1726 | 2.1679 | 2.1633 | 2.1588 | 2.1542 | 2.1497 | 2.1452 | 2.1405 | 2.1357 | 2.131 | 2.1263 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216 | 2.1216
8 | Rodney |  |  | 2052 | 1218.4319 | 1273.8021 | 1331.6885 | 1392.2055 | 1455.4726 | 1455.4726 | 1455.4726 | 1455.4726 | 1455.4726 | 1455.4726 | 1455.4726 | 1455.4726 | 1455.4726 | 1455.4726 | 1455.4726 | 1455.4726 | 1455.4726 | 1455.4726 | 1455.4726 | 1455.4726 | 1455.4726 | 1455.4726 | 1455.4726 | 1455.4726 | 1455.4726 | 1494.9069 | 1535.4096 | 1577.0097 | 1619.7368 | 1663.6217 | 1719.1581 | 1776.5484 | 1835.8546 | 1897.1407 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 | 1960.4726 |  | 3100 | 3238.0076 | 3382.1591 | 3532.728 | 3690 | 3673.7211 | 3657.514 | 3641.3784 | 3625.314 | 3609.3205 | 3593.0384 | 3576.8297 | 3560.6941 | 3544.6313 | 3528.641 | 3515.1735 | 3501.7573 | 3488.3924 | 3475.0785 | 3461.8153 | 3448.531 | 3435.2976 | 3422.1151 | 3408.9831 | 3395.9015 | 3472.0659 | 3549.9385 | 3629.5577 | 3710.9626 | 3794.1932 | 3919.1811 | 4048.2862 | 4181.6443 | 4319.3955 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 4461.6845 | 64.8021 | 1548.8235 | 2964 | 7.049% | 0 | 2080 | 1868 | 1883 | 1898 | 1913 | 1926.5 | 1947 | 1967 | 1987 | 2007 | 2027 | 2048.3 | 2036 | 2024 | 2012 | 2000 | 1988 | 1976 | 1964 | 1952 | 1940 | 1928 | 1916 | 1904 | 1892 | 1880 | 1868 | 1856 | 1844 | 1832 | 1820 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1807.4 | 1081 | 8487.2 | 8728.2 | 26.68% | 0 | 2080 | 2.5443 | 2.542 | 2.5398 | 2.5375 | 2.5353 | 2.5241 | 2.5129 | 2.5019 | 2.4908 | 2.4798 | 2.4686 | 2.4575 | 2.4464 | 2.4354 | 2.4244 | 2.4151 | 2.4059 | 2.3967 | 2.3876 | 2.3785 | 2.3694 | 2.3603 | 2.3512 | 2.3422 | 2.3332 | 2.3226 | 2.312 | 2.3015 | 2.2911 | 2.2807 | 2.2797 | 2.2787 | 2.2778 | 2.2768 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758 | 2.2758
9 | Rodney |  |  | 2052 | 206.1602 | 204.9787 | 203.804 | 202.636 | 201.4747 | 201.4747 | 201.4747 | 201.4747 | 201.4747 | 201.4747 | 201.4747 | 201.4747 | 201.4747 | 201.4747 | 201.4747 | 216.3239 | 232.2675 | 249.3862 | 267.7666 | 287.5017 | 309.0586 | 332.2318 | 357.1426 | 383.9212 | 412.7077 | 423.6638 | 434.9107 | 446.4562 | 458.3081 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 | 470.4747 |  | 440 | 437.4784 | 434.9713 | 432.4785 | 430 | 431.9302 | 433.8691 | 435.8167 | 437.7731 | 439.7382 | 441.6688 | 443.6079 | 445.5555 | 447.5116 | 449.4764 | 479.0023 | 510.4678 | 544.0002 | 579.7354 | 617.818 | 659.9147 | 704.8798 | 752.9087 | 804.2101 | 859.0072 | 877.1739 | 895.7248 | 914.668 | 934.0118 | 953.7647 | 953.8117 | 953.8586 | 953.9056 | 953.9526 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 953.9995 | 36.056 | 286.7582 | 597 | 7.825% | 0 | 2080 | 33 | 33 | 33 | 33 | 33.5 | 34 | 34 | 34 | 34 | 34 | 34.9 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 34.9 | 349 | 2408.3 | 2624 | 61.75% | 4.5475e-12 | 2080 | 2.1343 | 2.1343 | 2.1343 | 2.1343 | 2.1343 | 2.1438 | 2.1535 | 2.1631 | 2.1728 | 2.1826 | 2.1922 | 2.2018 | 2.2115 | 2.2212 | 2.2309 | 2.2143 | 2.1978 | 2.1814 | 2.1651 | 2.1489 | 2.1352 | 2.1217 | 2.1081 | 2.0947 | 2.0814 | 2.0704 | 2.0596 | 2.0487 | 2.038 | 2.0272 | 2.0273 | 2.0274 | 2.0275 | 2.0276 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277 | 2.0277
10 | Rodney |  |  | 2052 | 292.9742 | 304.1644 | 315.782 | 327.8433 | 340.3653 | 340.3653 | 340.3653 | 340.3653 | 340.3653 | 340.3653 | 340.3653 | 340.3653 | 340.3653 | 340.3653 | 340.3653 | 383.7221 | 432.6017 | 487.7078 | 549.8335 | 619.8729 | 685.6916 | 758.499 | 839.0371 | 928.1268 | 1026.6762 | 1061.7363 | 1097.9937 | 1135.4892 | 1174.2652 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 | 1214.3653 |  | 900 | 933.1258 | 967.4709 | 1003.0801 | 1040 | 1026.0056 | 1012.1995 | 998.5792 | 985.1421 | 971.8859 | 957.8643 | 944.045 | 930.425 | 917.0016 | 903.7718 | 1008.9029 | 1126.2633 | 1257.2757 | 1403.528 | 1566.7931 | 1722.8582 | 1894.4685 | 2083.1725 | 2290.673 | 2518.8422 | 2592.2398 | 2667.7761 | 2745.5134 | 2825.516 | 2907.8498 | 2907.7207 | 2907.5915 | 2907.4624 | 2907.3332 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2907.2041 | 2.9439 | -1.9691 | 784 | 3.443% | 1.4779e-12 | 2080 | 424 | 426 | 428 | 430 | 433.3 | 454 | 475 | 496 | 517 | 538 | 558.3 | 574 | 590 | 606 | 622 | 638 | 654 | 670 | 686 | 702 | 718 | 734 | 750 | 766 | 782 | 798 | 814 | 830 | 846 | 862 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 15 | 33.2 | 214.2 | -3.204% | 0 | 2080 | 3.0719 | 3.0678 | 3.0637 | 3.0596 | 3.0555 | 3.0144 | 2.9739 | 2.9338 | 2.8944 | 2.8554 | 2.8142 | 2.7736 | 2.7336 | 2.6942 | 2.6553 | 2.6293 | 2.6035 | 2.5779 | 2.5526 | 2.5276 | 2.5126 | 2.4977 | 2.4828 | 2.4681 | 2.4534 | 2.4415 | 2.4297 | 2.4179 | 2.4062 | 2.3945 | 2.3944 | 2.3943 | 2.3942 | 2.3941 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394 | 2.394
11 | Rodney |  |  | 2052 | 66.6989 | 68.2218 | 69.7795 | 71.3728 | 73.0024 | 73.0024 | 73.0024 | 73.0024 | 73.0024 | 73.0024 | 73.0024 | 73.0024 | 73.0024 | 73.0024 | 73.0024 | 78.9301 | 85.3391 | 92.2685 | 99.7605 | 107.8609 | 116.5062 | 125.8445 | 135.9312 | 146.8265 | 158.595 | 163.0223 | 167.5732 | 172.2511 | 177.0596 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 | 182.0024 |  | 220 | 224.8381 | 229.7825 | 234.8357 | 240 | 239.2638 | 238.5298 | 237.7981 | 237.0686 | 236.3414 | 235.6051 | 234.8711 | 234.1394 | 233.4099 | 232.6828 | 250.1891 | 269.0126 | 289.2523 | 311.0148 | 334.4146 | 359.4232 | 386.3021 | 415.1911 | 446.2404 | 479.6118 | 491.0983 | 502.86 | 514.9034 | 527.2352 | 539.8623 | 539.8629 | 539.8635 | 539.864 | 539.8646 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 539.8652 | 688.3135 | 5073.3806 | 8352 | 4.366% | 0 | 2080 | 102 | 94 | 86 | 78 | 69.7 | 116 | 162 | 208 | 254 | 300 | 347.1 | 417 | 487 | 557 | 627 | 697 | 767 | 837 | 907 | 977 | 1047 | 1117 | 1187 | 1257 | 1327 | 1397 | 1467 | 1537 | 1607 | 1677 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 1749.8 | 3 | 8.6 | 764 | 39.26% | 0 | 2080 | 3.2984 | 3.2957 | 3.293 | 3.2903 | 3.2876 | 3.2775 | 3.2674 | 3.2574 | 3.2474 | 3.2374 | 3.2274 | 3.2173 | 3.2073 | 3.1973 | 3.1873 | 3.1698 | 3.1523 | 3.1349 | 3.1176 | 3.1004 | 3.085 | 3.0697 | 3.0544 | 3.0392 | 3.0241 | 3.0125 | 3.0008 | 2.9893 | 2.9777 | 2.9662 | 2.9662 | 2.9662 | 2.9662 | 2.9662 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663 | 2.9663
12 | Rodney |  |  | 2052 | 486.8627 | 493.9883 | 501.2181 | 508.5538 | 515.9968 | 515.9968 | 515.9968 | 515.9968 | 515.9968 | 515.9968 | 515.9968 | 515.9968 | 515.9968 | 515.9968 | 515.9968 | 521.9348 | 527.9412 | 534.0166 | 540.162 | 546.3781 | 554.9485 | 563.6534 | 572.4948 | 581.4749 | 590.5958 | 594.6208 | 598.6732 | 602.7532 | 606.861 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 | 610.9968 |  | 1130 | 1144.7103 | 1159.612 | 1174.7077 | 1190 | 1191.407 | 1192.8157 | 1194.226 | 1195.638 | 1197.0517 | 1198.4588 | 1199.8674 | 1201.2778 | 1202.6898 | 1204.1035 | 1216.5243 | 1229.0733 | 1241.7517 | 1254.5609 | 1267.5023 | 1285.4417 | 1303.635 | 1322.0859 | 1340.7979 | 1359.7747 | 1368.1845 | 1376.6463 | 1385.1604 | 1393.7272 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 1402.3469 | 138.9614 | 1517.4369 | 11036 | 25.64% | 0 | 2080 | 1227 | 1235 | 1243 | 1251 | 1258.8 | 1276 | 1293 | 1310 | 1327 | 1344 | 1359.1 | 1348 | 1337 | 1326 | 1315 | 1304 | 1293 | 1282 | 1271 | 1260 | 1249 | 1238 | 1227 | 1216 | 1205 | 1194 | 1183 | 1172 | 1161 | 1150 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 1138.2 | 11 | 24.7 | 1149 | 27.65% | 0 | 2080 | 2.321 | 2.3173 | 2.3136 | 2.3099 | 2.3062 | 2.3089 | 2.3117 | 2.3144 | 2.3171 | 2.3199 | 2.3226 | 2.3253 | 2.3281 | 2.3308 | 2.3335 | 2.3308 | 2.328 | 2.3253 | 2.3226 | 2.3198 | 2.3163 | 2.3128 | 2.3093 | 2.3059 | 2.3024 | 2.3009 | 2.2995 | 2.2981 | 2.2966 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952 | 2.2952
13 | Rodney |  |  | 2052 | 45.4765 | 45.4765 | 45.4765 | 45.4765 | 45.4765 | 45.4765 | 45.4765 | 45.4765 | 45.4765 | 45.4765 | 45.4765 | 45.4765 | 45.4765 | 45.4765 | 45.4765 | 55.9322 | 68.7918 | 84.608 | 104.0606 | 127.9856 | 146.098 | 166.7737 | 190.3754 | 217.3172 | 248.0717 | 258.2776 | 268.9035 | 279.9664 | 291.4845 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 | 303.4765 |  | 110 | 110 | 110 | 110 | 110 | 109.6879 | 109.3767 | 109.0664 | 108.757 | 108.4484 | 108.1363 | 107.8251 | 107.5147 | 107.2053 | 106.8968 | 130.6274 | 159.6262 | 195.0626 | 238.3657 | 291.282 | 330.544 | 375.0981 | 425.6577 | 483.0323 | 548.1404 | 567.0534 | 586.6189 | 606.8596 | 627.7986 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | 649.4601 | -10.6488 | -21.2557 | 3729 | 47.25% | 0 | 2080 | 57 | 57 | 57 | 57 | 56.9 | 57 | 57 | 57 | 57 | 57 | 59.7 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 50.5 | 1 | 2.9 | 348 | 40.44% | 0 | 2080 | 2.4188 | 2.4188 | 2.4188 | 2.4188 | 2.4188 | 2.412 | 2.4051 | 2.3983 | 2.3915 | 2.3847 | 2.3778 | 2.371 | 2.3642 | 2.3574 | 2.3506 | 2.3355 | 2.3204 | 2.3055 | 2.2906 | 2.2759 | 2.2625 | 2.2491 | 2.2359 | 2.2227 | 2.2096 | 2.1955 | 2.1815 | 2.1676 | 2.1538 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401 | 2.1401
14 | Rodney |  |  | 2052 | 42.4447 | 42.4447 | 42.4447 | 42.4447 | 42.4447 | 42.4447 | 42.4447 | 42.4447 | 42.4447 | 42.4447 | 42.4447 | 42.4447 | 42.4447 | 42.4447 | 42.4447 | 42.4447 | 42.4447 | 42.4447 | 42.4447 | 42.4447 | 42.4447 | 42.4447 | 42.4447 | 42.4447 | 42.4447 | 72.5161 | 123.8926 | 211.6686 | 361.6323 | 617.8429 | 731.6125 | 866.3315 | 1025.8577 | 1214.7591 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 | 1438.4447 |  | 120 | 120 | 120 | 120 | 120 | 119.3341 | 118.6719 | 118.0134 | 117.3585 | 116.7073 | 116.0412 | 115.3789 | 114.7204 | 114.0656 | 113.4146 | 113.5486 | 113.6827 | 113.8171 | 113.9515 | 114.0862 | 113.8031 | 113.5208 | 113.2391 | 112.9582 | 112.6779 | 187.1024 | 310.6849 | 515.8944 | 856.6462 | 1422.467 | 1682.4613 | 1989.9766 | 2353.6986 | 2783.9007 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | 3292.7338 | -29.7201 | -67.7385 | 4751 | 28.93% | 0 | 2080 | 17 | 17 | 17 | 17 | 18.5 | 19 | 19 | 19 | 19 | 19 | 18.9 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 15.9 | 246 | 725.4 | 873.4 | -7.779% | 0 | 2080 | 2.8272 | 2.8272 | 2.8272 | 2.8272 | 2.8272 | 2.8115 | 2.7959 | 2.7804 | 2.765 | 2.7496 | 2.7339 | 2.7183 | 2.7028 | 2.6874 | 2.6721 | 2.6752 | 2.6784 | 2.6815 | 2.6847 | 2.6879 | 2.6812 | 2.6746 | 2.6679 | 2.6613 | 2.6547 | 2.5801 | 2.5077 | 2.4373 | 2.3688 | 2.3023 | 2.2997 | 2.297 | 2.2944 | 2.2917 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891 | 2.2891
15 | Rodney |  |  | 2052 | 60.6353 | 62.3531 | 64.1195 | 65.936 | 67.8039 | 67.8039 | 67.8039 | 67.8039 | 67.8039 | 67.8039 | 67.8039 | 67.8039 | 67.8039 | 67.8039 | 67.8039 | 85.0925 | 106.7893 | 134.0184 | 168.1904 | 211.0755 | 242.168 | 277.8406 | 318.7679 | 365.7241 | 419.5971 | 463.7824 | 512.6205 | 566.6015 | 626.2669 | 692.2154 | 736.4942 | 783.6054 | 833.7302 | 887.0613 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 | 943.8039 |  | 200 | 204.8227 | 209.7618 | 214.8199 | 220 | 219.1348 | 218.273 | 217.4146 | 216.5595 | 215.7078 | 214.8425 | 213.9806 | 213.1222 | 212.2672 | 211.4157 | 259.7161 | 319.0513 | 391.9423 | 481.4861 | 591.4872 | 672.5463 | 764.7139 | 869.5125 | 988.673 | 1124.1635 | 1234.7496 | 1356.2142 | 1489.6276 | 1636.1651 | 1797.1177 | 1910.3217 | 2030.6566 | 2158.5717 | 2294.5444 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 2439.0823 | 151.0298 | 1464.7849 | 2914 | 2.115% | 0 | 2080 | 31 | 31 | 31 | 31 | 30.9 | 31 | 32 | 33 | 34 | 35 | 33.9 | 46 | 58 | 70 | 82 | 94 | 106 | 118 | 130 | 142 | 154 | 166 | 178 | 190 | 202 | 214 | 226 | 238 | 250 | 262 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 277.4 | 245 | 925.6 | 2591.6 | -16.97% | 0 | 2080 | 3.2984 | 3.2849 | 3.2714 | 3.258 | 3.2447 | 3.2319 | 3.2192 | 3.2065 | 3.1939 | 3.1813 | 3.1686 | 3.1559 | 3.1432 | 3.1306 | 3.118 | 3.0522 | 2.9877 | 2.9245 | 2.8627 | 2.8023 | 2.7772 | 2.7523 | 2.7277 | 2.7033 | 2.6791 | 2.6623 | 2.6456 | 2.6291 | 2.6126 | 2.5962 | 2.5938 | 2.5914 | 2.5891 | 2.5867 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843 | 2.5843
16 | Rodney |  |  | 2052 | 832.1193 | 857.4532 | 883.5584 | 910.4584 | 938.1774 | 943.125 | 948.0986 | 953.0985 | 958.1247 | 963.1774 | 968.1263 | 973.1006 | 978.1005 | 983.126 | 988.1774 | 993.1276 | 998.1025 | 1003.1024 | 1008.1273 | 1013.1774 | 1018.1288 | 1023.1044 | 1028.1042 | 1033.1285 | 1038.1774 | 1043.1299 | 1048.1061 | 1053.106 | 1058.1297 | 1063.1774 | 1068.131 | 1073.1077 | 1078.1076 | 1083.1308 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 | 1088.1774 |  | 2200 | 2266.8873 | 2335.8082 | 2406.8245 | 2480 | 2480.2765 | 2480.5531 | 2480.8297 | 2481.1064 | 2481.383 | 2480.9878 | 2480.5926 | 2480.1974 | 2479.8023 | 2479.4073 | 2481.047 | 2482.6879 | 2484.3298 | 2485.9728 | 2487.6169 | 2488.9153 | 2490.2143 | 2491.514 | 2492.8143 | 2494.1154 | 2494.5522 | 2494.989 | 2495.426 | 2495.863 | 2496.3001 | 2507.931 | 2519.6161 | 2531.3557 | 2543.1499 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 2554.9991 | 62.9314 | 183.1087 | 333.1087 | -7.214% | 0 | 2080 | 473 | 474 | 475 | 476 | 475 | 479 | 483 | 487 | 491 | 495 | 501 | 498 | 495 | 492 | 489 | 486 | 483 | 480 | 477 | 474 | 471 | 468 | 465 | 462 | 459 | 456 | 453 | 450 | 447 | 444 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 435.9 | 44 | 128 | 1194 | 29.93% | 0 | 2080 | 2.6439 | 2.6437 | 2.6436 | 2.6435 | 2.6434 | 2.6298 | 2.6163 | 2.6029 | 2.5895 | 2.5762 | 2.5627 | 2.5492 | 2.5357 | 2.5224 | 2.5091 | 2.4982 | 2.4874 | 2.4766 | 2.4659 | 2.4553 | 2.4446 | 2.434 | 2.4234 | 2.4129 | 2.4024 | 2.3914 | 2.3805 | 2.3696 | 2.3587 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348 | 2.348
17 | Rodney |  |  | 2052 | 2391.0214 | 2456.3571 | 2523.4781 | 2592.4333 | 2663.2727 | 2663.2727 | 2663.2727 | 2663.2727 | 2663.2727 | 2663.2727 | 2663.2727 | 2663.2727 | 2663.2727 | 2663.2727 | 2663.2727 | 2705.8315 | 2749.0704 | 2793.0003 | 2837.6321 | 2882.9772 | 2944.268 | 3006.8618 | 3070.7863 | 3136.0699 | 3202.7413 | 3231.7185 | 3260.9578 | 3290.4617 | 3320.2325 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 | 3350.2727 |  | 6890 | 7079.5348 | 7274.2835 | 7474.3894 | 7680 | 7640.8026 | 7601.8052 | 7563.0069 | 7524.4066 | 7486.0033 | 7446.7954 | 7407.7928 | 7368.9945 | 7330.3995 | 7292.0065 | 7376.914 | 7462.8102 | 7549.7065 | 7637.6146 | 7726.5464 | 7857.1867 | 7990.0359 | 8125.1313 | 8262.511 | 8402.2134 | 8439.6525 | 8477.2584 | 8515.0319 | 8552.9737 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 8591.0846 | 210.682 | 3287.9606 | 9473 | 13.34% | 0 | 2080 | 1621 | 1624 | 1627 | 1630 | 1634.9 | 1651 | 1667 | 1683 | 1699 | 1715 | 1728.5 | 1716 | 1704 | 1692 | 1680 | 1668 | 1656 | 1644 | 1632 | 1620 | 1608 | 1596 | 1584 | 1572 | 1560 | 1548 | 1536 | 1524 | 1512 | 1500 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 1482.3 | 10 | 21.3 | 889 | 34.3% | 0 | 2080 | 2.8816 | 2.8821 | 2.8826 | 2.8832 | 2.8837 | 2.869 | 2.8543 | 2.8397 | 2.8252 | 2.8108 | 2.7961 | 2.7815 | 2.7669 | 2.7524 | 2.738 | 2.7263 | 2.7147 | 2.7031 | 2.6915 | 2.6801 | 2.6686 | 2.6573 | 2.6459 | 2.6347 | 2.6234 | 2.6115 | 2.5996 | 2.5878 | 2.576 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643
18 | Hibiscus and Bays |  |  | 2052 | 826.3957 | 821.1551 | 815.9478 | 810.7735 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 | 805.632 |  | 1990 | 1977.3805 | 1964.841 | 1952.381 | 1940 | 1938.1305 | 1936.2628 | 1934.3969 | 1932.5328 | 1930.6704 | 1928.8009 | 1926.9332 | 1925.0673 | 1923.2032 | 1921.3409 | 1917.824 | 1914.3135 | 1910.8094 | 1907.3118 | 1903.8206 | 1900.3058 | 1896.7975 | 1893.2957 | 1889.8004 | 1886.3115 | 1882.7791 | 1879.2533 | 1875.7342 | 1872.2216 | 1868.7156 | 1868.7238 | 1868.7319 | 1868.7401 | 1868.7483 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 1868.7565 | 62.1827 | 571.5706 | 901.5706 | -1.685% | 0 | 2080 | 267 | 267 | 267 | 267 | 268.6 | 271 | 274 | 277 | 280 | 283 | 285.5 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 301 | 40 | -1015.4 | 2008 | -1.44% | -1.819e-12 | 2080 | 2.408 | 2.408 | 2.408 | 2.408 | 2.408 | 2.4057 | 2.4034 | 2.4011 | 2.3988 | 2.3965 | 2.3941 | 2.3918 | 2.3895 | 2.3872 | 2.3849 | 2.3805 | 2.3762 | 2.3718 | 2.3675 | 2.3631 | 2.3588 | 2.3544 | 2.3501 | 2.3457 | 2.3414 | 2.337 | 2.3326 | 2.3283 | 2.3239 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196 | 2.3196
19 | Hibiscus and Bays |  |  | 2052 | 1419.6765 | 1409.6191 | 1399.633 | 1389.7176 | 1379.8724 | 1382.5494 | 1385.2315 | 1387.9188 | 1390.6113 | 1393.309 | 1396.0381 | 1398.7725 | 1401.5122 | 1404.2573 | 1407.0078 | 1409.5069 | 1412.0104 | 1414.5184 | 1417.0308 | 1419.5477 | 1421.7749 | 1424.0055 | 1426.2397 | 1428.4773 | 1430.7185 | 1433.7152 | 1436.7181 | 1439.7273 | 1442.7428 | 1445.7647 | 1448.5753 | 1451.3914 | 1454.2129 | 1457.0399 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 | 1459.8724 |  | 3210 | 3187.2595 | 3164.6801 | 3142.2606 | 3120 | 3121.8125 | 3123.6261 | 3125.4408 | 3127.2565 | 3129.0732 | 3130.9205 | 3132.7688 | 3134.6183 | 3136.4688 | 3138.3204 | 3137.1691 | 3136.0182 | 3134.8677 | 3133.7176 | 3132.568 | 3130.7066 | 3128.8464 | 3126.9873 | 3125.1293 | 3123.2724 | 3122.9707 | 3122.669 | 3122.3674 | 3122.0658 | 3121.7643 | 3127.7899 | 3133.8272 | 3139.8762 | 3145.9368 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 3152.0091 | 115.4852 | 1406.7634 | 1536.7634 | -2.954% | 0 | 2080 | 427 | 430 | 433 | 436 | 439.3 | 444 | 449 | 454 | 459 | 464 | 469.4 | 473 | 477 | 481 | 485 | 489 | 493 | 497 | 501 | 505 | 509 | 513 | 517 | 521 | 525 | 529 | 533 | 537 | 541 | 545 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 542.1 | 10 | 25.5 | 807 | 35.5% | 0 | 2080 | 2.2611 | 2.2611 | 2.2611 | 2.2611 | 2.2611 | 2.258 | 2.2549 | 2.2519 | 2.2488 | 2.2458 | 2.2427 | 2.2397 | 2.2366 | 2.2335 | 2.2305 | 2.2257 | 2.221 | 2.2162 | 2.2115 | 2.2067 | 2.202 | 2.1972 | 2.1925 | 2.1877 | 2.183 | 2.1782 | 2.1735 | 2.1687 | 2.164 | 2.1592 | 2.1592 | 2.1592 | 2.1592 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591 | 2.1591
20 | Hibiscus and Bays |  |  | 2052 | 1127.0745 | 1138.4862 | 1150.0134 | 1161.6573 | 1173.4191 | 1176.7591 | 1180.1087 | 1183.4679 | 1186.8365 | 1190.2148 | 1193.62 | 1197.0349 | 1200.4595 | 1203.894 | 1207.3383 | 1210.2672 | 1213.2031 | 1216.1462 | 1219.0964 | 1222.0537 | 1224.5569 | 1227.0652 | 1229.5786 | 1232.0972 | 1234.6209 | 1236.8442 | 1239.0714 | 1241.3027 | 1243.538 | 1245.7774 | 1247.302 | 1248.8284 | 1250.3568 | 1251.887 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 | 1253.4191 |  | 2300 | 2322.1772 | 2344.5682 | 2367.1751 | 2390 | 2401.0864 | 2412.2242 | 2423.4137 | 2434.6551 | 2445.9487 | 2457.2942 | 2468.6924 | 2480.1434 | 2491.6476 | 2503.2051 | 2510.3225 | 2517.4601 | 2524.6179 | 2531.7961 | 2538.9948 | 2545.3015 | 2551.6238 | 2557.9619 | 2564.3157 | 2570.6853 | 2576.4625 | 2582.2527 | 2588.0559 | 2593.8722 | 2599.7015 | 2602.748 | 2605.798 | 2608.8517 | 2611.9089 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 2614.9697 | 140.0851 | 2361.9095 | 4567 | 6.981% | 0 | 2080 | 2034 | 2056 | 2078 | 2100 | 2122.1 | 2149 | 2176 | 2203 | 2230 | 2257 | 2282.7 | 2306 | 2330 | 2354 | 2378 | 2402 | 2426 | 2450 | 2474 | 2498 | 2522 | 2546 | 2570 | 2594 | 2618 | 2642 | 2666 | 2690 | 2714 | 2738 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2753.5 | 2 | 5.8 | 407 | 35.41% | 0 | 2080 | 2.0407 | 2.0397 | 2.0387 | 2.0378 | 2.0368 | 2.0404 | 2.0441 | 2.0477 | 2.0514 | 2.055 | 2.0587 | 2.0623 | 2.066 | 2.0697 | 2.0733 | 2.0742 | 2.0751 | 2.0759 | 2.0768 | 2.0776 | 2.0785 | 2.0795 | 2.0804 | 2.0813 | 2.0822 | 2.0831 | 2.084 | 2.085 | 2.0859 | 2.0868 | 2.0867 | 2.0866 | 2.0865 | 2.0864 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863 | 2.0863
21 | Hibiscus and Bays |  |  | 2052 | 1652.7378 | 1677.9211 | 1703.4882 | 1729.4448 | 1755.7969 | 1757.9749 | 1760.1557 | 1762.3391 | 1764.5253 | 1766.7141 | 1768.9346 | 1771.1579 | 1773.3839 | 1775.6128 | 1777.8444 | 1779.9093 | 1781.9766 | 1784.0463 | 1786.1184 | 1788.193 | 1790.0509 | 1791.9108 | 1793.7726 | 1795.6363 | 1797.502 | 1800.0027 | 1802.5069 | 1805.0146 | 1807.5258 | 1810.0404 | 1812.3856 | 1814.7339 | 1817.0852 | 1819.4395 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 | 1821.7969 |  | 3730 | 3783.8237 | 3838.4242 | 3893.8125 | 3950 | 3953.2429 | 3956.4885 | 3959.7367 | 3962.9876 | 3966.2411 | 3969.557 | 3972.8756 | 3976.197 | 3979.5211 | 3982.8481 | 3982.1009 | 3981.3538 | 3980.6068 | 3979.86 | 3979.1134 | 3977.8732 | 3976.6334 | 3975.3941 | 3974.1551 | 3972.9165 | 3972.9715 | 3973.0265 | 3973.0815 | 3973.1365 | 3973.1915 | 3978.0793 | 3982.973 | 3987.8728 | 3992.7786 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | 3997.6904 | -20.2504 | -34.0364 | 3438 | 37.44% | 0 | 2080 | 831 | 842 | 853 | 864 | 875 | 886 | 897 | 908 | 919 | 930 | 939.4 | 950 | 960 | 970 | 980 | 990 | 1000 | 1010 | 1020 | 1030 | 1040 | 1050 | 1060 | 1070 | 1080 | 1090 | 1100 | 1110 | 1120 | 1130 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 1144.4 | 2 | -8.4 | 405 | 25.1% | 0 | 2080 | 2.2569 | 2.2551 | 2.2533 | 2.2515 | 2.2497 | 2.2487 | 2.2478 | 2.2469 | 2.2459 | 2.245 | 2.244 | 2.2431 | 2.2422 | 2.2412 | 2.2403 | 2.2372 | 2.2342 | 2.2312 | 2.2282 | 2.2252 | 2.2222 | 2.2192 | 2.2162 | 2.2132 | 2.2102 | 2.2072 | 2.2042 | 2.2011 | 2.1981 | 2.1951 | 2.1949 | 2.1948 | 2.1947 | 2.1945 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944 | 2.1944
22 | Hibiscus and Bays |  |  | 2052 | 461.2833 | 539.536 | 631.0636 | 738.118 | 863.3333 | 900.3328 | 938.9181 | 979.157 | 1021.1203 | 1064.8821 | 1103.1305 | 1142.7526 | 1183.7978 | 1226.3174 | 1270.3641 | 1305.9351 | 1342.5022 | 1380.0931 | 1418.7367 | 1458.4622 | 1490.5328 | 1523.3087 | 1556.8052 | 1591.0383 | 1626.0242 | 1668.847 | 1712.7975 | 1757.9055 | 1804.2015 | 1851.7167 | 1892.2282 | 1933.626 | 1975.9295 | 2019.1585 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 | 2063.3333 |  | 1290 | 1495.4823 | 1733.6955 | 2009.8533 | 2330 | 2429.126 | 2532.4692 | 2640.209 | 2752.5323 | 2869.6343 | 2973.2492 | 3080.6054 | 3191.8379 | 3307.0867 | 3426.4969 | 3519.8711 | 3615.7899 | 3714.3225 | 3815.5401 | 3919.516 | 4003.6631 | 4089.6166 | 4177.4155 | 4267.0993 | 4358.7085 | 4471.075 | 4586.3383 | 4704.573 | 4825.8559 | 4950.2653 | 5056.5361 | 5165.0882 | 5275.9707 | 5389.2335 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | 5504.9279 | -15.2308 | -27.963 | 4333 | 46.65% | 0 | 2080 | 244 | 246 | 248 | 250 | 253.1 | 257 | 261 | 265 | 269 | 273 | 274.1 | 277 | 280 | 283 | 286 | 289 | 292 | 295 | 298 | 301 | 304 | 307 | 310 | 313 | 316 | 319 | 322 | 325 | 328 | 331 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 327.8 | 1 | -1.2 | 419 | 34.65% | 0 | 2080 | 2.7965 | 2.7718 | 2.7473 | 2.7229 | 2.6988 | 2.698 | 2.6972 | 2.6964 | 2.6956 | 2.6948 | 2.6953 | 2.6958 | 2.6963 | 2.6968 | 2.6973 | 2.6953 | 2.6933 | 2.6914 | 2.6894 | 2.6874 | 2.6861 | 2.6847 | 2.6833 | 2.682 | 2.6806 | 2.6791 | 2.6777 | 2.6762 | 2.6748 | 2.6733 | 2.6723 | 2.6712 | 2.6701 | 2.669 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668 | 2.668
23 | Hibiscus and Bays |  |  | 2052 | 2195.9433 | 2288.827 | 2385.6394 | 2486.5468 | 2591.7224 | 2607.4855 | 2623.3444 | 2639.2997 | 2655.3521 | 2671.5022 | 2687.5749 | 2703.7444 | 2720.0111 | 2736.3757 | 2752.8388 | 2767.6027 | 2782.4457 | 2797.3684 | 2812.3711 | 2827.4542 | 2840.6425 | 2853.8922 | 2867.2038 | 2880.5775 | 2894.0136 | 2911.645 | 2929.3838 | 2947.2308 | 2965.1864 | 2983.2515 | 2999.7619 | 3016.3637 | 3033.0574 | 3049.8434 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 | 3066.7224 |  | 7170 | 7477.1885 | 7797.5381 | 8131.6126 | 8480 | 8497.1598 | 8514.3543 | 8531.5837 | 8548.8478 | 8566.147 | 8582.1801 | 8598.2432 | 8614.3364 | 8630.4597 | 8646.6132 | 8654.5975 | 8662.5892 | 8670.5883 | 8678.5947 | 8686.6086 | 8687.6577 | 8688.707 | 8689.7563 | 8690.8058 | 8691.8555 | 8704.4889 | 8717.1406 | 8729.8108 | 8742.4993 | 8755.2063 | 8804.204 | 8853.4759 | 8903.0235 | 8952.8484 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | 9002.9522 | -145.9297 | -341.5553 | 4005 | -1.093% | 4.5475e-12 | 2080 | 2458 | 2479 | 2500 | 2521 | 2541.1 | 2573 | 2604 | 2635 | 2666 | 2697 | 2729.9 | 2755 | 2780 | 2805 | 2830 | 2855 | 2880 | 2905 | 2930 | 2955 | 2980 | 3005 | 3030 | 3055 | 3080 | 3105 | 3130 | 3155 | 3180 | 3205 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 3224.8 | 37 | -20.2 | 538.8 | -4.11% | 0 | 2080 | 3.2651 | 3.2668 | 3.2685 | 3.2702 | 3.272 | 3.2588 | 3.2456 | 3.2325 | 3.2195 | 3.2065 | 3.1933 | 3.1801 | 3.167 | 3.154 | 3.141 | 3.1271 | 3.1133 | 3.0996 | 3.0859 | 3.0722 | 3.0583 | 3.0445 | 3.0307 | 3.017 | 3.0034 | 2.9895 | 2.9758 | 2.962 | 2.9484 | 2.9348 | 2.935 | 2.9351 | 2.9353 | 2.9355 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357 | 2.9357
24 | Hibiscus and Bays |  |  | 2052 | 1124.4177 | 1206.8057 | 1295.2304 | 1390.1341 | 1491.9916 | 1510.6654 | 1529.573 | 1548.7171 | 1568.1009 | 1587.7273 | 1606.7851 | 1626.0716 | 1645.5896 | 1665.3419 | 1685.3313 | 1702.8333 | 1720.5171 | 1738.3845 | 1756.4374 | 1774.6779 | 1790.3181 | 1806.0963 | 1822.0134 | 1838.0709 | 1854.2698 | 1875.2313 | 1896.4298 | 1917.8678 | 1939.5483 | 1961.4738 | 1981.1775 | 2001.0791 | 2021.1807 | 2041.4842 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 | 2061.9916 |  | 2970 | 3179.3145 | 3403.3807 | 3643.2382 | 3900 | 3932.6486 | 3965.5706 | 3998.7681 | 4032.2436 | 4065.9993 | 4097.7699 | 4129.7887 | 4162.0577 | 4194.5788 | 4227.3541 | 4251.9725 | 4276.7344 | 4301.6404 | 4326.6915 | 4351.8884 | 4370.2329 | 4388.6546 | 4407.1541 | 4425.7315 | 4444.3872 | 4473.4174 | 4502.6372 | 4532.0479 | 4561.6507 | 4591.4468 | 4636.3385 | 4681.6692 | 4727.443 | 4773.6644 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | 4820.3377 | -60.2967 | -129.6957 | 4788 | 12.15% | 0 | 2080 | 913 | 922 | 931 | 940 | 948.7 | 961 | 973 | 985 | 997 | 1009 | 1021.8 | 1032 | 1042 | 1052 | 1062 | 1072 | 1082 | 1092 | 1102 | 1112 | 1122 | 1132 | 1142 | 1152 | 1162 | 1172 | 1182 | 1192 | 1202 | 1212 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 1229.1 | 57 | -45.5 | 1014 | -1.197% | 0 | 2080 | 2.6414 | 2.6345 | 2.6276 | 2.6208 | 2.614 | 2.6033 | 2.5926 | 2.582 | 2.5714 | 2.5609 | 2.5503 | 2.5397 | 2.5292 | 2.5187 | 2.5083 | 2.497 | 2.4857 | 2.4745 | 2.4633 | 2.4522 | 2.441 | 2.4299 | 2.4188 | 2.4078 | 2.3968 | 2.3855 | 2.3743 | 2.3631 | 2.3519 | 2.3408 | 2.3402 | 2.3396 | 2.339 | 2.3383 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377 | 2.3377
25 | Hibiscus and Bays |  |  | 2052 | 1550.5924 | 1544.7151 | 1538.8601 | 1533.0273 | 1527.2166 | 1539.6953 | 1552.276 | 1564.9594 | 1577.7465 | 1590.6381 | 1603.3646 | 1616.193 | 1629.124 | 1642.1584 | 1655.2972 | 1667.0061 | 1678.7978 | 1690.6729 | 1702.6321 | 1714.6758 | 1725.1477 | 1735.6835 | 1746.2837 | 1756.9486 | 1767.6787 | 1781.6684 | 1795.7689 | 1809.9809 | 1824.3054 | 1838.7433 | 1851.8498 | 1865.0497 | 1878.3437 | 1891.7324 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 | 1905.2166 |  | 3980 | 3964.9144 | 3949.8861 | 3934.9147 | 3920 | 3935.4421 | 3950.945 | 3966.5089 | 3982.1342 | 3997.821 | 4012.5846 | 4027.4027 | 4042.2755 | 4057.2032 | 4072.1861 | 4082.23 | 4092.2987 | 4102.3923 | 4112.5107 | 4122.6541 | 4128.5242 | 4134.4026 | 4140.2894 | 4146.1846 | 4152.0881 | 4164.8957 | 4177.7427 | 4190.6293 | 4203.5557 | 4216.5219 | 4246.0533 | 4275.7915 | 4305.738 | 4335.8943 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | 4366.2617 | -23.3349 | -45.0445 | 5754 | 38.76% | 0 | 2080 | 875 | 882 | 889 | 896 | 902.8 | 913 | 923 | 933 | 943 | 953 | 965.7 | 974 | 982 | 990 | 998 | 1006 | 1014 | 1022 | 1030 | 1038 | 1046 | 1054 | 1062 | 1070 | 1078 | 1086 | 1094 | 1102 | 1110 | 1118 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 1130.1 | 5 | 1.4 | 567 | 29.33% | 0 | 2080 | 2.5668 | 2.5668 | 2.5668 | 2.5668 | 2.5668 | 2.556 | 2.5453 | 2.5346 | 2.5239 | 2.5133 | 2.5026 | 2.4919 | 2.4813 | 2.4707 | 2.4601 | 2.4488 | 2.4376 | 2.4265 | 2.4154 | 2.4043 | 2.3931 | 2.382 | 2.3709 | 2.3599 | 2.3489 | 2.3376 | 2.3264 | 2.3153 | 2.3042 | 2.2932 | 2.2929 | 2.2926 | 2.2923 | 2.292 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917 | 2.2917
26 | Hibiscus and Bays |  |  | 2052 | 1585.7027 | 1586.6629 | 1587.6238 | 1588.5852 | 1589.5472 | 1589.9669 | 1590.3866 | 1590.8065 | 1591.2265 | 1591.6466 | 1592.0745 | 1592.5025 | 1592.9306 | 1593.3588 | 1593.7871 | 1594.1947 | 1594.6025 | 1595.0104 | 1595.4183 | 1595.8264 | 1596.1986 | 1596.5709 | 1596.9432 | 1597.3157 | 1597.6882 | 1598.1071 | 1598.5261 | 1598.9452 | 1599.3644 | 1599.7837 | 1600.1362 | 1600.4889 | 1600.8416 | 1601.1943 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 | 1601.5472 |  | 4130 | 4132.4977 | 4134.997 | 4137.4977 | 4140 | 4123.7582 | 4107.5801 | 4091.4655 | 4075.4141 | 4059.4256 | 4043.1559 | 4026.9514 | 4010.8118 | 3994.7369 | 3978.7265 | 3961.7002 | 3944.7468 | 3927.8659 | 3911.0573 | 3894.3206 | 3877.1683 | 3860.0915 | 3843.0899 | 3826.1632 | 3809.3111 | 3792.2285 | 3775.2225 | 3758.2928 | 3741.439 | 3724.6608 | 3725.4821 | 3726.3035 | 3727.1252 | 3727.947 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 3728.769 | 151.359 | 132.4021 | 3615 | 7.576% | 0 | 2080 | 514 | 518 | 522 | 526 | 528.2 | 535 | 542 | 549 | 556 | 563 | 567.6 | 572 | 576 | 580 | 584 | 588 | 592 | 596 | 600 | 604 | 608 | 612 | 616 | 620 | 624 | 628 | 632 | 636 | 640 | 644 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 655.8 | 946 | 707.2 | 2807 | 9.002% | 3.638e-12 | 2080 | 2.6045 | 2.6045 | 2.6045 | 2.6045 | 2.6045 | 2.5936 | 2.5828 | 2.5719 | 2.5612 | 2.5505 | 2.5396 | 2.5287 | 2.5179 | 2.5071 | 2.4964 | 2.4851 | 2.4738 | 2.4626 | 2.4514 | 2.4403 | 2.429 | 2.4177 | 2.4065 | 2.3954 | 2.3843 | 2.373 | 2.3617 | 2.3505 | 2.3393 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282 | 2.3282
27 | Hibiscus and Bays |  |  | 2052 | 3284.2533 | 3317.68 | 3351.4469 | 3385.5574 | 3420.0152 | 3422.6983 | 3425.3835 | 3428.0708 | 3430.7602 | 3433.4518 | 3436.1872 | 3438.9248 | 3441.6645 | 3444.4065 | 3447.1506 | 3449.6549 | 3452.1611 | 3454.669 | 3457.1788 | 3459.6905 | 3461.9217 | 3464.1545 | 3466.3886 | 3468.6242 | 3470.8613 | 3473.8653 | 3476.8719 | 3479.8811 | 3482.893 | 3485.9074 | 3488.7244 | 3491.5437 | 3494.3652 | 3497.1891 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 | 3500.0152 |  | 8710 | 8798.6378 | 8888.1775 | 8978.6285 | 9070 | 9040.0137 | 9010.1265 | 8980.3381 | 8950.6482 | 8921.0564 | 8890.9091 | 8860.8637 | 8830.9199 | 8801.0772 | 8771.3353 | 8738.6492 | 8706.0848 | 8673.6418 | 8641.3196 | 8609.1179 | 8575.4873 | 8541.9881 | 8508.6197 | 8475.3816 | 8442.2734 | 8410.2657 | 8378.3793 | 8346.6138 | 8314.9687 | 8283.4436 | 8290.1406 | 8296.8429 | 8303.5507 | 8310.2638 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | 8316.9824 | -183.6451 | -420.6892 | 4737 | 4.389% | 0 | 2080 | 2882 | 2904 | 2926 | 2948 | 2970.6 | 3004 | 3037 | 3070 | 3103 | 3136 | 3168.9 | 3196 | 3223 | 3250 | 3277 | 3304 | 3331 | 3358 | 3385 | 3412 | 3439 | 3466 | 3493 | 3520 | 3547 | 3574 | 3601 | 3628 | 3655 | 3682 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 3705.2 | 47 | -41.7 | 706.3 | -0.7779% | 0 | 2080 | 2.652 | 2.652 | 2.652 | 2.652 | 2.652 | 2.6412 | 2.6304 | 2.6196 | 2.6089 | 2.5983 | 2.5874 | 2.5766 | 2.5659 | 2.5552 | 2.5445 | 2.5332 | 2.5219 | 2.5107 | 2.4995 | 2.4884 | 2.4771 | 2.4658 | 2.4546 | 2.4434 | 2.4323 | 2.421 | 2.4097 | 2.3985 | 2.3874 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763 | 2.3763
28 | Hibiscus and Bays |  |  | 2052 | 2825.4387 | 2821.4843 | 2817.5354 | 2813.592 | 2809.6541 | 2810.3256 | 2810.9973 | 2811.6691 | 2812.3411 | 2813.0133 | 2813.6979 | 2814.3827 | 2815.0676 | 2815.7527 | 2816.438 | 2817.0902 | 2817.7427 | 2818.3953 | 2819.048 | 2819.7009 | 2820.2964 | 2820.892 | 2821.4878 | 2822.0837 | 2822.6797 | 2823.4159 | 2824.1522 | 2824.8887 | 2825.6254 | 2826.3623 | 2827.0204 | 2827.6786 | 2828.3369 | 2828.9955 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 2829.6541 | 0 | 7160 | 7149.979 | 7139.972 | 7129.979 | 7120 | 7091.7523 | 7063.6166 | 7035.5926 | 7007.6798 | 6979.8776 | 6951.5857 | 6923.4085 | 6895.3455 | 6867.3962 | 6839.5602 | 6809.9846 | 6780.5369 | 6751.2165 | 6722.0229 | 6692.9556 | 6663.1831 | 6633.543 | 6604.0348 | 6574.6579 | 6545.4116 | 6515.9012 | 6486.5239 | 6457.279 | 6428.166 | 6399.1842 | 6400.6853 | 6402.1867 | 6403.6885 | 6405.1907 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 6406.6931 | 12501.9217 | 55190.4977 | 62265 |  | 0 |  | 1225 | 1231 | 1237 | 1243 | 1249.5 | 1264 | 1279 | 1294 | 1309 | 1324 | 1337.3 | 1346 | 1355 | 1364 | 1373 | 1382 | 1391 | 1400 | 1409 | 1418 | 1427 | 1436 | 1445 | 1454 | 1463 | 1472 | 1481 | 1490 | 1499 | 1508 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1514.8 | 1150 | 6081.7 | 12511.9 |  | 0 |  | 2.5341 | 2.5341 | 2.5341 | 2.5341 | 2.5341 | 2.5235 | 2.5129 | 2.5023 | 2.4918 | 2.4813 | 2.4706 | 2.46 | 2.4494 | 2.4389 | 2.4284 | 2.4174 | 2.4064 | 2.3954 | 2.3845 | 2.3736 | 2.3626 | 2.3516 | 2.3406 | 2.3297 | 2.3189 | 2.3078 | 2.2968 | 2.2859 | 2.275 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641 | 2.2641
29 | Hibiscus and Bays |  |  | 2052 | 3165.718 | 3181.1959 | 3196.7494 | 3212.379 | 3228.0849 | 3242.645 | 3257.2707 | 3271.9624 | 3286.7203 | 3301.5448 | 3316.3894 | 3331.3008 | 3346.2792 | 3361.3249 | 3376.4383 | 3390.028 | 3403.6725 | 3417.3718 | 3431.1263 | 3444.9362 | 3457.0479 | 3469.2022 | 3481.3992 | 3493.6391 | 3505.922 | 3522.1988 | 3538.5511 | 3554.9794 | 3571.4839 | 3588.065 | 3603.3384 | 3618.6768 | 3634.0805 | 3649.5498 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 | 3665.0849 |  | 8550 | 8592.1867 | 8634.5816 | 8677.1857 | 8720 | 8727.2106 | 8734.4272 | 8741.6498 | 8748.8783 | 8756.1128 | 8762.6078 | 8769.1076 | 8775.6122 | 8782.1217 | 8788.6359 | 8787.7478 | 8786.8597 | 8785.9718 | 8785.0839 | 8784.1961 | 8778.0509 | 8771.9099 | 8765.7733 | 8759.641 | 8753.5129 | 8756.5318 | 8759.5518 | 8762.5728 | 8765.5948 | 8768.6179 | 8806.3638 | 8844.2722 | 8882.3437 | 8920.5791 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | 8958.9792 | [6 empty] | 1216 | 1224 | 1232 | 1240 | 1246.1 | 1260 | 1274 | 1288 | 1302 | 1316 | 1327.3 | 1334 | 1341 | 1348 | 1355 | 1362 | 1369 | 1376 | 1383 | 1390 | 1397 | 1404 | 1411 | 1418 | 1425 | 1432 | 1439 | 1446 | 1453 | 1460 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | [6 empty] | 2.7008 | 2.7009 | 2.7011 | 2.7012 | 2.7013 | 2.6914 | 2.6815 | 2.6717 | 2.6619 | 2.6521 | 2.6422 | 2.6323 | 2.6225 | 2.6127 | 2.6029 | 2.5922 | 2.5816 | 2.571 | 2.5604 | 2.5499 | 2.5392 | 2.5285 | 2.5179 | 2.5073 | 2.4968 | 2.4861 | 2.4755 | 2.4649 | 2.4543 | 2.4438 | 2.4439 | 2.4441 | 2.4442 | 2.4443 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444 | 2.4444
30 | Hibiscus and Bays |  |  | 2052 | 274.0224 | 300.5914 | 329.7364 | 361.7073 | 396.7781 | 403.5768 | 410.4921 | 417.5258 | 424.68 | 431.9569 | 438.9029 | 445.9606 | 453.1318 | 460.4184 | 467.8221 | 474.225 | 480.7156 | 487.295 | 493.9644 | 500.7251 | 506.4624 | 512.2655 | 518.135 | 524.0718 | 530.0766 | 537.6874 | 545.4075 | 553.2385 | 561.1819 | 569.2393 | 576.3663 | 583.5826 | 590.8893 | 598.2874 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 | 605.7781 |  | 820 | 890.403 | 966.8506 | 1049.8617 | 1140 | 1153.9536 | 1168.078 | 1182.3753 | 1196.8476 | 1211.497 | 1225.2276 | 1239.1139 | 1253.1575 | 1267.3604 | 1281.7241 | 1292.5581 | 1303.4836 | 1314.5015 | 1325.6125 | 1336.8174 | 1345.3335 | 1353.9039 | 1362.5289 | 1371.2089 | 1379.9441 | 1392.3178 | 1404.8024 | 1417.3989 | 1430.1084 | 1442.9319 | 1459.6601 | 1476.5823 | 1493.7007 | 1511.0175 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | 1528.5351 | [6 empty] | 4906 | 4924 | 4942 | 4960 | 4976.2 | 5037 | 5098 | 5159 | 5220 | 5281 | 5339.5 | 5370 | 5401 | 5432 | 5463 | 5494 | 5525 | 5556 | 5587 | 5618 | 5649 | 5680 | 5711 | 5742 | 5773 | 5804 | 5835 | 5866 | 5897 | 5928 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | [6 empty] | 2.9925 | 2.9622 | 2.9322 | 2.9025 | 2.8731 | 2.8593 | 2.8456 | 2.8319 | 2.8182 | 2.8047 | 2.7916 | 2.7785 | 2.7655 | 2.7526 | 2.7398 | 2.7256 | 2.7115 | 2.6975 | 2.6836 | 2.6698 | 2.6563 | 2.643 | 2.6297 | 2.6165 | 2.6033 | 2.5895 | 2.5757 | 2.562 | 2.5484 | 2.5348 | 2.5325 | 2.5302 | 2.5279 | 2.5256 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233 | 2.5233
31 | Rodney |  |  | 2052 | 63.6671 | 69.9592 | 76.8732 | 84.4704 | 92.8186 | 108.2216 | 126.1807 | 147.1201 | 171.5343 | 200 | 223.6854 | 250.1758 | 279.8033 | 312.9395 | 350 | 375.8793 | 403.6722 | 433.5201 | 465.575 | 500 | 534.8052 | 572.0332 | 611.8526 | 654.4439 | 700 | 700 | 700 | 700 | 700 | 700 | 709.7259 | 719.587 | 729.5851 | 739.7221 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 |  | 210 | 229.5857 | 250.998 | 274.4074 | 300 | 347.7752 | 403.1587 | 467.362 | 541.7897 | 628.0701 | 698.2965 | 776.3752 | 863.1841 | 959.6993 | 1067.0061 | 1139.7727 | 1217.5018 | 1300.5317 | 1389.2241 | 1483.965 | 1578.6709 | 1679.4209 | 1786.6008 | 1900.6208 | 2021.9175 | 2010.4181 | 1998.9841 | 1987.6151 | 1976.3108 | 1965.0708 | 1992.3739 | 2020.0563 | 2048.1233 | 2076.5803 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | 2105.4327 | [6 empty] | 33 | 33 | 33 | 33 | 32.9 | 33 | 33 | 33 | 33 | 33 | 33.9 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | [6 empty] | 3.2984 | 3.2817 | 3.2651 | 3.2486 | 3.2321 | 3.2135 | 3.1951 | 3.1767 | 3.1585 | 3.1404 | 3.1218 | 3.1033 | 3.085 | 3.0667 | 3.0486 | 3.0323 | 3.0161 | 2.9999 | 2.9839 | 2.9679 | 2.9519 | 2.9359 | 2.92 | 2.9042 | 2.8885 | 2.872 | 2.8557 | 2.8395 | 2.8233 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072 | 2.8072
32 | Rodney |  |  | 2052 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 | 93.9848 |  | 280 | 280 | 280 | 280 | 280 | 279.6074 | 279.2154 | 278.8239 | 278.433 | 278.0426 | 277.65 | 277.258 | 276.8665 | 276.4756 | 276.0852 | 275.4616 | 274.8393 | 274.2185 | 273.599 | 272.981 | 272.364 | 271.7484 | 271.1342 | 270.5214 | 269.91 | 269.2779 | 268.6473 | 268.0182 | 267.3905 | 266.7644 | 266.7643 | 266.7643 | 266.7643 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | 266.7642 | [6 empty] | 48 | 49 | 50 | 51 | 50.3 | 51 | 51 | 51 | 51 | 51 | 51.7 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | [6 empty] | 2.9792 | 2.9792 | 2.9792 | 2.9792 | 2.9792 | 2.975 | 2.9709 | 2.9667 | 2.9625 | 2.9584 | 2.9542 | 2.95 | 2.9459 | 2.9417 | 2.9376 | 2.9309 | 2.9243 | 2.9177 | 2.9111 | 2.9045 | 2.898 | 2.8914 | 2.8849 | 2.8784 | 2.8718 | 2.8651 | 2.8584 | 2.8517 | 2.845 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384 | 2.8384
33 | Rodney |  |  | 2052 | 97.3612 | 141.3669 | 205.2624 | 298.0377 | 432.7459 | 521.8242 | 629.2389 | 758.7643 | 914.9517 | 1103.2895 | 1214.9895 | 1337.9983 | 1473.4608 | 1622.638 | 1786.9183 | 1890.7427 | 2000.5997 | 2116.8396 | 2239.8333 | 2369.9733 | 2461.654 | 2556.8812 | 2655.7923 | 2758.5296 | 2865.2413 | 2909.5504 | 2954.5448 | 3000.2349 | 3046.6317 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 | 3093.7459 |  | 270 | 390.3852 | 564.4466 | 816.117 | 1180 | 1421.0933 | 1711.446 | 2061.1224 | 2482.2434 | 2989.4064 | 3288.876 | 3618.3454 | 3980.8201 | 4379.6064 | 4818.3419 | 5089.126 | 5375.1278 | 5677.2024 | 5996.2533 | 6333.2343 | 6566.7027 | 6808.7777 | 7059.7765 | 7320.0281 | 7589.8737 | 7693.4332 | 7798.4057 | 7904.8105 | 8012.6671 | 8121.9954 | 8121.8467 | 8121.6979 | 8121.5492 | 8121.4005 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | 8121.2517 | [6 empty] | 148 | 151 | 154 | 157 | 159.2 | 172 | 184 | 196 | 208 | 220 | 233.7 | 281 | 328 | 375 | 422 | 469 | 516 | 563 | 610 | 657 | 704 | 751 | 798 | 845 | 892 | 939 | 986 | 1033 | 1080 | 1127 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | 1177.4 | [6 empty] | 2.7732 | 2.7615 | 2.7499 | 2.7383 | 2.7268 | 2.7233 | 2.7199 | 2.7164 | 2.713 | 2.7095 | 2.7069 | 2.7043 | 2.7017 | 2.6991 | 2.6965 | 2.6916 | 2.6868 | 2.6819 | 2.6771 | 2.6723 | 2.6676 | 2.6629 | 2.6583 | 2.6536 | 2.6489 | 2.6442 | 2.6395 | 2.6347 | 2.63 | 2.6253 | 2.6252 | 2.6252 | 2.6252 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251 | 2.6251
34 | Rodney |  |  | 2052 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 | 30.3177 |  | 70 | 70 | 70 | 70 | 70 | 70.09 | 70.1801 | 70.2704 | 70.3607 | 70.4512 | 70.5412 | 70.6313 | 70.7216 | 70.8119 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | 70.9024 | [6 empty] | 128 | 128 | 128 | 128 | 128 | 136 | 144 | 152 | 160 | 168 | 173.9 | 393 | 612 | 831 | 1050 | 1269 | 1488 | 1707 | 1926 | 2145 | 2364 | 2583 | 2802 | 3021 | 3240 | 3459 | 3678 | 3897 | 4116 | 4335 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | 4552.4 | [6 empty] | 2.3089 | 2.3089 | 2.3089 | 2.3089 | 2.3089 | 2.3119 | 2.3148 | 2.3178 | 2.3208 | 2.3238 | 2.3267 | 2.3297 | 2.3327 | 2.3357 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386 | 2.3386
35 | Hibiscus and Bays |  |  | 2052 | 21.2224 | 30.0352 | 42.5078 | 60.1597 | 85.1418 | 94.6217 | 105.157 | 116.8654 | 129.8774 | 144.3382 | 154.7834 | 165.9844 | 177.996 | 190.8768 | 204.6898 | 214.7208 | 225.2434 | 236.2816 | 247.8608 | 260.0074 | 269.1981 | 278.7136 | 288.5654 | 298.7655 | 309.3261 | 321.5352 | 334.2261 | 347.418 | 361.1306 | 375.3843 | 386.995 | 398.9648 | 411.3049 | 424.0266 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 | 437.1418 |  | 60 | 82.0669 | 112.2497 | 153.5332 | 210 | 237.292 | 268.1309 | 302.9777 | 342.3532 | 386.8461 | 422.166 | 460.7108 | 502.7747 | 548.6793 | 598.775 | 624.853 | 652.0669 | 680.4659 | 710.1018 | 741.0284 | 763.366 | 786.3768 | 810.0813 | 834.5004 | 859.6555 | 889.0129 | 919.3728 | 950.7695 | 983.2385 | 1016.8162 | 1047.9883 | 1080.1161 | 1113.2288 | 1147.3566 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | 1182.5306 | [6 empty] | 424 | 429 | 434 | 439 | 445.8 | 453 | 460 | 467 | 474 | 481 | 490.3 | 506 | 522 | 538 | 554 | 570 | 586 | 602 | 618 | 634 | 650 | 666 | 682 | 698 | 714 | 730 | 746 | 762 | 778 | 794 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | 808.1 | [6 empty] | 2.8272 | 2.7324 | 2.6407 | 2.5521 | 2.4665 | 2.5078 | 2.5498 | 2.5925 | 2.636 | 2.6801 | 2.7275 | 2.7756 | 2.8246 | 2.8745 | 2.9253 | 2.9101 | 2.8949 | 2.8799 | 2.8649 | 2.85 | 2.8357 | 2.8215 | 2.8073 | 2.7932 | 2.7791 | 2.7649 | 2.7508 | 2.7367 | 2.7227 | 2.7087 | 2.708 | 2.7073 | 2.7066 | 2.7059 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051 | 2.7051
36 | Hibiscus and Bays |  |  | 2052 | 162.6764 | 165.977 | 169.3445 | 172.7804 | 176.286 | 189.0437 | 202.7247 | 217.3958 | 233.1286 | 250 | 267.4026 | 286.0166 | 305.9263 | 327.222 | 350 | 375.8793 | 403.6722 | 433.5201 | 465.575 | 500 | 549.2803 | 603.4176 | 662.8908 | 728.2257 | 800 | 867.5774 | 940.8632 | 1020.3396 | 1106.5295 | 1200 | 1294.0546 | 1395.4811 | 1504.8573 | 1622.8063 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 |  | 470 | 479.6958 | 489.5917 | 499.6917 | 510 | 545.7619 | 584.0314 | 624.9844 | 668.8092 | 715.7069 | 763.9057 | 815.3504 | 870.2595 | 928.8665 | 991.4204 | 1050.5125 | 1113.1268 | 1179.4731 | 1249.7739 | 1324.2649 | 1448.79 | 1585.0246 | 1734.0698 | 1897.1303 | 2075.5239 | 2243.4362 | 2424.9329 | 2621.1128 | 2833.1639 | 3062.3702 | 3301.3904 | 3559.0662 | 3836.8538 | 4136.3229 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | 4459.1658 | [6 empty] | 87 | 87 | 87 | 87 | 87.1 | 88 | 89 | 90 | 91 | 92 | 93.6 | 98 | 102 | 106 | 110 | 114 | 118 | 122 | 126 | 130 | 134 | 138 | 142 | 146 | 150 | 154 | 158 | 162 | 166 | 170 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | 180.4 | [6 empty] | 2.8892 | 2.8901 | 2.8911 | 2.8921 | 2.893 | 2.887 | 2.8809 | 2.8749 | 2.8688 | 2.8628 | 2.8568 | 2.8507 | 2.8447 | 2.8386 | 2.8326 | 2.7948 | 2.7575 | 2.7207 | 2.6844 | 2.6485 | 2.6376 | 2.6267 | 2.6159 | 2.6051 | 2.5944 | 2.5859 | 2.5773 | 2.5689 | 2.5604 | 2.552 | 2.5512 | 2.5504 | 2.5496 | 2.5489 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481 | 2.5481
37 | Hibiscus and Bays |  |  | 2052 | 654.9085 | 659.3693 | 663.8606 | 668.3824 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 | 672.935 |  | 1840 | 1852.3746 | 1864.8324 | 1877.374 | 1890 | 1882.633 | 1875.2947 | 1867.985 | 1860.7039 | 1853.4511 | 1846.0829 | 1838.7441 | 1831.4344 | 1824.1538 | 1816.9021 | 1809.1435 | 1801.4179 | 1793.7254 | 1786.0657 | 1778.4387 | 1770.6833 | 1762.9618 | 1755.2739 | 1747.6195 | 1739.9985 | 1732.2444 | 1724.5248 | 1716.8397 | 1709.1888 | 1701.5719 | 1701.5728 | 1701.5736 | 1701.5744 | 1701.5753 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | 1701.5761 | [6 empty] | 398 | 399 | 400 | 401 | 402 | 407 | 412 | 417 | 422 | 427 | 431.6 | 434 | 436 | 438 | 440 | 442 | 444 | 446 | 448 | 450 | 452 | 454 | 456 | 458 | 460 | 462 | 464 | 466 | 468 | 470 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | 473.2 | [6 empty] | 2.8096 | 2.8093 | 2.8091 | 2.8088 | 2.8086 | 2.7976 | 2.7867 | 2.7759 | 2.7651 | 2.7543 | 2.7433 | 2.7324 | 2.7216 | 2.7107 | 2.7 | 2.6884 | 2.677 | 2.6655 | 2.6541 | 2.6428 | 2.6313 | 2.6198 | 2.6084 | 2.597 | 2.5857 | 2.5742 | 2.5627 | 2.5513 | 2.5399 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286 | 2.5286
38 | Rodney |  |  | 2052 | 284.8285 | 292.5495 | 300.4798 | 308.6251 | 316.9912 | 317.3239 | 317.6568 | 317.9902 | 318.3239 | 318.6579 | 318.9905 | 319.3235 | 319.6568 | 319.9905 | 320.3245 | 320.6572 | 320.9902 | 321.3235 | 321.6572 | 321.9912 | 322.3239 | 322.6569 | 322.9902 | 323.3239 | 323.6579 | 323.9905 | 324.3235 | 324.6569 | 324.9905 | 325.3245 | 325.6572 | 325.9902 | 326.3235 | 326.6572 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 | 326.9912 |  | 820 | 841.6291 | 863.8287 | 886.6138 | 910 | 907.0174 | 904.0446 | 901.0815 | 898.1282 | 895.1845 | 892.16 | 889.1458 | 886.1417 | 883.1478 | 880.1639 | 877.8456 | 875.5334 | 873.2272 | 870.9272 | 868.6332 | 866.2908 | 863.9548 | 861.625 | 859.3015 | 856.9843 | 854.5088 | 852.0405 | 849.5793 | 847.1251 | 844.6781 | 845.5526 | 846.428 | 847.3043 | 848.1815 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | 849.0596 | [6 empty] | 386 | 388 | 390 | 392 | 393.5 | 402 | 410 | 418 | 426 | 434 | 441.7 | 451 | 461 | 471 | 481 | 491 | 501 | 511 | 521 | 531 | 541 | 551 | 561 | 571 | 581 | 591 | 601 | 611 | 621 | 631 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | 633 | [6 empty] | 2.8789 | 2.8769 | 2.8748 | 2.8728 | 2.8707 | 2.8583 | 2.846 | 2.8337 | 2.8214 | 2.8092 | 2.7968 | 2.7845 | 2.7722 | 2.7599 | 2.7477 | 2.7376 | 2.7276 | 2.7176 | 2.7076 | 2.6977 | 2.6876 | 2.6776 | 2.6677 | 2.6577 | 2.6478 | 2.6375 | 2.6271 | 2.6169 | 2.6066 | 2.5964 | 2.5964 | 2.5965 | 2.5965 | 2.5965 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966 | 2.5966
39 | Rodney |  |  | 2052 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 |  | 180 | 180 | 180 | 180 | 180 | 179.8855 | 179.7711 | 179.6567 | 179.5424 | 179.4282 | 179.3137 | 179.1993 | 179.085 | 178.9707 | 178.8565 | 178.4146 | 177.9739 | 177.5342 | 177.0956 | 176.6582 | 176.4531 | 176.2482 | 176.0436 | 175.8392 | 175.6351 | 175.4339 | 175.2331 | 175.0324 | 174.832 | 174.6317 | 174.6106 | 174.5895 | 174.5683 | 174.5472 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | 174.5261 | [6 empty] | 86 | 87 | 88 | 89 | 88.5 | 91 | 93 | 95 | 97 | 99 | 100.7 | 133 | 165 | 197 | 229 | 261 | 293 | 325 | 357 | 389 | 421 | 453 | 485 | 517 | 549 | 581 | 613 | 645 | 677 | 709 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | 741.4 | [6 empty] | 3.1248 | 3.1248 | 3.1248 | 3.1248 | 3.1248 | 3.1228 | 3.1208 | 3.1188 | 3.1169 | 3.1149 | 3.1129 | 3.1109 | 3.1089 | 3.1069 | 3.105 | 3.0973 | 3.0896 | 3.082 | 3.0744 | 3.0668 | 3.0632 | 3.0597 | 3.0561 | 3.0526 | 3.049 | 3.0455 | 3.0421 | 3.0386 | 3.0351 | 3.0316 | 3.0312 | 3.0309 | 3.0305 | 3.0301 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298 | 3.0298
40 | Rodney |  |  | 2052 | 96.0572 | 98.529 | 101.0644 | 103.6651 | 106.3326 | 106.4165 | 106.5004 | 106.5844 | 106.6684 | 106.7525 | 106.838 | 106.9236 | 107.0092 | 107.0949 | 107.1806 | 109.63 | 112.1353 | 114.6978 | 117.319 | 120 | 121.9365 | 123.9042 | 125.9037 | 127.9355 | 130 | 131.9412 | 133.9113 | 135.9109 | 137.9403 | 140 | 141.9452 | 143.9174 | 145.917 | 147.9444 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 |  | 270 | 277.2063 | 284.605 | 292.2011 | 300 | 299.9323 | 299.8646 | 299.7969 | 299.7292 | 299.6615 | 299.5961 | 299.5307 | 299.4652 | 299.3998 | 299.3345 | 305.6546 | 312.1081 | 318.6979 | 325.4269 | 332.2979 | 336.992 | 341.7525 | 346.5802 | 351.476 | 356.4411 | 361.0033 | 365.6238 | 370.3036 | 375.0432 | 379.8434 | 385.1069 | 390.4434 | 395.8537 | 401.3391 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | 406.9005 | [6 empty] | 173 | 214 | 255 | 296 | 335.5 | 362 | 388 | 414 | 440 | 466 | 494 | 572 | 650 | 728 | 806 | 884 | 962 | 1040 | 1118 | 1196 | 1274 | 1352 | 1430 | 1508 | 1586 | 1664 | 1742 | 1820 | 1898 | 1976 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | 2055.9 | [6 empty] | 2.8108 | 2.8134 | 2.8161 | 2.8187 | 2.8213 | 2.8185 | 2.8156 | 2.8128 | 2.8099 | 2.8071 | 2.8042 | 2.8014 | 2.7985 | 2.7957 | 2.7928 | 2.7881 | 2.7833 | 2.7786 | 2.7739 | 2.7691 | 2.7637 | 2.7582 | 2.7527 | 2.7473 | 2.7419 | 2.7361 | 2.7303 | 2.7246 | 2.7189 | 2.7132 | 2.7131 | 2.713 | 2.7129 | 2.7128 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127 | 2.7127
41 | Rodney |  |  | 2052 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 | 60.6353 |  | 200 | 200 | 200 | 200 | 200 | 199.0633 | 198.131 | 197.2031 | 196.2796 | 195.3603 | 194.4234 | 193.4911 | 192.5631 | 191.6397 | 190.7206 | 192.5003 | 194.2966 | 196.1097 | 197.9397 | 199.7867 | 198.9099 | 198.0368 | 197.1676 | 196.3023 | 195.4407 | 194.3893 | 193.3435 | 192.3034 | 191.2688 | 190.2399 | 190.2703 | 190.3007 | 190.3311 | 190.3615 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | 190.3919 | [6 empty] | 35 | 36 | 37 | 38 | 38.9 | 39 | 40 | 41 | 42 | 43 | 41.9 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | 65.4 | [6 empty] | 3.2984 | 3.2984 | 3.2984 | 3.2984 | 3.2984 | 3.283 | 3.2676 | 3.2523 | 3.237 | 3.2219 | 3.2064 | 3.1911 | 3.1758 | 3.1605 | 3.1454 | 3.1747 | 3.2043 | 3.2342 | 3.2644 | 3.2949 | 3.2804 | 3.266 | 3.2517 | 3.2374 | 3.2232 | 3.2059 | 3.1886 | 3.1715 | 3.1544 | 3.1374 | 3.1379 | 3.1384 | 3.1389 | 3.1394 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399 | 3.1399
42 | Rodney |  |  | 2052 | 112.1753 | 110.7815 | 109.4051 | 108.0458 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 | 106.7033 |  | 410 | 404.9058 | 399.875 | 394.9066 | 390 | 387.8489 | 385.7098 | 383.5824 | 381.4667 | 379.3627 | 377.211 | 375.0715 | 372.9441 | 370.8288 | 368.7254 | 365.8791 | 363.0547 | 360.2521 | 357.4711 | 354.7116 | 352.697 | 350.6939 | 348.7021 | 346.7217 | 344.7525 | 342.8683 | 340.9944 | 339.1308 | 337.2774 | 335.4341 | 335.3509 | 335.2677 | 335.1845 | 335.1013 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | 335.0182 | [6 empty] | 167 | 168 | 169 | 170 | 169.6 | 174 | 179 | 184 | 189 | 194 | 198.2 | 358 | 517 | 676 | 835 | 994 | 1153 | 1312 | 1471 | 1630 | 1789 | 1948 | 2107 | 2266 | 2425 | 2584 | 2743 | 2902 | 3061 | 3220 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | 3384.6 | [6 empty] | 3.655 | 3.655 | 3.655 | 3.655 | 3.655 | 3.6348 | 3.6148 | 3.5948 | 3.575 | 3.5553 | 3.5351 | 3.5151 | 3.4951 | 3.4753 | 3.4556 | 3.4289 | 3.4025 | 3.3762 | 3.3501 | 3.3243 | 3.3054 | 3.2866 | 3.268 | 3.2494 | 3.2309 | 3.2133 | 3.1957 | 3.1783 | 3.1609 | 3.1436 | 3.1428 | 3.1421 | 3.1413 | 3.1405 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397 | 3.1397
43 | Rodney |  |  | 2052 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 | 72.7624 |  | 230 | 230 | 230 | 230 | 230 | 229.2475 | 228.4976 | 227.75 | 227.0049 | 226.2623 | 225.5097 | 224.7597 | 224.0122 | 223.2671 | 222.5246 | 222.434 | 222.3435 | 222.253 | 222.1625 | 222.0721 | 221.5603 | 221.0497 | 220.5402 | 220.032 | 219.5249 | 218.8915 | 218.26 | 217.6303 | 217.0024 | 216.3764 | 216.437 | 216.4977 | 216.5584 | 216.6191 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | 216.6798 | [6 empty] | 98 | 98 | 98 | 98 | 97.6 | 99 | 100 | 101 | 102 | 103 | 103.5 | 103 | 102 | 101 | 100 | 99 | 98 | 97 | 96 | 95 | 94 | 93 | 92 | 91 | 90 | 89 | 88 | 87 | 86 | 85 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | 85.1 | [6 empty] | 3.161 | 3.161 | 3.161 | 3.161 | 3.161 | 3.1506 | 3.1403 | 3.1301 | 3.1198 | 3.1096 | 3.0993 | 3.089 | 3.0787 | 3.0684 | 3.0582 | 3.057 | 3.0557 | 3.0545 | 3.0533 | 3.052 | 3.045 | 3.038 | 3.031 | 3.024 | 3.017 | 3.0083 | 2.9996 | 2.991 | 2.9823 | 2.9737 | 2.9746 | 2.9754 | 2.9762 | 2.9771 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779 | 2.9779
44 | Rodney |  |  | 2052 | 93.9848 | 96.563 | 99.2119 | 101.9335 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 | 104.7297 |  | 310 | 317.2422 | 324.6537 | 332.2382 | 340 | 340.2119 | 340.424 | 340.6362 | 340.8486 | 341.0611 | 341.273 | 341.4851 | 341.6973 | 341.9097 | 342.1221 | 341.9197 | 341.7174 | 341.5152 | 341.3132 | 341.1112 | 340.9913 | 340.8715 | 340.7516 | 340.6318 | 340.5121 | 340.397 | 340.2819 | 340.1669 | 340.052 | 339.937 | 339.9445 | 339.9519 | 339.9594 | 339.9668 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | 339.9742 | [6 empty] | 43 | 43 | 43 | 43 | 44.4 | 44 | 44 | 44 | 44 | 44 | 44.8 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | [6 empty] | 3.2984 | 3.2853 | 3.2723 | 3.2594 | 3.2465 | 3.2485 | 3.2505 | 3.2525 | 3.2546 | 3.2566 | 3.2586 | 3.2606 | 3.2627 | 3.2647 | 3.2667 | 3.2648 | 3.2629 | 3.2609 | 3.259 | 3.2571 | 3.2559 | 3.2548 | 3.2536 | 3.2525 | 3.2513 | 3.2502 | 3.2491 | 3.248 | 3.2469 | 3.2459 | 3.2459 | 3.246 | 3.2461 | 3.2461 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462 | 3.2462
45 | Rodney |  |  | 2052 | 169.779 | 173.444 | 177.1881 | 181.0131 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 | 184.9207 |  | 610 | 622.1332 | 634.5077 | 647.1283 | 660 | 656.8793 | 653.7733 | 650.682 | 647.6053 | 644.5432 | 641.4218 | 638.3154 | 635.2241 | 632.1478 | 629.0864 | 622.1926 | 615.3743 | 608.6307 | 601.961 | 595.3645 | 592.6933 | 590.034 | 587.3868 | 584.7513 | 582.1278 | 579.7944 | 577.4704 | 575.1557 | 572.8502 | 570.5541 | 570.4649 | 570.3758 | 570.2866 | 570.1975 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | 570.1084 | [6 empty] | 142 | 143 | 144 | 145 | 146.8 | 148 | 149 | 150 | 151 | 152 | 155.4 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | 166.7 | [6 empty] | 3.5929 | 3.5869 | 3.581 | 3.575 | 3.5691 | 3.5522 | 3.5354 | 3.5187 | 3.5021 | 3.4855 | 3.4686 | 3.4518 | 3.4351 | 3.4185 | 3.4019 | 3.3646 | 3.3278 | 3.2913 | 3.2552 | 3.2196 | 3.2051 | 3.1907 | 3.1764 | 3.1622 | 3.148 | 3.1354 | 3.1228 | 3.1103 | 3.0978 | 3.0854 | 3.0849 | 3.0844 | 3.084 | 3.0835 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083
46 | Rodney |  |  | 2052 | 186.3515 | 187.9892 | 189.6412 | 191.3077 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 | 192.9889 |  | 580 | 584.9366 | 589.9152 | 594.9363 | 600 | 597.3255 | 594.6629 | 592.0121 | 589.3732 | 586.746 | 584.071 | 581.4081 | 578.7574 | 576.1187 | 573.4921 | 574.1315 | 574.7717 | 575.4126 | 576.0542 | 576.6965 | 574.6357 | 572.5821 | 570.536 | 568.4971 | 566.4656 | 564.1817 | 561.907 | 559.6414 | 557.385 | 555.1377 | 555.3234 | 555.5092 | 555.695 | 555.8809 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | 556.0669 | [6 empty] | 181 | 183 | 185 | 187 | 187 | 189 | 191 | 193 | 195 | 197 | 197.2 | 197 | 197 | 197 | 197 | 197 | 197 | 197 | 197 | 197 | 197 | 197 | 197 | 197 | 197 | 197 | 197 | 197 | 197 | 197 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | 190.7 | [6 empty] | 3.1124 | 3.1115 | 3.1107 | 3.1098 | 3.109 | 3.0951 | 3.0813 | 3.0676 | 3.0539 | 3.0403 | 3.0264 | 3.0127 | 2.9989 | 2.9852 | 2.9716 | 2.9749 | 2.9783 | 2.9816 | 2.9849 | 2.9882 | 2.9776 | 2.9669 | 2.9563 | 2.9458 | 2.9352 | 2.9234 | 2.9116 | 2.8999 | 2.8882 | 2.8765 | 2.8775 | 2.8785 | 2.8794 | 2.8804 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813 | 2.8813
47 | Rodney |  |  | 2052 | 504.8313 | 511.3611 | 517.9755 | 524.6753 | 531.4619 | 531.7948 | 532.1279 | 532.4613 | 532.7948 | 533.1286 | 533.4615 | 533.7946 | 534.1279 | 534.4615 | 534.7952 | 535.1281 | 535.4613 | 535.7946 | 536.1281 | 536.4619 | 536.7948 | 537.1279 | 537.4613 | 537.7948 | 538.1286 | 538.4615 | 538.7946 | 539.1279 | 539.4615 | 539.7952 | 540.1281 | 540.4613 | 540.7946 | 541.1281 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 | 541.4619 |  | 1590 | 1609.6333 | 1629.5091 | 1649.6303 | 1670 | 1664.3642 | 1658.7473 | 1653.1495 | 1647.5705 | 1642.0103 | 1636.3317 | 1630.6727 | 1625.0333 | 1619.4134 | 1613.8129 | 1609.1995 | 1604.5992 | 1600.0121 | 1595.438 | 1590.8771 | 1586.3276 | 1581.7911 | 1577.2676 | 1572.757 | 1568.2593 | 1563.5085 | 1558.7722 | 1554.0502 | 1549.3425 | 1544.649 | 1545.6017 | 1546.555 | 1547.5088 | 1548.4632 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | 1549.4183 | [6 empty] | 438 | 440 | 442 | 444 | 447.6 | 452 | 456 | 460 | 464 | 468 | 472.9 | 470 | 467 | 464 | 461 | 458 | 455 | 452 | 449 | 446 | 443 | 440 | 437 | 434 | 431 | 428 | 425 | 422 | 419 | 416 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | 406.7 | [6 empty] | 3.1496 | 3.1477 | 3.1459 | 3.1441 | 3.1423 | 3.1297 | 3.1172 | 3.1047 | 3.0923 | 3.08 | 3.0674 | 3.0549 | 3.0424 | 3.03 | 3.0176 | 3.0071 | 2.9967 | 2.9862 | 2.9759 | 2.9655 | 2.9552 | 2.9449 | 2.9347 | 2.9245 | 2.9143 | 2.9037 | 2.8931 | 2.8825 | 2.872 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615 | 2.8615
48 | Hibiscus and Bays |  |  | 2052 | 294.0814 | 299.0285 | 304.0589 | 309.1739 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 | 314.3749 |  | 910 | 924.6428 | 939.5212 | 954.6389 | 970 | 966.2411 | 962.4967 | 958.7668 | 955.0514 | 951.3504 | 947.5909 | 943.8463 | 940.1164 | 936.4013 | 932.7009 | 928.6591 | 924.6349 | 920.6281 | 916.6387 | 912.6666 | 908.6264 | 904.6042 | 900.5997 | 896.613 | 892.6439 | 888.6043 | 884.583 | 880.5799 | 876.5948 | 872.6279 | 872.6283 | 872.6287 | 872.6291 | 872.6295 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | 872.6299 | [6 empty] | 207 | 208 | 209 | 210 | 209.2 | 212 | 215 | 218 | 221 | 224 | 224.8 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | 249.8 | [6 empty] | 3.0944 | 3.0922 | 3.0899 | 3.0877 | 3.0855 | 3.0735 | 3.0616 | 3.0498 | 3.0379 | 3.0262 | 3.0142 | 3.0023 | 2.9904 | 2.9786 | 2.9668 | 2.954 | 2.9412 | 2.9284 | 2.9158 | 2.9031 | 2.8903 | 2.8775 | 2.8647 | 2.8521 | 2.8394 | 2.8266 | 2.8138 | 2.801 | 2.7884 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758
49 | Hibiscus and Bays |  |  | 2052 | 583.3753 | 650.9405 | 726.331 | 810.453 | 904.3178 | 918.4715 | 932.8466 | 947.4468 | 962.2754 | 977.3362 | 991.7909 | 1006.4594 | 1021.3448 | 1036.4504 | 1051.7794 | 1065.0458 | 1078.4795 | 1092.0827 | 1105.8574 | 1119.8059 | 1131.6588 | 1143.6371 | 1155.7423 | 1167.9755 | 1180.3383 | 1196.212 | 1212.2992 | 1228.6028 | 1245.1256 | 1261.8706 | 1276.8024 | 1291.911 | 1307.1983 | 1322.6666 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 | 1338.3178 |  | 1860 | 2078.4243 | 2322.4987 | 2595.2353 | 2900 | 2935.8309 | 2972.1046 | 3008.8264 | 3046.002 | 3083.6368 | 3118.8134 | 3154.3913 | 3190.3751 | 3226.7693 | 3263.5787 | 3290.03 | 3316.6956 | 3343.5774 | 3370.6771 | 3397.9965 | 3418.2241 | 3438.5722 | 3459.0414 | 3479.6324 | 3500.3461 | 3530.8491 | 3561.618 | 3592.6549 | 3623.9624 | 3655.5427 | 3699.1883 | 3743.355 | 3788.049 | 3833.2767 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | 3879.0443 | [6 empty] | 827 | 833 | 839 | 845 | 849.1 | 860 | 870 | 880 | 890 | 900 | 911.5 | 919 | 926 | 933 | 940 | 947 | 954 | 961 | 968 | 975 | 982 | 989 | 996 | 1003 | 1010 | 1017 | 1024 | 1031 | 1038 | 1045 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | 1059.3 | [6 empty] | 3.1883 | 3.193 | 3.1976 | 3.2022 | 3.2068 | 3.1964 | 3.1861 | 3.1757 | 3.1654 | 3.1551 | 3.1446 | 3.1341 | 3.1237 | 3.1133 | 3.1029 | 3.0891 | 3.0753 | 3.0617 | 3.048 | 3.0345 | 3.0205 | 3.0067 | 2.9929 | 2.9792 | 2.9655 | 2.9517 | 2.9379 | 2.9242 | 2.9105 | 2.8969 | 2.8972 | 2.8975 | 2.8978 | 2.8981 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984
50 | Hibiscus and Bays |  |  | 2052 | 746.3567 | 745.4404 | 744.5251 | 743.6111 | 742.6981 | 743.0337 | 743.3695 | 743.7054 | 744.0414 | 744.3777 | 744.7198 | 745.0621 | 745.4046 | 745.7472 | 746.09 | 746.4671 | 746.8444 | 747.2218 | 747.5995 | 747.9773 | 748.3493 | 748.7215 | 749.0938 | 749.4664 | 749.8391 | 750.2577 | 750.6766 | 751.0957 | 751.515 | 751.9346 | 752.287 | 752.6395 | 752.9922 | 753.3451 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 | 753.6981 |  | 2040 | 2037.4954 | 2034.9939 | 2032.4954 | 2030 | 2022.6179 | 2015.2627 | 2007.9342 | 2000.6324 | 1993.3572 | 1985.9536 | 1978.5775 | 1971.2288 | 1963.9075 | 1956.6133 | 1948.9164 | 1941.2498 | 1933.6133 | 1926.0069 | 1918.4304 | 1910.6801 | 1902.961 | 1895.2732 | 1887.6164 | 1879.9905 | 1872.3125 | 1864.6658 | 1857.0503 | 1849.4659 | 1841.9126 | 1842.7635 | 1843.6149 | 1844.4667 | 1845.3188 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | 1846.1714 | [6 empty] | 546 | 550 | 554 | 558 | 562.2 | 569 | 576 | 583 | 590 | 597 | 605.3 | 610 | 615 | 620 | 625 | 630 | 635 | 640 | 645 | 650 | 655 | 660 | 665 | 670 | 675 | 680 | 685 | 690 | 695 | 700 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | 704.1 | [6 empty] | 2.7333 | 2.7333 | 2.7333 | 2.7333 | 2.7333 | 2.7221 | 2.711 | 2.6999 | 2.6889 | 2.6779 | 2.6667 | 2.6556 | 2.6445 | 2.6335 | 2.6225 | 2.6109 | 2.5993 | 2.5877 | 2.5763 | 2.5648 | 2.5532 | 2.5416 | 2.5301 | 2.5186 | 2.5072 | 2.4956 | 2.484 | 2.4725 | 2.461 | 2.4496 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495 | 2.4495
51 | Hibiscus and Bays |  |  | 2052 | 1483.7482 | 1480.3254 | 1476.9106 | 1473.5036 | 1470.1045 | 1470.7757 | 1471.4472 | 1472.1191 | 1472.7912 | 1473.4636 | 1474.148 | 1474.8326 | 1475.5175 | 1476.2028 | 1476.8883 | 1477.5403 | 1478.1926 | 1478.8452 | 1479.4981 | 1480.1512 | 1480.7465 | 1481.3421 | 1481.9378 | 1482.5339 | 1483.1301 | 1483.8659 | 1484.602 | 1485.3386 | 1486.0754 | 1486.8127 | 1487.4705 | 1488.1285 | 1488.7869 | 1489.4456 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 | 1490.1045 |  | 4350 | 4339.9653 | 4329.9538 | 4319.9654 | 4310 | 4294.4625 | 4278.981 | 4263.5553 | 4248.1852 | 4232.8705 | 4217.2869 | 4201.7606 | 4186.2916 | 4170.8794 | 4155.524 | 4139.0799 | 4122.7008 | 4106.3866 | 4090.1369 | 4073.9515 | 4057.285 | 4040.6866 | 4024.1561 | 4007.6932 | 3991.2977 | 3974.9218 | 3958.6132 | 3942.3714 | 3926.1963 | 3910.0875 | 3911.7517 | 3913.4166 | 3915.0821 | 3916.7484 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | 3918.4154 | [6 empty] | 510 | 512 | 514 | 516 | 519.3 | 526 | 532 | 538 | 544 | 550 | 556.5 | 560 | 564 | 568 | 572 | 576 | 580 | 584 | 588 | 592 | 596 | 600 | 604 | 608 | 612 | 616 | 620 | 624 | 628 | 632 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | 633.6 | [6 empty] | 2.9318 | 2.9318 | 2.9318 | 2.9318 | 2.9318 | 2.9199 | 2.908 | 2.8962 | 2.8844 | 2.8727 | 2.8608 | 2.849 | 2.8372 | 2.8254 | 2.8137 | 2.8013 | 2.789 | 2.7768 | 2.7645 | 2.7524 | 2.74 | 2.7277 | 2.7155 | 2.7033 | 2.6911 | 2.6788 | 2.6664 | 2.6542 | 2.642 | 2.6298 | 2.6298 | 2.6298 | 2.6297 | 2.6297 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296 | 2.6296
52 | Hibiscus and Bays |  |  | 2052 | 1887.7731 | 1880.3424 | 1872.941 | 1865.5687 | 1858.2254 | 1858.8967 | 1859.5683 | 1860.2401 | 1860.9122 | 1861.5845 | 1862.269 | 1862.9537 | 1863.6386 | 1864.3238 | 1865.0092 | 1865.6614 | 1866.3137 | 1866.9663 | 1867.6191 | 1868.2721 | 1868.8675 | 1869.4631 | 1870.0589 | 1870.6548 | 1871.251 | 1871.9869 | 1872.7232 | 1873.4597 | 1874.1965 | 1874.9336 | 1875.5915 | 1876.2496 | 1876.908 | 1877.5666 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 | 1878.2254 |  | 5750 | 5727.3667 | 5704.8225 | 5682.3671 | 5660 | 5638.7753 | 5617.6302 | 5596.5644 | 5575.5775 | 5554.6694 | 5533.3954 | 5512.2029 | 5491.0915 | 5470.061 | 5449.111 | 5426.7323 | 5404.4455 | 5382.2503 | 5360.1462 | 5338.1328 | 5315.5208 | 5293.0045 | 5270.5836 | 5248.2577 | 5226.0263 | 5203.9099 | 5181.8871 | 5159.9575 | 5138.1207 | 5116.3763 | 5117.9725 | 5119.5692 | 5121.1665 | 5122.7642 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | 5124.3624 | [6 empty] | 767 | 772 | 777 | 782 | 785 | 795 | 805 | 815 | 825 | 835 | 843.7 | 850 | 856 | 862 | 868 | 874 | 880 | 886 | 892 | 898 | 904 | 910 | 916 | 922 | 928 | 934 | 940 | 946 | 952 | 958 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | 971.5 | [6 empty] | 3.0459 | 3.0459 | 3.0459 | 3.0459 | 3.0459 | 3.0334 | 3.0209 | 3.0085 | 2.9962 | 2.9838 | 2.9713 | 2.9589 | 2.9464 | 2.9341 | 2.9218 | 2.9087 | 2.8958 | 2.8829 | 2.87 | 2.8573 | 2.8442 | 2.8313 | 2.8184 | 2.8056 | 2.7928 | 2.7799 | 2.767 | 2.7542 | 2.7415 | 2.7288 | 2.7287 | 2.7286 | 2.7285 | 2.7284 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283 | 2.7283
53 | Upper Harbour |  |  | 2052 | 1215.5031 | 1220.6244 | 1225.7672 | 1230.9317 | 1236.1179 | 1252.0764 | 1268.2408 | 1284.614 | 1301.1985 | 1317.9971 | 1334.285 | 1350.7741 | 1367.467 | 1384.3662 | 1401.4742 | 1416.419 | 1431.5232 | 1446.7885 | 1462.2165 | 1477.8091 | 1491.1569 | 1504.6253 | 1518.2154 | 1531.9282 | 1545.7648 | 1563.6522 | 1581.7465 | 1600.0503 | 1618.5658 | 1637.2957 | 1654.1111 | 1671.0993 | 1688.262 | 1705.6009 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 | 1723.1179 |  | 4210 | 4227.3919 | 4244.8557 | 4262.3916 | 4280 | 4318.4563 | 4357.2581 | 4396.4085 | 4435.9108 | 4475.7679 | 4513.2882 | 4551.123 | 4589.2749 | 4627.7467 | 4666.541 | 4696.3013 | 4726.2515 | 4756.3927 | 4786.7261 | 4817.2529 | 4839.8798 | 4862.613 | 4885.453 | 4908.4002 | 4931.4553 | 4966.4497 | 5001.6924 | 5037.1852 | 5072.9299 | 5108.9282 | 5160.5674 | 5212.7285 | 5265.4169 | 5318.6378 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | 5372.3967 | [6 empty] | 918 | 923 | 928 | 933 | 939.3 | 949 | 959 | 969 | 979 | 989 | 997.6 | 1001 | 1005 | 1009 | 1013 | 1017 | 1021 | 1025 | 1029 | 1033 | 1037 | 1041 | 1045 | 1049 | 1053 | 1057 | 1061 | 1065 | 1069 | 1073 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | 1068.2 | [6 empty] | 3.4636 | 3.4633 | 3.463 | 3.4627 | 3.4625 | 3.449 | 3.4357 | 3.4224 | 3.4091 | 3.3959 | 3.3826 | 3.3693 | 3.356 | 3.3429 | 3.3297 | 3.3156 | 3.3016 | 3.2876 | 3.2736 | 3.2597 | 3.2457 | 3.2318 | 3.2179 | 3.2041 | 3.1903 | 3.1762 | 3.1621 | 3.1481 | 3.1342 | 3.1203 | 3.1198 | 3.1193 | 3.1188 | 3.1183 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178 | 3.1178
54 | Upper Harbour |  |  | 2052 | 1834.3045 | 1823.3277 | 1812.4167 | 1801.5709 | 1790.79 | 1793.4693 | 1796.1526 | 1798.8399 | 1801.5312 | 1804.2266 | 1806.958 | 1809.6937 | 1812.4334 | 1815.1773 | 1817.9254 | 1820.4265 | 1822.931 | 1825.4389 | 1827.9504 | 1830.4652 | 1832.694 | 1834.9254 | 1837.1596 | 1839.3964 | 1841.636 | 1844.6355 | 1847.6398 | 1850.649 | 1853.6632 | 1856.6822 | 1859.4952 | 1862.3125 | 1865.1341 | 1867.9599 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 | 1870.79 |  | 5480 | 5447.2068 | 5414.6099 | 5382.208 | 5350 | 5348.3244 | 5346.6493 | 5344.9747 | 5343.3007 | 5341.6272 | 5339.9611 | 5338.2954 | 5336.6303 | 5334.9657 | 5333.3016 | 5327.1959 | 5321.0971 | 5315.0054 | 5308.9205 | 5302.8427 | 5295.7612 | 5288.6892 | 5281.6266 | 5274.5734 | 5267.5296 | 5262.4889 | 5257.4529 | 5252.4218 | 5247.3955 | 5242.374 | 5250.3451 | 5258.3284 | 5266.3238 | 5274.3313 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | 5282.351 | [6 empty] | 979 | 985 | 991 | 997 | 1001.8 | 1013 | 1024 | 1035 | 1046 | 1057 | 1068.4 | 1073 | 1078 | 1083 | 1088 | 1093 | 1098 | 1103 | 1108 | 1113 | 1118 | 1123 | 1128 | 1133 | 1138 | 1143 | 1148 | 1153 | 1158 | 1163 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | 1170.3 | [6 empty] | 2.9875 | 2.9875 | 2.9875 | 2.9875 | 2.9875 | 2.9821 | 2.9767 | 2.9713 | 2.966 | 2.9606 | 2.9552 | 2.9498 | 2.9445 | 2.9391 | 2.9337 | 2.9263 | 2.919 | 2.9116 | 2.9043 | 2.897 | 2.8896 | 2.8822 | 2.8749 | 2.8676 | 2.8602 | 2.8529 | 2.8455 | 2.8382 | 2.8308 | 2.8235 | 2.8235 | 2.8235 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236 | 2.8236
55 | Hibiscus and Bays |  |  | 2052 | 1322.4727 | 1310.8592 | 1299.3476 | 1287.9372 | 1276.627 | 1285.7338 | 1294.9055 | 1304.1427 | 1313.4458 | 1322.8152 | 1332.1019 | 1341.4537 | 1350.8711 | 1360.3547 | 1369.9049 | 1378.4476 | 1387.0437 | 1395.6934 | 1404.397 | 1413.1549 | 1420.7937 | 1428.4739 | 1436.1955 | 1443.9589 | 1451.7643 | 1461.9469 | 1472.2009 | 1482.5269 | 1492.9252 | 1503.3965 | 1512.9211 | 1522.5061 | 1532.1518 | 1541.8586 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 | 1551.627 |  | 3750 | 3717.0687 | 3684.4267 | 3652.0713 | 3620 | 3637.3252 | 3654.7334 | 3672.2249 | 3689.8 | 3707.4593 | 3724.6459 | 3741.9122 | 3759.2585 | 3776.6853 | 3794.1928 | 3806.404 | 3818.6545 | 3830.9445 | 3843.274 | 3855.6431 | 3864.603 | 3873.5836 | 3882.5851 | 3891.6076 | 3900.651 | 3915.9056 | 3931.2198 | 3946.594 | 3962.0282 | 3977.5228 | 4003.2463 | 4029.1361 | 4055.1934 | 4081.4192 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | 4107.8146 | [6 empty] | 779 | 785 | 791 | 797 | 804.2 | 813 | 822 | 831 | 840 | 849 | 858.8 | 866 | 873 | 880 | 887 | 894 | 901 | 908 | 915 | 922 | 929 | 936 | 943 | 950 | 957 | 964 | 971 | 978 | 985 | 992 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | 997.8 | [6 empty] | 2.8356 | 2.8356 | 2.8356 | 2.8356 | 2.8356 | 2.829 | 2.8224 | 2.8158 | 2.8093 | 2.8027 | 2.7961 | 2.7894 | 2.7828 | 2.7763 | 2.7697 | 2.7614 | 2.7531 | 2.7448 | 2.7366 | 2.7284 | 2.72 | 2.7117 | 2.7034 | 2.6951 | 2.6868 | 2.6786 | 2.6703 | 2.6621 | 2.6539 | 2.6457 | 2.646 | 2.6464 | 2.6467 | 2.6471 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474 | 2.6474
56 | Hibiscus and Bays |  |  | 2052 | 522.4509 | 522.4509 | 522.4509 | 522.4509 | 522.4509 | 523.538 | 524.6275 | 525.7192 | 526.8132 | 527.9095 | 529.0178 | 530.1285 | 531.2416 | 532.3569 | 533.4746 | 534.5055 | 535.5383 | 536.5732 | 537.61 | 538.6489 | 539.5766 | 540.5059 | 541.4368 | 542.3693 | 543.3034 | 544.5515 | 545.8025 | 547.0563 | 548.313 | 549.5726 | 550.7433 | 551.9164 | 553.0921 | 554.2702 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 | 555.4509 |  | 1680 | 1680 | 1680 | 1680 | 1680 | 1677.6628 | 1675.3288 | 1672.9981 | 1670.6707 | 1668.3464 | 1665.9545 | 1663.566 | 1661.1809 | 1658.7993 | 1656.421 | 1653.1877 | 1649.9606 | 1646.7399 | 1643.5255 | 1640.3173 | 1636.67 | 1633.0308 | 1629.3997 | 1625.7767 | 1622.1618 | 1619.3093 | 1616.4618 | 1613.6194 | 1610.7819 | 1607.9495 | 1611.1937 | 1614.4444 | 1617.7017 | 1620.9656 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | 1624.2361 | [6 empty] | 322 | 324 | 326 | 328 | 329.9 | 334 | 338 | 342 | 346 | 350 | 353.5 | 356 | 359 | 362 | 365 | 368 | 371 | 374 | 377 | 380 | 383 | 386 | 389 | 392 | 395 | 398 | 401 | 404 | 407 | 410 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | 403.8 | [6 empty] | 3.2156 | 3.2156 | 3.2156 | 3.2156 | 3.2156 | 3.2045 | 3.1934 | 3.1823 | 3.1713 | 3.1603 | 3.1491 | 3.138 | 3.127 | 3.116 | 3.105 | 3.0929 | 3.0809 | 3.069 | 3.0571 | 3.0452 | 3.0332 | 3.0213 | 3.0094 | 2.9975 | 2.9857 | 2.9737 | 2.9616 | 2.9496 | 2.9377 | 2.9258 | 2.9255 | 2.9252 | 2.9248 | 2.9245 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242 | 2.9242
57 | Hibiscus and Bays |  |  | 2052 | 1095.172 | 1094.249 | 1093.3268 | 1092.4053 | 1091.4846 | 1094.7403 | 1098.0057 | 1101.2808 | 1104.5657 | 1107.8604 | 1111.1796 | 1114.5087 | 1117.8477 | 1121.1968 | 1124.5558 | 1127.5801 | 1130.6126 | 1133.6532 | 1136.7019 | 1139.7589 | 1142.4458 | 1145.139 | 1147.8386 | 1150.5446 | 1153.2569 | 1156.8704 | 1160.4951 | 1164.1312 | 1167.7788 | 1171.4377 | 1174.8274 | 1178.2269 | 1181.6363 | 1185.0555 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 | 1188.4846 |  | 2970 | 2967.4968 | 2964.9958 | 2962.4968 | 2960 | 2956.8331 | 2953.6696 | 2950.5095 | 2947.3528 | 2944.1994 | 2940.841 | 2937.4864 | 2934.1357 | 2930.7887 | 2927.4456 | 2922.273 | 2917.1095 | 2911.9551 | 2906.8098 | 2901.6736 | 2895.2889 | 2888.9183 | 2882.5617 | 2876.2191 | 2869.8904 | 2865.5152 | 2861.1467 | 2856.7848 | 2852.4296 | 2848.081 | 2856.4163 | 2864.7759 | 2873.16 | 2881.5687 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | 2890.0019 | [6 empty] | 638 | 642 | 646 | 650 | 655.1 | 663 | 671 | 679 | 687 | 695 | 703.2 | 709 | 715 | 721 | 727 | 733 | 739 | 745 | 751 | 757 | 763 | 769 | 775 | 781 | 787 | 793 | 799 | 805 | 811 | 817 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | 818.7 | [6 empty] | 2.7119 | 2.7119 | 2.7119 | 2.7119 | 2.7119 | 2.7009 | 2.69 | 2.6792 | 2.6683 | 2.6576 | 2.6466 | 2.6357 | 2.6248 | 2.614 | 2.6032 | 2.5916 | 2.5801 | 2.5686 | 2.5572 | 2.5459 | 2.5343 | 2.5228 | 2.5113 | 2.4999 | 2.4885 | 2.477 | 2.4655 | 2.454 | 2.4426 | 2.4313 | 2.4313 | 2.4314 | 2.4315 | 2.4316 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317 | 2.4317
58 | Hibiscus and Bays |  |  | 2052 | 444.6116 | 455.7811 | 467.2311 | 478.9688 | 491.0014 | 506.004 | 521.4651 | 537.3985 | 553.8188 | 570.7408 | 586.1456 | 601.9661 | 618.2137 | 634.8998 | 652.0363 | 666.2612 | 680.7964 | 695.6488 | 710.8252 | 726.3326 | 739.0991 | 752.09 | 765.3093 | 778.7609 | 792.4489 | 809.509 | 826.9364 | 844.739 | 862.9248 | 881.5022 | 897.603 | 913.9979 | 930.6923 | 947.6916 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 | 965.0014 |  | 780 | 799.2738 | 819.0238 | 839.2619 | 860 | 890.7006 | 922.4971 | 955.4287 | 989.5359 | 1024.8607 | 1057.8048 | 1091.808 | 1126.9042 | 1163.1286 | 1200.5174 | 1230.34 | 1260.9033 | 1292.2259 | 1324.3267 | 1357.2248 | 1385.2118 | 1413.776 | 1442.9292 | 1472.6835 | 1503.0514 | 1539.9173 | 1577.6874 | 1616.3839 | 1656.0295 | 1696.6475 | 1727.4043 | 1758.7186 | 1790.6006 | 1823.0605 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | 1856.1089 | [6 empty] | 1466 | 1481 | 1496 | 1511 | 1526.5 | 1546 | 1566 | 1586 | 1606 | 1626 | 1646.4 | 1663 | 1680 | 1697 | 1714 | 1731 | 1748 | 1765 | 1782 | 1799 | 1816 | 1833 | 1850 | 1867 | 1884 | 1901 | 1918 | 1935 | 1952 | 1969 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | 1986 | [6 empty] | 1.7543 | 1.7536 | 1.7529 | 1.7522 | 1.7515 | 1.7603 | 1.769 | 1.7779 | 1.7868 | 1.7957 | 1.8047 | 1.8137 | 1.8228 | 1.832 | 1.8412 | 1.8466 | 1.8521 | 1.8576 | 1.8631 | 1.8686 | 1.8742 | 1.8798 | 1.8854 | 1.8911 | 1.8967 | 1.9023 | 1.9079 | 1.9135 | 1.9191 | 1.9247 | 1.9245 | 1.9242 | 1.9239 | 1.9237 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234 | 1.9234
59 | Hibiscus and Bays |  |  | 2052 | 478.6933 | 476.1627 | 473.6455 | 471.1415 | 468.6508 | 474.0492 | 479.5097 | 485.0331 | 490.6201 | 496.2715 | 501.7798 | 507.3492 | 512.9805 | 518.6742 | 524.4312 | 529.5021 | 534.622 | 539.7914 | 545.0107 | 550.2806 | 554.8187 | 559.3943 | 564.0075 | 568.6588 | 573.3485 | 579.3609 | 585.4364 | 591.5756 | 597.7791 | 604.0477 | 609.663 | 615.3304 | 621.0505 | 626.8238 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 | 632.6508 |  | 1430 | 1422.4403 | 1414.9205 | 1407.4405 | 1400 | 1415.2013 | 1430.5677 | 1446.101 | 1461.8029 | 1477.6753 | 1493.2878 | 1509.0653 | 1525.0094 | 1541.1221 | 1557.4049 | 1570.2516 | 1583.2042 | 1596.2637 | 1609.4309 | 1622.7067 | 1634.0717 | 1645.5162 | 1657.041 | 1668.6464 | 1680.3331 | 1695.5802 | 1710.9656 | 1726.4906 | 1742.1565 | 1757.9646 | 1772.9078 | 1787.978 | 1803.1764 | 1818.5039 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | 1833.9617 | [6 empty] | 307 | 310 | 313 | 316 | 319.5 | 323 | 327 | 331 | 335 | 339 | 342.7 | 346 | 349 | 352 | 355 | 358 | 361 | 364 | 367 | 370 | 373 | 376 | 379 | 382 | 385 | 388 | 391 | 394 | 397 | 400 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | 411 | [6 empty] | 2.9873 | 2.9873 | 2.9873 | 2.9873 | 2.9873 | 2.9853 | 2.9834 | 2.9814 | 2.9795 | 2.9776 | 2.976 | 2.9744 | 2.9728 | 2.9713 | 2.9697 | 2.9655 | 2.9614 | 2.9572 | 2.953 | 2.9489 | 2.9452 | 2.9416 | 2.938 | 2.9344 | 2.9307 | 2.9266 | 2.9225 | 2.9185 | 2.9144 | 2.9103 | 2.908 | 2.9057 | 2.9034 | 2.9011 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989 | 2.8989
60 | Hibiscus and Bays |  |  | 2052 | 1473.5213 | 1466.8837 | 1460.2759 | 1453.6979 | 1447.1496 | 1450.5448 | 1453.9479 | 1457.3591 | 1460.7782 | 1464.2054 | 1467.6668 | 1471.1363 | 1474.614 | 1478.0999 | 1481.5941 | 1484.7783 | 1487.9694 | 1491.1674 | 1494.3722 | 1497.5839 | 1500.43 | 1503.2815 | 1506.1385 | 1509.0008 | 1511.8687 | 1515.6973 | 1519.5357 | 1523.3837 | 1527.2415 | 1531.1091 | 1534.7003 | 1538.2999 | 1541.908 | 1545.5246 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 | 1549.1496 |  | 4470 | 4449.8644 | 4429.8194 | 4409.8648 | 4390 | 4388.2542 | 4386.5091 | 4384.7647 | 4383.021 | 4381.2779 | 4379.4459 | 4377.6145 | 4375.784 | 4373.9542 | 4372.1252 | 4367.0363 | 4361.9533 | 4356.8763 | 4351.8051 | 4346.7399 | 4340.358 | 4333.9856 | 4327.6225 | 4321.2687 | 4314.9243 | 4311.0976 | 4307.2744 | 4303.4545 | 4299.638 | 4295.8249 | 4306.0274 | 4316.2542 | 4326.5052 | 4336.7806 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | 4347.0804 | [6 empty] | 499 | 501 | 503 | 505 | 508.8 | 515 | 521 | 527 | 533 | 539 | 544.5 | 548 | 552 | 556 | 560 | 564 | 568 | 572 | 576 | 580 | 584 | 588 | 592 | 596 | 600 | 604 | 608 | 612 | 616 | 620 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | 616.5 | [6 empty] | 3.0335 | 3.0335 | 3.0335 | 3.0335 | 3.0335 | 3.0252 | 3.017 | 3.0087 | 3.0005 | 2.9923 | 2.984 | 2.9757 | 2.9674 | 2.9592 | 2.951 | 2.9412 | 2.9315 | 2.9218 | 2.9121 | 2.9025 | 2.8927 | 2.883 | 2.8733 | 2.8637 | 2.854 | 2.8443 | 2.8346 | 2.8249 | 2.8153 | 2.8057 | 2.8058 | 2.8059 | 2.8059 | 2.806 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061 | 2.8061
61 | Upper Harbour |  |  | 2052 | 545.6758 | 550.8404 | 556.0538 | 561.3166 | 566.6292 | 569.2914 | 571.9661 | 574.6534 | 577.3533 | 580.0658 | 582.7801 | 585.507 | 588.2467 | 590.9992 | 593.7646 | 596.2517 | 598.7491 | 601.2571 | 603.7755 | 606.3045 | 608.5224 | 610.7484 | 612.9825 | 615.2248 | 617.4753 | 620.4556 | 623.4503 | 626.4595 | 629.4832 | 632.5215 | 635.3182 | 638.1273 | 640.9488 | 643.7827 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 | 646.6292 |  | 1940 | 1957.2681 | 1974.6898 | 1992.2667 | 2010 | 2014.2668 | 2018.5426 | 2022.8275 | 2027.1215 | 2031.4247 | 2035.6456 | 2039.8753 | 2044.1137 | 2048.361 | 2052.6171 | 2054.8119 | 2057.009 | 2059.2085 | 2061.4103 | 2063.6145 | 2064.7 | 2065.786 | 2066.8726 | 2067.9598 | 2069.0476 | 2072.3157 | 2075.5889 | 2078.8673 | 2082.1508 | 2085.4396 | 2094.1474 | 2102.8915 | 2111.6722 | 2120.4895 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | 2129.3436 | [6 empty] | 478 | 481 | 484 | 487 | 490.3 | 496 | 501 | 506 | 511 | 516 | 521.6 | 524 | 526 | 528 | 530 | 532 | 534 | 536 | 538 | 540 | 542 | 544 | 546 | 548 | 550 | 552 | 554 | 556 | 558 | 560 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | 564.2 | [6 empty] | 3.5552 | 3.5532 | 3.5513 | 3.5493 | 3.5473 | 3.5382 | 3.5291 | 3.5201 | 3.5111 | 3.5021 | 3.493 | 3.4839 | 3.4749 | 3.4659 | 3.457 | 3.4462 | 3.4355 | 3.4248 | 3.4142 | 3.4036 | 3.393 | 3.3824 | 3.3718 | 3.3613 | 3.3508 | 3.34 | 3.3292 | 3.3184 | 3.3077 | 3.297 | 3.2962 | 3.2954 | 3.2946 | 3.2938 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293 | 3.293
62 | Upper Harbour |  |  | 2052 | 700.9127 | 694.3059 | 687.7612 | 681.2783 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 | 674.8565 |  | 2690 | 2664.6437 | 2639.5265 | 2614.646 | 2590 | 2593.3294 | 2596.663 | 2600.0009 | 2603.3432 | 2606.6897 | 2610.0191 | 2613.3528 | 2616.6907 | 2620.0329 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | 2623.3794 | [6 empty] | 719 | 722 | 725 | 728 | 730.8 | 739 | 747 | 755 | 763 | 771 | 781.4 | 784 | 787 | 790 | 793 | 796 | 799 | 802 | 805 | 808 | 811 | 814 | 817 | 820 | 823 | 826 | 829 | 832 | 835 | 838 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | 832.2 | [6 empty] | 3.8379 | 3.8379 | 3.8379 | 3.8379 | 3.8379 | 3.8428 | 3.8477 | 3.8527 | 3.8576 | 3.8626 | 3.8675 | 3.8725 | 3.8774 | 3.8824 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873 | 3.8873
63 | Hibiscus and Bays |  |  | 2052 | 1023.4631 | 1017.6168 | 1011.804 | 1006.0244 | 1000.2778 | 1007.7209 | 1015.2194 | 1022.7737 | 1030.3842 | 1038.0514 | 1045.6417 | 1053.2875 | 1060.9892 | 1068.7473 | 1076.562 | 1083.522 | 1090.5269 | 1097.5772 | 1104.673 | 1111.8147 | 1118.0257 | 1124.2714 | 1130.5519 | 1136.8676 | 1143.2185 | 1151.4837 | 1159.8086 | 1168.1937 | 1176.6394 | 1185.1462 | 1192.8712 | 1200.6465 | 1208.4725 | 1216.3495 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 | 1224.2778 |  | 3090 | 3072.3493 | 3054.7995 | 3037.3499 | 3020 | 3042.2272 | 3064.618 | 3087.1737 | 3109.8953 | 3132.7841 | 3155.4367 | 3178.2531 | 3201.2344 | 3224.3819 | 3247.6968 | 3265.0478 | 3282.4916 | 3300.0285 | 3317.6592 | 3335.384 | 3350.2623 | 3365.207 | 3380.2183 | 3395.2966 | 3410.4422 | 3431.2393 | 3452.1632 | 3473.2147 | 3494.3945 | 3515.7036 | 3538.6304 | 3561.7067 | 3584.9336 | 3608.3119 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | 3631.8426 | [6 empty] | 462 | 466 | 470 | 474 | 476.6 | 483 | 489 | 495 | 501 | 507 | 514.9 | 520 | 525 | 530 | 535 | 540 | 545 | 550 | 555 | 560 | 565 | 570 | 575 | 580 | 585 | 590 | 595 | 600 | 605 | 610 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | 615.2 | [6 empty] | 3.0192 | 3.0192 | 3.0192 | 3.0192 | 3.0192 | 3.0189 | 3.0187 | 3.0184 | 3.0182 | 3.0179 | 3.0177 | 3.0175 | 3.0172 | 3.017 | 3.0167 | 3.0134 | 3.01 | 3.0066 | 3.0033 | 2.9999 | 2.9966 | 2.9932 | 2.9899 | 2.9865 | 2.9832 | 2.9798 | 2.9765 | 2.9731 | 2.9698 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665 | 2.9665
64 | Hibiscus and Bays |  |  | 2052 | 1699.1032 | 1692.2101 | 1685.345 | 1678.5078 | 1671.6983 | 1676.2087 | 1680.7313 | 1685.2661 | 1689.8132 | 1694.3725 | 1698.9708 | 1703.5816 | 1708.2049 | 1712.8408 | 1717.4892 | 1721.7007 | 1725.9226 | 1730.1548 | 1734.3973 | 1738.6503 | 1742.4042 | 1746.1662 | 1749.9363 | 1753.7146 | 1757.501 | 1762.55 | 1767.6135 | 1772.6915 | 1777.7842 | 1782.8914 | 1787.6276 | 1792.3763 | 1797.1376 | 1801.9116 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 | 1806.6983 |  | 4960 | 4939.8779 | 4919.8374 | 4899.8782 | 4880 | 4874.4663 | 4868.9389 | 4863.4177 | 4857.9028 | 4852.3942 | 4846.6051 | 4840.8229 | 4835.0476 | 4829.2792 | 4823.5177 | 4814.8887 | 4806.2751 | 4797.6769 | 4789.0941 | 4780.5267 | 4770.1474 | 4759.7906 | 4749.4563 | 4739.1445 | 4728.8551 | 4721.5169 | 4714.1901 | 4706.8748 | 4699.5707 | 4692.278 | 4704.7984 | 4717.3522 | 4729.9395 | 4742.5604 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | 4755.2149 | [6 empty] | 1125 | 1134 | 1143 | 1152 | 1160.5 | 1174 | 1188 | 1202 | 1216 | 1230 | 1242.4 | 1253 | 1263 | 1273 | 1283 | 1293 | 1303 | 1313 | 1323 | 1333 | 1343 | 1353 | 1363 | 1373 | 1383 | 1393 | 1403 | 1413 | 1423 | 1433 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | 1449.4 | [6 empty] | 2.9192 | 2.9192 | 2.9192 | 2.9192 | 2.9192 | 2.908 | 2.8969 | 2.8858 | 2.8748 | 2.8638 | 2.8527 | 2.8416 | 2.8305 | 2.8195 | 2.8085 | 2.7966 | 2.7848 | 2.773 | 2.7612 | 2.7496 | 2.7377 | 2.7259 | 2.7141 | 2.7023 | 2.6907 | 2.6788 | 2.667 | 2.6552 | 2.6435 | 2.6318 | 2.6319 | 2.6319 | 2.6319 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632 | 2.632
65 | Hibiscus and Bays |  |  | 2052 | 1275.5013 | 1271.4456 | 1267.4028 | 1263.3728 | 1259.3557 | 1266.8279 | 1274.3445 | 1281.9057 | 1289.5117 | 1297.1629 | 1304.7818 | 1312.4455 | 1320.1542 | 1327.9082 | 1335.7078 | 1342.7476 | 1349.8245 | 1356.9387 | 1364.0904 | 1371.2797 | 1377.5915 | 1383.9324 | 1390.3024 | 1396.7018 | 1403.1306 | 1411.5352 | 1419.9902 | 1428.4957 | 1437.0523 | 1445.6601 | 1453.5134 | 1461.4094 | 1469.3483 | 1477.3303 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 | 1485.3557 |  | 3950 | 3937.4402 | 3924.9204 | 3912.4403 | 3900 | 3911.6765 | 3923.3879 | 3935.1344 | 3946.9161 | 3958.733 | 3970.1683 | 3981.6367 | 3993.1381 | 4004.6728 | 4016.2408 | 4023.3848 | 4030.5415 | 4037.711 | 4044.8932 | 4052.0882 | 4056.3362 | 4060.5887 | 4064.8456 | 4069.107 | 4073.3728 | 4083.0555 | 4092.7612 | 4102.49 | 4112.2418 | 4122.0169 | 4144.5715 | 4167.2494 | 4190.0514 | 4212.9782 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | 4236.0305 | [6 empty] | 901 | 908 | 915 | 922 | 930.8 | 941 | 951 | 961 | 971 | 981 | 992.6 | 1001 | 1009 | 1017 | 1025 | 1033 | 1041 | 1049 | 1057 | 1065 | 1073 | 1081 | 1089 | 1097 | 1105 | 1113 | 1121 | 1129 | 1137 | 1145 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | 1161.8 | [6 empty] | 3.0968 | 3.0968 | 3.0968 | 3.0968 | 3.0968 | 3.0878 | 3.0787 | 3.0698 | 3.0608 | 3.0518 | 3.0428 | 3.0338 | 3.0248 | 3.0158 | 3.0068 | 2.9964 | 2.986 | 2.9756 | 2.9653 | 2.955 | 2.9445 | 2.9341 | 2.9237 | 2.9134 | 2.9031 | 2.8926 | 2.8822 | 2.8719 | 2.8616 | 2.8513 | 2.8514 | 2.8515 | 2.8516 | 2.8518 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519 | 2.8519
66 | Upper Harbour |  |  | 2052 | 384.4159 | 372.9961 | 361.9156 | 351.1642 | 340.7323 | 362.8593 | 386.4232 | 411.5174 | 438.2411 | 466.7003 | 489.9506 | 514.3593 | 539.9839 | 566.8851 | 595.1265 | 611.3354 | 627.9858 | 645.0897 | 662.6594 | 680.7076 | 691.9653 | 703.4091 | 715.0423 | 726.8678 | 738.8888 | 750.0951 | 761.4712 | 773.02 | 784.7438 | 796.6455 | 805.2739 | 813.9958 | 822.8121 | 831.7239 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 | 840.7323 |  | 880 | 853.858 | 828.4926 | 803.8807 | 780 | 826.1004 | 874.9254 | 926.6362 | 981.4032 | 1039.4071 | 1089.6079 | 1142.2332 | 1197.4002 | 1255.2317 | 1315.8562 | 1351.5451 | 1388.202 | 1425.8531 | 1464.5253 | 1504.2465 | 1530.7943 | 1557.8106 | 1585.3037 | 1613.2821 | 1641.7542 | 1668.8294 | 1696.3512 | 1724.3269 | 1752.7639 | 1781.6699 | 1799.4872 | 1817.4827 | 1835.6582 | 1854.0155 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | 1872.5563 | [6 empty] | 11883 | 11976 | 12069 | 12162 | 12255.8 | 12392 | 12528 | 12664 | 12800 | 12936 | 13070 | 13135 | 13200 | 13265 | 13330 | 13395 | 13460 | 13525 | 13590 | 13655 | 13720 | 13785 | 13850 | 13915 | 13980 | 14045 | 14110 | 14175 | 14240 | 14305 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | 14362.6 | [6 empty] | 2.2892 | 2.2892 | 2.2892 | 2.2892 | 2.2892 | 2.2766 | 2.2642 | 2.2518 | 2.2394 | 2.2271 | 2.2239 | 2.2207 | 2.2175 | 2.2143 | 2.2111 | 2.2108 | 2.2106 | 2.2103 | 2.2101 | 2.2098 | 2.2122 | 2.2147 | 2.2171 | 2.2195 | 2.2219 | 2.2248 | 2.2277 | 2.2306 | 2.2335 | 2.2365 | 2.2346 | 2.2328 | 2.231 | 2.2291 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273 | 2.2273
67 | Upper Harbour |  |  | 2052 | 361.6358 | 356.9075 | 352.2411 | 347.6356 | 343.0904 | 345.0005 | 346.9213 | 348.8527 | 350.7949 | 352.7479 | 354.6955 | 356.6538 | 358.623 | 360.603 | 362.5939 | 364.3632 | 366.1411 | 367.9277 | 369.723 | 371.527 | 373.0962 | 374.6721 | 376.2546 | 377.8438 | 379.4397 | 381.5477 | 383.6674 | 385.7988 | 387.9422 | 390.0974 | 392.0758 | 394.0643 | 396.0628 | 398.0715 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 | 400.0904 |  | 1170 | 1154.7026 | 1139.6052 | 1124.7052 | 1110 | 1111.6597 | 1113.3218 | 1114.9864 | 1116.6535 | 1118.3231 | 1119.8554 | 1121.3898 | 1122.9262 | 1124.4648 | 1126.0055 | 1126.4683 | 1126.9313 | 1127.3946 | 1127.858 | 1128.3216 | 1127.9561 | 1127.5908 | 1127.2256 | 1126.8604 | 1126.4955 | 1127.4701 | 1128.4456 | 1129.4219 | 1130.3991 | 1131.3771 | 1136.9723 | 1142.5951 | 1148.2457 | 1153.9243 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | 1159.631 | [6 empty] | 742 | 751 | 760 | 769 | 777 | 786 | 795 | 804 | 813 | 822 | 833.7 | 840 | 847 | 854 | 861 | 868 | 875 | 882 | 889 | 896 | 903 | 910 | 917 | 924 | 931 | 938 | 945 | 952 | 959 | 966 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | 967.3 | [6 empty] | 3.2353 | 3.2353 | 3.2353 | 3.2353 | 3.2353 | 3.2222 | 3.2091 | 3.1962 | 3.1832 | 3.1703 | 3.1572 | 3.1442 | 3.1312 | 3.1183 | 3.1054 | 3.0916 | 3.0779 | 3.0642 | 3.0505 | 3.037 | 3.0232 | 3.0095 | 2.9959 | 2.9823 | 2.9688 | 2.955 | 2.9412 | 2.9275 | 2.9138 | 2.9002 | 2.8999 | 2.8995 | 2.8992 | 2.8988 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984 | 2.8984
68 | Upper Harbour |  |  | 2052 | 660.4699 | 685.5582 | 711.5994 | 738.6298 | 766.6869 | 768.1093 | 769.5343 | 770.9619 | 772.3922 | 773.8251 | 775.2752 | 776.7279 | 778.1834 | 779.6417 | 781.1026 | 782.4463 | 783.7924 | 785.1407 | 786.4914 | 787.8444 | 789.0508 | 790.2591 | 791.4693 | 792.6813 | 793.8952 | 795.5186 | 797.1452 | 798.7752 | 800.4086 | 802.0452 | 803.5678 | 805.0932 | 806.6215 | 808.1528 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 | 809.6869 |  | 1960 | 2033.2862 | 2109.3127 | 2188.1818 | 2270 | 2272.41 | 2274.8225 | 2277.2376 | 2279.6552 | 2282.0754 | 2284.5335 | 2286.9943 | 2289.4578 | 2291.9239 | 2294.3926 | 2294.4984 | 2294.6041 | 2294.7099 | 2294.8156 | 2294.9214 | 2294.5684 | 2294.2155 | 2293.8627 | 2293.5099 | 2293.1572 | 2293.9309 | 2294.7049 | 2295.4792 | 2296.2537 | 2297.0284 | 2301.3279 | 2305.6355 | 2309.9511 | 2314.2749 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | 2318.6067 | [6 empty] | 683 | 688 | 693 | 698 | 702.2 | 710 | 717 | 724 | 731 | 738 | 746.1 | 749 | 752 | 755 | 758 | 761 | 764 | 767 | 770 | 773 | 776 | 779 | 782 | 785 | 788 | 791 | 794 | 797 | 800 | 803 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | 810.1 | [6 empty] | 2.9676 | 2.9659 | 2.9642 | 2.9625 | 2.9608 | 2.9584 | 2.9561 | 2.9538 | 2.9514 | 2.9491 | 2.9467 | 2.9444 | 2.9421 | 2.9397 | 2.9374 | 2.9325 | 2.9276 | 2.9227 | 2.9178 | 2.9129 | 2.908 | 2.9031 | 2.8982 | 2.8934 | 2.8885 | 2.8836 | 2.8787 | 2.8737 | 2.8689 | 2.864 | 2.8639 | 2.8638 | 2.8637 | 2.8637 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636 | 2.8636
69 | Rodney |  |  | 2052 | 536.0448 | 552.6928 | 569.8578 | 587.556 | 605.8038 | 613.978 | 622.2626 | 630.659 | 639.1686 | 647.7931 | 656.1371 | 664.5886 | 673.149 | 681.8196 | 690.6019 | 693.6158 | 696.6429 | 699.6833 | 702.7368 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 | 705.8038 |  | 1630 | 1677.8513 | 1727.1074 | 1777.8095 | 1830 | 1846.1838 | 1862.5107 | 1878.9819 | 1895.5989 | 1912.3628 | 1928.0409 | 1943.8476 | 1959.7839 | 1975.8509 | 1992.0495 | 1993.3091 | 1994.5694 | 1995.8306 | 1997.0925 | 1998.3553 | 1991.3317 | 1984.3329 | 1977.3586 | 1970.4089 | 1963.4836 | 1956.2489 | 1949.0408 | 1941.8593 | 1934.7042 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | 1927.5755 | [6 empty] | 561 | 565 | 569 | 573 | 575 | 581 | 587 | 593 | 599 | 605 | 611.6 | 613 | 615 | 617 | 619 | 621 | 623 | 625 | 627 | 629 | 631 | 633 | 635 | 637 | 639 | 641 | 643 | 645 | 647 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | [6 empty] | 3.0408 | 3.0358 | 3.0308 | 3.0258 | 3.0208 | 3.0069 | 2.9931 | 2.9794 | 2.9657 | 2.9521 | 2.9385 | 2.9249 | 2.9114 | 2.8979 | 2.8845 | 2.8738 | 2.8631 | 2.8525 | 2.8419 | 2.8313 | 2.8214 | 2.8115 | 2.8016 | 2.7917 | 2.7819 | 2.7717 | 2.7614 | 2.7513 | 2.7411 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731 | 2.731
70 | Upper Harbour |  |  | 2052 | 464.6412 | 459.0081 | 453.4434 | 447.9461 | 442.5154 | 457.7252 | 473.4577 | 489.731 | 506.5636 | 523.9748 | 539.6217 | 555.736 | 572.3314 | 589.4224 | 607.0237 | 621.5484 | 636.4206 | 651.6487 | 667.2411 | 683.2066 | 696.2872 | 709.6182 | 723.2045 | 737.0508 | 751.1623 | 768.6364 | 786.5169 | 804.8134 | 823.5355 | 842.6932 | 859.1983 | 876.0267 | 893.1847 | 910.6787 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 | 928.5154 |  | 1260 | 1244.7244 | 1229.6341 | 1214.7267 | 1200 | 1238.0742 | 1277.3563 | 1317.8849 | 1359.6993 | 1402.8405 | 1440.8873 | 1479.966 | 1520.1045 | 1561.3316 | 1603.6769 | 1636.4381 | 1669.8686 | 1703.9821 | 1738.7924 | 1774.3139 | 1801.92 | 1829.9556 | 1858.4275 | 1887.3423 | 1916.707 | 1954.2884 | 1992.6067 | 2031.6762 | 2071.5119 | 2112.1285 | 2153.7005 | 2196.0907 | 2239.3152 | 2283.3905 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | 2328.3334 | [6 empty] | 300 | 302 | 304 | 306 | 308.8 | 312 | 315 | 318 | 321 | 324 | 326.6 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | 353.1 | [6 empty] | 2.7118 | 2.7118 | 2.7118 | 2.7118 | 2.7118 | 2.7048 | 2.6979 | 2.691 | 2.6842 | 2.6773 | 2.6702 | 2.6631 | 2.656 | 2.6489 | 2.6419 | 2.6328 | 2.6238 | 2.6149 | 2.6059 | 2.597 | 2.5879 | 2.5788 | 2.5697 | 2.5607 | 2.5517 | 2.5425 | 2.5335 | 2.5244 | 2.5154 | 2.5064 | 2.5066 | 2.5069 | 2.5071 | 2.5074 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076 | 2.5076
71 | Upper Harbour |  |  | 2052 | 678.0009 | 662.1019 | 646.5758 | 631.4137 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 | 616.6072 |  | 2540 | 2480.4375 | 2422.2717 | 2365.4698 | 2310 | 2302.7678 | 2295.5583 | 2288.3713 | 2281.2068 | 2274.0648 | 2266.8319 | 2259.622 | 2252.435 | 2245.2709 | 2238.1296 | 2230.4257 | 2222.7483 | 2215.0974 | 2207.4728 | 2199.8744 | 2192.1695 | 2184.4915 | 2176.8405 | 2169.2163 | 2161.6187 | 2153.9128 | 2146.2344 | 2138.5834 | 2130.9596 | 2123.363 | 2123.3633 | 2123.3636 | 2123.3639 | 2123.3642 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | 2123.3645 | [6 empty] | 842 | 849 | 856 | 863 | 870.5 | 879 | 887 | 895 | 903 | 911 | 918.7 | 924 | 929 | 934 | 939 | 944 | 949 | 954 | 959 | 964 | 969 | 974 | 979 | 984 | 989 | 994 | 999 | 1004 | 1009 | 1014 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | 1015.5 | [6 empty] | 3.7463 | 3.7463 | 3.7463 | 3.7463 | 3.7463 | 3.7346 | 3.7229 | 3.7112 | 3.6996 | 3.688 | 3.6763 | 3.6646 | 3.6529 | 3.6413 | 3.6297 | 3.6173 | 3.6048 | 3.5924 | 3.58 | 3.5677 | 3.5552 | 3.5428 | 3.5304 | 3.518 | 3.5057 | 3.4932 | 3.4807 | 3.4683 | 3.4559 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436 | 3.4436
72 | Upper Harbour |  |  | 2052 | 952.1436 | 933.9992 | 916.2006 | 898.7412 | 881.6145 | 888.2326 | 894.9005 | 901.6184 | 908.3868 | 915.2059 | 921.9551 | 928.754 | 935.603 | 942.5025 | 949.4529 | 955.6417 | 961.8707 | 968.1404 | 974.451 | 980.8026 | 986.3255 | 991.8794 | 997.4647 | 1003.0813 | 1008.7296 | 1016.1429 | 1023.6107 | 1031.1334 | 1038.7114 | 1046.345 | 1053.3057 | 1060.3127 | 1067.3662 | 1074.4667 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 | 1081.6145 |  | 3240 | 3178.2574 | 3117.6915 | 3058.2796 | 3000 | 3015.6979 | 3031.4779 | 3047.3405 | 3063.2861 | 3079.3151 | 3095.0302 | 3110.8255 | 3126.7014 | 3142.6583 | 3158.6967 | 3170.31 | 3181.9661 | 3193.665 | 3205.4069 | 3217.192 | 3226.277 | 3235.3877 | 3244.5241 | 3253.6863 | 3262.8743 | 3277.2205 | 3291.6298 | 3306.1024 | 3320.6386 | 3335.2387 | 3356.0094 | 3376.9094 | 3397.9396 | 3419.1007 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | 3440.3937 | [6 empty] | 1289 | 1300 | 1311 | 1322 | 1334.3 | 1348 | 1362 | 1376 | 1390 | 1404 | 1416.9 | 1425 | 1433 | 1441 | 1449 | 1457 | 1465 | 1473 | 1481 | 1489 | 1497 | 1505 | 1513 | 1521 | 1529 | 1537 | 1545 | 1553 | 1561 | 1569 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | 1570.6 | [6 empty] | 3.4028 | 3.4028 | 3.4028 | 3.4028 | 3.4028 | 3.3952 | 3.3875 | 3.3799 | 3.3722 | 3.3646 | 3.357 | 3.3495 | 3.3419 | 3.3344 | 3.3269 | 3.3175 | 3.3081 | 3.2988 | 3.2894 | 3.2802 | 3.271 | 3.2619 | 3.2528 | 3.2437 | 3.2346 | 3.2252 | 3.2157 | 3.2063 | 3.1969 | 3.1875 | 3.1862 | 3.1848 | 3.1835 | 3.1821 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808 | 3.1808
73 | Upper Harbour |  |  | 2052 | 337.1482 | 327.2374 | 317.6179 | 308.2812 | 299.219 | 308.3819 | 317.8254 | 327.558 | 337.5888 | 347.9266 | 357.3354 | 366.9987 | 376.9232 | 387.1162 | 397.5848 | 404.0931 | 410.7079 | 417.431 | 424.2641 | 431.2091 | 435.7663 | 440.3716 | 445.0256 | 449.7288 | 454.4816 | 459.3275 | 464.225 | 469.1747 | 474.1772 | 479.233 | 483.1651 | 487.1295 | 491.1265 | 495.1562 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 | 499.219 |  | 800 | 776.4832 | 753.6577 | 731.5032 | 710 | 728.1676 | 746.8001 | 765.9094 | 785.5076 | 805.6074 | 824.4316 | 843.6957 | 863.4099 | 883.5848 | 904.2311 | 916.655 | 929.2496 | 942.0172 | 954.9603 | 968.0811 | 976.7626 | 985.5218 | 994.3597 | 1003.2768 | 1012.2738 | 1021.5041 | 1030.8186 | 1040.218 | 1049.7031 | 1059.2747 | 1066.7586 | 1074.2953 | 1081.8853 | 1089.529 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | 1097.2266 | [6 empty] | 1383 | 1399 | 1415 | 1431 | 1448.5 | 1464 | 1480 | 1496 | 1512 | 1528 | 1544.3 | 1555 | 1566 | 1577 | 1588 | 1599 | 1610 | 1621 | 1632 | 1643 | 1654 | 1665 | 1676 | 1687 | 1698 | 1709 | 1720 | 1731 | 1742 | 1753 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | 1767.9 | [6 empty] | 2.3728 | 2.3728 | 2.3728 | 2.3728 | 2.3728 | 2.3613 | 2.3497 | 2.3382 | 2.3268 | 2.3155 | 2.3072 | 2.2989 | 2.2907 | 2.2825 | 2.2743 | 2.2684 | 2.2626 | 2.2567 | 2.2509 | 2.245 | 2.2415 | 2.2379 | 2.2344 | 2.2308 | 2.2273 | 2.2239 | 2.2205 | 2.2171 | 2.2137 | 2.2104 | 2.2079 | 2.2054 | 2.2029 | 2.2004 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979 | 2.1979
74 | Upper Harbour |  |  | 2052 | 123.2862 | 160.7259 | 209.5353 | 273.1671 | 356.1227 | 413.7391 | 480.6771 | 558.4449 | 648.7946 | 753.7618 | 821.516 | 895.3605 | 975.8427 | 1063.5594 | 1159.1606 | 1225.3596 | 1295.3391 | 1369.3151 | 1447.5159 | 1530.1826 | 1591.2105 | 1654.6724 | 1720.6654 | 1789.2903 | 1860.6521 | 1942.2059 | 2027.3342 | 2116.1937 | 2208.9481 | 2305.7679 | 2383.7786 | 2464.4286 | 2547.8072 | 2634.0068 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 | 2723.1227 |  | 150 | 200.6221 | 268.3282 | 358.8837 | 480 | 603.7205 | 759.3301 | 955.0483 | 1201.2131 | 1510.827 | 1739.3277 | 2002.3873 | 2305.2326 | 2653.8809 | 3055.2595 | 3234.8986 | 3425.0999 | 3626.4845 | 3839.7097 | 4065.472 | 4233.58 | 4408.6393 | 4590.9374 | 4780.7735 | 4978.4594 | 5203.833 | 5439.4092 | 5685.6499 | 5943.0379 | 6212.0777 | 6423.0347 | 6641.1557 | 6866.684 | 7099.8709 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | 7340.9767 | [6 empty] | 8350 | 8438 | 8526 | 8614 | 8701.2 | 8810 | 8919 | 9028 | 9137 | 9246 | 9354.5 | 9418 | 9482 | 9546 | 9610 | 9674 | 9738 | 9802 | 9866 | 9930 | 9994 | 10058 | 10122 | 10186 | 10250 | 10314 | 10378 | 10442 | 10506 | 10570 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | 10625.9 | [6 empty] | 1.2167 | 1.2482 | 1.2806 | 1.3138 | 1.3479 | 1.4592 | 1.5797 | 1.7102 | 1.8515 | 2.0044 | 2.1172 | 2.2364 | 2.3623 | 2.4953 | 2.6358 | 2.64 | 2.6442 | 2.6484 | 2.6526 | 2.6569 | 2.6606 | 2.6644 | 2.6681 | 2.6719 | 2.6757 | 2.6793 | 2.683 | 2.6867 | 2.6904 | 2.6941 | 2.6945 | 2.6948 | 2.6951 | 2.6955 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958 | 2.6958
75 | Upper Harbour |  |  | 2052 | 885.2535 | 872.4512 | 859.8342 | 847.3995 | 835.1448 | 851.303 | 867.7739 | 884.5635 | 901.6779 | 919.1235 | 935.6424 | 952.4583 | 969.5763 | 987.002 | 1004.741 | 1019.9484 | 1035.3861 | 1051.0574 | 1066.9659 | 1083.1152 | 1096.732 | 1110.5199 | 1124.4813 | 1138.6181 | 1152.9327 | 1171.1552 | 1189.6657 | 1208.4688 | 1227.5691 | 1246.9712 | 1264.1273 | 1281.5194 | 1299.1509 | 1317.0249 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 | 1335.1448 |  | 2650 | 2611.6767 | 2573.9075 | 2536.6846 | 2500 | 2552.3478 | 2605.7918 | 2660.3548 | 2716.0603 | 2772.9323 | 2827.5814 | 2883.3075 | 2940.1319 | 2998.0762 | 3057.1625 | 3104.5995 | 3152.7726 | 3201.6931 | 3251.3728 | 3301.8233 | 3345.0859 | 3388.9153 | 3433.319 | 3478.3046 | 3523.8795 | 3581.132 | 3639.3146 | 3698.4426 | 3758.5312 | 3819.596 | 3870.2464 | 3921.5685 | 3973.5711 | 4026.2633 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | 4079.6543 | [6 empty] | 3264 | 3293 | 3322 | 3351 | 3380.8 | 3468 | 3555 | 3642 | 3729 | 3816 | 3901 | 4138 | 4375 | 4612 | 4849 | 5086 | 5323 | 5560 | 5797 | 6034 | 6271 | 6508 | 6745 | 6982 | 7219 | 7456 | 7693 | 7930 | 8167 | 8404 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | 8645.8 | [6 empty] | 2.9935 | 2.9935 | 2.9935 | 2.9935 | 2.9935 | 2.9982 | 3.0028 | 3.0075 | 3.0122 | 3.0169 | 3.0221 | 3.0272 | 3.0324 | 3.0376 | 3.0427 | 3.0439 | 3.045 | 3.0462 | 3.0473 | 3.0485 | 3.05 | 3.0516 | 3.0532 | 3.0548 | 3.0564 | 3.0578 | 3.0591 | 3.0604 | 3.0618 | 3.0631 | 3.0616 | 3.0601 | 3.0586 | 3.0571 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556
76 | Upper Harbour |  |  | 2052 | 15.1588 | 15.1588 | 15.1588 | 15.1588 | 15.1588 | 22.2527 | 32.6664 | 47.9533 | 70.3941 | 103.3365 | 117.117 | 132.7353 | 150.4363 | 170.4979 | 193.2348 | 207.4683 | 222.7502 | 239.1578 | 256.7739 | 275.6877 | 289.0386 | 303.0361 | 317.7115 | 333.0976 | 349.2288 | 367.1118 | 385.9107 | 405.6721 | 426.4455 | 448.2827 | 465.4859 | 483.3493 | 501.8982 | 521.1589 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 | 541.1588 |  | 40 | 40 | 40 | 40 | 40 | 58.1484 | 84.5308 | 122.8832 | 178.6365 | 259.6854 | 293.294 | 331.2521 | 374.1228 | 422.5418 | 477.2272 | 511.7596 | 548.7908 | 588.5016 | 631.0859 | 676.7517 | 709.0998 | 742.9941 | 778.5085 | 815.7204 | 854.7111 | 898.031 | 943.5465 | 991.3689 | 1041.6151 | 1094.408 | 1136.0622 | 1179.3017 | 1224.1871 | 1270.7807 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | 1319.1478 | [6 empty] | 3132 | 3142 | 3152 | 3162 | 3173.9 | 3206 | 3239 | 3272 | 3305 | 3338 | 3369 | 3375 | 3381 | 3387 | 3393 | 3399 | 3405 | 3411 | 3417 | 3423 | 3429 | 3435 | 3441 | 3447 | 3453 | 3459 | 3465 | 3471 | 3477 | 3483 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | 3481.9 | [6 empty] | 2.6387 | 2.6387 | 2.6387 | 2.6387 | 2.6387 | 2.6131 | 2.5877 | 2.5626 | 2.5377 | 2.513 | 2.5043 | 2.4956 | 2.4869 | 2.4783 | 2.4697 | 2.4667 | 2.4637 | 2.4607 | 2.4577 | 2.4548 | 2.4533 | 2.4518 | 2.4504 | 2.4489 | 2.4474 | 2.4462 | 2.445 | 2.4438 | 2.4426 | 2.4413 | 2.4406 | 2.4399 | 2.4391 | 2.4384 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376 | 2.4376
77 | Upper Harbour |  |  | 2052 | 223.2488 | 216.643 | 210.2326 | 204.0119 | 197.9753 | 201.226 | 204.53 | 207.8882 | 211.3016 | 214.7711 | 218.0915 | 221.4633 | 224.8872 | 228.364 | 231.8946 | 234.9481 | 238.0418 | 241.1762 | 244.3519 | 247.5694 | 250.3012 | 253.0631 | 255.8554 | 258.6786 | 261.5329 | 265.1907 | 268.8997 | 272.6605 | 276.4739 | 280.3406 | 283.782 | 287.2657 | 290.7921 | 294.3618 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 | 297.9753 |  | 530 | 514.3176 | 499.0992 | 484.3311 | 470 | 479.1526 | 488.4834 | 497.9959 | 507.6936 | 517.5803 | 527.224 | 537.0474 | 547.0539 | 557.2467 | 567.6296 | 575.9615 | 584.4158 | 592.9942 | 601.6985 | 610.5305 | 618.2921 | 626.1523 | 634.1125 | 642.1738 | 650.3376 | 660.4352 | 670.6895 | 681.1031 | 691.6783 | 702.4177 | 710.5737 | 718.8243 | 727.1708 | 735.6141 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | 744.1555 | [6 empty] | 9700 | 9735 | 9770 | 9805 | 9840 | 9941 | 10042 | 10143 | 10244 | 10345 | 10444.5 | 10463 | 10482 | 10501 | 10520 | 10539 | 10558 | 10577 | 10596 | 10615 | 10634 | 10653 | 10672 | 10691 | 10710 | 10729 | 10748 | 10767 | 10786 | 10805 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | 10821 | [6 empty] | 2.374 | 2.374 | 2.374 | 2.374 | 2.374 | 2.3812 | 2.3883 | 2.3955 | 2.4027 | 2.4099 | 2.4174 | 2.425 | 2.4326 | 2.4402 | 2.4478 | 2.4514 | 2.4551 | 2.4588 | 2.4624 | 2.4661 | 2.4702 | 2.4743 | 2.4784 | 2.4825 | 2.4866 | 2.4904 | 2.4942 | 2.498 | 2.5018 | 2.5056 | 2.5039 | 2.5023 | 2.5007 | 2.499 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974 | 2.4974
78 | Upper Harbour |  |  | 2052 | 1285.8676 | 1268.487 | 1251.3414 | 1234.4275 | 1217.7422 | 1220.4177 | 1223.0991 | 1225.7864 | 1228.4796 | 1231.1788 | 1233.9064 | 1236.6401 | 1239.3798 | 1242.1257 | 1244.8776 | 1247.3755 | 1249.8784 | 1252.3864 | 1254.8994 | 1257.4174 | 1259.6437 | 1261.8739 | 1264.1081 | 1266.3462 | 1268.5882 | 1271.5833 | 1274.5854 | 1277.5946 | 1280.611 | 1283.6344 | 1286.4436 | 1289.259 | 1292.0806 | 1294.9083 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 | 1297.7422 |  | 4530 | 4468.7697 | 4408.367 | 4348.7808 | 4290 | 4288.3404 | 4286.6815 | 4285.0232 | 4283.3656 | 4281.7086 | 4279.9861 | 4278.2644 | 4276.5433 | 4274.8229 | 4273.1032 | 4268.1359 | 4263.1744 | 4258.2187 | 4253.2687 | 4248.3245 | 4242.1706 | 4236.0256 | 4229.8896 | 4223.7624 | 4217.6441 | 4213.7933 | 4209.9461 | 4206.1024 | 4202.2622 | 4198.4255 | 4207.608 | 4216.8105 | 4226.0332 | 4235.2761 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | 4244.5391 | [6 empty] | 1263 | 1272 | 1281 | 1290 | 1297 | 1310 | 1323 | 1336 | 1349 | 1362 | 1377.4 | 1383 | 1388 | 1393 | 1398 | 1403 | 1408 | 1413 | 1418 | 1423 | 1428 | 1433 | 1438 | 1443 | 1448 | 1453 | 1458 | 1463 | 1468 | 1473 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | 1486.5 | [6 empty] | 3.5229 | 3.5229 | 3.5229 | 3.5229 | 3.5229 | 3.5138 | 3.5048 | 3.4957 | 3.4867 | 3.4777 | 3.4686 | 3.4596 | 3.4506 | 3.4415 | 3.4325 | 3.4217 | 3.4109 | 3.4001 | 3.3893 | 3.3786 | 3.3678 | 3.3569 | 3.3461 | 3.3354 | 3.3247 | 3.3138 | 3.303 | 3.2922 | 3.2815 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707 | 3.2707
79 | Upper Harbour |  |  | 2052 | 966.8014 | 962.3357 | 957.8906 | 953.4661 | 949.0619 | 951.7342 | 954.4139 | 957.1012 | 959.7961 | 962.4985 | 965.2228 | 967.9548 | 970.6946 | 973.4421 | 976.1973 | 978.6925 | 981.1941 | 983.702 | 986.2164 | 988.7372 | 990.9613 | 993.1905 | 995.4246 | 997.6638 | 999.908 | 1002.8993 | 1005.8995 | 1008.9087 | 1011.9269 | 1014.9542 | 1017.7602 | 1020.5739 | 1023.3954 | 1026.2248 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 | 1029.0619 |  | 3270 | 3254.8957 | 3239.8611 | 3224.896 | 3210 | 3205.8287 | 3201.6628 | 3197.5024 | 3193.3473 | 3189.1977 | 3184.8261 | 3180.4604 | 3176.1008 | 3171.7472 | 3167.3995 | 3161.2452 | 3155.103 | 3148.9726 | 3142.8542 | 3136.7476 | 3129.3799 | 3122.0295 | 3114.6964 | 3107.3805 | 3100.0817 | 3094.7377 | 3089.4029 | 3084.0773 | 3078.7608 | 3073.4535 | 3081.8845 | 3090.3386 | 3098.8159 | 3107.3164 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | 3115.8403 | [6 empty] | 568 | 572 | 576 | 580 | 583 | 589 | 595 | 601 | 607 | 613 | 618.6 | 621 | 623 | 625 | 627 | 629 | 631 | 633 | 635 | 637 | 639 | 641 | 643 | 645 | 647 | 649 | 651 | 653 | 655 | 657 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | 668 | [6 empty] | 3.3823 | 3.3823 | 3.3823 | 3.3823 | 3.3823 | 3.3684 | 3.3546 | 3.3408 | 3.3271 | 3.3135 | 3.2996 | 3.2858 | 3.272 | 3.2583 | 3.2446 | 3.2301 | 3.2156 | 3.2011 | 3.1868 | 3.1725 | 3.1579 | 3.1434 | 3.129 | 3.1147 | 3.1004 | 3.0858 | 3.0713 | 3.0568 | 3.0425 | 3.0282 | 3.0281 | 3.028 | 3.028 | 3.0279 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278 | 3.0278
80 | Upper Harbour |  |  | 2052 | 1128.769 | 1112.9338 | 1097.3208 | 1081.9268 | 1066.7487 | 1068.0054 | 1069.2636 | 1070.5233 | 1071.7845 | 1073.0471 | 1074.3283 | 1075.611 | 1076.8953 | 1078.1811 | 1079.4684 | 1080.6256 | 1081.7839 | 1082.9436 | 1084.1044 | 1085.2665 | 1086.2886 | 1087.3116 | 1088.3356 | 1089.3606 | 1090.3865 | 1091.6802 | 1092.9755 | 1094.2723 | 1095.5706 | 1096.8705 | 1098.0436 | 1099.218 | 1100.3937 | 1101.5706 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 | 1102.7487 |  | 3640 | 3588.9355 | 3538.5873 | 3488.9454 | 3440 | 3432.0399 | 3424.0982 | 3416.1748 | 3408.2698 | 3400.3831 | 3392.3569 | 3384.3497 | 3376.3613 | 3368.3918 | 3360.4412 | 3350.8517 | 3341.2896 | 3331.7548 | 3322.2473 | 3312.7668 | 3302.6367 | 3292.5375 | 3282.4693 | 3272.4318 | 3262.425 | 3252.9547 | 3243.5119 | 3234.0965 | 3224.7085 | 3215.3477 | 3218.6854 | 3222.0266 | 3225.3712 | 3228.7194 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | 3232.071 | [6 empty] | 731 | 737 | 743 | 749 | 755.3 | 765 | 775 | 785 | 795 | 805 | 812.8 | 817 | 822 | 827 | 832 | 837 | 842 | 847 | 852 | 857 | 862 | 867 | 872 | 877 | 882 | 887 | 892 | 897 | 902 | 907 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | 906.1 | [6 empty] | 3.2248 | 3.2248 | 3.2248 | 3.2248 | 3.2248 | 3.2135 | 3.2023 | 3.1911 | 3.18 | 3.1689 | 3.1577 | 3.1464 | 3.1353 | 3.1241 | 3.1131 | 3.1008 | 3.0887 | 3.0766 | 3.0645 | 3.0525 | 3.0403 | 3.0281 | 3.016 | 3.004 | 2.992 | 2.9798 | 2.9676 | 2.9555 | 2.9434 | 2.9314 | 2.9313 | 2.9312 | 2.9311 | 2.931 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309 | 2.9309
81 | Upper Harbour |  |  | 2052 | 582.9062 | 578.97 | 575.0605 | 571.1774 | 567.3204 | 569.9826 | 572.6574 | 575.3446 | 578.0445 | 580.757 | 583.4713 | 586.1983 | 588.938 | 591.6905 | 594.4558 | 596.9429 | 599.4404 | 601.9483 | 604.4667 | 606.9957 | 609.2136 | 611.4396 | 613.6737 | 615.916 | 618.1665 | 621.1469 | 624.1416 | 627.1507 | 630.1744 | 633.2127 | 636.0094 | 638.8185 | 641.64 | 644.474 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 | 647.3204 |  | 1870 | 1857.3727 | 1844.8306 | 1832.3732 | 1820 | 1821.4776 | 1822.9564 | 1824.4364 | 1825.9177 | 1827.4001 | 1828.7047 | 1830.0103 | 1831.3168 | 1832.6243 | 1833.9326 | 1833.5958 | 1833.2591 | 1832.9224 | 1832.5857 | 1832.2492 | 1830.7452 | 1829.2424 | 1827.7409 | 1826.2406 | 1824.7416 | 1825.2187 | 1825.6959 | 1826.1732 | 1826.6506 | 1827.1282 | 1835.3606 | 1843.6301 | 1851.9368 | 1860.2809 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | 1868.6627 | [6 empty] | 455 | 456 | 457 | 458 | 460.7 | 466 | 471 | 476 | 481 | 486 | 489.6 | 490 | 491 | 492 | 493 | 494 | 495 | 496 | 497 | 498 | 499 | 500 | 501 | 502 | 503 | 504 | 505 | 506 | 507 | 508 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | 504.3 | [6 empty] | 3.2081 | 3.2081 | 3.2081 | 3.2081 | 3.2081 | 3.1957 | 3.1833 | 3.171 | 3.1588 | 3.1466 | 3.1342 | 3.1218 | 3.1095 | 3.0973 | 3.0851 | 3.0716 | 3.0583 | 3.045 | 3.0317 | 3.0186 | 3.0051 | 2.9917 | 2.9784 | 2.9651 | 2.9519 | 2.9385 | 2.9251 | 2.9119 | 2.8986 | 2.8855 | 2.8857 | 2.886 | 2.8863 | 2.8865 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868 | 2.8868
82 | Upper Harbour |  |  | 2052 | 792.5742 | 784.2564 | 776.0259 | 767.8818 | 759.8232 | 762.4917 | 765.1695 | 767.8568 | 770.5535 | 773.2597 | 775.9803 | 778.7104 | 781.4501 | 784.1995 | 786.9585 | 789.4507 | 791.9507 | 794.4587 | 796.9746 | 799.4984 | 801.7202 | 803.9481 | 806.1823 | 808.4226 | 810.6692 | 813.6564 | 816.6545 | 819.6637 | 822.684 | 825.7154 | 828.5179 | 831.3298 | 834.1513 | 836.9824 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 | 839.8232 |  | 2420 | 2394.603 | 2369.4725 | 2344.6058 | 2320 | 2323.7866 | 2327.5793 | 2331.3782 | 2335.1834 | 2338.9947 | 2342.7888 | 2346.5891 | 2350.3956 | 2354.2082 | 2358.027 | 2359.4241 | 2360.822 | 2362.2207 | 2363.6203 | 2365.0206 | 2365.4551 | 2365.8896 | 2366.3242 | 2366.7589 | 2367.1937 | 2369.6327 | 2372.0741 | 2374.5181 | 2376.9646 | 2379.4136 | 2387.2786 | 2395.1696 | 2403.0867 | 2411.0299 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | 2418.9994 | [6 empty] | 572 | 576 | 580 | 584 | 589.9 | 596 | 602 | 608 | 614 | 620 | 626.8 | 630 | 633 | 636 | 639 | 642 | 645 | 648 | 651 | 654 | 657 | 660 | 663 | 666 | 669 | 672 | 675 | 678 | 681 | 684 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | 688.4 | [6 empty] | 3.0533 | 3.0533 | 3.0533 | 3.0533 | 3.0533 | 3.0476 | 3.0419 | 3.0362 | 3.0305 | 3.0248 | 3.0191 | 3.0134 | 3.0077 | 3.0021 | 2.9964 | 2.9887 | 2.981 | 2.9734 | 2.9657 | 2.9581 | 2.9505 | 2.9428 | 2.9352 | 2.9276 | 2.92 | 2.9123 | 2.9046 | 2.8969 | 2.8893 | 2.8816 | 2.8814 | 2.8811 | 2.8809 | 2.8806 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804 | 2.8804
83 | Upper Harbour |  |  | 2052 | 1240.7438 | 1235.0503 | 1229.383 | 1223.7416 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 | 1218.1261 |  | 3840 | 3822.3791 | 3804.839 | 3787.3795 | 3770 | 3773.0265 | 3776.0554 | 3779.0868 | 3782.1205 | 3785.1568 | 3788.1833 | 3791.2122 | 3794.2435 | 3797.2773 | 3800.3135 | 3798.866 | 3797.4191 | 3795.9727 | 3794.5269 | 3793.0816 | 3791.6341 | 3790.1872 | 3788.7408 | 3787.295 | 3785.8497 | 3784.4022 | 3782.9552 | 3781.5088 | 3780.063 | 3778.6177 | 3778.6178 | 3778.6178 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | 3778.6179 | [6 empty] | 548 | 552 | 556 | 560 | 565.7 | 572 | 579 | 586 | 593 | 600 | 604.8 | 608 | 612 | 616 | 620 | 624 | 628 | 632 | 636 | 640 | 644 | 648 | 652 | 656 | 660 | 664 | 668 | 672 | 676 | 680 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | 676.1 | [6 empty] | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0974 | 3.0999 | 3.1024 | 3.1049 | 3.1074 | 3.1098 | 3.1123 | 3.1148 | 3.1173 | 3.1198 | 3.1186 | 3.1174 | 3.1162 | 3.1151 | 3.1139 | 3.1127 | 3.1115 | 3.1103 | 3.1091 | 3.1079 | 3.1067 | 3.1056 | 3.1044 | 3.1032 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102 | 3.102
84 | Kaipatiki |  |  | 2052 | 1492.5421 | 1473.2252 | 1454.1584 | 1435.3383 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 | 1416.7618 |  | 4530 | 4471.3716 | 4413.502 | 4356.3814 | 4300 | 4303.2381 | 4306.4787 | 4309.7218 | 4312.9672 | 4316.2151 | 4319.4533 | 4322.6939 | 4325.9369 | 4329.1824 | 4332.4303 | 4330.4854 | 4328.5414 | 4326.5983 | 4324.656 | 4322.7146 | 4320.7697 | 4318.8257 | 4316.8826 | 4314.9403 | 4312.9989 | 4311.0541 | 4309.1101 | 4307.167 | 4305.2248 | 4303.2834 | 4303.2834 | 4303.2833 | 4303.2833 | 4303.2833 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | 4303.2832 | [6 empty] | 1263 | 1271 | 1279 | 1287 | 1294.3 | 1310 | 1325 | 1340 | 1355 | 1370 | 1386.6 | 1397 | 1407 | 1417 | 1427 | 1437 | 1447 | 1457 | 1467 | 1477 | 1487 | 1497 | 1507 | 1517 | 1527 | 1537 | 1547 | 1557 | 1567 | 1577 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | 1587.4 | [6 empty] | 3.0351 | 3.0351 | 3.0351 | 3.0351 | 3.0351 | 3.0374 | 3.0397 | 3.042 | 3.0442 | 3.0465 | 3.0488 | 3.0511 | 3.0534 | 3.0557 | 3.058 | 3.0566 | 3.0552 | 3.0539 | 3.0525 | 3.0511 | 3.0498 | 3.0484 | 3.047 | 3.0456 | 3.0443 | 3.0429 | 3.0415 | 3.0401 | 3.0388 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374 | 3.0374
85 | Kaipatiki |  |  | 2052 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 4.1858 | 5.779 | 7.9787 | 11.0157 | 15.2087 | 17.1367 | 19.3092 | 21.7571 | 24.5153 | 27.6232 | 29.6062 | 31.7315 | 34.0094 | 36.4508 | 39.0674 | 40.9293 | 42.8799 | 44.9234 | 47.0643 | 49.3073 | 51.8006 | 54.4199 | 57.1716 | 60.0626 | 63.0996 | 65.4969 | 67.9852 | 70.568 | 73.249 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 | 76.0318 |  | 10 | 10 | 10 | 10 | 10 | 12.346 | 15.2423 | 18.818 | 23.2327 | 28.683 | 31.7913 | 35.2365 | 39.055 | 43.2873 | 47.9783 | 51.0797 | 54.3815 | 57.8968 | 61.6394 | 65.6239 | 68.5153 | 71.5342 | 74.6861 | 77.9768 | 81.4126 | 85.2804 | 89.332 | 93.576 | 98.0217 | 102.6786 | 106.3886 | 110.2327 | 114.2156 | 118.3425 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | 122.6184 | [6 empty] | 1570 | 1579 | 1588 | 1597 | 1605.5 | 1625 | 1645 | 1665 | 1685 | 1705 | 1722.7 | 1735 | 1747 | 1759 | 1771 | 1783 | 1795 | 1807 | 1819 | 1831 | 1843 | 1855 | 1867 | 1879 | 1891 | 1903 | 1915 | 1927 | 1939 | 1951 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | 1966.6 | [6 empty] | 3.2984 | 3.2984 | 3.2984 | 3.2984 | 3.2984 | 2.9495 | 2.6375 | 2.3585 | 2.1091 | 1.886 | 1.8552 | 1.8249 | 1.795 | 1.7657 | 1.7369 | 1.7253 | 1.7138 | 1.7024 | 1.691 | 1.6798 | 1.674 | 1.6682 | 1.6625 | 1.6568 | 1.6511 | 1.6463 | 1.6415 | 1.6368 | 1.632 | 1.6272 | 1.6243 | 1.6214 | 1.6185 | 1.6156 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127 | 1.6127
86 | Kaipatiki |  |  | 2052 | 794.1129 | 785.7789 | 777.5325 | 769.3726 | 761.2983 | 762.1362 | 762.9751 | 763.8149 | 764.6556 | 765.4972 | 766.3515 | 767.2067 | 768.0629 | 768.92 | 769.7781 | 770.5921 | 771.407 | 772.2227 | 773.0393 | 773.8567 | 774.6 | 775.344 | 776.0887 | 776.8342 | 777.5803 | 778.4988 | 779.4183 | 780.339 | 781.2607 | 782.1835 | 783.0047 | 783.8268 | 784.6498 | 785.4736 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 | 786.2983 |  | 2420 | 2394.603 | 2369.4725 | 2344.6058 | 2320 | 2324.4254 | 2328.8593 | 2333.3016 | 2337.7523 | 2342.2116 | 2346.7072 | 2351.2114 | 2355.7242 | 2360.2457 | 2364.7759 | 2366.3612 | 2367.9475 | 2369.5349 | 2371.1233 | 2372.7128 | 2374.0768 | 2375.4415 | 2376.807 | 2378.1733 | 2379.5403 | 2381.4207 | 2383.3025 | 2385.1858 | 2387.0706 | 2388.9569 | 2391.413 | 2393.8717 | 2396.3329 | 2398.7966 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | 2401.2628 | [6 empty] | 204 | 205 | 206 | 207 | 206.5 | 209 | 212 | 215 | 218 | 221 | 224 | 226 | 228 | 230 | 232 | 234 | 236 | 238 | 240 | 242 | 244 | 246 | 248 | 250 | 252 | 254 | 256 | 258 | 260 | 262 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | 257.6 | [6 empty] | 3.0474 | 3.0474 | 3.0474 | 3.0474 | 3.0474 | 3.0499 | 3.0523 | 3.0548 | 3.0573 | 3.0597 | 3.0622 | 3.0646 | 3.0671 | 3.0696 | 3.072 | 3.0708 | 3.0696 | 3.0685 | 3.0673 | 3.0661 | 3.0649 | 3.0637 | 3.0625 | 3.0614 | 3.0602 | 3.059 | 3.0578 | 3.0566 | 3.0554 | 3.0542 | 3.0541 | 3.0541 | 3.054 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539 | 3.0539
87 | Kaipatiki |  |  | 2052 | 632.7219 | 634.386 | 636.0545 | 637.7274 | 639.4047 | 639.8241 | 640.2437 | 640.6636 | 641.0838 | 641.5042 | 641.9317 | 642.3595 | 642.7876 | 643.216 | 643.6446 | 644.052 | 644.4596 | 644.8674 | 645.2756 | 645.6839 | 646.0559 | 646.428 | 646.8004 | 647.173 | 647.5457 | 647.9643 | 648.3831 | 648.8022 | 649.2216 | 649.6413 | 649.9936 | 650.3461 | 650.6988 | 651.0517 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 | 651.4047 |  | 1920 | 1924.9806 | 1929.9741 | 1934.9806 | 1940 | 1940.7818 | 1941.5638 | 1942.3462 | 1943.1289 | 1943.912 | 1944.7151 | 1945.5185 | 1946.3222 | 1947.1263 | 1947.9307 | 1946.7569 | 1945.5837 | 1944.4112 | 1943.2395 | 1942.0684 | 1940.7745 | 1939.4814 | 1938.1891 | 1936.8978 | 1935.6073 | 1934.4368 | 1933.267 | 1932.098 | 1930.9297 | 1929.762 | 1930.7942 | 1931.827 | 1932.8603 | 1933.8942 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | 1934.9286 | [6 empty] | 3297 | 3316 | 3335 | 3354 | 3372.8 | 3414 | 3455 | 3496 | 3537 | 3578 | 3619.6 | 3646 | 3672 | 3698 | 3724 | 3750 | 3776 | 3802 | 3828 | 3854 | 3880 | 3906 | 3932 | 3958 | 3984 | 4010 | 4036 | 4062 | 4088 | 4114 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | 4141.7 | [6 empty] | 3.0345 | 3.0344 | 3.0343 | 3.0342 | 3.0341 | 3.0333 | 3.0325 | 3.0318 | 3.031 | 3.0302 | 3.0295 | 3.0287 | 3.0279 | 3.0272 | 3.0264 | 3.0227 | 3.0189 | 3.0152 | 3.0115 | 3.0078 | 3.004 | 3.0003 | 2.9966 | 2.9929 | 2.9891 | 2.9854 | 2.9817 | 2.9779 | 2.9742 | 2.9705 | 2.9705 | 2.9705 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704
88 | Kaipatiki |  |  | 2052 | 1327.4008 | 1317.6278 | 1307.9269 | 1298.2973 | 1288.7386 | 1289.5773 | 1290.4166 | 1291.2564 | 1292.0967 | 1292.9376 | 1293.7926 | 1294.6482 | 1295.5044 | 1296.3611 | 1297.2184 | 1298.0331 | 1298.8483 | 1299.6641 | 1300.4803 | 1301.2971 | 1302.0409 | 1302.7852 | 1303.5299 | 1304.2751 | 1305.0207 | 1305.94 | 1306.86 | 1307.7806 | 1308.7019 | 1309.6239 | 1310.4458 | 1311.2682 | 1312.0912 | 1312.9146 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 | 1313.7386 |  | 4120 | 4089.6666 | 4059.5566 | 4029.6683 | 4000 | 4003.8989 | 4007.8015 | 4011.708 | 4015.6183 | 4019.5324 | 4023.4902 | 4027.4519 | 4031.4176 | 4035.3871 | 4039.3606 | 4038.7528 | 4038.145 | 4037.5374 | 4036.9298 | 4036.3223 | 4035.4773 | 4034.6324 | 4033.7877 | 4032.9432 | 4032.0988 | 4031.7729 | 4031.4469 | 4031.1211 | 4030.7952 | 4030.4694 | 4032.9767 | 4035.4856 | 4037.9961 | 4040.5081 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | 4043.0217 | [6 empty] | 779 | 784 | 789 | 794 | 799.4 | 810 | 820 | 830 | 840 | 850 | 860.6 | 868 | 876 | 884 | 892 | 900 | 908 | 916 | 924 | 932 | 940 | 948 | 956 | 964 | 972 | 980 | 988 | 996 | 1004 | 1012 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | 1018.4 | [6 empty] | 3.1038 | 3.1038 | 3.1038 | 3.1038 | 3.1038 | 3.1048 | 3.1058 | 3.1068 | 3.1078 | 3.1088 | 3.1098 | 3.1108 | 3.1119 | 3.1129 | 3.1139 | 3.1114 | 3.109 | 3.1066 | 3.1042 | 3.1018 | 3.0993 | 3.0969 | 3.0945 | 3.0921 | 3.0897 | 3.0873 | 3.0848 | 3.0824 | 3.08 | 3.0776 | 3.0776 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775 | 3.0775
89 | Kaipatiki |  |  | 2052 | 976.9622 | 967.6284 | 958.3838 | 949.2276 | 940.1588 | 942.3322 | 944.5106 | 946.694 | 948.8825 | 951.076 | 953.2917 | 955.5126 | 957.7386 | 959.9699 | 962.2063 | 964.2037 | 966.2053 | 968.2111 | 970.221 | 972.235 | 973.9974 | 975.7629 | 977.5316 | 979.3035 | 981.0786 | 983.4494 | 985.826 | 988.2083 | 990.5963 | 992.9901 | 995.2139 | 997.4426 | 999.6763 | 1001.9151 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 | 1004.1588 |  | 2920 | 2892.1028 | 2864.472 | 2837.1053 | 2810 | 2818.9895 | 2828.0077 | 2837.0548 | 2846.1308 | 2855.2359 | 2864.4106 | 2873.6148 | 2882.8486 | 2892.1121 | 2901.4053 | 2906.4627 | 2911.529 | 2916.6041 | 2921.688 | 2926.7808 | 2931.1211 | 2935.4678 | 2939.8209 | 2944.1805 | 2948.5465 | 2954.6761 | 2960.8183 | 2966.9734 | 2973.1412 | 2979.3218 | 2985.9115 | 2992.5157 | 2999.1345 | 3005.768 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | 3012.4161 | [6 empty] | 359 | 361 | 363 | 365 | 367.2 | 372 | 377 | 382 | 387 | 392 | 394.3 | 398 | 401 | 404 | 407 | 410 | 413 | 416 | 419 | 422 | 425 | 428 | 431 | 434 | 437 | 440 | 443 | 446 | 449 | 452 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | 462.2 | [6 empty] | 2.9889 | 2.9889 | 2.9889 | 2.9889 | 2.9889 | 2.9915 | 2.9942 | 2.9968 | 2.9995 | 3.0021 | 3.0048 | 3.0074 | 3.0101 | 3.0127 | 3.0154 | 3.0144 | 3.0134 | 3.0124 | 3.0114 | 3.0104 | 3.0094 | 3.0084 | 3.0074 | 3.0064 | 3.0054 | 3.0044 | 3.0034 | 3.0024 | 3.0014 | 3.0004 | 3.0003 | 3.0002 | 3.0001 | 3 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999 | 2.9999
90 | Kaipatiki |  |  | 2052 | 2329.9252 | 2305.1264 | 2280.5916 | 2256.318 | 2232.3026 | 2233.1418 | 2233.9813 | 2234.821 | 2235.6612 | 2236.5016 | 2237.3571 | 2238.2129 | 2239.0691 | 2239.9256 | 2240.7824 | 2241.5976 | 2242.413 | 2243.2287 | 2244.0447 | 2244.8611 | 2245.6053 | 2246.3498 | 2247.0945 | 2247.8394 | 2248.5847 | 2249.5868 | 2250.5895 | 2251.5925 | 2252.5961 | 2253.6 | 2254.5398 | 2255.4799 | 2256.4204 | 2257.3613 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 | 2258.3026 |  | 7160 | 7083.7919 | 7008.395 | 6933.8005 | 6860 | 6824.538 | 6789.2592 | 6754.1629 | 6719.248 | 6684.5135 | 6648.9458 | 6613.5673 | 6578.3771 | 6543.3741 | 6508.5574 | 6473.6452 | 6438.9204 | 6404.3818 | 6370.0285 | 6335.8594 | 6300.6013 | 6265.5393 | 6230.6725 | 6195.9997 | 6161.5198 | 6126.8266 | 6092.3286 | 6058.0249 | 6023.9144 | 5989.9959 | 5992.4893 | 5994.9836 | 5997.479 | 5999.9754 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | 6002.4729 | [6 empty] | 820 | 825 | 830 | 835 | 841.6 | 852 | 863 | 874 | 885 | 896 | 905.4 | 913 | 921 | 929 | 937 | 945 | 953 | 961 | 969 | 977 | 985 | 993 | 1001 | 1009 | 1017 | 1025 | 1033 | 1041 | 1049 | 1057 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | 1063.6 | [6 empty] | 3.0731 | 3.0731 | 3.0731 | 3.0731 | 3.0731 | 3.056 | 3.0391 | 3.0222 | 3.0055 | 2.9888 | 2.9718 | 2.9548 | 2.938 | 2.9212 | 2.9046 | 2.888 | 2.8714 | 2.855 | 2.8386 | 2.8224 | 2.8057 | 2.7892 | 2.7728 | 2.7564 | 2.7402 | 2.7235 | 2.707 | 2.6906 | 2.6742 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658 | 2.658
91 | Kaipatiki |  |  | 2052 | 1543.0369 | 1525.2346 | 1507.6376 | 1490.2437 | 1473.0504 | 1481.7644 | 1490.53 | 1499.3475 | 1508.2171 | 1517.1392 | 1526.0244 | 1534.9616 | 1543.9511 | 1552.9933 | 1562.0884 | 1570.248 | 1578.4502 | 1586.6953 | 1594.9834 | 1603.3148 | 1610.6024 | 1617.9231 | 1625.277 | 1632.6644 | 1640.0854 | 1649.8732 | 1659.7195 | 1669.6245 | 1679.5887 | 1689.6123 | 1698.7995 | 1708.0366 | 1717.3239 | 1726.6618 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 | 1736.0504 |  | 4630 | 4576.5827 | 4523.7816 | 4471.5897 | 4420 | 4441.5982 | 4463.302 | 4485.1118 | 4507.0282 | 4529.0517 | 4550.905 | 4572.8637 | 4594.9284 | 4617.0995 | 4639.3776 | 4654.858 | 4670.3901 | 4685.974 | 4701.6099 | 4717.2979 | 4729.8079 | 4742.3511 | 4754.9275 | 4767.5373 | 4780.1805 | 4799.4827 | 4818.8628 | 4838.3211 | 4857.8581 | 4877.4739 | 4903.6793 | 4930.0256 | 4956.5134 | 4983.1435 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | 5009.9167 | [6 empty] | 1782 | 1800 | 1818 | 1836 | 1854.2 | 1878 | 1902 | 1926 | 1950 | 1974 | 1995.5 | 2016 | 2036 | 2056 | 2076 | 2096 | 2116 | 2136 | 2156 | 2176 | 2196 | 2216 | 2236 | 2256 | 2276 | 2296 | 2316 | 2336 | 2356 | 2376 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | 2402.7 | [6 empty] | 3.0006 | 3.0006 | 3.0006 | 3.0006 | 3.0006 | 2.9975 | 2.9944 | 2.9914 | 2.9883 | 2.9853 | 2.9822 | 2.9791 | 2.9761 | 2.973 | 2.97 | 2.9644 | 2.9588 | 2.9533 | 2.9477 | 2.9422 | 2.9367 | 2.9311 | 2.9256 | 2.9201 | 2.9146 | 2.909 | 2.9034 | 2.8978 | 2.8923 | 2.8867 | 2.8866 | 2.8864 | 2.8862 | 2.886 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858 | 2.8858
92 | Kaipatiki |  |  | 2052 | 1434.6855 | 1416.711 | 1398.9616 | 1381.4346 | 1364.1272 | 1365.2172 | 1366.3081 | 1367.3998 | 1368.4924 | 1369.5859 | 1370.6971 | 1371.8092 | 1372.9222 | 1374.0362 | 1375.151 | 1376.1843 | 1377.2184 | 1378.2532 | 1379.2889 | 1380.3253 | 1381.2549 | 1382.1852 | 1383.1161 | 1384.0476 | 1384.9798 | 1386.2314 | 1387.4841 | 1388.7379 | 1389.9929 | 1391.249 | 1392.4227 | 1393.5973 | 1394.773 | 1395.9496 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 | 1397.1272 |  | 4270 | 4216.503 | 4163.6763 | 4111.5114 | 4060 | 4061.5158 | 4063.0323 | 4064.5492 | 4066.0668 | 4067.5849 | 4069.1497 | 4070.7151 | 4072.2811 | 4073.8478 | 4075.415 | 4072.8513 | 4070.2893 | 4067.7288 | 4065.17 | 4062.6128 | 4059.7046 | 4056.7985 | 4053.8945 | 4050.9926 | 4048.0927 | 4046.0792 | 4044.0666 | 4042.0551 | 4040.0446 | 4038.035 | 4041.4158 | 4044.7994 | 4048.1858 | 4051.5751 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | 4054.9672 | [6 empty] | 707 | 712 | 717 | 722 | 727.9 | 737 | 746 | 755 | 764 | 773 | 782.9 | 790 | 797 | 804 | 811 | 818 | 825 | 832 | 839 | 846 | 853 | 860 | 867 | 874 | 881 | 888 | 895 | 902 | 909 | 916 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | 922.1 | [6 empty] | 2.9763 | 2.9763 | 2.9763 | 2.9763 | 2.9763 | 2.975 | 2.9737 | 2.9725 | 2.9712 | 2.9699 | 2.9687 | 2.9674 | 2.9661 | 2.9649 | 2.9636 | 2.9595 | 2.9554 | 2.9514 | 2.9473 | 2.9432 | 2.9391 | 2.9351 | 2.931 | 2.9269 | 2.9229 | 2.9188 | 2.9147 | 2.9106 | 2.9065 | 2.9025 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024 | 2.9024
93 | Kaipatiki |  |  | 2052 | 233.8564 | 233.1312 | 232.4083 | 231.6877 | 230.9693 | 232.0508 | 233.1374 | 234.2291 | 235.3259 | 236.4279 | 237.5306 | 238.6384 | 239.7514 | 240.8696 | 241.993 | 243.0191 | 244.0496 | 245.0844 | 246.1237 | 247.1673 | 248.0913 | 249.0187 | 249.9496 | 250.8839 | 251.8218 | 252.9825 | 254.1485 | 255.3199 | 256.4966 | 257.6789 | 258.7284 | 259.7821 | 260.8402 | 261.9026 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 | 262.9693 |  | 810 | 807.4883 | 804.9845 | 802.4884 | 800 | 803.4549 | 806.9247 | 810.4095 | 813.9094 | 817.4244 | 820.9453 | 824.4814 | 828.0328 | 831.5994 | 835.1814 | 837.6378 | 840.1014 | 842.5723 | 845.0504 | 847.5358 | 849.6264 | 851.7223 | 853.8233 | 855.9295 | 858.0409 | 860.8563 | 863.6809 | 866.5148 | 869.358 | 872.2106 | 875.555 | 878.9122 | 882.2823 | 885.6653 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | 889.0613 | [6 empty] | 2052 | 2063 | 2074 | 2085 | 2095.9 | 2122 | 2148 | 2174 | 2200 | 2226 | 2253.1 | 2269 | 2285 | 2301 | 2317 | 2333 | 2349 | 2365 | 2381 | 2397 | 2413 | 2429 | 2445 | 2461 | 2477 | 2493 | 2509 | 2525 | 2541 | 2557 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | 2575.2 | [6 empty] | 3.4637 | 3.4637 | 3.4637 | 3.4637 | 3.4637 | 3.4624 | 3.4612 | 3.4599 | 3.4586 | 3.4574 | 3.4562 | 3.4549 | 3.4537 | 3.4525 | 3.4513 | 3.4468 | 3.4423 | 3.4379 | 3.4334 | 3.429 | 3.4247 | 3.4203 | 3.416 | 3.4117 | 3.4073 | 3.4028 | 3.3983 | 3.3938 | 3.3894 | 3.3849 | 3.3841 | 3.3833 | 3.3825 | 3.3817 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809 | 3.3809
94 | Kaipatiki |  |  | 2052 | 6.0635 | 6.0635 | 6.0635 | 6.0635 | 6.0635 | 7.2148 | 8.5846 | 10.2145 | 12.1538 | 14.4614 | 15.8709 | 17.4178 | 19.1154 | 20.9785 | 23.0231 | 24.4125 | 25.8857 | 27.4478 | 29.1042 | 30.8606 | 32.1454 | 33.4837 | 34.8777 | 36.3298 | 37.8423 | 39.4907 | 41.2108 | 43.0059 | 44.8791 | 46.834 | 48.3751 | 49.9669 | 51.6111 | 53.3094 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 | 55.0635 |  | 40 | 40 | 40 | 40 | 40 | 43.7882 | 47.9353 | 52.475 | 57.4447 | 62.8851 | 67.0759 | 71.546 | 76.3139 | 81.3996 | 86.8243 | 90.845 | 95.0518 | 99.4535 | 104.0591 | 108.8779 | 112.6114 | 116.4729 | 120.4669 | 124.5978 | 128.8703 | 133.6762 | 138.6613 | 143.8323 | 149.1962 | 154.7601 | 159.1092 | 163.5805 | 168.1775 | 172.9037 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | 177.7627 | [6 empty] | 3003 | 3018 | 3033 | 3048 | 3062.5 | 3100 | 3137 | 3174 | 3211 | 3248 | 3286.2 | 3309 | 3332 | 3355 | 3378 | 3401 | 3424 | 3447 | 3470 | 3493 | 3516 | 3539 | 3562 | 3585 | 3608 | 3631 | 3654 | 3677 | 3700 | 3723 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | 3738.1 | [6 empty] | 6.5968 | 6.5968 | 6.5968 | 6.5968 | 6.5968 | 6.0693 | 5.5839 | 5.1373 | 4.7265 | 4.3485 | 4.2263 | 4.1076 | 3.9923 | 3.8802 | 3.7712 | 3.7212 | 3.672 | 3.6234 | 3.5754 | 3.5281 | 3.5032 | 3.4785 | 3.454 | 3.4296 | 3.4055 | 3.385 | 3.3647 | 3.3445 | 3.3244 | 3.3044 | 3.2891 | 3.2738 | 3.2586 | 3.2434 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283 | 3.2283
95 | Kaipatiki |  |  | 2052 | 554.8366 | 559.288 | 563.775 | 568.2981 | 572.8574 | 574.4442 | 576.0353 | 577.6309 | 579.2309 | 580.8354 | 582.4531 | 584.0753 | 585.702 | 587.3332 | 588.969 | 590.4981 | 592.0312 | 593.5683 | 595.1094 | 596.6544 | 598.0443 | 599.4374 | 600.8337 | 602.2333 | 603.6362 | 605.4239 | 607.2169 | 609.0152 | 610.8189 | 612.6279 | 614.265 | 615.9065 | 617.5524 | 619.2027 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 | 620.8574 |  | 1560 | 1572.3525 | 1584.8028 | 1597.3517 | 1610 | 1614.2585 | 1618.5283 | 1622.8093 | 1627.1017 | 1631.4054 | 1635.7457 | 1640.0974 | 1644.4608 | 1648.8357 | 1653.2224 | 1655.6315 | 1658.0441 | 1660.4602 | 1662.8798 | 1665.303 | 1667.2812 | 1669.2617 | 1671.2445 | 1673.2297 | 1675.2173 | 1678.2417 | 1681.2716 | 1684.3069 | 1687.3478 | 1690.3941 | 1694.8567 | 1699.331 | 1703.8172 | 1708.3152 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | 1712.8251 | [6 empty] | 1581 | 1590 | 1599 | 1608 | 1616.7 | 1636 | 1656 | 1676 | 1696 | 1716 | 1735.3 | 1748 | 1761 | 1774 | 1787 | 1800 | 1813 | 1826 | 1839 | 1852 | 1865 | 1878 | 1891 | 1904 | 1917 | 1930 | 1943 | 1956 | 1969 | 1982 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | 1988.1 | [6 empty] | 2.8116 | 2.8113 | 2.8111 | 2.8108 | 2.8105 | 2.8101 | 2.8098 | 2.8094 | 2.8091 | 2.8087 | 2.8084 | 2.808 | 2.8077 | 2.8073 | 2.807 | 2.8038 | 2.8006 | 2.7974 | 2.7942 | 2.7911 | 2.7879 | 2.7847 | 2.7815 | 2.7784 | 2.7752 | 2.772 | 2.7688 | 2.7656 | 2.7624 | 2.7593 | 2.7592 | 2.7591 | 2.759 | 2.7589 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588 | 2.7588
96 | Kaipatiki |  |  | 2052 | 1623.7447 | 1605.8377 | 1588.1282 | 1570.614 | 1553.293 | 1555.971 | 1558.6537 | 1561.341 | 1564.033 | 1566.7296 | 1569.4598 | 1572.1948 | 1574.9345 | 1577.679 | 1580.4284 | 1582.9284 | 1585.4324 | 1587.9404 | 1590.4523 | 1592.9682 | 1595.1962 | 1597.4272 | 1599.6613 | 1601.8986 | 1604.139 | 1607.137 | 1610.1406 | 1613.1499 | 1616.1647 | 1619.1852 | 1621.997 | 1624.8136 | 1627.6352 | 1630.4616 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 | 1633.293 |  | 4840 | 4786.6235 | 4733.8357 | 4681.63 | 4630 | 4643.9383 | 4657.9185 | 4671.9409 | 4686.0054 | 4700.1123 | 4714.31 | 4728.5506 | 4742.8341 | 4757.1609 | 4771.5309 | 4778.9834 | 4786.4476 | 4793.9234 | 4801.4109 | 4808.9101 | 4815.5514 | 4822.2019 | 4828.8615 | 4835.5304 | 4842.2084 | 4851.1454 | 4860.0988 | 4869.0688 | 4878.0554 | 4887.0585 | 4895.4403 | 4903.8364 | 4912.247 | 4920.6719 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | 4929.1114 | [6 empty] | 620 | 624 | 628 | 632 | 636.3 | 644 | 651 | 658 | 665 | 672 | 681.2 | 688 | 694 | 700 | 706 | 712 | 718 | 724 | 730 | 736 | 742 | 748 | 754 | 760 | 766 | 772 | 778 | 784 | 790 | 796 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | 807.7 | [6 empty] | 2.9808 | 2.9808 | 2.9808 | 2.9808 | 2.9808 | 2.9846 | 2.9884 | 2.9923 | 2.9961 | 3 | 3.0038 | 3.0076 | 3.0114 | 3.0153 | 3.0191 | 3.0191 | 3.019 | 3.019 | 3.0189 | 3.0188 | 3.0188 | 3.0187 | 3.0187 | 3.0186 | 3.0186 | 3.0185 | 3.0184 | 3.0184 | 3.0183 | 3.0182 | 3.0182 | 3.0181 | 3.018 | 3.018 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179 | 3.0179
97 | Kaipatiki |  |  | 2052 | 1263.7424 | 1254.1382 | 1244.6069 | 1235.1481 | 1225.7611 | 1229.7658 | 1233.7836 | 1237.8146 | 1241.8587 | 1245.916 | 1249.9988 | 1254.095 | 1258.2046 | 1262.3276 | 1266.4642 | 1270.2672 | 1274.0816 | 1277.9075 | 1281.7449 | 1285.5938 | 1289.0198 | 1292.455 | 1295.8993 | 1299.3528 | 1302.8155 | 1307.3407 | 1311.8817 | 1316.4384 | 1321.011 | 1325.5995 | 1329.805 | 1334.0239 | 1338.2562 | 1342.5019 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 | 1346.7611 |  | 3660 | 3632.1845 | 3604.5804 | 3577.1861 | 3550 | 3567.5304 | 3585.1474 | 3602.8514 | 3620.6428 | 3638.5221 | 3656.4755 | 3674.5176 | 3692.6487 | 3710.8692 | 3729.1796 | 3741.3799 | 3753.62 | 3765.9002 | 3778.2206 | 3790.5812 | 3801.7029 | 3812.8572 | 3824.0442 | 3835.264 | 3846.5167 | 3860.9055 | 3875.3481 | 3889.8447 | 3904.3955 | 3919.0008 | 3931.4075 | 3943.8535 | 3956.3388 | 3968.8637 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | 3981.4283 | [6 empty] | 529 | 533 | 537 | 541 | 545.2 | 552 | 558 | 564 | 570 | 576 | 583.7 | 589 | 594 | 599 | 604 | 609 | 614 | 619 | 624 | 629 | 634 | 639 | 644 | 649 | 654 | 659 | 664 | 669 | 674 | 679 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | 689.8 | [6 empty] | 2.8962 | 2.8962 | 2.8962 | 2.8962 | 2.8962 | 2.901 | 2.9058 | 2.9107 | 2.9155 | 2.9204 | 2.9252 | 2.93 | 2.9349 | 2.9397 | 2.9446 | 2.9453 | 2.9461 | 2.9469 | 2.9477 | 2.9485 | 2.9493 | 2.9501 | 2.9509 | 2.9517 | 2.9525 | 2.9533 | 2.954 | 2.9548 | 2.9556 | 2.9564 | 2.9564 | 2.9564 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563 | 2.9563
98 | Kaipatiki |  |  | 2052 | 1128.7722 | 1116.5145 | 1104.3898 | 1092.3969 | 1080.5341 | 1081.2889 | 1082.0441 | 1082.8 | 1083.5563 | 1084.3132 | 1085.0826 | 1085.8526 | 1086.6232 | 1087.3943 | 1088.1659 | 1088.8863 | 1089.6072 | 1090.3286 | 1091.0504 | 1091.7727 | 1092.4236 | 1093.0748 | 1093.7265 | 1094.3785 | 1095.0309 | 1095.9072 | 1096.7842 | 1097.6619 | 1098.5402 | 1099.4193 | 1100.2411 | 1101.0634 | 1101.8864 | 1102.7099 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 | 1103.5341 |  | 3510 | 3471.8836 | 3434.1811 | 3396.8881 | 3360 | 3361.743 | 3363.487 | 3365.2318 | 3366.9776 | 3368.7242 | 3370.5082 | 3372.2931 | 3374.0789 | 3375.8657 | 3377.6535 | 3375.9311 | 3374.2097 | 3372.4891 | 3370.7694 | 3369.0506 | 3367.0921 | 3365.1347 | 3363.1785 | 3361.2234 | 3359.2694 | 3357.9649 | 3356.6609 | 3355.3575 | 3354.0545 | 3352.7521 | 3355.2098 | 3357.6693 | 3360.1307 | 3362.5938 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | 3365.0588 | [6 empty] | 350 | 352 | 354 | 356 | 358 | 362 | 366 | 370 | 374 | 378 | 384.2 | 387 | 390 | 393 | 396 | 399 | 402 | 405 | 408 | 411 | 414 | 417 | 420 | 423 | 426 | 429 | 432 | 435 | 438 | 441 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | 445.3 | [6 empty] | 3.1096 | 3.1096 | 3.1096 | 3.1096 | 3.1096 | 3.109 | 3.1085 | 3.1079 | 3.1073 | 3.1068 | 3.1062 | 3.1057 | 3.1051 | 3.1045 | 3.104 | 3.1004 | 3.0967 | 3.0931 | 3.0895 | 3.0859 | 3.0822 | 3.0786 | 3.075 | 3.0714 | 3.0677 | 3.0641 | 3.0605 | 3.0568 | 3.0532 | 3.0496 | 3.0495 | 3.0495 | 3.0494 | 3.0494 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493 | 3.0493
99 | Kaipatiki |  |  | 2052 | 1069.2126 | 1057.9983 | 1046.9017 | 1035.9214 | 1025.0563 | 1026.3965 | 1027.7384 | 1029.082 | 1030.4274 | 1031.7746 | 1033.1409 | 1034.5089 | 1035.8788 | 1037.2505 | 1038.624 | 1039.875 | 1041.1275 | 1042.3814 | 1043.6369 | 1044.8939 | 1046.0086 | 1047.1245 | 1048.2416 | 1049.3599 | 1050.4793 | 1051.9797 | 1053.4821 | 1054.9867 | 1056.4935 | 1058.0024 | 1059.4095 | 1060.8184 | 1062.2291 | 1063.6418 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 | 1065.0563 |  | 3390 | 3354.4445 | 3319.262 | 3284.4484 | 3250 | 3251.1474 | 3252.2951 | 3253.4433 | 3254.5919 | 3255.7409 | 3256.9287 | 3258.117 | 3259.3056 | 3260.4948 | 3261.6843 | 3259.8307 | 3257.9782 | 3256.1267 | 3254.2763 | 3252.4269 | 3250.1033 | 3247.7813 | 3245.4611 | 3243.1424 | 3240.8255 | 3239.5709 | 3238.3168 | 3237.0631 | 3235.81 | 3234.5573 | 3238.6477 | 3242.7433 | 3246.844 | 3250.9499 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | 3255.061 | [6 empty] | 953 | 960 | 967 | 974 | 982.7 | 996 | 1009 | 1022 | 1035 | 1048 | 1059.6 | 1068 | 1077 | 1086 | 1095 | 1104 | 1113 | 1122 | 1131 | 1140 | 1149 | 1158 | 1167 | 1176 | 1185 | 1194 | 1203 | 1212 | 1221 | 1230 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | 1230.5 | [6 empty] | 3.1706 | 3.1706 | 3.1706 | 3.1706 | 3.1706 | 3.1675 | 3.1645 | 3.1615 | 3.1585 | 3.1555 | 3.1525 | 3.1494 | 3.1464 | 3.1434 | 3.1404 | 3.1348 | 3.1293 | 3.1237 | 3.1182 | 3.1127 | 3.1071 | 3.1016 | 3.0961 | 3.0906 | 3.0851 | 3.0795 | 3.0739 | 3.0683 | 3.0628 | 3.0572 | 3.057 | 3.0568 | 3.0566 | 3.0564 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562 | 3.0562
100 | Kaipatiki |  |  | 2052 | 2085.7332 | 2064.8868 | 2044.2488 | 2023.8171 | 2003.5896 | 2005.2663 | 2006.9445 | 2008.6241 | 2010.3051 | 2011.9874 | 2013.6969 | 2015.4078 | 2017.1201 | 2018.8339 | 2020.5492 | 2022.1142 | 2023.6805 | 2025.248 | 2026.8167 | 2028.3866 | 2029.781 | 2031.1764 | 2032.5728 | 2033.9701 | 2035.3684 | 2037.1635 | 2038.9603 | 2040.7586 | 2042.5585 | 2044.36 | 2046.0033 | 2047.6479 | 2049.2938 | 2050.941 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 | 2052.5896 |  | 5840 | 5781.6307 | 5723.8449 | 5666.6365 | 5610 | 5592.6616 | 5575.3768 | 5558.1454 | 5540.9673 | 5523.8423 | 5506.4056 | 5489.024 | 5471.6973 | 5454.4253 | 5437.2078 | 5418.0363 | 5398.9324 | 5379.8958 | 5360.9264 | 5342.0238 | 5322.2245 | 5302.4985 | 5282.8457 | 5263.2657 | 5243.7583 | 5224.8122 | 5205.9346 | 5187.1252 | 5168.3837 | 5149.71 | 5153.8112 | 5157.9156 | 5162.0234 | 5166.1344 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | 5170.2486 | [6 empty] | 685 | 690 | 695 | 700 | 705.2 | 714 | 722 | 730 | 738 | 746 | 756.1 | 763 | 770 | 777 | 784 | 791 | 798 | 805 | 812 | 819 | 826 | 833 | 840 | 847 | 854 | 861 | 868 | 875 | 882 | 889 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | 894.3 | [6 empty] | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.789 | 2.778 | 2.7671 | 2.7563 | 2.7455 | 2.7345 | 2.7235 | 2.7126 | 2.7018 | 2.691 | 2.6794 | 2.6679 | 2.6564 | 2.645 | 2.6336 | 2.6221 | 2.6106 | 2.5991 | 2.5877 | 2.5763 | 2.5647 | 2.5532 | 2.5418 | 2.5303 | 2.519 | 2.519 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189 | 2.5189
101 | Kaipatiki |  |  | 2052 | 1435.6914 | 1420.3824 | 1405.2366 | 1390.2523 | 1375.4278 | 1376.099 | 1376.7705 | 1377.4423 | 1378.1145 | 1378.787 | 1379.4712 | 1380.1558 | 1380.8408 | 1381.5261 | 1382.2117 | 1382.8381 | 1383.4648 | 1384.0918 | 1384.7191 | 1385.3466 | 1385.9047 | 1386.4631 | 1387.0216 | 1387.5804 | 1388.1393 | 1388.8908 | 1389.6427 | 1390.395 | 1391.1478 | 1391.9009 | 1392.6056 | 1393.3106 | 1394.016 | 1394.7217 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 | 1395.4278 |  | 4050 | 4006.8142 | 3964.0888 | 3921.819 | 3880 | 3872.223 | 3864.4616 | 3856.7158 | 3848.9855 | 3841.2707 | 3833.4829 | 3825.711 | 3817.9548 | 3810.2143 | 3802.4895 | 3792.387 | 3782.3113 | 3772.2624 | 3762.2402 | 3752.2447 | 3741.8991 | 3731.5821 | 3721.2935 | 3711.0333 | 3700.8014 | 3690.9316 | 3681.0881 | 3671.2709 | 3661.4799 | 3651.715 | 3653.6023 | 3655.4905 | 3657.3798 | 3659.27 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | 3661.1612 | [6 empty] | 396 | 399 | 402 | 405 | 408.7 | 413 | 418 | 423 | 428 | 433 | 436.3 | 440 | 444 | 448 | 452 | 456 | 460 | 464 | 468 | 472 | 476 | 480 | 484 | 488 | 492 | 496 | 500 | 504 | 508 | 512 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | 510.2 | [6 empty] | 2.8209 | 2.8209 | 2.8209 | 2.8209 | 2.8209 | 2.8139 | 2.8069 | 2.7999 | 2.7929 | 2.786 | 2.779 | 2.7719 | 2.7649 | 2.758 | 2.751 | 2.7425 | 2.7339 | 2.7254 | 2.717 | 2.7085 | 2.7 | 2.6914 | 2.6829 | 2.6745 | 2.666 | 2.6575 | 2.6489 | 2.6405 | 2.632 | 2.6235 | 2.6236 | 2.6236 | 2.6236 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237 | 2.6237
102 | Kaipatiki |  |  | 2052 | 1796.2409 | 1778.7486 | 1761.4267 | 1744.2735 | 1727.2873 | 1728.1263 | 1728.9656 | 1729.8054 | 1730.6456 | 1731.4862 | 1732.3416 | 1733.1973 | 1734.0535 | 1734.9101 | 1735.7671 | 1736.5821 | 1737.3974 | 1738.2131 | 1739.0292 | 1739.8457 | 1740.5898 | 1741.3342 | 1742.0789 | 1742.824 | 1743.5693 | 1744.489 | 1745.4091 | 1746.3298 | 1747.2509 | 1748.1725 | 1748.9947 | 1749.8173 | 1750.6402 | 1751.4636 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 | 1752.2873 |  | 5210 | 5159.2637 | 5109.0214 | 5059.2685 | 5010 | 4995.0845 | 4980.2134 | 4965.3866 | 4950.6039 | 4935.8652 | 4920.9096 | 4905.9993 | 4891.1342 | 4876.3141 | 4861.5389 | 4844.8787 | 4828.2755 | 4811.7293 | 4795.2397 | 4778.8067 | 4761.8639 | 4744.9811 | 4728.1582 | 4711.395 | 4694.6912 | 4678.1288 | 4661.6248 | 4645.179 | 4628.7913 | 4612.4614 | 4614.5999 | 4616.7394 | 4618.8799 | 4621.0214 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | 4623.1638 | [6 empty] | 580 | 585 | 590 | 595 | 599.4 | 607 | 614 | 621 | 628 | 635 | 644.3 | 650 | 656 | 662 | 668 | 674 | 680 | 686 | 692 | 698 | 704 | 710 | 716 | 722 | 728 | 734 | 740 | 746 | 752 | 758 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | [6 empty] | 2.9005 | 2.9005 | 2.9005 | 2.9005 | 2.9005 | 2.8905 | 2.8805 | 2.8705 | 2.8606 | 2.8507 | 2.8406 | 2.8306 | 2.8206 | 2.8107 | 2.8008 | 2.7899 | 2.779 | 2.7682 | 2.7574 | 2.7467 | 2.7358 | 2.7249 | 2.7141 | 2.7033 | 2.6926 | 2.6817 | 2.6708 | 2.66 | 2.6492 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384 | 2.6384
103 | Kaipatiki |  |  | 2052 | 1399.5557 | 1395.8871 | 1392.2281 | 1388.5787 | 1384.9389 | 1388.365 | 1391.7996 | 1395.2427 | 1398.6944 | 1402.1545 | 1405.6474 | 1409.149 | 1412.6593 | 1416.1783 | 1419.7061 | 1422.9209 | 1426.1429 | 1429.3722 | 1432.6088 | 1435.8528 | 1438.727 | 1441.6071 | 1444.4928 | 1447.3844 | 1450.2817 | 1454.0664 | 1457.861 | 1461.6654 | 1465.4798 | 1469.3042 | 1472.8143 | 1476.3328 | 1479.8598 | 1483.3951 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 | 1486.9389 |  | 3830 | 3819.9606 | 3809.9475 | 3799.9607 | 3790 | 3794.111 | 3798.2264 | 3802.3463 | 3806.4706 | 3810.5994 | 3814.7647 | 3818.9345 | 3823.1089 | 3827.2878 | 3831.4713 | 3832.0005 | 3832.5298 | 3833.0592 | 3833.5887 | 3834.1182 | 3833.6261 | 3833.1339 | 3832.6419 | 3832.1499 | 3831.658 | 3833.2594 | 3834.8616 | 3836.4644 | 3838.0678 | 3839.672 | 3848.2644 | 3856.8761 | 3865.507 | 3874.1573 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | 3882.8269 | [6 empty] | 721 | 727 | 733 | 739 | 744.6 | 753 | 761 | 769 | 777 | 785 | 795 | 802 | 809 | 816 | 823 | 830 | 837 | 844 | 851 | 858 | 865 | 872 | 879 | 886 | 893 | 900 | 907 | 914 | 921 | 928 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | 932.4 | [6 empty] | 2.7366 | 2.7366 | 2.7366 | 2.7366 | 2.7366 | 2.7328 | 2.729 | 2.7252 | 2.7214 | 2.7177 | 2.7139 | 2.7101 | 2.7063 | 2.7025 | 2.6988 | 2.6931 | 2.6873 | 2.6816 | 2.6759 | 2.6703 | 2.6646 | 2.6589 | 2.6533 | 2.6476 | 2.642 | 2.6362 | 2.6305 | 2.6247 | 2.619 | 2.6133 | 2.6129 | 2.6125 | 2.6121 | 2.6117 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113 | 2.6113
104 | Kaipatiki |  |  | 2052 | 1240.8169 | 1217.8525 | 1195.3131 | 1173.1908 | 1151.478 | 1162.2749 | 1173.1729 | 1184.1732 | 1195.2766 | 1206.4841 | 1217.4971 | 1228.6106 | 1239.8256 | 1251.1429 | 1262.5635 | 1272.6521 | 1282.8212 | 1293.0716 | 1303.4039 | 1313.8187 | 1322.8174 | 1331.8777 | 1341.0001 | 1350.185 | 1359.4328 | 1371.5042 | 1383.6828 | 1395.9696 | 1408.3654 | 1420.8713 | 1432.2102 | 1443.6396 | 1455.1603 | 1466.7728 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 | 1478.478 |  | 3750 | 3680.5969 | 3612.4784 | 3545.6205 | 3480 | 3500.2294 | 3520.5764 | 3541.0416 | 3561.6258 | 3582.3297 | 3602.0124 | 3621.8033 | 3641.7028 | 3661.7118 | 3681.8306 | 3696.3154 | 3710.8572 | 3725.4561 | 3740.1125 | 3754.8266 | 3764.9642 | 3775.1292 | 3785.3217 | 3795.5416 | 3805.7892 | 3823.4927 | 3841.2786 | 3859.1472 | 3877.099 | 3895.1342 | 3926.5128 | 3958.1442 | 3990.0303 | 4022.1734 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | 4054.5754 | [6 empty] | 1274 | 1284 | 1294 | 1304 | 1314.7 | 1331 | 1347 | 1363 | 1379 | 1395 | 1411 | 1424 | 1437 | 1450 | 1463 | 1476 | 1489 | 1502 | 1515 | 1528 | 1541 | 1554 | 1567 | 1580 | 1593 | 1606 | 1619 | 1632 | 1645 | 1658 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | 1665.5 | [6 empty] | 3.0222 | 3.0222 | 3.0222 | 3.0222 | 3.0222 | 3.0115 | 3.0009 | 2.9903 | 2.9798 | 2.9692 | 2.9585 | 2.9479 | 2.9373 | 2.9267 | 2.9162 | 2.9044 | 2.8927 | 2.8811 | 2.8695 | 2.8579 | 2.8462 | 2.8344 | 2.8228 | 2.8111 | 2.7995 | 2.7878 | 2.7761 | 2.7645 | 2.7529 | 2.7414 | 2.7416 | 2.7418 | 2.742 | 2.7422 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424 | 2.7424
105 | Kaipatiki |  |  | 2052 | 1237.1157 | 1224.7096 | 1212.4279 | 1200.2693 | 1188.2327 | 1193.4769 | 1198.7442 | 1204.0347 | 1209.3487 | 1214.686 | 1220.0326 | 1225.4028 | 1230.7966 | 1236.2141 | 1241.6555 | 1246.6015 | 1251.5672 | 1256.5527 | 1261.558 | 1266.5832 | 1271.0204 | 1275.473 | 1279.9413 | 1284.4252 | 1288.9248 | 1294.8069 | 1300.7159 | 1306.6518 | 1312.6148 | 1318.605 | 1324.0848 | 1329.5874 | 1335.1128 | 1340.6613 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 | 1346.2327 |  | 3290 | 3257.007 | 3224.3449 | 3192.0103 | 3160 | 3174.5652 | 3189.1975 | 3203.8973 | 3218.6648 | 3233.5004 | 3248.3627 | 3263.2933 | 3278.2925 | 3293.3607 | 3308.4981 | 3318.6705 | 3328.8742 | 3339.1092 | 3349.3757 | 3359.6737 | 3368.3624 | 3377.0736 | 3385.8074 | 3394.5637 | 3403.3426 | 3415.7628 | 3428.2283 | 3440.7392 | 3453.2958 | 3465.8983 | 3480.4166 | 3494.9957 | 3509.6359 | 3524.3374 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | 3539.1005 | [6 empty] | 519 | 524 | 529 | 534 | 537.8 | 545 | 552 | 559 | 566 | 573 | 579 | 584 | 589 | 594 | 599 | 604 | 609 | 614 | 619 | 624 | 629 | 634 | 639 | 644 | 649 | 654 | 659 | 664 | 669 | 674 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | 684.2 | [6 empty] | 2.6594 | 2.6594 | 2.6594 | 2.6594 | 2.6594 | 2.6599 | 2.6604 | 2.661 | 2.6615 | 2.662 | 2.6625 | 2.663 | 2.6636 | 2.6641 | 2.6646 | 2.6622 | 2.6598 | 2.6574 | 2.655 | 2.6525 | 2.6501 | 2.6477 | 2.6453 | 2.6429 | 2.6405 | 2.638 | 2.6356 | 2.6332 | 2.6309 | 2.6285 | 2.6285 | 2.6286 | 2.6287 | 2.6288 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289 | 2.6289
106 | Kaipatiki |  |  | 2052 | 204.6925 | 214.1838 | 224.1151 | 234.507 | 245.3807 | 260.2593 | 276.0401 | 292.7778 | 310.5304 | 329.3594 | 344.9378 | 361.2531 | 378.3401 | 396.2353 | 414.9769 | 429.5862 | 444.7099 | 460.366 | 476.5732 | 493.3511 | 506.5853 | 520.1745 | 534.1282 | 548.4562 | 563.1686 | 580.8329 | 599.0512 | 617.841 | 637.2202 | 657.2071 | 673.9652 | 691.1505 | 708.774 | 726.8469 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 | 745.3807 |  | 460 | 481.0155 | 502.9911 | 525.9706 | 550 | 586.7856 | 626.0316 | 667.9024 | 712.5737 | 760.2327 | 800.9482 | 843.8443 | 889.0378 | 936.6516 | 986.8155 | 1025.7536 | 1066.228 | 1108.2995 | 1152.0311 | 1197.4882 | 1234.6558 | 1272.977 | 1312.4877 | 1353.2246 | 1395.226 | 1444.7714 | 1496.0763 | 1549.203 | 1604.2163 | 1661.1832 | 1703.3659 | 1746.6198 | 1790.9721 | 1836.4506 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | 1883.084 | [6 empty] | 956 | 967 | 978 | 989 | 1000.8 | 1014 | 1028 | 1042 | 1056 | 1070 | 1081.9 | 1093 | 1105 | 1117 | 1129 | 1141 | 1153 | 1165 | 1177 | 1189 | 1201 | 1213 | 1225 | 1237 | 1249 | 1261 | 1273 | 1285 | 1297 | 1309 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | [6 empty] | 2.2473 | 2.2458 | 2.2443 | 2.2429 | 2.2414 | 2.2546 | 2.2679 | 2.2813 | 2.2947 | 2.3082 | 2.322 | 2.3359 | 2.3498 | 2.3639 | 2.378 | 2.3878 | 2.3976 | 2.4074 | 2.4173 | 2.4273 | 2.4372 | 2.4472 | 2.4573 | 2.4673 | 2.4775 | 2.4874 | 2.4974 | 2.5074 | 2.5175 | 2.5276 | 2.5274 | 2.5271 | 2.5269 | 2.5266 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263 | 2.5263
107 | Kaipatiki |  |  | 2052 | 891.3598 | 874.5165 | 857.9914 | 841.7786 | 825.8722 | 827.6283 | 829.3881 | 831.1516 | 832.9189 | 834.69 | 836.4802 | 838.2743 | 840.0723 | 841.8741 | 843.6798 | 845.3351 | 846.9937 | 848.6556 | 850.3207 | 851.989 | 853.4733 | 854.9601 | 856.4496 | 857.9416 | 859.4362 | 861.4331 | 863.4346 | 865.4407 | 867.4515 | 869.467 | 871.34 | 873.2169 | 875.098 | 876.983 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 | 878.8722 |  | 2450 | 2403.7042 | 2358.2833 | 2313.7206 | 2270 | 2278.3989 | 2286.8288 | 2295.29 | 2303.7824 | 2312.3063 | 2320.8763 | 2329.4781 | 2338.1118 | 2346.7774 | 2355.4752 | 2360.5703 | 2365.6765 | 2370.7936 | 2375.9219 | 2381.0612 | 2385.6925 | 2390.3328 | 2394.9822 | 2399.6406 | 2404.308 | 2410.37 | 2416.4472 | 2422.5397 | 2428.6476 | 2434.7709 | 2439.9692 | 2445.1787 | 2450.3993 | 2455.631 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | 2460.8739 | [6 empty] | 1077 | 1088 | 1099 | 1110 | 1119.2 | 1134 | 1149 | 1164 | 1179 | 1194 | 1206.6 | 1219 | 1231 | 1243 | 1255 | 1267 | 1279 | 1291 | 1303 | 1315 | 1327 | 1339 | 1351 | 1363 | 1375 | 1387 | 1399 | 1411 | 1423 | 1435 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | 1445.8 | [6 empty] | 2.7486 | 2.7486 | 2.7486 | 2.7486 | 2.7486 | 2.7529 | 2.7572 | 2.7616 | 2.7659 | 2.7703 | 2.7746 | 2.7789 | 2.7832 | 2.7876 | 2.7919 | 2.7925 | 2.793 | 2.7936 | 2.7941 | 2.7947 | 2.7953 | 2.7958 | 2.7964 | 2.797 | 2.7975 | 2.7981 | 2.7986 | 2.7992 | 2.7998 | 2.8003 | 2.8002 | 2.8002 | 2.8001 | 2.8001 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8
108 | Kaipatiki |  |  | 2052 | 1677.3957 | 1667.6815 | 1658.0235 | 1648.4215 | 1638.8751 | 1645.8693 | 1652.8935 | 1659.9475 | 1667.0317 | 1674.1461 | 1681.277 | 1688.4382 | 1695.63 | 1702.8524 | 1710.1055 | 1716.6388 | 1723.1971 | 1729.7804 | 1736.3889 | 1743.0227 | 1748.8483 | 1754.6933 | 1760.5579 | 1766.4421 | 1772.346 | 1780.1758 | 1788.0401 | 1795.9392 | 1803.8732 | 1811.8422 | 1819.189 | 1826.5655 | 1833.972 | 1841.4084 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 | 1848.8751 |  | 4790 | 4762.26 | 4734.6806 | 4707.2609 | 4680 | 4705.5998 | 4731.3396 | 4757.2203 | 4783.2425 | 4809.407 | 4835.6508 | 4862.0378 | 4888.5688 | 4915.2446 | 4942.066 | 4960.5397 | 4979.0824 | 4997.6945 | 5016.3762 | 5035.1276 | 5051.5998 | 5068.1258 | 5084.7059 | 5101.3403 | 5118.029 | 5140.169 | 5162.4047 | 5184.7365 | 5207.165 | 5229.6905 | 5250.4643 | 5271.3206 | 5292.2598 | 5313.2821 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | 5334.3879 | [6 empty] | 1123 | 1134 | 1145 | 1156 | 1168.8 | 1184 | 1200 | 1216 | 1232 | 1248 | 1261.9 | 1275 | 1288 | 1301 | 1314 | 1327 | 1340 | 1353 | 1366 | 1379 | 1392 | 1405 | 1418 | 1431 | 1444 | 1457 | 1470 | 1483 | 1496 | 1509 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | 1529.9 | [6 empty] | 2.8556 | 2.8556 | 2.8556 | 2.8556 | 2.8556 | 2.859 | 2.8625 | 2.8659 | 2.8693 | 2.8728 | 2.8762 | 2.8796 | 2.883 | 2.8865 | 2.8899 | 2.8897 | 2.8894 | 2.8892 | 2.889 | 2.8887 | 2.8885 | 2.8883 | 2.8881 | 2.8879 | 2.8877 | 2.8875 | 2.8872 | 2.8869 | 2.8867 | 2.8864 | 2.8862 | 2.8859 | 2.8857 | 2.8854 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852 | 2.8852
109 | Kaipatiki |  |  | 2052 | 1171.9088 | 1173.6553 | 1175.4044 | 1177.1562 | 1178.9105 | 1190.1165 | 1201.4291 | 1212.8492 | 1224.3778 | 1236.016 | 1247.4466 | 1258.9829 | 1270.6259 | 1282.3766 | 1294.2359 | 1304.7234 | 1315.296 | 1325.9542 | 1336.6987 | 1347.5304 | 1356.8945 | 1366.3237 | 1375.8184 | 1385.3791 | 1395.0063 | 1407.5673 | 1420.2414 | 1433.0296 | 1445.9329 | 1458.9525 | 1470.7517 | 1482.6463 | 1494.6371 | 1506.7249 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 | 1518.9105 |  | 3400 | 3404.989 | 3409.9853 | 3414.989 | 3420 | 3457.3004 | 3495.0076 | 3533.1261 | 3571.6603 | 3610.6148 | 3649.0647 | 3687.9241 | 3727.1974 | 3766.8888 | 3807.003 | 3838.1131 | 3869.4775 | 3901.0982 | 3932.9773 | 3965.1169 | 3993.0179 | 4021.1152 | 4049.4103 | 4077.9044 | 4106.599 | 4143.8447 | 4181.4282 | 4219.3526 | 4257.621 | 4296.2364 | 4330.5639 | 4365.1657 | 4400.044 | 4435.201 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | 4470.6388 | [6 empty] | 1498 | 1513 | 1528 | 1543 | 1557 | 1580 | 1603 | 1626 | 1649 | 1672 | 1694.8 | 1713 | 1732 | 1751 | 1770 | 1789 | 1808 | 1827 | 1846 | 1865 | 1884 | 1903 | 1922 | 1941 | 1960 | 1979 | 1998 | 2017 | 2036 | 2055 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | 2065.1 | [6 empty] | 2.9012 | 2.9012 | 2.9011 | 2.9011 | 2.901 | 2.905 | 2.909 | 2.9131 | 2.9171 | 2.9212 | 2.9252 | 2.9293 | 2.9334 | 2.9374 | 2.9415 | 2.9417 | 2.9419 | 2.9421 | 2.9423 | 2.9425 | 2.9428 | 2.943 | 2.9433 | 2.9435 | 2.9438 | 2.944 | 2.9442 | 2.9444 | 2.9445 | 2.9447 | 2.9445 | 2.9442 | 2.9439 | 2.9436 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433 | 2.9433
110 | Kaipatiki |  |  | 2052 | 324.82 | 331.2853 | 337.8792 | 344.6044 | 351.4635 | 378.8468 | 408.3636 | 440.1801 | 474.4755 | 511.4429 | 540.5549 | 571.324 | 603.8445 | 638.2161 | 674.5442 | 702.0792 | 730.7381 | 760.5669 | 791.6133 | 823.9271 | 848.9802 | 874.7951 | 901.395 | 928.8037 | 957.0458 | 990.4859 | 1025.0944 | 1060.9121 | 1097.9814 | 1136.3459 | 1168.1398 | 1200.8233 | 1234.4212 | 1268.9592 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 | 1304.4635 |  | 800 | 809.8178 | 819.7561 | 829.8163 | 840 | 889.8373 | 942.6315 | 998.5579 | 1057.8025 | 1120.562 | 1176.823 | 1235.9087 | 1297.9609 | 1363.1287 | 1431.5683 | 1485.8962 | 1542.2858 | 1600.8154 | 1661.5662 | 1724.6225 | 1777.4233 | 1831.8406 | 1887.924 | 1945.7244 | 2005.2944 | 2076.0257 | 2149.2518 | 2225.0608 | 2303.5437 | 2384.7949 | 2443.188 | 2503.0109 | 2564.2986 | 2627.087 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | 2691.4128 | [6 empty] | 3995 | 4036 | 4077 | 4118 | 4157.8 | 4210 | 4262 | 4314 | 4366 | 4418 | 4471.1 | 4518 | 4565 | 4612 | 4659 | 4706 | 4753 | 4800 | 4847 | 4894 | 4941 | 4988 | 5035 | 5082 | 5129 | 5176 | 5223 | 5270 | 5317 | 5364 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | 5408.4 | [6 empty] | 2.4629 | 2.4445 | 2.4262 | 2.408 | 2.39 | 2.3488 | 2.3083 | 2.2685 | 2.2294 | 2.191 | 2.1771 | 2.1632 | 2.1495 | 2.1358 | 2.1223 | 2.1164 | 2.1106 | 2.1048 | 2.099 | 2.0932 | 2.0936 | 2.094 | 2.0944 | 2.0949 | 2.0953 | 2.096 | 2.0966 | 2.0973 | 2.098 | 2.0987 | 2.0915 | 2.0844 | 2.0773 | 2.0703 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632 | 2.0632
111 | Kaipatiki |  |  | 2052 | 1171.3929 | 1146.966 | 1123.0486 | 1099.6298 | 1076.6995 | 1095.3567 | 1114.3372 | 1133.6466 | 1153.2906 | 1173.275 | 1192.3374 | 1211.7096 | 1231.3965 | 1251.4032 | 1271.7351 | 1289.2406 | 1306.987 | 1324.9777 | 1343.2161 | 1361.7055 | 1377.3532 | 1393.1807 | 1409.1901 | 1425.3835 | 1441.7629 | 1462.7114 | 1483.9643 | 1505.526 | 1527.401 | 1549.5938 | 1569.3069 | 1589.2709 | 1609.4888 | 1629.9639 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 | 1650.6995 |  | 3340 | 3270.3516 | 3202.1555 | 3135.3815 | 3070 | 3118.527 | 3167.821 | 3217.8943 | 3268.759 | 3320.4277 | 3369.3789 | 3419.0517 | 3469.4568 | 3520.605 | 3572.5072 | 3613.4788 | 3654.9203 | 3696.8371 | 3739.2345 | 3782.1183 | 3816.9226 | 3852.0472 | 3887.495 | 3923.2691 | 3959.3723 | 4007.6302 | 4056.4763 | 4105.9177 | 4155.9617 | 4206.6156 | 4259.6974 | 4313.4491 | 4367.879 | 4422.9957 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | 4478.8079 | [6 empty] | 543 | 547 | 551 | 555 | 560.1 | 569 | 578 | 587 | 596 | 605 | 611.5 | 618 | 624 | 630 | 636 | 642 | 648 | 654 | 660 | 666 | 672 | 678 | 684 | 690 | 696 | 702 | 708 | 714 | 720 | 726 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | 740.3 | [6 empty] | 2.8513 | 2.8513 | 2.8513 | 2.8513 | 2.8513 | 2.847 | 2.8428 | 2.8385 | 2.8343 | 2.8301 | 2.8259 | 2.8217 | 2.8175 | 2.8133 | 2.8092 | 2.8028 | 2.7964 | 2.7901 | 2.7838 | 2.7775 | 2.7712 | 2.7649 | 2.7587 | 2.7524 | 2.7462 | 2.7399 | 2.7335 | 2.7272 | 2.7209 | 2.7147 | 2.7144 | 2.7141 | 2.7138 | 2.7136 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133 | 2.7133
112 | Kaipatiki |  |  | 2052 | 939.8951 | 923.9509 | 908.2773 | 892.8695 | 877.723 | 878.6449 | 879.5677 | 880.4914 | 881.4162 | 882.3419 | 883.2817 | 884.2224 | 885.1642 | 886.107 | 887.0508 | 887.9591 | 888.8682 | 889.7783 | 890.6893 | 891.6013 | 892.4375 | 893.2745 | 894.1123 | 894.9509 | 895.7903 | 896.8339 | 897.8787 | 898.9247 | 899.972 | 901.0205 | 901.959 | 902.8986 | 903.8391 | 904.7806 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 | 905.723 |  | 2570 | 2526.4031 | 2483.5459 | 2441.4156 | 2400 | 2400.6326 | 2401.2655 | 2401.8984 | 2402.5316 | 2403.1649 | 2403.8261 | 2404.4875 | 2405.149 | 2405.8107 | 2406.4726 | 2404.9339 | 2403.3962 | 2401.8595 | 2400.3237 | 2398.7889 | 2397.021 | 2395.2543 | 2393.489 | 2391.7249 | 2389.9622 | 2388.6963 | 2387.431 | 2386.1665 | 2384.9026 | 2383.6393 | 2386.0639 | 2388.4909 | 2390.9203 | 2393.3523 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | 2395.7867 | [6 empty] | 765 | 772 | 779 | 786 | 794.4 | 804 | 814 | 824 | 834 | 844 | 851.9 | 860 | 868 | 876 | 884 | 892 | 900 | 908 | 916 | 924 | 932 | 940 | 948 | 956 | 964 | 972 | 980 | 988 | 996 | 1004 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | 1021.7 | [6 empty] | 2.7343 | 2.7343 | 2.7343 | 2.7343 | 2.7343 | 2.7322 | 2.7301 | 2.7279 | 2.7258 | 2.7236 | 2.7215 | 2.7193 | 2.7172 | 2.715 | 2.7129 | 2.7084 | 2.7039 | 2.6994 | 2.6949 | 2.6904 | 2.6859 | 2.6814 | 2.6769 | 2.6725 | 2.668 | 2.6635 | 2.659 | 2.6545 | 2.65 | 2.6455 | 2.6454 | 2.6454 | 2.6453 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452 | 2.6452
113 | Devonport - Takapuna |  |  | 2052 | 1185.6605 | 1176.7966 | 1167.999 | 1159.2672 | 1150.6006 | 1161.4782 | 1172.4586 | 1183.5428 | 1194.7318 | 1206.0266 | 1217.122 | 1228.3196 | 1239.6201 | 1251.0247 | 1262.5341 | 1272.714 | 1282.976 | 1293.3207 | 1303.7489 | 1314.2611 | 1323.3504 | 1332.5026 | 1341.7181 | 1350.9973 | 1360.3406 | 1372.4537 | 1384.6745 | 1397.0042 | 1409.4437 | 1421.9939 | 1433.333 | 1444.7624 | 1456.2831 | 1467.8955 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 | 1479.6006 |  | 3720 | 3692.1897 | 3664.5873 | 3637.1912 | 3610 | 3632.1644 | 3654.465 | 3676.9024 | 3699.4776 | 3722.1915 | 3743.9463 | 3765.8284 | 3787.8383 | 3809.9769 | 3832.2448 | 3848.5615 | 3864.9476 | 3881.4034 | 3897.9293 | 3914.5256 | 3926.5346 | 3938.5804 | 3950.6631 | 3962.7829 | 3974.9399 | 3994.5901 | 4014.3375 | 4034.1825 | 4054.1256 | 4074.1672 | 4106.1038 | 4138.2907 | 4170.7299 | 4203.4234 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | 4236.3731 | [6 empty] | 582 | 587 | 592 | 597 | 601.2 | 611 | 621 | 631 | 641 | 651 | 658.2 | 666 | 674 | 682 | 690 | 698 | 706 | 714 | 722 | 730 | 738 | 746 | 754 | 762 | 770 | 778 | 786 | 794 | 802 | 810 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | [6 empty] | 3.1375 | 3.1375 | 3.1375 | 3.1375 | 3.1375 | 3.1272 | 3.1169 | 3.1067 | 3.0965 | 3.0863 | 3.0761 | 3.0658 | 3.0556 | 3.0455 | 3.0354 | 3.0239 | 3.0125 | 3.0011 | 2.9898 | 2.9785 | 2.9671 | 2.9558 | 2.9445 | 2.9332 | 2.922 | 2.9105 | 2.8991 | 2.8877 | 2.8764 | 2.8651 | 2.8647 | 2.8643 | 2.864 | 2.8636 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632 | 2.8632
114 | Devonport - Takapuna |  |  | 2052 | 1322.5106 | 1309.0179 | 1295.6628 | 1282.444 | 1269.3601 | 1274.3593 | 1279.3781 | 1284.4168 | 1289.4753 | 1294.5537 | 1299.6504 | 1304.7673 | 1309.9042 | 1315.0614 | 1320.2389 | 1324.9713 | 1329.7206 | 1334.487 | 1339.2704 | 1344.071 | 1348.3261 | 1352.5947 | 1356.8768 | 1361.1724 | 1365.4817 | 1371.1202 | 1376.782 | 1382.4671 | 1388.1758 | 1393.908 | 1399.1587 | 1404.4292 | 1409.7195 | 1415.0298 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 | 1420.3601 |  | 4230 | 4186.844 | 4144.1284 | 4101.8485 | 4060 | 4070.9593 | 4081.9481 | 4092.9666 | 4104.0149 | 4115.0929 | 4126.1661 | 4137.269 | 4148.4019 | 4159.5647 | 4170.7575 | 4177.1602 | 4183.5728 | 4189.9952 | 4196.4275 | 4202.8696 | 4207.4896 | 4212.1146 | 4216.7448 | 4221.38 | 4226.0204 | 4234.6143 | 4243.2256 | 4251.8545 | 4260.5009 | 4269.165 | 4285.1479 | 4301.1907 | 4317.2935 | 4333.4566 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | 4349.6803 | [6 empty] | 674 | 680 | 686 | 692 | 696.5 | 705 | 714 | 723 | 732 | 741 | 750.2 | 758 | 766 | 774 | 782 | 790 | 798 | 806 | 814 | 822 | 830 | 838 | 846 | 854 | 862 | 870 | 878 | 886 | 894 | 902 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | 901.2 | [6 empty] | 3.1985 | 3.1985 | 3.1985 | 3.1985 | 3.1985 | 3.1945 | 3.1906 | 3.1866 | 3.1827 | 3.1788 | 3.1748 | 3.1709 | 3.167 | 3.163 | 3.1591 | 3.1526 | 3.1462 | 3.1398 | 3.1334 | 3.127 | 3.1205 | 3.1141 | 3.1077 | 3.1013 | 3.0949 | 3.0884 | 3.082 | 3.0756 | 3.0691 | 3.0627 | 3.0627 | 3.0626 | 3.0625 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624 | 3.0624
115 | Hibiscus and Bays |  |  | 2052 | 1739.583 | 1735.261 | 1730.9498 | 1726.6493 | 1722.3594 | 1731.7445 | 1741.1808 | 1750.6685 | 1760.2079 | 1769.7993 | 1779.3684 | 1788.9892 | 1798.6621 | 1808.3872 | 1818.1649 | 1826.9489 | 1835.7753 | 1844.6443 | 1853.5562 | 1862.5111 | 1870.3538 | 1878.2296 | 1886.1385 | 1894.0808 | 1902.0565 | 1912.5191 | 1923.0393 | 1933.6173 | 1944.2536 | 1954.9483 | 1964.7321 | 1974.5649 | 1984.4468 | 1994.3783 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 | 2004.3594 |  | 5050 | 5037.4533 | 5024.9378 | 5012.4534 | 5000 | 5007.2816 | 5014.5738 | 5021.8767 | 5029.1902 | 5036.5143 | 5043.2182 | 5049.9311 | 5056.6529 | 5063.3836 | 5070.1233 | 5072.3153 | 5074.5081 | 5076.702 | 5078.8968 | 5081.0925 | 5079.6234 | 5078.1547 | 5076.6864 | 5075.2185 | 5073.7511 | 5078.3454 | 5082.9439 | 5087.5465 | 5092.1534 | 5096.7644 | 5122.5387 | 5148.4434 | 5174.4791 | 5200.6464 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | 5226.9461 | [6 empty] | 1123 | 1131 | 1139 | 1147 | 1156.4 | 1170 | 1184 | 1198 | 1212 | 1226 | 1239 | 1250 | 1261 | 1272 | 1283 | 1294 | 1305 | 1316 | 1327 | 1338 | 1349 | 1360 | 1371 | 1382 | 1393 | 1404 | 1415 | 1426 | 1437 | 1448 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | 1449.9 | [6 empty] | 2.903 | 2.903 | 2.903 | 2.903 | 2.903 | 2.8915 | 2.88 | 2.8685 | 2.8572 | 2.8458 | 2.8343 | 2.8228 | 2.8113 | 2.7999 | 2.7886 | 2.7764 | 2.7642 | 2.7521 | 2.7401 | 2.7281 | 2.7159 | 2.7037 | 2.6916 | 2.6795 | 2.6675 | 2.6553 | 2.6432 | 2.6311 | 2.6191 | 2.6071 | 2.6072 | 2.6074 | 2.6075 | 2.6077 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078 | 2.6078
116 | Hibiscus and Bays |  |  | 2052 | 1108.8645 | 1100.3407 | 1091.8824 | 1083.4892 | 1075.1604 | 1081.7307 | 1088.3412 | 1094.9921 | 1101.6836 | 1108.416 | 1115.1154 | 1121.8553 | 1128.636 | 1135.4576 | 1142.3205 | 1148.4614 | 1154.6353 | 1160.8423 | 1167.0827 | 1173.3567 | 1178.8349 | 1184.3386 | 1189.868 | 1195.4233 | 1201.0044 | 1208.3616 | 1215.7638 | 1223.2114 | 1230.7046 | 1238.2437 | 1245.1496 | 1252.094 | 1259.0771 | 1266.0992 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 | 1273.1604 |  | 3290 | 3264.7099 | 3239.6142 | 3214.7114 | 3190 | 3196.3585 | 3202.7297 | 3209.1136 | 3215.5103 | 3221.9196 | 3227.8568 | 3233.8048 | 3239.7638 | 3245.7338 | 3251.7148 | 3254.5699 | 3257.4276 | 3260.2878 | 3263.1504 | 3266.0156 | 3266.2768 | 3266.538 | 3266.7992 | 3267.0604 | 3267.3216 | 3271.9469 | 3276.5787 | 3281.2171 | 3285.862 | 3290.5135 | 3308.7459 | 3327.0793 | 3345.5144 | 3364.0515 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | 3382.6914 | [6 empty] | 753 | 759 | 765 | 771 | 777.7 | 786 | 795 | 804 | 813 | 822 | 830 | 837 | 844 | 851 | 858 | 865 | 872 | 879 | 886 | 893 | 900 | 907 | 914 | 921 | 928 | 935 | 942 | 949 | 956 | 963 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | 972.9 | [6 empty] | 2.967 | 2.967 | 2.967 | 2.967 | 2.967 | 2.9549 | 2.9428 | 2.9307 | 2.9187 | 2.9068 | 2.8946 | 2.8826 | 2.8705 | 2.8585 | 2.8466 | 2.8339 | 2.8212 | 2.8086 | 2.796 | 2.7835 | 2.7708 | 2.7581 | 2.7455 | 2.733 | 2.7205 | 2.7078 | 2.6951 | 2.6825 | 2.6699 | 2.6574 | 2.6573 | 2.6572 | 2.6571 | 2.657 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569 | 2.6569
117 | Devonport - Takapuna |  |  | 2052 | 1860.6586 | 1837.8801 | 1815.3803 | 1793.1561 | 1771.2039 | 1777.2923 | 1783.4017 | 1789.5321 | 1795.6835 | 1801.8561 | 1808.0633 | 1814.2918 | 1820.5418 | 1826.8134 | 1833.1065 | 1838.8082 | 1844.5277 | 1850.2649 | 1856.02 | 1861.793 | 1866.8851 | 1871.991 | 1877.1109 | 1882.2448 | 1887.3928 | 1894.1578 | 1900.9471 | 1907.7608 | 1914.5988 | 1921.4614 | 1927.7684 | 1934.096 | 1940.4445 | 1946.8137 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 | 1953.2039 |  | 5200 | 5136.3405 | 5073.4604 | 5011.35 | 4950 | 4961.9205 | 4973.8696 | 4985.8476 | 4997.8544 | 5009.8901 | 5021.9645 | 5034.068 | 5046.2007 | 5058.3626 | 5070.5538 | 5076.7455 | 5082.9447 | 5089.1514 | 5095.3658 | 5101.5877 | 5105.8077 | 5110.0312 | 5114.2581 | 5118.4885 | 5122.7225 | 5131.2208 | 5139.7332 | 5148.2598 | 5156.8005 | 5165.3553 | 5182.3595 | 5199.4196 | 5216.5359 | 5233.7085 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | 5250.9377 | [6 empty] | 843 | 848 | 853 | 858 | 862.4 | 873 | 884 | 895 | 906 | 917 | 926 | 933 | 940 | 947 | 954 | 961 | 968 | 975 | 982 | 989 | 996 | 1003 | 1010 | 1017 | 1024 | 1031 | 1038 | 1045 | 1052 | 1059 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | 1070.3 | [6 empty] | 2.7947 | 2.7947 | 2.7947 | 2.7947 | 2.7947 | 2.7918 | 2.789 | 2.7861 | 2.7833 | 2.7804 | 2.7775 | 2.7747 | 2.7718 | 2.769 | 2.7661 | 2.7609 | 2.7557 | 2.7505 | 2.7453 | 2.7401 | 2.7349 | 2.7297 | 2.7245 | 2.7194 | 2.7142 | 2.709 | 2.7038 | 2.6986 | 2.6934 | 2.6882 | 2.6883 | 2.6883 | 2.6883 | 2.6883 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884 | 2.6884
118 | Devonport - Takapuna |  |  | 2052 | 1220.6101 | 1204.6289 | 1188.8571 | 1173.2917 | 1157.9301 | 1159.9386 | 1161.9506 | 1163.9661 | 1165.985 | 1168.0075 | 1170.0552 | 1172.1064 | 1174.1612 | 1176.2196 | 1178.2816 | 1180.2202 | 1182.1619 | 1184.1069 | 1186.055 | 1188.0063 | 1189.7698 | 1191.5359 | 1193.3046 | 1195.0759 | 1196.8499 | 1199.141 | 1201.4364 | 1203.7363 | 1206.0406 | 1208.3493 | 1210.4581 | 1212.5705 | 1214.6867 | 1216.8065 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 | 1218.9301 |  | 3700 | 3651.5569 | 3603.748 | 3556.5651 | 3510 | 3516.3863 | 3522.7842 | 3529.1938 | 3535.615 | 3542.0479 | 3548.5579 | 3555.0799 | 3561.6139 | 3568.1599 | 3574.7179 | 3577.1108 | 3579.5054 | 3581.9016 | 3584.2993 | 3586.6987 | 3588.5105 | 3590.3232 | 3592.1368 | 3593.9514 | 3595.7668 | 3599.0998 | 3602.4359 | 3605.775 | 3609.1173 | 3612.4626 | 3618.7241 | 3624.9965 | 3631.2797 | 3637.5738 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | 3643.8788 | [6 empty] | 484 | 486 | 488 | 490 | 492.2 | 498 | 504 | 510 | 516 | 522 | 529.6 | 533 | 537 | 541 | 545 | 549 | 553 | 557 | 561 | 565 | 569 | 573 | 577 | 581 | 585 | 589 | 593 | 597 | 601 | 605 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | 606.8 | [6 empty] | 3.0313 | 3.0313 | 3.0313 | 3.0313 | 3.0313 | 3.0315 | 3.0318 | 3.032 | 3.0323 | 3.0326 | 3.0328 | 3.0331 | 3.0333 | 3.0336 | 3.0338 | 3.0309 | 3.0279 | 3.025 | 3.022 | 3.0191 | 3.0161 | 3.0132 | 3.0102 | 3.0073 | 3.0044 | 3.0014 | 2.9984 | 2.9955 | 2.9925 | 2.9896 | 2.9895 | 2.9895 | 2.9895 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894 | 2.9894
119 | Devonport - Takapuna |  |  | 2052 | 1481.3676 | 1465.2459 | 1449.2996 | 1433.5268 | 1417.9257 | 1428.7601 | 1439.6773 | 1450.6778 | 1461.7625 | 1472.9318 | 1483.9807 | 1495.1124 | 1506.3277 | 1517.6271 | 1529.0112 | 1539.1275 | 1549.3107 | 1559.5613 | 1569.8797 | 1580.2664 | 1589.2857 | 1598.3564 | 1607.479 | 1616.6535 | 1625.8805 | 1637.9866 | 1650.1828 | 1662.4698 | 1674.8483 | 1687.319 | 1698.6862 | 1710.1299 | 1721.6507 | 1733.2492 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 | 1744.9257 |  | 4670 | 4619.1763 | 4568.9058 | 4519.1823 | 4470 | 4494.3342 | 4518.8008 | 4543.4006 | 4568.1344 | 4593.0027 | 4617.2812 | 4641.6879 | 4666.2237 | 4690.8892 | 4715.6851 | 4733.4576 | 4751.2971 | 4769.2039 | 4787.1781 | 4805.2201 | 4818.8471 | 4832.5127 | 4846.2171 | 4859.9604 | 4873.7427 | 4895.7157 | 4917.7878 | 4939.9595 | 4962.231 | 4984.603 | 5017.7788 | 5051.1753 | 5084.7941 | 5118.6366 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | 5152.7044 | [6 empty] | 817 | 824 | 831 | 838 | 845.6 | 855 | 865 | 875 | 885 | 895 | 903 | 912 | 921 | 930 | 939 | 948 | 957 | 966 | 975 | 984 | 993 | 1002 | 1011 | 1020 | 1029 | 1038 | 1047 | 1056 | 1065 | 1074 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | 1074.1 | [6 empty] | 3.1525 | 3.1525 | 3.1525 | 3.1525 | 3.1525 | 3.1456 | 3.1388 | 3.1319 | 3.1251 | 3.1183 | 3.1114 | 3.1046 | 3.0977 | 3.0909 | 3.0841 | 3.0754 | 3.0667 | 3.058 | 3.0494 | 3.0408 | 3.0321 | 3.0234 | 3.0148 | 3.0062 | 2.9976 | 2.9889 | 2.9801 | 2.9715 | 2.9628 | 2.9542 | 2.9539 | 2.9537 | 2.9534 | 2.9532 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953 | 2.953
120 | Devonport - Takapuna |  |  | 2052 | 1450.6269 | 1434.1086 | 1417.7783 | 1401.634 | 1385.6735 | 1388.3504 | 1391.0326 | 1393.7199 | 1396.4124 | 1399.1101 | 1401.8392 | 1404.5736 | 1407.3133 | 1410.0584 | 1412.8089 | 1415.308 | 1417.8115 | 1420.3195 | 1422.8319 | 1425.3487 | 1427.5759 | 1429.8066 | 1432.0408 | 1434.2784 | 1436.5195 | 1439.5162 | 1442.5192 | 1445.5284 | 1448.5439 | 1451.5657 | 1454.3764 | 1457.1924 | 1460.014 | 1462.841 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 | 1465.6735 |  | 4020 | 3974.224 | 3928.9693 | 3884.2299 | 3840 | 3852.3427 | 3864.7251 | 3877.1473 | 3889.6095 | 3902.1117 | 3914.6953 | 3927.3196 | 3939.9845 | 3952.6903 | 3965.4371 | 3972.3599 | 3979.2947 | 3986.2417 | 3993.2008 | 4000.172 | 4006.3415 | 4012.5205 | 4018.709 | 4024.907 | 4031.1146 | 4039.4158 | 4047.7341 | 4056.0695 | 4064.4221 | 4072.7919 | 4080.5776 | 4088.3783 | 4096.1938 | 4104.0243 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | 4111.8698 | [6 empty] | 930 | 938 | 946 | 954 | 963.4 | 978 | 993 | 1008 | 1023 | 1038 | 1051 | 1063 | 1075 | 1087 | 1099 | 1111 | 1123 | 1135 | 1147 | 1159 | 1171 | 1183 | 1195 | 1207 | 1219 | 1231 | 1243 | 1255 | 1267 | 1279 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | 1296.7 | [6 empty] | 2.7712 | 2.7712 | 2.7712 | 2.7712 | 2.7712 | 2.7748 | 2.7783 | 2.7819 | 2.7854 | 2.789 | 2.7925 | 2.7961 | 2.7996 | 2.8032 | 2.8068 | 2.8067 | 2.8066 | 2.8066 | 2.8065 | 2.8065 | 2.8064 | 2.8063 | 2.8063 | 2.8062 | 2.8062 | 2.8061 | 2.806 | 2.8059 | 2.8059 | 2.8058 | 2.8057 | 2.8057 | 2.8056 | 2.8055 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054 | 2.8054
121 | Devonport - Takapuna |  |  | 2052 | 651.8301 | 632.4663 | 613.6778 | 595.4474 | 577.7585 | 601.503 | 626.2233 | 651.9595 | 678.7534 | 706.6485 | 731.1679 | 756.538 | 782.7885 | 809.9498 | 838.0536 | 860.8268 | 884.2188 | 908.2465 | 932.9271 | 958.2784 | 978.7936 | 999.748 | 1021.1511 | 1043.0123 | 1065.3415 | 1092.737 | 1120.8369 | 1149.6594 | 1179.223 | 1209.5469 | 1235.4553 | 1261.9186 | 1288.9488 | 1316.558 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 | 1344.7585 |  | 1320 | 1280.787 | 1242.7389 | 1205.8211 | 1170 | 1229.9349 | 1292.9401 | 1359.1729 | 1428.7985 | 1501.9907 | 1571.2905 | 1643.7877 | 1719.6299 | 1798.9713 | 1881.9733 | 1948.4506 | 2017.276 | 2088.5325 | 2162.3061 | 2238.6856 | 2305.4991 | 2374.3067 | 2445.1679 | 2518.1439 | 2593.2979 | 2680.962 | 2771.5894 | 2865.2804 | 2962.1386 | 3062.2709 | 3124.9197 | 3188.8501 | 3254.0884 | 3320.6614 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | 3388.5963 | [6 empty] | 7595 | 7704 | 7813 | 7922 | 8031.8 | 8127 | 8222 | 8317 | 8412 | 8507 | 8602.2 | 8699 | 8796 | 8893 | 8990 | 9087 | 9184 | 9281 | 9378 | 9475 | 9572 | 9669 | 9766 | 9863 | 9960 | 10057 | 10154 | 10251 | 10348 | 10445 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | 10535.5 | [6 empty] | 2.0251 | 2.0251 | 2.0251 | 2.0251 | 2.0251 | 2.0448 | 2.0647 | 2.0848 | 2.105 | 2.1255 | 2.149 | 2.1728 | 2.1968 | 2.2211 | 2.2456 | 2.2635 | 2.2814 | 2.2995 | 2.3178 | 2.3362 | 2.3554 | 2.3749 | 2.3945 | 2.4143 | 2.4342 | 2.4534 | 2.4728 | 2.4923 | 2.5119 | 2.5318 | 2.5294 | 2.527 | 2.5246 | 2.5222 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199 | 2.5199
122 | Devonport - Takapuna |  |  | 2052 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 6.8885 | 15.6514 | 35.5616 | 80.7998 | 183.586 | 210.9413 | 242.3728 | 278.4878 | 319.9841 | 367.6636 | 396.5031 | 427.6048 | 461.1461 | 497.3184 | 536.328 | 563.4999 | 592.0483 | 622.043 | 653.5574 | 686.6684 | 723.0929 | 761.4495 | 801.8408 | 844.3747 | 889.1647 | 924.2567 | 960.7337 | 998.6503 | 1038.0633 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 | 1079.0318 |  | 0 | 0 | 0 | 0 | 0 | 55 | 195 | 301 | 460 | 579.8848 | 666.8209 | 766.7905 | 881.7475 | 1013.9388 | 1165.9482 | 1257.7179 | 1356.7107 | 1463.495 | 1578.6841 | 1702.9395 | 1789.4272 | 1880.3074 | 1975.8031 | 2076.1488 | 2181.5908 | 2297.5351 | 2419.6414 | 2548.2372 | 2683.6675 | 2826.2955 | 2938.0076 | 3054.1352 | 3174.8528 | 3300.342 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | 3430.7912 | [6 empty] | 3660 | 3707 | 3754 | 3801 | 3846.4 | 3898 | 3949 | 4000 | 4051 | 4102 | 4154.9 | 4198 | 4241 | 4284 | 4327 | 4370 | 4413 | 4456 | 4499 | 4542 | 4585 | 4628 | 4671 | 4714 | 4757 | 4800 | 4843 | 4886 | 4929 | 4972 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | 5019.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 7.9843 | 12.459 | 8.4642 | 5.6931 | 3.1587 | 3.1612 | 3.1637 | 3.1662 | 3.1687 | 3.1712 | 3.172 | 3.1728 | 3.1736 | 3.1744 | 3.1752 | 3.1756 | 3.1759 | 3.1763 | 3.1767 | 3.1771 | 3.1774 | 3.1777 | 3.178 | 3.1783 | 3.1786 | 3.1788 | 3.179 | 3.1791 | 3.1793 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795 | 3.1795
123 | Devonport - Takapuna |  |  | 2052 | 853.7922 | 842.3905 | 831.1411 | 820.042 | 809.091 | 814.7226 | 820.3934 | 826.1037 | 831.8537 | 837.6438 | 843.3865 | 849.1686 | 854.9903 | 860.8519 | 866.7537 | 878.5987 | 890.6056 | 902.7766 | 915.1139 | 927.6198 | 941.8827 | 956.3648 | 971.0696 | 986.0005 | 1001.1609 | 1030.8622 | 1061.4446 | 1092.9343 | 1125.3581 | 1158.7439 | 1192.0436 | 1226.3003 | 1261.5414 | 1297.7953 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 | 1335.091 |  | 1910 | 1884.4936 | 1859.3278 | 1834.4981 | 1810 | 1834.4925 | 1859.3164 | 1884.4762 | 1909.9765 | 1935.8218 | 1961.4281 | 1987.3732 | 2013.6615 | 2040.2974 | 2067.2858 | 2103.6573 | 2140.6688 | 2178.3315 | 2216.6568 | 2255.6564 | 2299.012 | 2343.201 | 2388.2392 | 2434.1432 | 2480.9295 | 2563.4365 | 2648.6875 | 2736.7736 | 2827.7891 | 2921.8316 | 3004.4088 | 3089.3199 | 3176.6307 | 3266.4091 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | 3358.7249 | [6 empty] | 1618 | 1635 | 1652 | 1669 | 1685.9 | 1709 | 1732 | 1755 | 1778 | 1801 | 1824.1 | 1844 | 1864 | 1884 | 1904 | 1924 | 1944 | 1964 | 1984 | 2004 | 2024 | 2044 | 2064 | 2084 | 2104 | 2124 | 2144 | 2164 | 2184 | 2204 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | 2219.1 | [6 empty] | 2.2371 | 2.2371 | 2.2371 | 2.2371 | 2.2371 | 2.2517 | 2.2664 | 2.2812 | 2.296 | 2.311 | 2.3257 | 2.3404 | 2.3552 | 2.3701 | 2.3851 | 2.3943 | 2.4036 | 2.4129 | 2.4223 | 2.4317 | 2.4409 | 2.4501 | 2.4594 | 2.4687 | 2.4781 | 2.4867 | 2.4954 | 2.5041 | 2.5128 | 2.5216 | 2.5204 | 2.5192 | 2.5181 | 2.5169 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157 | 2.5157
124 | Devonport - Takapuna |  |  | 2052 | 706.1404 | 698.8863 | 691.7068 | 684.601 | 677.5682 | 680.2345 | 682.9112 | 685.5985 | 688.2964 | 691.0048 | 693.7231 | 696.4521 | 699.1918 | 701.9423 | 704.7036 | 707.1939 | 709.693 | 712.201 | 714.7178 | 717.2435 | 719.4639 | 721.6911 | 723.9252 | 726.1663 | 728.4143 | 731.399 | 734.3959 | 737.4051 | 740.4266 | 743.4605 | 746.2608 | 749.0718 | 751.8933 | 754.7254 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 | 757.5682 |  | 1730 | 1712.228 | 1694.6386 | 1677.2299 | 1660 | 1670.388 | 1680.841 | 1691.3595 | 1701.9437 | 1712.5942 | 1723.2659 | 1734.0041 | 1744.8093 | 1755.6817 | 1766.6219 | 1774.2481 | 1781.9072 | 1789.5993 | 1797.3246 | 1805.0833 | 1812.0921 | 1819.1281 | 1826.1914 | 1833.2821 | 1840.4004 | 1849.36 | 1858.3632 | 1867.4103 | 1876.5013 | 1885.6367 | 1892.636 | 1899.6612 | 1906.7125 | 1913.79 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | 1920.8938 | [6 empty] | 423 | 427 | 431 | 435 | 437.3 | 443 | 449 | 455 | 461 | 467 | 472.3 | 477 | 482 | 487 | 492 | 497 | 502 | 507 | 512 | 517 | 522 | 527 | 532 | 537 | 542 | 547 | 552 | 557 | 562 | 567 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | 569.9 | [6 empty] | 2.4499 | 2.4499 | 2.4499 | 2.4499 | 2.4499 | 2.4556 | 2.4613 | 2.467 | 2.4727 | 2.4784 | 2.4841 | 2.4898 | 2.4955 | 2.5012 | 2.5069 | 2.5089 | 2.5108 | 2.5128 | 2.5147 | 2.5167 | 2.5187 | 2.5206 | 2.5226 | 2.5246 | 2.5266 | 2.5285 | 2.5305 | 2.5324 | 2.5344 | 2.5363 | 2.5362 | 2.536 | 2.5359 | 2.5357 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356 | 2.5356
125 | Devonport - Takapuna |  |  | 2052 | 857.9364 | 905.7707 | 956.2721 | 1009.5891 | 1065.8789 | 1099.0994 | 1133.3552 | 1168.6787 | 1205.1032 | 1242.6629 | 1276.7837 | 1311.8414 | 1347.8618 | 1384.8711 | 1422.8967 | 1454.4782 | 1486.7606 | 1519.7596 | 1553.491 | 1587.971 | 1616.3581 | 1645.2527 | 1674.6638 | 1704.6007 | 1735.0728 | 1772.9209 | 1811.5946 | 1851.112 | 1891.4913 | 1932.7515 | 1968.4348 | 2004.777 | 2041.79 | 2079.4865 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 | 2117.8789 |  | 1880 | 1983.6149 | 2092.9405 | 2208.2915 | 2330 | 2396.9015 | 2465.724 | 2536.5226 | 2609.354 | 2684.2766 | 2751.4988 | 2820.4044 | 2891.0356 | 2963.4356 | 3037.6487 | 3095.32 | 3154.0863 | 3213.9683 | 3274.9872 | 3337.1646 | 3386.1237 | 3435.801 | 3486.2072 | 3537.3528 | 3589.2488 | 3655.7576 | 3723.4988 | 3792.4953 | 3862.7702 | 3934.3474 | 4006.5721 | 4080.1226 | 4155.0234 | 4231.2992 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | 4308.9752 | [6 empty] | 5945 | 6017 | 6089 | 6161 | 6231.8 | 6318 | 6404 | 6490 | 6576 | 6662 | 6748.3 | 6824 | 6900 | 6976 | 7052 | 7128 | 7204 | 7280 | 7356 | 7432 | 7508 | 7584 | 7660 | 7736 | 7812 | 7888 | 7964 | 8040 | 8116 | 8192 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | 8268.9 | [6 empty] | 2.1913 | 2.19 | 2.1886 | 2.1873 | 2.186 | 2.1808 | 2.1756 | 2.1704 | 2.1653 | 2.1601 | 2.155 | 2.15 | 2.1449 | 2.1399 | 2.1348 | 2.1281 | 2.1214 | 2.1148 | 2.1081 | 2.1015 | 2.0949 | 2.0883 | 2.0817 | 2.0752 | 2.0686 | 2.062 | 2.0554 | 2.0488 | 2.0422 | 2.0356 | 2.0354 | 2.0352 | 2.035 | 2.0348 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346 | 2.0346
126 | Devonport - Takapuna |  |  | 2052 | 802.9868 | 786.7565 | 770.8542 | 755.2734 | 740.0074 | 766.6562 | 794.2647 | 822.8674 | 852.5001 | 883.1999 | 910.6386 | 938.9297 | 968.0998 | 998.1761 | 1029.1867 | 1054.638 | 1080.7186 | 1107.4443 | 1134.8308 | 1162.8946 | 1185.804 | 1209.1648 | 1232.9858 | 1257.2761 | 1282.0449 | 1312.6459 | 1343.9774 | 1376.0567 | 1408.9018 | 1442.5308 | 1471.4436 | 1500.936 | 1531.0195 | 1561.7059 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 | 1593.0074 |  | 2040 | 1998.7666 | 1958.3667 | 1918.7833 | 1880 | 1950.3569 | 2023.3469 | 2099.0684 | 2177.6237 | 2259.1189 | 2333.667 | 2410.675 | 2490.2243 | 2572.3986 | 2657.2845 | 2724.7309 | 2793.8893 | 2864.8029 | 2937.5165 | 3012.0757 | 3074.1406 | 3137.4843 | 3202.1333 | 3268.1143 | 3335.455 | 3417.9411 | 3502.467 | 3589.0833 | 3677.8417 | 3768.795 | 3842.4954 | 3917.6369 | 3994.248 | 4072.3571 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | 4151.9938 | [6 empty] | 814 | 822 | 830 | 838 | 847.6 | 860 | 872 | 884 | 896 | 908 | 920.9 | 930 | 939 | 948 | 957 | 966 | 975 | 984 | 993 | 1002 | 1011 | 1020 | 1029 | 1038 | 1047 | 1056 | 1065 | 1074 | 1083 | 1092 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | 1109.5 | [6 empty] | 2.5405 | 2.5405 | 2.5405 | 2.5405 | 2.5405 | 2.544 | 2.5474 | 2.5509 | 2.5544 | 2.5579 | 2.5627 | 2.5675 | 2.5723 | 2.5771 | 2.5819 | 2.5836 | 2.5852 | 2.5869 | 2.5885 | 2.5902 | 2.5925 | 2.5948 | 2.5971 | 2.5994 | 2.6017 | 2.6039 | 2.606 | 2.6082 | 2.6104 | 2.6126 | 2.6114 | 2.6101 | 2.6089 | 2.6076 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064 | 2.6064
127 | Devonport - Takapuna |  |  | 2052 | 133.3977 | 127.6589 | 122.167 | 116.9114 | 111.8819 | 130.1452 | 151.3897 | 176.1022 | 204.8486 | 238.2875 | 259.8077 | 283.2714 | 308.8542 | 336.7475 | 367.1598 | 388.2102 | 410.4674 | 434.0008 | 458.8834 | 485.1926 | 504.6112 | 524.8069 | 545.8109 | 567.6556 | 590.3745 | 616.325 | 643.4161 | 671.6981 | 701.2232 | 732.0461 | 756.8714 | 782.5386 | 809.0763 | 836.5139 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 | 864.8819 |  | 310 | 296.6638 | 283.9014 | 271.688 | 260 | 302.0376 | 350.8719 | 407.602 | 473.5043 | 550.0619 | 603.7743 | 662.7316 | 727.4459 | 798.4794 | 876.4492 | 932.0025 | 991.077 | 1053.8959 | 1120.6965 | 1191.7312 | 1246.9702 | 1304.7695 | 1365.2479 | 1428.5297 | 1494.7446 | 1569.7772 | 1648.5763 | 1731.3309 | 1818.2395 | 1909.5108 | 1973.6193 | 2039.8801 | 2108.3655 | 2179.1501 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | 2252.3113 | [6 empty] | 2162 | 2187 | 2212 | 2237 | 2262 | 2292 | 2322 | 2352 | 2382 | 2412 | 2443 | 2470 | 2497 | 2524 | 2551 | 2578 | 2605 | 2632 | 2659 | 2686 | 2713 | 2740 | 2767 | 2794 | 2821 | 2848 | 2875 | 2902 | 2929 | 2956 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | 2987.6 | [6 empty] | 2.3239 | 2.3239 | 2.3239 | 2.3239 | 2.3239 | 2.3208 | 2.3177 | 2.3146 | 2.3115 | 2.3084 | 2.3239 | 2.3396 | 2.3553 | 2.3712 | 2.3871 | 2.4008 | 2.4145 | 2.4283 | 2.4422 | 2.4562 | 2.4712 | 2.4862 | 2.5013 | 2.5165 | 2.5319 | 2.547 | 2.5622 | 2.5775 | 2.593 | 2.6085 | 2.6076 | 2.6067 | 2.6059 | 2.605 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042 | 2.6042
128 | Devonport - Takapuna |  |  | 2052 | 582.5245 | 580.142 | 577.7691 | 575.406 | 573.0526 | 594.9895 | 617.7662 | 641.4148 | 665.9687 | 691.4625 | 714.0781 | 737.4334 | 761.5525 | 786.4605 | 812.1832 | 833.2005 | 854.7616 | 876.8806 | 899.5721 | 922.8508 | 941.7922 | 961.1224 | 980.8493 | 1000.9811 | 1021.5262 | 1046.8234 | 1072.7471 | 1099.3127 | 1126.5363 | 1154.434 | 1178.3463 | 1202.754 | 1227.6673 | 1253.0966 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 | 1279.0526 |  | 1230 | 1224.9692 | 1219.959 | 1214.9693 | 1210 | 1256.0409 | 1303.8336 | 1353.4449 | 1404.9438 | 1458.4024 | 1506.3192 | 1555.8103 | 1606.9275 | 1659.7242 | 1714.2556 | 1757.2019 | 1801.2241 | 1846.3492 | 1892.6048 | 1940.0192 | 1978.6132 | 2017.975 | 2058.1198 | 2099.0633 | 2140.8212 | 2192.3979 | 2245.2172 | 2299.309 | 2354.704 | 2411.4336 | 2460.466 | 2510.4954 | 2561.5421 | 2613.6268 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | 2666.7705 | [6 empty] | 2973 | 3009 | 3045 | 3081 | 3117.7 | 3161 | 3205 | 3249 | 3293 | 3337 | 3379.2 | 3418 | 3456 | 3494 | 3532 | 3570 | 3608 | 3646 | 3684 | 3722 | 3760 | 3798 | 3836 | 3874 | 3912 | 3950 | 3988 | 4026 | 4064 | 4102 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | 4146 | [6 empty] | 2.1115 | 2.1115 | 2.1115 | 2.1115 | 2.1115 | 2.111 | 2.1106 | 2.1101 | 2.1096 | 2.1092 | 2.1095 | 2.1098 | 2.1101 | 2.1104 | 2.1107 | 2.109 | 2.1073 | 2.1056 | 2.1039 | 2.1022 | 2.1009 | 2.0996 | 2.0983 | 2.097 | 2.0957 | 2.0943 | 2.093 | 2.0916 | 2.0902 | 2.0888 | 2.0881 | 2.0873 | 2.0865 | 2.0857 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085 | 2.085
129 | Devonport - Takapuna |  |  | 2052 | 2305.8978 | 2289.3009 | 2272.8234 | 2256.4646 | 2240.2235 | 2256.7729 | 2273.4446 | 2290.2394 | 2307.1583 | 2324.2022 | 2341.0788 | 2358.078 | 2375.2006 | 2392.4475 | 2409.8197 | 2425.2945 | 2440.8687 | 2456.5429 | 2472.3177 | 2488.1939 | 2502.0032 | 2515.8893 | 2529.8523 | 2543.8929 | 2558.0114 | 2576.5485 | 2595.2199 | 2614.0266 | 2632.9696 | 2652.0499 | 2669.4547 | 2686.9737 | 2704.6076 | 2722.3573 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 | 2740.2235 |  | 6320 | 6274.5112 | 6229.3499 | 6184.5136 | 6140 | 6160.2654 | 6180.5977 | 6200.9971 | 6221.4639 | 6241.9982 | 6261.2924 | 6280.6463 | 6300.06 | 6319.5337 | 6339.0676 | 6351.39 | 6363.7363 | 6376.1067 | 6388.5011 | 6400.9195 | 6407.1682 | 6413.423 | 6419.6839 | 6425.9509 | 6432.2241 | 6448.6647 | 6465.1473 | 6481.672 | 6498.239 | 6514.8483 | 6557.5315 | 6600.4943 | 6643.7386 | 6687.2662 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | 6731.0789 | [6 empty] | 1360 | 1373 | 1386 | 1399 | 1410.5 | 1430 | 1449 | 1468 | 1487 | 1506 | 1526.9 | 1544 | 1561 | 1578 | 1595 | 1612 | 1629 | 1646 | 1663 | 1680 | 1697 | 1714 | 1731 | 1748 | 1765 | 1782 | 1799 | 1816 | 1833 | 1850 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | 1869.4 | [6 empty] | 2.7408 | 2.7408 | 2.7408 | 2.7408 | 2.7408 | 2.7297 | 2.7186 | 2.7076 | 2.6966 | 2.6857 | 2.6745 | 2.6635 | 2.6524 | 2.6415 | 2.6305 | 2.6188 | 2.6072 | 2.5956 | 2.584 | 2.5725 | 2.5608 | 2.5492 | 2.5376 | 2.526 | 2.5145 | 2.5028 | 2.4912 | 2.4796 | 2.468 | 2.4565 | 2.4565 | 2.4565 | 2.4565 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564 | 2.4564
130 | Devonport - Takapuna |  |  | 2052 | 1435.4103 | 1412.6789 | 1390.3075 | 1368.2904 | 1346.622 | 1366.1993 | 1386.0612 | 1406.2119 | 1426.6556 | 1447.3964 | 1467.3849 | 1487.6494 | 1508.1937 | 1529.0217 | 1550.1374 | 1568.5067 | 1587.0936 | 1605.9008 | 1624.9309 | 1644.1865 | 1660.6112 | 1677.2001 | 1693.9546 | 1710.8765 | 1727.9675 | 1749.9693 | 1772.2512 | 1794.8168 | 1817.6698 | 1840.8137 | 1861.505 | 1882.4288 | 1903.5878 | 1924.9846 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 | 1946.622 |  | 3880 | 3818.5558 | 3758.0846 | 3698.5711 | 3640 | 3678.2139 | 3716.8291 | 3755.8496 | 3795.2797 | 3835.1238 | 3872.2815 | 3909.7991 | 3947.6803 | 3985.9285 | 4024.5473 | 4054.4241 | 4084.5227 | 4114.8448 | 4145.392 | 4176.1659 | 4199.0074 | 4221.9739 | 4245.066 | 4268.2844 | 4291.6298 | 4326.3882 | 4361.4281 | 4396.7518 | 4432.3616 | 4468.2598 | 4518.5389 | 4569.3838 | 4620.8008 | 4672.7964 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | 4725.377 | [6 empty] | 725 | 733 | 741 | 749 | 757.1 | 766 | 775 | 784 | 793 | 802 | 812 | 821 | 830 | 839 | 848 | 857 | 866 | 875 | 884 | 893 | 902 | 911 | 920 | 929 | 938 | 947 | 956 | 965 | 974 | 983 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | 990.5 | [6 empty] | 2.7031 | 2.7031 | 2.7031 | 2.7031 | 2.7031 | 2.6923 | 2.6816 | 2.6709 | 2.6603 | 2.6497 | 2.6389 | 2.6282 | 2.6175 | 2.6068 | 2.5963 | 2.5849 | 2.5736 | 2.5623 | 2.5511 | 2.54 | 2.5286 | 2.5173 | 2.506 | 2.4948 | 2.4836 | 2.4723 | 2.461 | 2.4497 | 2.4385 | 2.4273 | 2.4274 | 2.4274 | 2.4274 | 2.4274 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275 | 2.4275
131 | Devonport - Takapuna |  |  | 2052 | 917.115 | 898.0377 | 879.3573 | 861.0654 | 843.1541 | 850.5802 | 858.0717 | 865.6292 | 873.2533 | 880.9445 | 888.5187 | 896.158 | 903.863 | 911.6343 | 919.4724 | 926.4513 | 933.4831 | 940.5684 | 947.7074 | 954.9007 | 961.1485 | 967.4372 | 973.767 | 980.1383 | 986.5513 | 994.854 | 1003.2267 | 1011.6698 | 1020.184 | 1028.7699 | 1036.5288 | 1044.3462 | 1052.2226 | 1060.1584 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 | 1068.1541 |  | 2480 | 2428.4126 | 2377.8982 | 2328.4347 | 2280 | 2296.551 | 2313.2221 | 2330.0143 | 2346.9283 | 2363.9652 | 2380.6038 | 2397.3596 | 2414.2332 | 2431.2257 | 2448.3377 | 2461.2724 | 2474.2754 | 2487.3472 | 2500.488 | 2513.6982 | 2524.2879 | 2534.9222 | 2545.6013 | 2556.3254 | 2567.0946 | 2582.6325 | 2598.2643 | 2613.9908 | 2629.8125 | 2645.7299 | 2665.666 | 2685.7522 | 2705.9899 | 2726.38 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | 2746.9238 | [6 empty] | 296 | 298 | 300 | 302 | 303.9 | 308 | 312 | 316 | 320 | 324 | 325.8 | 328 | 331 | 334 | 337 | 340 | 343 | 346 | 349 | 352 | 355 | 358 | 361 | 364 | 367 | 370 | 373 | 376 | 379 | 382 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | 379.3 | [6 empty] | 2.7041 | 2.7041 | 2.7041 | 2.7041 | 2.7041 | 2.7 | 2.6958 | 2.6917 | 2.6876 | 2.6834 | 2.6793 | 2.6752 | 2.671 | 2.6669 | 2.6628 | 2.6567 | 2.6506 | 2.6445 | 2.6385 | 2.6324 | 2.6263 | 2.6202 | 2.6142 | 2.6081 | 2.6021 | 2.596 | 2.5899 | 2.5838 | 2.5778 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717 | 2.5717
132 | Devonport - Takapuna |  |  | 2052 | 1412.2162 | 1413.1215 | 1414.0274 | 1414.9338 | 1415.8409 | 1422.5787 | 1429.3486 | 1436.1507 | 1442.9852 | 1449.8523 | 1456.7219 | 1463.624 | 1470.5589 | 1477.5266 | 1484.5273 | 1490.8378 | 1497.175 | 1503.5392 | 1509.9304 | 1516.3488 | 1521.9853 | 1527.6427 | 1533.3211 | 1539.0206 | 1544.7413 | 1552.3151 | 1559.9261 | 1567.5744 | 1575.2602 | 1582.9836 | 1590.091 | 1597.2302 | 1604.4015 | 1611.605 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 | 1618.8409 |  | 3960 | 3962.4976 | 3964.9968 | 3967.4976 | 3970 | 3973.0535 | 3976.1094 | 3979.1677 | 3982.2283 | 3985.2912 | 3987.9607 | 3990.632 | 3993.3051 | 3995.98 | 3998.6567 | 3998.1865 | 3997.7164 | 3997.2464 | 3996.7764 | 3996.3064 | 3993.365 | 3990.4257 | 3987.4886 | 3984.5536 | 3981.6208 | 3982.9171 | 3984.2139 | 3985.511 | 3986.8086 | 3988.1066 | 4005.7284 | 4023.428 | 4041.2058 | 4059.0622 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | 4076.9974 | [6 empty] | 712 | 718 | 724 | 730 | 736.7 | 745 | 753 | 761 | 769 | 777 | 787.2 | 794 | 801 | 808 | 815 | 822 | 829 | 836 | 843 | 850 | 857 | 864 | 871 | 878 | 885 | 892 | 899 | 906 | 913 | 920 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | 931.5 | [6 empty] | 2.8041 | 2.8041 | 2.804 | 2.804 | 2.804 | 2.7929 | 2.7818 | 2.7707 | 2.7597 | 2.7488 | 2.7376 | 2.7265 | 2.7155 | 2.7045 | 2.6936 | 2.6818 | 2.6702 | 2.6586 | 2.647 | 2.6355 | 2.6238 | 2.6121 | 2.6006 | 2.589 | 2.5775 | 2.5658 | 2.5541 | 2.5425 | 2.5309 | 2.5194 | 2.5192 | 2.519 | 2.5188 | 2.5186 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185 | 2.5185
133 | Devonport - Takapuna |  |  | 2052 | 2130.9025 | 2092.1612 | 2054.1242 | 2016.7788 | 1980.1124 | 1985.7072 | 1991.3179 | 1996.9444 | 2002.5868 | 2008.2452 | 2013.9491 | 2019.6692 | 2025.4055 | 2031.1581 | 2036.9271 | 2042.1355 | 2047.3571 | 2052.5922 | 2057.8406 | 2063.1025 | 2067.7361 | 2072.3802 | 2077.0346 | 2081.6996 | 2086.375 | 2092.6069 | 2098.8574 | 2105.1266 | 2111.4145 | 2117.7212 | 2123.567 | 2129.4291 | 2135.3072 | 2141.2017 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 | 2147.1124 |  | 5370 | 5272.3696 | 5176.5143 | 5082.4016 | 4990 | 4987.1567 | 4984.3151 | 4981.4751 | 4978.6367 | 4975.7999 | 4972.7467 | 4969.6954 | 4966.6459 | 4963.5984 | 4960.5527 | 4954.0716 | 4947.5991 | 4941.135 | 4934.6793 | 4928.2321 | 4919.8927 | 4911.5674 | 4903.2561 | 4894.9589 | 4886.6758 | 4881.6271 | 4876.5835 | 4871.5452 | 4866.5121 | 4861.4841 | 4874.9024 | 4888.3576 | 4901.85 | 4915.3796 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | 4928.9466 | [6 empty] | 1960 | 1975 | 1990 | 2005 | 2019.7 | 2046 | 2072 | 2098 | 2124 | 2150 | 2174.6 | 2194 | 2213 | 2232 | 2251 | 2270 | 2289 | 2308 | 2327 | 2346 | 2365 | 2384 | 2403 | 2422 | 2441 | 2460 | 2479 | 2498 | 2517 | 2536 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | 2562.2 | [6 empty] | 2.5201 | 2.5201 | 2.5201 | 2.5201 | 2.5201 | 2.5115 | 2.503 | 2.4945 | 2.4861 | 2.4777 | 2.4692 | 2.4606 | 2.4522 | 2.4437 | 2.4353 | 2.4259 | 2.4166 | 2.4073 | 2.398 | 2.3887 | 2.3794 | 2.37 | 2.3607 | 2.3514 | 2.3422 | 2.3328 | 2.3234 | 2.3141 | 2.3049 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956 | 2.2956
134 | Devonport - Takapuna |  |  | 2052 | 688.6222 | 674.4162 | 660.5032 | 646.8773 | 633.5324 | 636.4448 | 639.3705 | 642.3097 | 645.2624 | 648.2287 | 651.198 | 654.1809 | 657.1774 | 660.1877 | 663.2118 | 665.9167 | 668.6327 | 671.3598 | 674.098 | 676.8473 | 679.2505 | 681.6623 | 684.0826 | 686.5115 | 688.949 | 692.1786 | 695.4233 | 698.6832 | 701.9585 | 705.249 | 708.2795 | 711.3231 | 714.3797 | 717.4495 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 | 720.5324 |  | 2250 | 2203.5833 | 2158.1242 | 2113.6029 | 2070 | 2071.3355 | 2072.6718 | 2074.009 | 2075.3471 | 2076.686 | 2077.8601 | 2079.0349 | 2080.2103 | 2081.3864 | 2082.5632 | 2082.2208 | 2081.8786 | 2081.5364 | 2081.1942 | 2080.8521 | 2079.3883 | 2077.9255 | 2076.4637 | 2075.003 | 2073.5433 | 2073.9564 | 2074.3697 | 2074.783 | 2075.1964 | 2075.6099 | 2083.3943 | 2091.2078 | 2099.0506 | 2106.9229 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | 2114.8247 | [6 empty] | 3317 | 3364 | 3411 | 3458 | 3503.4 | 3543 | 3583 | 3623 | 3663 | 3703 | 3743.9 | 3795 | 3846 | 3897 | 3948 | 3999 | 4050 | 4101 | 4152 | 4203 | 4254 | 4305 | 4356 | 4407 | 4458 | 4509 | 4560 | 4611 | 4662 | 4713 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | 4767.2 | [6 empty] | 3.2674 | 3.2674 | 3.2674 | 3.2674 | 3.2674 | 3.2545 | 3.2417 | 3.229 | 3.2163 | 3.2036 | 3.1908 | 3.1781 | 3.1654 | 3.1527 | 3.1401 | 3.1268 | 3.1136 | 3.1005 | 3.0874 | 3.0743 | 3.0613 | 3.0483 | 3.0354 | 3.0225 | 3.0097 | 2.9963 | 2.9829 | 2.9696 | 2.9563 | 2.9431 | 2.9415 | 2.9399 | 2.9383 | 2.9367 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351 | 2.9351
135 | Rodney |  |  | 2052 | 1642.4042 | 1680.9182 | 1720.3354 | 1760.6768 | 1801.9643 | 1812.3345 | 1822.7644 | 1833.2543 | 1843.8046 | 1854.4156 | 1864.9893 | 1875.6233 | 1886.3179 | 1897.0735 | 1907.8904 | 1915.784 | 1923.7103 | 1931.6694 | 1939.6614 | 1947.6864 | 1953.7056 | 1959.7433 | 1965.7997 | 1971.8748 | 1977.9687 | 1982.8838 | 1987.8112 | 1992.7508 | 1997.7026 | 2002.6668 | 2005.717 | 2008.7718 | 2011.8313 | 2014.8955 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 | 2017.9643 |  | 4190 | 4286.6072 | 4385.4418 | 4486.5552 | 4590 | 4597.2105 | 4604.4323 | 4611.6654 | 4618.91 | 4626.1659 | 4632.7858 | 4639.4153 | 4646.0542 | 4652.7027 | 4659.3607 | 4661.605 | 4663.8505 | 4666.0971 | 4668.3447 | 4670.5934 | 4668.021 | 4665.45 | 4662.8805 | 4660.3123 | 4657.7456 | 4651.5825 | 4645.4277 | 4639.281 | 4633.1424 | 4627.012 | 4633.9702 | 4640.9389 | 4647.9181 | 4654.9078 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | 4661.908 | [6 empty] | 1324 | 1333 | 1342 | 1351 | 1360 | 1373 | 1386 | 1399 | 1412 | 1425 | 1439.1 | 1431 | 1423 | 1415 | 1407 | 1399 | 1391 | 1383 | 1375 | 1367 | 1359 | 1351 | 1343 | 1335 | 1327 | 1319 | 1311 | 1303 | 1295 | 1287 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | 1272.8 | [6 empty] | 2.5511 | 2.5502 | 2.5492 | 2.5482 | 2.5472 | 2.5366 | 2.5261 | 2.5156 | 2.5051 | 2.4947 | 2.4841 | 2.4735 | 2.463 | 2.4526 | 2.4422 | 2.4333 | 2.4244 | 2.4156 | 2.4068 | 2.398 | 2.3893 | 2.3806 | 2.372 | 2.3634 | 2.3548 | 2.3459 | 2.337 | 2.3281 | 2.3192 | 2.3104 | 2.3104 | 2.3103 | 2.3103 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102 | 2.3102
136 | Rodney |  |  | 2052 | 959.8785 | 979.6711 | 999.8718 | 1020.489 | 1041.5314 | 1041.8645 | 1042.1978 | 1042.5311 | 1042.8645 | 1043.1981 | 1043.5312 | 1043.8644 | 1044.1978 | 1044.5312 | 1044.8648 | 1045.1979 | 1045.5311 | 1045.8644 | 1046.1979 | 1046.5314 | 1046.8645 | 1047.1978 | 1047.5311 | 1047.8645 | 1048.1981 | 1048.5312 | 1048.8644 | 1049.1978 | 1049.5312 | 1049.8648 | 1050.1979 | 1050.5311 | 1050.8644 | 1051.1979 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 | 1051.5314 |  | 2390 | 2438.5034 | 2487.9912 | 2538.4832 | 2590 | 2585.1935 | 2580.3959 | 2575.6073 | 2570.8275 | 2566.0566 | 2561.2319 | 2556.4162 | 2551.6096 | 2546.812 | 2542.0235 | 2537.088 | 2532.1621 | 2527.2458 | 2522.3391 | 2517.4418 | 2512.5892 | 2507.7458 | 2502.9118 | 2498.0872 | 2493.2718 | 2488.2318 | 2483.2019 | 2478.1822 | 2473.1727 | 2468.1733 | 2468.9564 | 2469.7398 | 2470.5235 | 2471.3074 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | 2472.0915 | [6 empty] | 332 | 333 | 334 | 335 | 334.5 | 337 | 340 | 343 | 346 | 349 | 349.7 | 348 | 347 | 346 | 345 | 344 | 343 | 342 | 341 | 340 | 339 | 338 | 337 | 336 | 335 | 334 | 333 | 332 | 331 | 330 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | 320.9 | [6 empty] | 2.4899 | 2.4891 | 2.4883 | 2.4875 | 2.4867 | 2.4813 | 2.4759 | 2.4705 | 2.4652 | 2.4598 | 2.4544 | 2.449 | 2.4436 | 2.4382 | 2.4329 | 2.4274 | 2.4219 | 2.4164 | 2.411 | 2.4055 | 2.4001 | 2.3947 | 2.3893 | 2.384 | 2.3786 | 2.3731 | 2.3675 | 2.362 | 2.3565 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509 | 2.3509
137 | Rodney |  |  | 2052 | 423.2149 | 430.0898 | 437.0763 | 444.1763 | 451.3917 | 451.7245 | 452.0576 | 452.3909 | 452.7245 | 453.0583 | 453.3912 | 453.7243 | 454.0576 | 454.3912 | 454.725 | 455.0578 | 455.3909 | 455.7243 | 456.0578 | 456.3917 | 456.7245 | 457.0576 | 457.3909 | 457.7245 | 458.0583 | 458.3912 | 458.7243 | 459.0576 | 459.3912 | 459.725 | 460.0579 | 460.3909 | 460.7243 | 461.0579 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 | 461.3917 |  | 1160 | 1179.5026 | 1199.3331 | 1219.4971 | 1240 | 1234.3841 | 1228.7936 | 1223.2284 | 1217.6884 | 1212.1735 | 1206.5078 | 1200.8686 | 1195.2557 | 1189.6691 | 1184.1086 | 1179.7169 | 1175.3416 | 1170.9825 | 1166.6395 | 1162.3127 | 1157.975 | 1153.6536 | 1149.3482 | 1145.059 | 1140.7857 | 1136.2532 | 1131.7387 | 1127.2421 | 1122.7633 | 1118.3024 | 1119.1121 | 1119.9224 | 1120.7332 | 1121.5446 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | 1122.3567 | [6 empty] | 264 | 265 | 266 | 267 | 267.7 | 270 | 272 | 274 | 276 | 278 | 280.3 | 278 | 276 | 274 | 272 | 270 | 268 | 266 | 264 | 262 | 260 | 258 | 256 | 254 | 252 | 250 | 248 | 246 | 244 | 242 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | 238.7 | [6 empty] | 2.7409 | 2.7425 | 2.744 | 2.7455 | 2.7471 | 2.7326 | 2.7182 | 2.7039 | 2.6897 | 2.6755 | 2.6611 | 2.6467 | 2.6324 | 2.6182 | 2.604 | 2.5925 | 2.581 | 2.5695 | 2.5581 | 2.5467 | 2.5354 | 2.5241 | 2.5128 | 2.5016 | 2.4905 | 2.4788 | 2.4671 | 2.4556 | 2.444 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325 | 2.4325
138 | Rodney |  |  | 2052 | 372.3734 | 380.0056 | 387.7943 | 395.7426 | 403.8538 | 404.1866 | 404.5196 | 404.853 | 405.1866 | 405.5205 | 405.8533 | 406.1863 | 406.5196 | 406.8533 | 407.1871 | 407.5199 | 407.853 | 408.1863 | 408.5199 | 408.8538 | 409.1866 | 409.5197 | 409.853 | 410.1866 | 410.5205 | 410.8533 | 411.1863 | 411.5197 | 411.8533 | 412.1871 | 412.5199 | 412.853 | 413.1863 | 413.5199 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 | 413.8538 |  | 1120 | 1141.8521 | 1164.1306 | 1186.8437 | 1210 | 1205.3501 | 1200.7181 | 1196.1039 | 1191.5074 | 1186.9285 | 1182.2311 | 1177.5522 | 1172.8919 | 1168.2499 | 1163.6264 | 1159.6935 | 1155.7739 | 1151.8676 | 1147.9744 | 1144.0944 | 1140.2076 | 1136.334 | 1132.4736 | 1128.6262 | 1124.792 | 1120.7202 | 1116.6631 | 1112.6207 | 1108.5929 | 1104.5797 | 1105.4716 | 1106.3641 | 1107.2574 | 1108.1514 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | 1109.0461 | [6 empty] | 369 | 370 | 371 | 372 | 373.5 | 377 | 381 | 385 | 389 | 393 | 395 | 392 | 389 | 386 | 383 | 380 | 377 | 374 | 371 | 368 | 365 | 362 | 359 | 356 | 353 | 350 | 347 | 344 | 341 | 338 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | 327.9 | [6 empty] | 3.0077 | 3.0048 | 3.0019 | 2.999 | 2.9961 | 2.9822 | 2.9683 | 2.9544 | 2.9406 | 2.9269 | 2.913 | 2.899 | 2.8852 | 2.8714 | 2.8577 | 2.8457 | 2.8338 | 2.8219 | 2.8101 | 2.7983 | 2.7865 | 2.7748 | 2.7631 | 2.7515 | 2.7399 | 2.7278 | 2.7157 | 2.7037 | 2.6917 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798 | 2.6798
139 | Rodney |  |  | 2052 | 1995.7701 | 2038.9175 | 2082.9977 | 2128.0308 | 2174.0376 | 2174.8767 | 2175.7162 | 2176.556 | 2177.3961 | 2178.2365 | 2179.092 | 2179.9479 | 2180.8041 | 2181.6606 | 2182.5174 | 2182.8214 | 2183.1254 | 2183.4294 | 2183.7335 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 | 2184.0376 |  | 5620 | 5741.0336 | 5864.6739 | 5990.9769 | 6120 | 6090.4627 | 6061.068 | 6031.8152 | 6002.7036 | 5973.7324 | 5944.1082 | 5914.631 | 5885.2999 | 5856.1143 | 5827.0734 | 5802.438 | 5777.9068 | 5753.4793 | 5729.155 | 5704.9336 | 5679.921 | 5655.018 | 5630.2243 | 5605.5392 | 5580.9624 | 5555.1944 | 5529.5454 | 5504.0148 | 5478.602 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | 5453.3066 | [6 empty] | 1303 | 1306 | 1309 | 1312 | 1313.6 | 1327 | 1340 | 1353 | 1366 | 1379 | 1393.8 | 1388 | 1382 | 1376 | 1370 | 1364 | 1358 | 1352 | 1346 | 1340 | 1334 | 1328 | 1322 | 1316 | 1310 | 1304 | 1298 | 1292 | 1286 | 1280 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | 1269 | [6 empty] | 2.816 | 2.8157 | 2.8155 | 2.8153 | 2.815 | 2.8004 | 2.7858 | 2.7713 | 2.7568 | 2.7425 | 2.7278 | 2.7132 | 2.6987 | 2.6842 | 2.6699 | 2.6582 | 2.6466 | 2.6351 | 2.6236 | 2.6121 | 2.6007 | 2.5892 | 2.5779 | 2.5666 | 2.5553 | 2.5435 | 2.5318 | 2.5201 | 2.5085 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969 | 2.4969
140 | Rodney |  |  | 2052 | 447.5404 | 450.8758 | 454.2361 | 457.6214 | 461.032 | 465.3184 | 469.6447 | 474.0112 | 478.4183 | 482.8664 | 487.2386 | 491.6505 | 496.1022 | 500.5943 | 505.127 | 509.1382 | 513.1813 | 517.2565 | 521.3641 | 525.5043 | 529.0856 | 532.6914 | 536.3218 | 539.9768 | 543.6568 | 548.4612 | 553.308 | 558.1976 | 563.1304 | 568.1069 | 572.6196 | 577.1682 | 581.753 | 586.3741 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 | 591.032 |  | 1390 | 1399.8939 | 1409.8581 | 1419.8934 | 1430 | 1437.9773 | 1445.9991 | 1454.0656 | 1462.1771 | 1470.3339 | 1478.1204 | 1485.9482 | 1493.8175 | 1501.7284 | 1509.6812 | 1516.6057 | 1523.562 | 1530.5501 | 1537.5704 | 1544.6228 | 1550.0599 | 1555.5161 | 1560.9915 | 1566.4862 | 1572.0003 | 1580.3612 | 1588.7666 | 1597.2167 | 1605.7117 | 1614.2519 | 1626.5808 | 1639.0038 | 1651.5218 | 1664.1353 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | 1676.8452 | [6 empty] | 627 | 629 | 631 | 633 | 636.7 | 643 | 650 | 657 | 664 | 671 | 675.7 | 672 | 668 | 664 | 660 | 656 | 652 | 648 | 644 | 640 | 636 | 632 | 628 | 624 | 620 | 616 | 612 | 608 | 604 | 600 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | 595.1 | [6 empty] | 3.1059 | 3.1048 | 3.1038 | 3.1028 | 3.1017 | 3.0903 | 3.0789 | 3.0676 | 3.0563 | 3.045 | 3.0337 | 3.0224 | 3.0111 | 2.9999 | 2.9887 | 2.9788 | 2.9689 | 2.959 | 2.9491 | 2.9393 | 2.9297 | 2.9201 | 2.9106 | 2.901 | 2.8915 | 2.8814 | 2.8714 | 2.8614 | 2.8514 | 2.8415 | 2.8406 | 2.8397 | 2.8389 | 2.838 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371 | 2.8371
141 | Rodney |  |  | 2052 | 130.3659 | 132.0475 | 133.7508 | 135.4761 | 137.2236 | 137.5553 | 137.8878 | 138.2212 | 138.5553 | 138.8902 | 139.222 | 139.5545 | 139.8879 | 140.222 | 140.5569 | 140.8887 | 141.2212 | 141.5545 | 141.8887 | 142.2236 | 142.5554 | 142.8879 | 143.2212 | 143.5553 | 143.8902 | 144.222 | 144.5546 | 144.8879 | 145.222 | 145.5569 | 145.8887 | 146.2213 | 146.5546 | 146.8887 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 | 147.2236 |  | 410 | 414.9111 | 419.8809 | 424.9103 | 430 | 429.6238 | 429.2478 | 428.8723 | 428.497 | 428.1221 | 427.7116 | 427.3016 | 426.8919 | 426.4826 | 426.0738 | 425.8043 | 425.5351 | 425.266 | 424.9971 | 424.7283 | 424.4516 | 424.175 | 423.8986 | 423.6224 | 423.3464 | 423.0018 | 422.6574 | 422.3133 | 421.9695 | 421.626 | 422.5872 | 423.5505 | 424.516 | 425.4838 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | 426.4537 | [6 empty] | 200 | 200 | 200 | 200 | 201.5 | 203 | 205 | 207 | 209 | 211 | 211.7 | 210 | 208 | 206 | 204 | 202 | 200 | 198 | 196 | 194 | 192 | 190 | 188 | 186 | 184 | 182 | 180 | 178 | 176 | 174 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | 173.3 | [6 empty] | 3.145 | 3.1421 | 3.1393 | 3.1364 | 3.1336 | 3.1233 | 3.113 | 3.1028 | 3.0926 | 3.0824 | 3.0722 | 3.0619 | 3.0517 | 3.0415 | 3.0313 | 3.0223 | 3.0133 | 3.0043 | 2.9953 | 2.9863 | 2.9775 | 2.9686 | 2.9597 | 2.9509 | 2.9421 | 2.933 | 2.9239 | 2.9148 | 2.9057 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966 | 2.8966
142 | Rodney | Northwest | Kumeu-Huapai | 2080 | 66.6989 | 68.3031 | 69.946 | 71.6284 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 73.3512 | 124.3029 | 175.2547 | 226.2064 | 277.1582 | 328.1099 | 379.0617 | 430.0134 | 480.9651 | 531.9169 | 582.8686 | 633.8204 | 684.7721 | 735.7239 | 786.6756 | 837.6273 | 888.5791 | 939.5308 | 990.4826 | 1041.4343 | 1092.3861 | 1143.3378 | 1194.2895 | 1245.2413 | 1296.193 | 1347.1448 | 1398.0965 | 1449.0483 | 1500 |  | 230 | 234.8448 | 239.7916 | 244.8426 | 250 | 247.5343 | 245.0928 | 242.6755 | 240.282 | 237.9121 | 235.4438 | 233.0011 | 230.5838 | 228.1916 | 225.8241 | 225.3327 | 224.8424 | 224.3531 | 223.8649 | 223.3778 | 222.6974 | 222.0191 | 221.3429 | 220.6687 | 219.9966 | 219.1836 | 218.3737 | 217.5668 | 216.7628 | 215.9619 | 215.9622 | 215.9626 | 215.9629 | 215.9633 | 215.9636 | 331.0364 | 446.1091 | 561.1818 | 676.2545 | 791.3273 | 906.4 | 1021.4727 | 1136.5455 | 1251.6182 | 1366.6909 | 1481.7636 | 1596.8364 | 1711.9091 | 1826.9818 | 1942.0545 | 2057.1273 | 2172.2 | 2287.2727 | 2402.3455 | 2517.4182 | 2632.4909 | 2747.5636 | 2862.6364 | 2977.7091 | 3092.7818 | 3207.8545 | 3322.9273 | 3438 | [6 empty] | 62 | 62 | 62 | 62 | 62.8 | 63 | 63 | 63 | 63 | 63 | 65.7 | 65 | 64 | 63 | 62 | 61 | 60 | 59 | 58 | 57 | 56 | 55 | 54 | 53 | 52 | 51 | 50 | 49 | 48 | 47 | 53.6 | 66.15 | 78.7 | 91.25 | 103.8 | 116.35 | 128.9 | 141.45 | 154 | 166.55 | 179.1 | 191.65 | 204.2 | 216.75 | 229.3 | 241.85 | 254.4 | 266.95 | 279.5 | 292.05 | 304.6 | 317.15 | 329.7 | 342.25 | 354.8 | 367.35 | 379.9 | 392.45 | 405 | [6 empty] | 3.4483 | 3.4383 | 3.4282 | 3.4182 | 3.4083 | 3.3746 | 3.3414 | 3.3084 | 3.2758 | 3.2435 | 3.2098 | 3.1765 | 3.1436 | 3.1109 | 3.0787 | 3.072 | 3.0653 | 3.0586 | 3.052 | 3.0453 | 3.036 | 3.0268 | 3.0176 | 3.0084 | 2.9992 | 2.9881 | 2.9771 | 2.9661 | 2.9551 | 2.9442 | 2.9442 | 2.9442 | 2.9442 | 2.9442 | 2.9442 | 2.6631 | 2.5455 | 2.4808 | 2.44 | 2.4118 | 2.3912 | 2.3754 | 2.3631 | 2.353 | 2.3448 | 2.3378 | 2.3319 | 2.3268 | 2.3224 | 2.3185 | 2.3151 | 2.312 | 2.3093 | 2.3068 | 2.3045 | 2.3025 | 2.3006 | 2.2989 | 2.2973 | 2.2958 | 2.2944 | 2.2932 | 2.292
143 | Rodney | Northwest | Kumeu-Huapai | 2080 | 36.3812 | 41.3731 | 47.0499 | 53.5057 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 60.8472 | 123.9598 | 187.0724 | 250.185 | 313.2976 | 376.4102 | 439.5228 | 502.6354 | 565.748 | 628.8606 | 691.9732 | 755.0858 | 818.1984 | 881.311 | 944.4236 | 1007.5362 | 1070.6488 | 1133.7614 | 1196.874 | 1259.9866 | 1323.0992 | 1386.2118 | 1449.3244 | 1512.437 | 1575.5496 | 1638.6622 | 1701.7748 | 1764.8874 | 1828 |  | 120 | 134.6091 | 150.9967 | 169.3794 | 190 | 187.5316 | 185.0953 | 182.6906 | 180.3172 | 177.9746 | 175.5017 | 173.0633 | 170.6586 | 168.2874 | 165.9492 | 167.8954 | 169.8645 | 171.8566 | 173.8722 | 175.9113 | 174.686 | 173.4692 | 172.2609 | 171.061 | 169.8695 | 168.2709 | 166.6874 | 165.1189 | 163.565 | 162.0258 | 162.0281 | 162.0303 | 162.0325 | 162.0348 | 162.037 | 311 | 459.963 | 608.9259 | 757.8889 | 906.8518 | 1055.8148 | 1204.7778 | 1353.7407 | 1502.7037 | 1651.6667 | 1800.6296 | 1949.5926 | 2098.5555 | 2247.5185 | 2396.4815 | 2545.4444 | 2694.4074 | 2843.3704 | 2992.3333 | 3141.2963 | 3290.2593 | 3439.2222 | 3588.1852 | 3737.1481 | 3886.1111 | 4035.0741 | 4184.037 | 4333 | [6 empty] | 32 | 32 | 32 | 32 | 31.4 | 32 | 32 | 32 | 32 | 32 | 32.9 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 30.8 | 44.6643 | 58.5286 | 72.3929 | 86.2571 | 100.1214 | 113.9857 | 127.85 | 141.7143 | 155.5786 | 169.4429 | 183.3071 | 197.1714 | 211.0357 | 224.9 | 238.7643 | 252.6286 | 266.4929 | 280.3571 | 294.2214 | 308.0857 | 321.95 | 335.8143 | 349.6786 | 363.5429 | 377.4071 | 391.2714 | 405.1357 | 419 | [6 empty] | 3.2984 | 3.2535 | 3.2093 | 3.1656 | 3.1226 | 3.082 | 3.042 | 3.0024 | 2.9634 | 2.9249 | 2.8843 | 2.8442 | 2.8047 | 2.7657 | 2.7273 | 2.7593 | 2.7917 | 2.8244 | 2.8575 | 2.891 | 2.8709 | 2.8509 | 2.831 | 2.8113 | 2.7917 | 2.7655 | 2.7394 | 2.7137 | 2.6881 | 2.6628 | 2.6629 | 2.6629 | 2.6629 | 2.663 | 2.663 | 2.5089 | 2.4587 | 2.4339 | 2.4191 | 2.4092 | 2.4022 | 2.3969 | 2.3928 | 2.3896 | 2.3869 | 2.3847 | 2.3828 | 2.3812 | 2.3798 | 2.3786 | 2.3775 | 2.3765 | 2.3757 | 2.3749 | 2.3742 | 2.3736 | 2.373 | 2.3725 | 2.372 | 2.3715 | 2.3711 | 2.3707 | 2.3704
144 | Rodney | Northwest | Kumeu-Huapai | 2080 | 975.2053 | 1042.8451 | 1115.1764 | 1192.5245 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1275.2375 | 1294.0504 | 1312.8633 | 1331.6763 | 1350.4892 | 1369.3022 | 1388.1151 | 1406.9281 | 1425.741 | 1444.554 | 1463.3669 | 1482.1799 | 1500.9928 | 1519.8058 | 1538.6187 | 1557.4317 | 1576.2446 | 1595.0576 | 1613.8705 | 1632.6835 | 1651.4964 | 1670.3094 | 1689.1223 | 1707.9353 | 1726.7482 | 1745.5612 | 1764.3741 | 1783.1871 | 1802 |  | 2940 | 3142.9922 | 3360 | 3591.9911 | 3840 | 3824.6825 | 3809.4262 | 3794.2307 | 3779.0958 | 3764.0213 | 3748.7013 | 3733.4437 | 3718.2482 | 3703.1146 | 3688.0426 | 3675.749 | 3663.4964 | 3651.2847 | 3639.1137 | 3626.9833 | 3614.7818 | 3602.6215 | 3590.502 | 3578.4233 | 3566.3852 | 3552.6727 | 3539.013 | 3525.4057 | 3511.8508 | 3498.348 | 3498.3674 | 3498.3867 | 3498.4061 | 3498.4254 | 3498.4447 | 3516.536 | 3534.6273 | 3552.7185 | 3570.8098 | 3588.901 | 3606.9923 | 3625.0836 | 3643.1748 | 3661.2661 | 3679.3573 | 3697.4486 | 3715.5399 | 3733.6311 | 3751.7224 | 3769.8136 | 3787.9049 | 3805.9962 | 3824.0874 | 3842.1787 | 3860.2699 | 3878.3612 | 3896.4524 | 3914.5437 | 3932.635 | 3950.7262 | 3968.8175 | 3986.9087 | 4005 | [6 empty] | 559 | 563 | 567 | 571 | 574.8 | 581 | 587 | 593 | 599 | 605 | 611.5 | 608 | 604 | 600 | 596 | 592 | 588 | 584 | 580 | 576 | 572 | 568 | 564 | 560 | 556 | 552 | 548 | 544 | 540 | 536 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | 538.8 | [6 empty] | 3.0147 | 3.0139 | 3.013 | 3.0121 | 3.0112 | 2.9992 | 2.9872 | 2.9753 | 2.9634 | 2.9516 | 2.9396 | 2.9276 | 2.9157 | 2.9039 | 2.892 | 2.8824 | 2.8728 | 2.8632 | 2.8537 | 2.8442 | 2.8346 | 2.8251 | 2.8156 | 2.8061 | 2.7966 | 2.7859 | 2.7752 | 2.7645 | 2.7539 | 2.7433 | 2.7433 | 2.7433 | 2.7433 | 2.7434 | 2.7434 | 2.7175 | 2.6923 | 2.6679 | 2.6441 | 2.621 | 2.5985 | 2.5766 | 2.5553 | 2.5345 | 2.5143 | 2.4946 | 2.4754 | 2.4567 | 2.4384 | 2.4205 | 2.4031 | 2.3861 | 2.3695 | 2.3533 | 2.3374 | 2.3219 | 2.3068 | 2.292 | 2.2775 | 2.2633 | 2.2494 | 2.2358 | 2.2225
145 | Rodney | Northwest | Kumeu-Huapai | 2080 | 296.5656 | 346.9107 | 405.8024 | 474.6916 | 555.2754 | 555.9404 | 556.6063 | 557.273 | 557.9404 | 558.6087 | 559.2738 | 559.9397 | 560.6063 | 561.2738 | 561.942 | 562.6071 | 563.273 | 563.9397 | 564.6071 | 565.2754 | 565.9405 | 566.6064 | 567.273 | 567.9405 | 568.6087 | 569.2738 | 569.9397 | 570.6064 | 571.2738 | 571.942 | 572.6072 | 573.273 | 573.9397 | 574.6072 | 575.2754 | 626.837 | 678.3986 | 729.9602 | 781.5217 | 833.0833 | 884.6449 | 936.2065 | 987.7681 | 1039.3297 | 1090.8913 | 1142.4529 | 1194.0145 | 1245.5761 | 1297.1377 | 1348.6993 | 1400.2609 | 1451.8225 | 1503.3841 | 1554.9457 | 1606.5072 | 1658.0688 | 1709.6304 | 1761.192 | 1812.7536 | 1864.3152 | 1915.8768 | 1967.4384 | 2019 |  | 920 | 1066.2717 | 1235.7993 | 1432.2803 | 1660 | 1654.0859 | 1648.1929 | 1642.3209 | 1636.4698 | 1630.6396 | 1624.6295 | 1618.6416 | 1612.6757 | 1606.7318 | 1600.8098 | 1594.34 | 1587.8962 | 1581.4785 | 1575.0868 | 1568.7209 | 1563.9325 | 1559.1587 | 1554.3994 | 1549.6547 | 1544.9245 | 1540.1982 | 1535.4864 | 1530.789 | 1526.106 | 1521.4373 | 1523.2066 | 1524.9779 | 1526.7513 | 1528.5268 | 1530.3043 | 1646.6506 | 1762.9969 | 1879.3432 | 1995.6894 | 2112.0357 | 2228.382 | 2344.7283 | 2461.0745 | 2577.4208 | 2693.7671 | 2810.1133 | 2926.4596 | 3042.8059 | 3159.1522 | 3275.4984 | 3391.8447 | 3508.191 | 3624.5373 | 3740.8835 | 3857.2298 | 3973.5761 | 4089.9224 | 4206.2686 | 4322.6149 | 4438.9612 | 4555.3075 | 4671.6537 | 4788 | [6 empty] | 932 | 938 | 944 | 950 | 954.3 | 964 | 974 | 984 | 994 | 1004 | 1013.2 | 1007 | 1001 | 995 | 989 | 983 | 977 | 971 | 965 | 959 | 953 | 947 | 941 | 935 | 929 | 923 | 917 | 911 | 905 | 899 | 886.5 | 891.0536 | 895.6071 | 900.1607 | 904.7143 | 909.2679 | 913.8214 | 918.375 | 922.9286 | 927.4821 | 932.0357 | 936.5893 | 941.1429 | 945.6964 | 950.25 | 954.8036 | 959.3571 | 963.9107 | 968.4643 | 973.0179 | 977.5714 | 982.125 | 986.6786 | 991.2321 | 995.7857 | 1000.3393 | 1004.8929 | 1009.4464 | 1014 | [6 empty] | 3.1022 | 3.0736 | 3.0453 | 3.0173 | 2.9895 | 2.9753 | 2.9611 | 2.9471 | 2.9331 | 2.9191 | 2.9049 | 2.8907 | 2.8767 | 2.8627 | 2.8487 | 2.8338 | 2.8191 | 2.8043 | 2.7897 | 2.7751 | 2.7634 | 2.7517 | 2.7401 | 2.7286 | 2.717 | 2.7055 | 2.6941 | 2.6827 | 2.6714 | 2.6601 | 2.6601 | 2.6601 | 2.6601 | 2.6601 | 2.6601 | 2.6269 | 2.5988 | 2.5746 | 2.5536 | 2.5352 | 2.519 | 2.5045 | 2.4916 | 2.4799 | 2.4693 | 2.4597 | 2.4509 | 2.4429 | 2.4355 | 2.4286 | 2.4223 | 2.4164 | 2.4109 | 2.4058 | 2.401 | 2.3965 | 2.3923 | 2.3883 | 2.3846 | 2.381 | 2.3777 | 2.3745 | 2.3715
146 | Rodney |  |  | 2052 | 123.6665 | 128.229 | 132.9598 | 137.8651 | 142.9515 | 143.2832 | 143.6158 | 143.9491 | 144.2832 | 144.6181 | 144.9499 | 145.2825 | 145.6158 | 145.9499 | 146.2848 | 146.6166 | 146.9492 | 147.2825 | 147.6166 | 147.9515 | 148.2833 | 148.6159 | 148.9492 | 149.2833 | 149.6181 | 149.95 | 150.2826 | 150.6159 | 150.95 | 151.2848 | 151.6167 | 151.9493 | 152.2826 | 152.6167 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 | 152.9515 |  | 400 | 411.9534 | 424.2641 | 436.9426 | 450 | 449.1085 | 448.2187 | 447.3307 | 446.4444 | 445.5599 | 444.6233 | 443.6887 | 442.756 | 441.8253 | 440.8966 | 443.5747 | 446.269 | 448.9798 | 451.7069 | 454.4507 | 455.5069 | 456.5656 | 457.6267 | 458.6903 | 459.7564 | 458.7996 | 457.8448 | 456.8919 | 455.9411 | 454.9922 | 456.0203 | 457.0506 | 458.0833 | 459.1184 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | 460.1557 | [6 empty] | 348 | 348 | 348 | 348 | 349.5 | 354 | 358 | 362 | 366 | 370 | 374.8 | 372 | 369 | 366 | 363 | 360 | 357 | 354 | 351 | 348 | 345 | 342 | 339 | 336 | 333 | 330 | 327 | 324 | 321 | 318 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | 312.8 | [6 empty] | 3.2345 | 3.2126 | 3.1909 | 3.1693 | 3.1479 | 3.1344 | 3.121 | 3.1076 | 3.0942 | 3.0809 | 3.0674 | 3.054 | 3.0406 | 3.0272 | 3.014 | 3.0254 | 3.0369 | 3.0484 | 3.06 | 3.0716 | 3.0719 | 3.0721 | 3.0724 | 3.0726 | 3.0729 | 3.0597 | 3.0466 | 3.0335 | 3.0205 | 3.0075 | 3.0077 | 3.0079 | 3.0081 | 3.0083 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085 | 3.0085
147 | Rodney | Northwest | Riverhead | 2080 | 967.5281 | 1027.6409 | 1091.4886 | 1159.3031 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1231.331 | 1251.8906 | 1272.4502 | 1293.0098 | 1313.5694 | 1334.129 | 1354.6886 | 1375.2482 | 1395.8078 | 1416.3675 | 1436.9271 | 1457.4867 | 1478.0463 | 1498.6059 | 1519.1655 | 1539.7251 | 1560.2847 | 1580.8443 | 1601.4039 | 1621.9635 | 1642.5231 | 1663.0827 | 1683.6424 | 1704.202 | 1724.7616 | 1745.3212 | 1765.8808 | 1786.4404 | 1807 |  | 2970 | 3154.5709 | 3350.6119 | 3558.8359 | 3780 | 3760.6647 | 3741.4284 | 3722.2904 | 3703.2504 | 3684.3077 | 3664.9673 | 3645.7284 | 3626.5904 | 3607.553 | 3588.6155 | 3573.1661 | 3557.7833 | 3542.4667 | 3527.216 | 3512.031 | 3496.852 | 3481.7386 | 3466.6905 | 3451.7074 | 3436.7891 | 3421.1518 | 3405.5856 | 3390.0903 | 3374.6655 | 3359.3108 | 3359.3108 | 3359.3108 | 3359.3108 | 3359.3108 | 3359.3108 | 3408.514 | 3457.7172 | 3506.9204 | 3556.1236 | 3605.3267 | 3654.5299 | 3703.7331 | 3752.9363 | 3802.1395 | 3851.3427 | 3900.5459 | 3949.749 | 3998.9522 | 4048.1554 | 4097.3586 | 4146.5618 | 4195.765 | 4244.9682 | 4294.1713 | 4343.3745 | 4392.5777 | 4441.7809 | 4490.9841 | 4540.1873 | 4589.3904 | 4638.5936 | 4687.7968 | 4737 | [6 empty] | 748 | 752 | 756 | 760 | 765.6 | 774 | 782 | 790 | 798 | 806 | 813.3 | 808 | 803 | 798 | 793 | 788 | 783 | 778 | 773 | 768 | 763 | 758 | 753 | 748 | 743 | 738 | 733 | 728 | 723 | 718 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | 706.3 | [6 empty] | 3.0697 | 3.0697 | 3.0698 | 3.0698 | 3.0698 | 3.0541 | 3.0385 | 3.023 | 3.0075 | 2.9921 | 2.9764 | 2.9608 | 2.9453 | 2.9298 | 2.9144 | 2.9019 | 2.8894 | 2.8769 | 2.8646 | 2.8522 | 2.8399 | 2.8276 | 2.8154 | 2.8032 | 2.7911 | 2.7784 | 2.7658 | 2.7532 | 2.7407 | 2.7282 | 2.7282 | 2.7282 | 2.7282 | 2.7282 | 2.7282 | 2.7227 | 2.7174 | 2.7122 | 2.7072 | 2.7024 | 2.6977 | 2.6931 | 2.6887 | 2.6844 | 2.6803 | 2.6762 | 2.6723 | 2.6684 | 2.6647 | 2.6611 | 2.6576 | 2.6541 | 2.6508 | 2.6475 | 2.6443 | 2.6412 | 2.6382 | 2.6352 | 2.6324 | 2.6295 | 2.6268 | 2.6241 | 2.6215
148 | Rodney |  |  | 2052 | 348.0896 | 355.0145 | 362.0772 | 369.2804 | 376.627 | 376.9597 | 377.2928 | 377.6261 | 377.9597 | 378.2936 | 378.6264 | 378.9594 | 379.2928 | 379.6264 | 379.9603 | 380.2931 | 380.6261 | 380.9594 | 381.2931 | 381.627 | 381.9597 | 382.2928 | 382.6261 | 382.9597 | 383.2936 | 383.6264 | 383.9594 | 384.2928 | 384.6264 | 384.9603 | 385.2931 | 385.6261 | 385.9594 | 386.2931 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 | 386.627 |  | 1030 | 1049.4425 | 1069.2521 | 1089.4355 | 1110 | 1107.4337 | 1104.8733 | 1102.3188 | 1099.7703 | 1097.2276 | 1094.6297 | 1092.0379 | 1089.4523 | 1086.8728 | 1084.2994 | 1082.0781 | 1079.8613 | 1077.649 | 1075.4413 | 1073.2381 | 1071.0449 | 1068.8563 | 1066.6721 | 1064.4923 | 1062.3171 | 1060.0025 | 1057.6929 | 1055.3884 | 1053.0889 | 1050.7944 | 1051.7027 | 1052.6118 | 1053.5216 | 1054.4323 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | 1055.3438 | [6 empty] | 278 | 279 | 280 | 281 | 282.3 | 285 | 288 | 291 | 294 | 297 | 298.4 | 296 | 294 | 292 | 290 | 288 | 286 | 284 | 282 | 280 | 278 | 276 | 274 | 272 | 270 | 268 | 266 | 264 | 262 | 260 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | 258.8 | [6 empty] | 2.959 | 2.9561 | 2.9531 | 2.9502 | 2.9472 | 2.9378 | 2.9284 | 2.9191 | 2.9098 | 2.9005 | 2.8911 | 2.8817 | 2.8723 | 2.863 | 2.8537 | 2.8454 | 2.8371 | 2.8288 | 2.8205 | 2.8123 | 2.8041 | 2.7959 | 2.7878 | 2.7796 | 2.7715 | 2.7631 | 2.7547 | 2.7463 | 2.738 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296 | 2.7296
149 | Rodney |  |  | 2052 | 116.8171 | 121.4522 | 126.2712 | 131.2815 | 136.4905 | 136.8222 | 137.1547 | 137.4881 | 137.8222 | 138.1572 | 138.4889 | 138.8214 | 139.1548 | 139.4889 | 139.8238 | 140.1556 | 140.4881 | 140.8215 | 141.1556 | 141.4905 | 141.8223 | 142.1548 | 142.4882 | 142.8223 | 143.1572 | 143.489 | 143.8215 | 144.1549 | 144.489 | 144.8238 | 145.1557 | 145.4882 | 145.8216 | 146.1556 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 | 146.4905 |  | 310 | 321.808 | 334.0659 | 346.7906 | 360 | 361.3352 | 362.6754 | 364.0206 | 365.3708 | 366.7259 | 368.0725 | 369.4239 | 370.7803 | 372.1417 | 373.5081 | 374.3943 | 375.2826 | 376.1731 | 377.0656 | 377.9602 | 378.8465 | 379.7348 | 380.6253 | 381.5178 | 382.4124 | 383.2987 | 384.187 | 385.0775 | 385.9699 | 386.8645 | 387.7508 | 388.6392 | 389.5297 | 390.4221 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | 391.3166 | [6 empty] | 245 | 246 | 247 | 248 | 247.8 | 250 | 252 | 254 | 256 | 258 | 261.7 | 260 | 258 | 256 | 254 | 252 | 250 | 248 | 246 | 244 | 242 | 240 | 238 | 236 | 234 | 232 | 230 | 228 | 226 | 224 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | 229.2 | [6 empty] | 2.6537 | 2.6497 | 2.6456 | 2.6416 | 2.6375 | 2.6409 | 2.6443 | 2.6477 | 2.651 | 2.6544 | 2.6578 | 2.6611 | 2.6645 | 2.6679 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713
150 | Rodney |  |  | 2052 | 277.129 | 288.114 | 299.5345 | 311.4076 | 323.7514 | 324.0841 | 324.4171 | 324.7504 | 325.0841 | 325.4181 | 325.7507 | 326.0837 | 326.4171 | 326.7507 | 327.0848 | 327.4174 | 327.7504 | 328.0837 | 328.4174 | 328.7514 | 329.0841 | 329.4171 | 329.7504 | 330.0841 | 330.4181 | 330.7508 | 331.0837 | 331.4171 | 331.7507 | 332.0848 | 332.4174 | 332.7504 | 333.0838 | 333.4174 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 | 333.7514 |  | 920 | 948.6351 | 978.1615 | 1008.607 | 1040 | 1037.508 | 1035.022 | 1032.542 | 1030.0678 | 1027.5997 | 1025.0708 | 1022.5482 | 1020.0317 | 1017.5215 | 1015.0174 | 1013.0789 | 1011.1442 | 1009.2131 | 1007.2856 | 1005.3619 | 1003.4385 | 1001.5188 | 999.6028 | 997.6904 | 995.7817 | 993.7372 | 991.6969 | 989.6607 | 987.6287 | 985.6009 | 986.5653 | 987.5306 | 988.4968 | 989.464 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | 990.4322 | [6 empty] | 577 | 579 | 581 | 583 | 584 | 590 | 596 | 602 | 608 | 614 | 619.1 | 615 | 611 | 607 | 603 | 599 | 595 | 591 | 587 | 583 | 579 | 575 | 571 | 567 | 563 | 559 | 555 | 551 | 547 | 543 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | 536.6 | [6 empty] | 3.3198 | 3.2926 | 3.2656 | 3.2389 | 3.2123 | 3.2014 | 3.1904 | 3.1795 | 3.1686 | 3.1578 | 3.1468 | 3.1358 | 3.1249 | 3.1141 | 3.1032 | 3.0942 | 3.0851 | 3.0761 | 3.0671 | 3.0581 | 3.0492 | 3.0403 | 3.0314 | 3.0225 | 3.0137 | 3.0045 | 2.9953 | 2.9861 | 2.977 | 2.9679 | 2.9679 | 2.9678 | 2.9677 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676 | 2.9676
151 | Rodney | Northwest | Kumeu-Huapai | 2080 | 136.7757 | 138.5797 | 140.4075 | 142.2594 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 144.1358 | 229.4166 | 314.6975 | 399.9784 | 485.2592 | 570.5401 | 655.821 | 741.1018 | 826.3827 | 911.6636 | 996.9444 | 1082.2253 | 1167.5061 | 1252.787 | 1338.0679 | 1423.3487 | 1508.6296 | 1593.9105 | 1679.1913 | 1764.4722 | 1849.7531 | 1935.0339 | 2020.3148 | 2105.5957 | 2190.8765 | 2276.1574 | 2361.4383 | 2446.7191 | 2532 |  | 360 | 364.8991 | 369.8648 | 374.8982 | 380 | 377.2213 | 374.4629 | 371.7246 | 369.0064 | 366.3081 | 363.5278 | 360.7687 | 358.0304 | 355.313 | 352.6162 | 351.8713 | 351.128 | 350.3862 | 349.646 | 348.9074 | 347.6801 | 346.4571 | 345.2384 | 344.024 | 342.8138 | 341.227 | 339.6475 | 338.0753 | 336.5104 | 334.9528 | 334.9533 | 334.9539 | 334.9544 | 334.955 | 334.9555 | 528.4928 | 722.0301 | 915.5674 | 1109.1047 | 1302.642 | 1496.1794 | 1689.7167 | 1883.254 | 2076.7913 | 2270.3286 | 2463.8659 | 2657.4032 | 2850.9405 | 3044.4778 | 3238.0151 | 3431.5524 | 3625.0897 | 3818.627 | 4012.1643 | 4205.7016 | 4399.2389 | 4592.7762 | 4786.3135 | 4979.8508 | 5173.3881 | 5366.9254 | 5560.4627 | 5754 | [6 empty] | 61 | 61 | 61 | 61 | 61.8 | 63 | 64 | 65 | 66 | 67 | 66.7 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 62.4 | 80.4214 | 98.4429 | 116.4643 | 134.4857 | 152.5071 | 170.5286 | 188.55 | 206.5714 | 224.5929 | 242.6143 | 260.6357 | 278.6571 | 296.6786 | 314.7 | 332.7214 | 350.7429 | 368.7643 | 386.7857 | 404.8071 | 422.8286 | 440.85 | 458.8714 | 476.8929 | 494.9143 | 512.9357 | 530.9571 | 548.9786 | 567 | [6 empty] | 2.632 | 2.6331 | 2.6342 | 2.6353 | 2.6364 | 2.6171 | 2.598 | 2.579 | 2.5601 | 2.5414 | 2.5221 | 2.503 | 2.484 | 2.4651 | 2.4464 | 2.4412 | 2.4361 | 2.4309 | 2.4258 | 2.4207 | 2.4122 | 2.4037 | 2.3952 | 2.3868 | 2.3784 | 2.3674 | 2.3564 | 2.3455 | 2.3347 | 2.3239 | 2.3239 | 2.3239 | 2.3239 | 2.3239 | 2.3239 | 2.3036 | 2.2944 | 2.289 | 2.2856 | 2.2832 | 2.2814 | 2.28 | 2.2789 | 2.278 | 2.2773 | 2.2767 | 2.2761 | 2.2757 | 2.2753 | 2.2749 | 2.2746 | 2.2743 | 2.2741 | 2.2739 | 2.2737 | 2.2735 | 2.2733 | 2.2731 | 2.273 | 2.2729 | 2.2727 | 2.2726 | 2.2725
152 | Rodney | Northwest | Kumeu-Huapai | 2080 | 166.8397 | 222.3092 | 296.2207 | 394.7057 | 525.9343 | 534.0761 | 542.344 | 550.7399 | 559.2658 | 567.9236 | 576.2383 | 584.6747 | 593.2347 | 601.9199 | 610.7324 | 613.7429 | 616.7683 | 619.8086 | 622.8639 | 625.9343 | 625.9343 | 625.9343 | 625.9343 | 625.9343 | 625.9343 | 625.9343 | 625.9343 | 625.9343 | 625.9343 | 625.9343 | 625.9343 | 625.9343 | 625.9343 | 625.9343 | 625.9343 | 661.4009 | 696.8675 | 732.3342 | 767.8008 | 803.2674 | 838.7341 | 874.2007 | 909.6673 | 945.134 | 980.6006 | 1016.0672 | 1051.5339 | 1087.0005 | 1122.4671 | 1157.9338 | 1193.4004 | 1228.867 | 1264.3337 | 1299.8003 | 1335.2669 | 1370.7336 | 1406.2002 | 1441.6668 | 1477.1335 | 1512.6001 | 1548.0667 | 1583.5334 | 1619 |  | 490 | 645.9702 | 851.5868 | 1122.6524 | 1480 | 1497.8982 | 1516.0128 | 1534.3465 | 1552.9019 | 1571.6817 | 1589.3424 | 1607.2015 | 1625.2614 | 1643.5242 | 1661.9922 | 1664.6798 | 1667.3718 | 1670.0681 | 1672.7688 | 1675.4739 | 1669.5244 | 1663.596 | 1657.6887 | 1651.8024 | 1645.937 | 1639.1739 | 1632.4386 | 1625.7311 | 1619.051 | 1612.3985 | 1612.3992 | 1612.3999 | 1612.4007 | 1612.4014 | 1612.4021 | 1683.9235 | 1755.4448 | 1826.9662 | 1898.4875 | 1970.0089 | 2041.5302 | 2113.0516 | 2184.5729 | 2256.0943 | 2327.6156 | 2399.137 | 2470.6584 | 2542.1797 | 2613.7011 | 2685.2224 | 2756.7438 | 2828.2651 | 2899.7865 | 2971.3078 | 3042.8292 | 3114.3505 | 3185.8719 | 3257.3932 | 3328.9146 | 3400.4359 | 3471.9573 | 3543.4786 | 3615 | [6 empty] | 1228 | 1234 | 1240 | 1246 | 1251.8 | 1412 | 1572 | 1732 | 1892 | 2052 | 2214.4 | 2200 | 2186 | 2172 | 2158 | 2144 | 2130 | 2116 | 2102 | 2088 | 2074 | 2060 | 2046 | 2032 | 2018 | 2004 | 1990 | 1976 | 1962 | 1948 | 1935.2 | 1966.3357 | 1997.4714 | 2028.6071 | 2059.7429 | 2090.8786 | 2122.0143 | 2153.15 | 2184.2857 | 2215.4214 | 2246.5571 | 2277.6929 | 2308.8286 | 2339.9643 | 2371.1 | 2402.2357 | 2433.3714 | 2464.5071 | 2495.6429 | 2526.7786 | 2557.9143 | 2589.05 | 2620.1857 | 2651.3214 | 2682.4571 | 2713.5929 | 2744.7286 | 2775.8643 | 2807 | [6 empty] | 2.937 | 2.9057 | 2.8748 | 2.8443 | 2.814 | 2.8047 | 2.7953 | 2.786 | 2.7767 | 2.7674 | 2.7581 | 2.7489 | 2.7397 | 2.7305 | 2.7213 | 2.7123 | 2.7034 | 2.6945 | 2.6856 | 2.6768 | 2.6673 | 2.6578 | 2.6483 | 2.6389 | 2.6296 | 2.6188 | 2.608 | 2.5973 | 2.5866 | 2.576 | 2.576 | 2.576 | 2.576 | 2.576 | 2.576 | 2.546 | 2.5191 | 2.4947 | 2.4726 | 2.4525 | 2.4341 | 2.4171 | 2.4015 | 2.3871 | 2.3737 | 2.3612 | 2.3496 | 2.3387 | 2.3285 | 2.319 | 2.31 | 2.3015 | 2.2935 | 2.286 | 2.2788 | 2.272 | 2.2656 | 2.2595 | 2.2536 | 2.2481 | 2.2428 | 2.2377 | 2.2329
153 | Rodney |  |  | 2052 | 169.7789 | 171.5605 | 173.3608 | 175.1799 | 177.0182 | 177.3502 | 177.6829 | 178.0163 | 178.3502 | 178.6848 | 179.0169 | 179.3496 | 179.683 | 180.0169 | 180.3515 | 180.6836 | 181.0163 | 181.3496 | 181.6836 | 182.0182 | 182.3503 | 182.683 | 183.0163 | 183.3503 | 183.6848 | 184.017 | 184.3497 | 184.683 | 185.0169 | 185.3515 | 185.6836 | 186.0164 | 186.3497 | 186.6836 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 | 187.0182 |  | 510 | 514.9281 | 519.9038 | 524.9276 | 530 | 528.9302 | 527.8625 | 526.797 | 525.7336 | 524.6724 | 523.5637 | 522.4573 | 521.3533 | 520.2516 | 519.1523 | 518.3458 | 517.5405 | 516.7365 | 515.9337 | 515.1322 | 514.3246 | 513.5182 | 512.7131 | 511.9093 | 511.1067 | 510.2143 | 509.3235 | 508.4342 | 507.5465 | 506.6603 | 507.5682 | 508.4777 | 509.3889 | 510.3017 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | 511.2162 | [6 empty] | 136 | 136 | 136 | 136 | 135 | 137 | 139 | 141 | 143 | 145 | 145.1 | 144 | 143 | 142 | 141 | 140 | 139 | 138 | 137 | 136 | 135 | 134 | 133 | 132 | 131 | 130 | 129 | 128 | 127 | 126 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | 121.9 | [6 empty] | 3.0039 | 3.0014 | 2.999 | 2.9965 | 2.994 | 2.9824 | 2.9708 | 2.9593 | 2.9478 | 2.9363 | 2.9247 | 2.9131 | 2.9015 | 2.89 | 2.8786 | 2.8688 | 2.8591 | 2.8494 | 2.8397 | 2.8301 | 2.8205 | 2.811 | 2.8015 | 2.792 | 2.7825 | 2.7726 | 2.7628 | 2.753 | 2.7432 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335 | 2.7335
154 | Rodney |  |  | 2052 | 160.6836 | 160.6836 | 160.6836 | 160.6836 | 160.6836 | 161.0155 | 161.3482 | 161.6815 | 162.0155 | 162.3503 | 162.6822 | 163.0149 | 163.3482 | 163.6822 | 164.0169 | 164.3489 | 164.6816 | 165.0149 | 165.3489 | 165.6836 | 166.0156 | 166.3483 | 166.6816 | 167.0156 | 167.3503 | 167.6823 | 168.0149 | 168.3483 | 168.6823 | 169.0169 | 169.3489 | 169.6816 | 170.015 | 170.3489 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 | 170.6836 |  | 510 | 510 | 510 | 510 | 510 | 508.6375 | 507.2787 | 505.9235 | 504.5719 | 503.2239 | 501.8112 | 500.4025 | 498.9978 | 497.5969 | 496.2001 | 495.2437 | 494.2892 | 493.3365 | 492.3856 | 491.4366 | 490.4754 | 489.5161 | 488.5587 | 487.6031 | 486.6494 | 485.5902 | 484.5333 | 483.4787 | 482.4264 | 481.3764 | 482.322 | 483.2695 | 484.2189 | 485.1701 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | 486.1232 | [6 empty] | 143 | 144 | 145 | 146 | 145.9 | 147 | 148 | 149 | 150 | 151 | 154.3 | 153 | 152 | 151 | 150 | 149 | 148 | 147 | 146 | 145 | 144 | 143 | 142 | 141 | 140 | 139 | 138 | 137 | 136 | 135 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | 130.9 | [6 empty] | 3.1739 | 3.1739 | 3.1739 | 3.1739 | 3.1739 | 3.1589 | 3.144 | 3.1291 | 3.1143 | 3.0996 | 3.0846 | 3.0697 | 3.0548 | 3.04 | 3.0253 | 3.0134 | 3.0015 | 2.9896 | 2.9779 | 2.9661 | 2.9544 | 2.9427 | 2.9311 | 2.9195 | 2.908 | 2.8959 | 2.8839 | 2.8719 | 2.86 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481 | 2.8481
155 | Rodney |  |  | 2052 | 136.8162 | 138.6241 | 140.4559 | 142.3119 | 144.1925 | 144.5243 | 144.8568 | 145.1902 | 145.5243 | 145.8591 | 146.191 | 146.5235 | 146.8569 | 147.191 | 147.5258 | 147.8576 | 148.1902 | 148.5236 | 148.8576 | 149.1925 | 149.5243 | 149.8569 | 150.1902 | 150.5243 | 150.8591 | 151.191 | 151.5236 | 151.8569 | 152.191 | 152.5258 | 152.8577 | 153.1903 | 153.5236 | 153.8577 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 | 154.1925 |  | 360 | 364.8991 | 369.8648 | 374.8982 | 380 | 380.1089 | 380.2179 | 380.3269 | 380.4359 | 380.545 | 380.6364 | 380.7278 | 380.8192 | 380.9106 | 381.0021 | 381.0203 | 381.0386 | 381.0568 | 381.0751 | 381.0933 | 381.1077 | 381.1221 | 381.1364 | 381.1508 | 381.1652 | 381.1359 | 381.1066 | 381.0773 | 381.048 | 381.0187 | 381.8478 | 382.6787 | 383.5113 | 384.3458 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | 385.1821 | [6 empty] | 57 | 57 | 57 | 57 | 57.4 | 58 | 59 | 60 | 61 | 62 | 62.8 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | [6 empty] | 2.6313 | 2.6323 | 2.6333 | 2.6343 | 2.6354 | 2.6301 | 2.6248 | 2.6195 | 2.6142 | 2.609 | 2.6037 | 2.5984 | 2.5931 | 2.5879 | 2.5826 | 2.5769 | 2.5713 | 2.5656 | 2.56 | 2.5544 | 2.5488 | 2.5432 | 2.5377 | 2.5322 | 2.5266 | 2.5209 | 2.5152 | 2.5094 | 2.5037 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981 | 2.4981
156 | Waitakere Ranges |  |  | 2052 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 | 333.14 |  | 970 | 970 | 970 | 970 | 970 | 968.5892 | 967.1805 | 965.7738 | 964.3692 | 962.9666 | 961.5558 | 960.147 | 958.7403 | 957.3357 | 955.9332 | 953.8364 | 951.7442 | 949.6566 | 947.5735 | 945.4951 | 943.3982 | 941.3059 | 939.2183 | 937.1353 | 935.057 | 932.96 | 930.8677 | 928.7801 | 926.6972 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | 924.6189 | [6 empty] | 154 | 154 | 154 | 154 | 153.7 | 156 | 158 | 160 | 162 | 164 | 165.1 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | 180.2 | [6 empty] | 2.9117 | 2.9117 | 2.9117 | 2.9117 | 2.9117 | 2.9075 | 2.9032 | 2.899 | 2.8948 | 2.8906 | 2.8863 | 2.8821 | 2.8779 | 2.8737 | 2.8695 | 2.8632 | 2.8569 | 2.8506 | 2.8444 | 2.8381 | 2.8318 | 2.8256 | 2.8193 | 2.813 | 2.8068 | 2.8005 | 2.7942 | 2.788 | 2.7817 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755 | 2.7755
157 | Henderson - Massey | Northwest | Redhills | 2065 | 30.3177 | 31.2365 | 32.1832 | 33.1586 | 34.1636 | 35.4125 | 36.7071 | 38.049 | 39.44 | 40.8819 | 42.1682 | 43.495 | 44.8636 | 46.2752 | 47.7313 | 48.3911 | 49.0601 | 49.7383 | 50.4259 | 51.123 | 51.3992 | 51.677 | 51.9563 | 52.237 | 52.5193 | 52.8098 | 53.1019 | 53.3956 | 53.6909 | 53.9879 | 54.221 | 54.4551 | 54.6903 | 54.9264 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 | 55.1636 |  | 110 | 112.419 | 114.8913 | 117.4178 | 120 | 122.9359 | 125.9435 | 129.0248 | 132.1814 | 135.4153 | 138.3031 | 141.2525 | 144.2648 | 147.3413 | 150.4835 | 151.6274 | 152.7801 | 153.9415 | 155.1118 | 156.2909 | 156.9685 | 157.649 | 158.3324 | 159.0188 | 159.7082 | 160.4206 | 161.1362 | 161.855 | 162.577 | 163.3022 | 163.8737 | 164.4472 | 165.0226 | 165.6001 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | 166.1796 | [6 empty] | 158 | 160 | 162 | 164 | 165.8 | 168 | 170 | 172 | 174 | 176 | 176.6 | 178 | 180 | 182 | 184 | 186 | 188 | 190 | 192 | 194 | 196 | 198 | 200 | 202 | 204 | 206 | 208 | 210 | 212 | 214 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | 212.8 | [6 empty] | 3.6282 | 3.599 | 3.5699 | 3.5411 | 3.5125 | 3.4715 | 3.431 | 3.391 | 3.3515 | 3.3124 | 3.2798 | 3.2476 | 3.2156 | 3.184 | 3.1527 | 3.1334 | 3.1141 | 3.095 | 3.076 | 3.0572 | 3.0539 | 3.0507 | 3.0474 | 3.0442 | 3.0409 | 3.0377 | 3.0345 | 3.0312 | 3.028 | 3.0248 | 3.0223 | 3.0199 | 3.0174 | 3.0149 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125 | 3.0125
158 | Rodney | Northwest | Redhills | 2065 | 27.2859 | 27.2859 | 27.2859 | 27.2859 | 27.2859 | 57.2582 | 120.1538 | 252.1373 | 529.0988 | 1110.2902 | 1274.6811 | 1463.4119 | 1680.0864 | 1928.842 | 2214.4287 | 2287.8188 | 2363.6412 | 2441.9765 | 2522.908 | 2606.5217 | 2606.5217 | 2606.5217 | 2606.5217 | 2606.5217 | 2606.5217 | 2606.5217 | 2606.5217 | 2606.5217 | 2606.5217 | 2606.5217 | 2606.5217 | 2606.5217 | 2606.5217 | 2606.5217 | 2606.5217 | 2654.5585 | 2702.5953 | 2750.632 | 2798.6688 | 2846.7056 | 2894.7424 | 2942.7792 | 2990.816 | 3038.8528 | 3086.8896 | 3134.9264 | 3182.9632 | 3231 | 3231 | 3231 | 3231 | 3231 | 3231 | 3231 | 3231 | 3231 | 3231 | 3231 | 3231 | 3231 | 3231 | 3231 | 3231 |  | 70 | 70 | 70 | 70 | 70 | 146.7989 | 307.8562 | 645.6137 | 1353.9345 | 2839.3738 | 3258.7047 | 3739.9642 | 4292.2982 | 4926.2032 | 5653.7261 | 5815.8178 | 5982.5567 | 6154.0759 | 6330.5126 | 6512.0077 | 6482.6061 | 6453.3371 | 6424.2003 | 6395.1951 | 6366.3209 | 6336.0193 | 6305.862 | 6275.8483 | 6245.9774 | 6216.2486 | 6216.2486 | 6216.2486 | 6216.2486 | 6216.2486 | 6216.2486 | 6322.0757 | 6427.9027 | 6533.7297 | 6639.5567 | 6745.3838 | 6851.2108 | 6957.0378 | 7062.8649 | 7168.6919 | 7274.5189 | 7380.3459 | 7486.173 | 7592 | 7592 | 7592 | 7592 | 7592 | 7592 | 7592 | 7592 | 7592 | 7592 | 7592 | 7592 | 7592 | 7592 | 7592 | 7592 | [6 empty] | 15 | 15 | 15 | 15 | 14.6 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 13.9 | 63.9077 | 113.9154 | 163.9231 | 213.9308 | 263.9385 | 313.9462 | 363.9538 | 413.9615 | 463.9692 | 513.9769 | 563.9846 | 613.9923 | 664 | 664 | 664 | 664 | 664 | 664 | 664 | 664 | 664 | 664 | 664 | 664 | 664 | 664 | 664 | 664 | [6 empty] | 2.5654 | 2.5654 | 2.5654 | 2.5654 | 2.5654 | 2.5638 | 2.5622 | 2.5606 | 2.5589 | 2.5573 | 2.5565 | 2.5556 | 2.5548 | 2.554 | 2.5531 | 2.5421 | 2.5311 | 2.5201 | 2.5092 | 2.4984 | 2.4871 | 2.4758 | 2.4647 | 2.4535 | 2.4425 | 2.4308 | 2.4193 | 2.4077 | 2.3963 | 2.3849 | 2.3849 | 2.3849 | 2.3849 | 2.3849 | 2.3849 | 2.3816 | 2.3784 | 2.3754 | 2.3724 | 2.3695 | 2.3668 | 2.3641 | 2.3615 | 2.359 | 2.3566 | 2.3542 | 2.352 | 2.3497 | 2.3497 | 2.3497 | 2.3497 | 2.3497 | 2.3497 | 2.3497 | 2.3497 | 2.3497 | 2.3497 | 2.3497 | 2.3497 | 2.3497 | 2.3497 | 2.3497 | 2.3497
159 | Henderson - Massey | Northwest | Redhills | 2065 | 24.2541 | 29.0915 | 34.8936 | 41.8529 | 50.2002 | 102.7028 | 210.1159 | 429.8684 | 879.4519 | 1799.2382 | 2064.9329 | 2369.8628 | 2719.8219 | 3121.4597 | 3582.4076 | 3700.9443 | 3823.4032 | 3949.9142 | 4080.6111 | 4215.6327 | 4215.6327 | 4215.6327 | 4215.6327 | 4215.6327 | 4215.6327 | 4215.6327 | 4215.6327 | 4215.6327 | 4215.6327 | 4215.6327 | 4215.6327 | 4215.6327 | 4215.6327 | 4215.6327 | 4215.6327 | 4250.1994 | 4284.7661 | 4319.3328 | 4353.8996 | 4388.4663 | 4423.033 | 4457.5997 | 4492.1664 | 4526.7331 | 4561.2999 | 4595.8666 | 4630.4333 | 4665 | 4665 | 4665 | 4665 | 4665 | 4665 | 4665 | 4665 | 4665 | 4665 | 4665 | 4665 | 4665 | 4665 | 4665 | 4665 |  | 80 | 93.6139 | 109.5445 | 128.1861 | 150 | 302.5718 | 610.3313 | 1231.1269 | 2483.3618 | 5009.3017 | 5776.2138 | 6660.5383 | 7680.2508 | 8856.0789 | 10211.9234 | 10506.0516 | 10808.6515 | 11119.9669 | 11440.2491 | 11769.7561 | 11698.832 | 11628.3354 | 11558.2635 | 11488.6139 | 11419.384 | 11139.0533 | 10865.6043 | 10598.8681 | 10338.6799 | 10084.879 | 10084.8793 | 10084.8795 | 10084.8797 | 10084.8799 | 10084.8801 | 10154.274 | 10223.6678 | 10293.0616 | 10362.4555 | 10431.8493 | 10501.2431 | 10570.637 | 10640.0308 | 10709.4247 | 10778.8185 | 10848.2123 | 10917.6062 | 10987 | 10987 | 10987 | 10987 | 10987 | 10987 | 10987 | 10987 | 10987 | 10987 | 10987 | 10987 | 10987 | 10987 | 10987 | 10987 | [6 empty] | 4 | 5 | 6 | 7 | 7.8 | 15 | 22 | 29 | 36 | 43 | 49.9 | 67 | 84 | 101 | 118 | 135 | 152 | 169 | 186 | 203 | 220 | 237 | 254 | 271 | 288 | 305 | 322 | 339 | 356 | 373 | 395.3 | 439.3538 | 483.4077 | 527.4615 | 571.5154 | 615.5692 | 659.6231 | 703.6769 | 747.7308 | 791.7846 | 835.8385 | 879.8923 | 923.9462 | 968 | 968 | 968 | 968 | 968 | 968 | 968 | 968 | 968 | 968 | 968 | 968 | 968 | 968 | 968 | 968 | [6 empty] | 3.2984 | 3.2179 | 3.1394 | 3.0628 | 2.988 | 2.9461 | 2.9047 | 2.864 | 2.8238 | 2.7841 | 2.7973 | 2.8105 | 2.8238 | 2.8372 | 2.8506 | 2.8387 | 2.827 | 2.8152 | 2.8036 | 2.7919 | 2.7751 | 2.7584 | 2.7418 | 2.7252 | 2.7088 | 2.6423 | 2.5775 | 2.5142 | 2.4525 | 2.3923 | 2.3923 | 2.3923 | 2.3923 | 2.3923 | 2.3923 | 2.3891 | 2.3861 | 2.383 | 2.38 | 2.3771 | 2.3742 | 2.3714 | 2.3686 | 2.3658 | 2.3631 | 2.3604 | 2.3578 | 2.3552 | 2.3552 | 2.3552 | 2.3552 | 2.3552 | 2.3552 | 2.3552 | 2.3552 | 2.3552 | 2.3552 | 2.3552 | 2.3552 | 2.3552 | 2.3552 | 2.3552 | 2.3552
160 | Henderson - Massey | Northwest | Redhills | 2065 | 54.5718 | 56.9413 | 59.4137 | 61.9935 | 64.6853 | 97.8697 | 148.0782 | 224.0444 | 338.9823 | 512.885 | 582.5795 | 661.7446 | 751.6672 | 853.8092 | 969.831 | 1008.0299 | 1047.7333 | 1089.0005 | 1131.8931 | 1176.4751 | 1189.1179 | 1201.8966 | 1214.8127 | 1227.8675 | 1241.0626 | 1257.5762 | 1274.3094 | 1291.2654 | 1308.4469 | 1325.857 | 1341.1848 | 1356.6897 | 1372.3739 | 1388.2394 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 | 1404.2884 |  | 180 | 187.0722 | 194.4222 | 202.061 | 210 | 308.5799 | 453.4359 | 666.2915 | 979.0674 | 1438.6691 | 1606.7704 | 1794.5136 | 2004.1936 | 2238.3738 | 2499.9167 | 2584.6068 | 2672.1661 | 2762.6916 | 2856.2838 | 2953.0467 | 2970.7438 | 2988.547 | 3006.4568 | 3024.474 | 3042.5991 | 3069.7929 | 3097.2298 | 3124.9119 | 3152.8415 | 3181.0206 | 3217.5304 | 3254.4593 | 3291.812 | 3329.5934 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | 3367.8085 | [6 empty] | 143 | 145 | 147 | 149 | 149.1 | 151 | 153 | 155 | 157 | 159 | 161.6 | 163 | 165 | 167 | 169 | 171 | 173 | 175 | 177 | 179 | 181 | 183 | 185 | 187 | 189 | 191 | 193 | 195 | 197 | 199 | 191.8 | 201.4308 | 211.0615 | 220.6923 | 230.3231 | 239.9538 | 249.5846 | 259.2154 | 268.8462 | 278.4769 | 288.1077 | 297.7385 | 307.3692 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | [6 empty] | 3.2984 | 3.2854 | 3.2723 | 3.2594 | 3.2465 | 3.153 | 3.0621 | 2.9739 | 2.8883 | 2.8051 | 2.758 | 2.7118 | 2.6663 | 2.6216 | 2.5777 | 2.564 | 2.5504 | 2.5369 | 2.5235 | 2.5101 | 2.4983 | 2.4865 | 2.4748 | 2.4632 | 2.4516 | 2.441 | 2.4305 | 2.42 | 2.4096 | 2.3992 | 2.399 | 2.3988 | 2.3986 | 2.3984 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982 | 2.3982
161 | Henderson - Massey | Northwest | Redhills | 2065 | 36.8448 | 65.5235 | 116.5248 | 207.2239 | 368.5202 | 467.5772 | 593.2604 | 752.7269 | 955.0574 | 1211.7738 | 1348.9427 | 1501.6388 | 1671.6195 | 1860.8416 | 2071.4829 | 2129.2308 | 2188.5886 | 2249.6011 | 2312.3144 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 | 2376.7761 |  | 80 | 148.8968 | 277.1281 | 515.7936 | 960 | 1222.4883 | 1556.7476 | 1982.4018 | 2524.4407 | 3214.6868 | 3584.0848 | 3995.9301 | 4455.1004 | 4967.0337 | 5537.793 | 5661.1915 | 5787.3398 | 5916.299 | 6048.1317 | 6182.9021 | 6147.221 | 6111.7457 | 6076.4752 | 6041.4082 | 6006.5436 | 5970.4449 | 5934.5632 | 5898.8971 | 5863.4453 | 5828.2067 | 5828.2067 | 5828.2067 | 5828.2067 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | 5828.2068 | [6 empty] | 51 | 51 | 51 | 51 | 52.9 | 54 | 55 | 56 | 57 | 58 | 59.7 | 62 | 64 | 66 | 68 | 70 | 72 | 74 | 76 | 78 | 80 | 82 | 84 | 86 | 88 | 90 | 92 | 94 | 96 | 98 | 97.2 | 131.1077 | 165.0154 | 198.9231 | 232.8308 | 266.7385 | 300.6462 | 334.5538 | 368.4615 | 402.3692 | 436.2769 | 470.1846 | 504.0923 | 538 | 538 | 538 | 538 | 538 | 538 | 538 | 538 | 538 | 538 | 538 | 538 | 538 | 538 | 538 | 538 | [6 empty] | 2.1713 | 2.2724 | 2.3783 | 2.4891 | 2.605 | 2.6145 | 2.6241 | 2.6336 | 2.6432 | 2.6529 | 2.657 | 2.661 | 2.6651 | 2.6692 | 2.6733 | 2.6588 | 2.6443 | 2.6299 | 2.6156 | 2.6014 | 2.5864 | 2.5714 | 2.5566 | 2.5418 | 2.5272 | 2.512 | 2.4969 | 2.4819 | 2.467 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521 | 2.4521
162 | Rodney |  |  | 2052 | 72.7624 | 77.2203 | 81.9513 | 86.9721 | 92.3005 | 93.2063 | 94.121 | 95.0447 | 95.9775 | 96.9194 | 97.8434 | 98.7762 | 99.7179 | 100.6686 | 101.6283 | 101.9606 | 102.2939 | 102.6284 | 102.9639 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 | 103.3005 |  | 250 | 263.8125 | 278.3882 | 293.7692 | 310 | 310.963 | 311.9289 | 312.8979 | 313.8699 | 314.8448 | 315.6625 | 316.4823 | 317.3042 | 318.1282 | 318.9544 | 318.2073 | 317.462 | 316.7184 | 315.9766 | 315.2365 | 313.4543 | 311.6821 | 309.92 | 308.1678 | 306.4255 | 304.6041 | 302.7935 | 300.9937 | 299.2046 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | 297.4261 | [6 empty] | 147 | 147 | 147 | 147 | 148.6 | 150 | 151 | 152 | 153 | 154 | 157.2 | 156 | 155 | 154 | 153 | 152 | 151 | 150 | 149 | 148 | 147 | 146 | 145 | 144 | 143 | 142 | 141 | 140 | 139 | 138 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | 134.8 | [6 empty] | 3.4358 | 3.4164 | 3.397 | 3.3777 | 3.3586 | 3.3363 | 3.3141 | 3.2921 | 3.2702 | 3.2485 | 3.2262 | 3.204 | 3.182 | 3.1602 | 3.1384 | 3.1209 | 3.1034 | 3.0861 | 3.0688 | 3.0516 | 3.0344 | 3.0172 | 3.0002 | 2.9832 | 2.9663 | 2.9487 | 2.9312 | 2.9138 | 2.8964 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792 | 2.8792
163 | Henderson - Massey | Northwest | Redhills | 2065 | 90.953 | 91.8142 | 92.6835 | 93.5611 | 94.4469 | 94.4469 | 94.4469 | 94.4469 | 94.4469 | 94.4469 | 94.4469 | 94.4469 | 94.4469 | 94.4469 | 94.4469 | 94.7477 | 95.0494 | 95.3521 | 95.6557 | 95.9603 | 121.3716 | 153.512 | 194.1636 | 245.5801 | 310.6121 | 390.296 | 490.4217 | 616.2335 | 774.3207 | 972.9634 | 1081.1384 | 1201.3404 | 1334.9065 | 1483.3227 | 1648.24 | 1793.0677 | 1937.8954 | 2082.723 | 2227.5507 | 2372.3784 | 2517.2061 | 2662.0338 | 2806.8615 | 2951.6892 | 3096.5169 | 3241.3446 | 3386.1723 | 3531 | 3531 | 3531 | 3531 | 3531 | 3531 | 3531 | 3531 | 3531 | 3531 | 3531 | 3531 | 3531 | 3531 | 3531 | 3531 |  | 340 | 342.4729 | 344.9638 | 347.4728 | 350 | 349.6238 | 349.2481 | 348.8727 | 348.4978 | 348.1232 | 347.747 | 347.3713 | 346.9959 | 346.621 | 346.2464 | 345.4883 | 344.7318 | 343.977 | 343.2238 | 342.4723 | 430.4416 | 541.0071 | 679.9731 | 854.6346 | 1074.1605 | 1342.0718 | 1676.804 | 2095.0232 | 2617.5524 | 3270.408 | 3634.0151 | 4038.0484 | 4487.0025 | 4985.8717 | 5540.2057 | 5788.9591 | 6037.7125 | 6286.4659 | 6535.2194 | 6783.9728 | 7032.7262 | 7281.4796 | 7530.233 | 7778.9864 | 8027.7398 | 8276.4932 | 8525.2466 | 8774 | 8774 | 8774 | 8774 | 8774 | 8774 | 8774 | 8774 | 8774 | 8774 | 8774 | 8774 | 8774 | 8774 | 8774 | 8774 | [6 empty] | 292 | 220 | 148 | 76 | 5.8 | 6 | 6 | 6 | 6 | 6 | 7 | 26 | 45 | 64 | 83 | 102 | 121 | 140 | 159 | 178 | 197 | 216 | 235 | 254 | 273 | 292 | 311 | 330 | 349 | 368 | 392 | 492.5385 | 593.0769 | 693.6154 | 794.1538 | 894.6923 | 995.2308 | 1095.7692 | 1196.3077 | 1296.8462 | 1397.3846 | 1497.9231 | 1598.4615 | 1699 | 1699 | 1699 | 1699 | 1699 | 1699 | 1699 | 1699 | 1699 | 1699 | 1699 | 1699 | 1699 | 1699 | 1699 | 1699 | [6 empty] | 3.7382 | 3.7301 | 3.722 | 3.7139 | 3.7058 | 3.7018 | 3.6978 | 3.6938 | 3.6899 | 3.6859 | 3.6819 | 3.678 | 3.674 | 3.67 | 3.666 | 3.6464 | 3.6269 | 3.6074 | 3.5881 | 3.5689 | 3.5465 | 3.5242 | 3.5021 | 3.4801 | 3.4582 | 3.4386 | 3.4191 | 3.3997 | 3.3804 | 3.3613 | 3.3613 | 3.3613 | 3.3613 | 3.3613 | 3.3613 | 3.2285 | 3.1156 | 3.0184 | 2.9338 | 2.8596 | 2.7939 | 2.7353 | 2.6828 | 2.6354 | 2.5925 | 2.5534 | 2.5177 | 2.4848 | 2.4848 | 2.4848 | 2.4848 | 2.4848 | 2.4848 | 2.4848 | 2.4848 | 2.4848 | 2.4848 | 2.4848 | 2.4848 | 2.4848 | 2.4848 | 2.4848 | 2.4848
164 | Henderson - Massey | Northwest | Westgate | 2060 | 12.1271 | 11.2855 | 10.5023 | 9.7735 | 9.0953 | 10.7814 | 12.78 | 15.1491 | 17.9574 | 21.2862 | 33.2559 | 51.9565 | 81.1727 | 126.8178 | 198.1301 | 227.3663 | 260.9167 | 299.4177 | 343.6 | 394.3019 | 452.7087 | 519.7673 | 596.759 | 685.1552 | 786.6454 | 852.9531 | 924.85 | 1002.8072 | 1087.3356 | 1178.989 | 1242.4105 | 1309.2437 | 1379.672 | 1453.8889 | 1532.0982 | 1646.2109 | 1760.3236 | 1874.4364 | 1988.5491 | 2102.6618 | 2216.7745 | 2330.8873 | 2445 | 2445 | 2445 | 2445 | 2445 | 2445 | 2445 | 2445 | 2445 | 2445 | 2445 | 2445 | 2445 | 2445 | 2445 | 2445 | 2445 | 2445 | 2445 | 2445 | 2445 |  | 40 | 37.2242 | 34.641 | 32.2371 | 30 | 35.3838 | 41.7338 | 49.2234 | 58.057 | 68.4759 | 108.4552 | 171.7762 | 272.0668 | 430.9115 | 682.4968 | 777.2436 | 885.1434 | 1008.0223 | 1147.9597 | 1307.3237 | 1490.7209 | 1699.8459 | 1938.3079 | 2210.2224 | 2520.2822 | 2713.3934 | 2921.3013 | 3145.1397 | 3386.1292 | 3645.5841 | 3841.6915 | 4048.3482 | 4266.1216 | 4495.6098 | 4737.4428 | 5040.0124 | 5342.5821 | 5645.1517 | 5947.7214 | 6250.291 | 6552.8607 | 6855.4303 | 7158 | 7158 | 7158 | 7158 | 7158 | 7158 | 7158 | 7158 | 7158 | 7158 | 7158 | 7158 | 7158 | 7158 | 7158 | 7158 | 7158 | 7158 | 7158 | 7158 | 7158 | [6 empty] | 2560 | 2584 | 2608 | 2632 | 2656.2 | 2691 | 2726 | 2761 | 2796 | 2831 | 2864 | 2891 | 2918 | 2945 | 2972 | 2999 | 3026 | 3053 | 3080 | 3107 | 3134 | 3161 | 3188 | 3215 | 3242 | 3269 | 3296 | 3323 | 3350 | 3377 | 3413.4 | 4321.725 | 5230.05 | 6138.375 | 7046.7 | 7955.025 | 8863.35 | 9771.675 | 10680 | 10680 | 10680 | 10680 | 10680 | 10680 | 10680 | 10680 | 10680 | 10680 | 10680 | 10680 | 10680 | 10680 | 10680 | 10680 | 10680 | 10680 | 10680 | 10680 | 10680 | [6 empty] | 3.2984 | 3.2984 | 3.2984 | 3.2984 | 3.2984 | 3.2819 | 3.2656 | 3.2493 | 3.233 | 3.2169 | 3.2612 | 3.3062 | 3.3517 | 3.3979 | 3.4447 | 3.4185 | 3.3924 | 3.3666 | 3.341 | 3.3155 | 3.2929 | 3.2704 | 3.2481 | 3.2259 | 3.2038 | 3.1812 | 3.1587 | 3.1363 | 3.1142 | 3.0921 | 3.0921 | 3.0921 | 3.0921 | 3.0921 | 3.0921 | 3.0616 | 3.035 | 3.0117 | 2.991 | 2.9726 | 2.956 | 2.9411 | 2.9276 | 2.9276 | 2.9276 | 2.9276 | 2.9276 | 2.9276 | 2.9276 | 2.9276 | 2.9276 | 2.9276 | 2.9276 | 2.9276 | 2.9276 | 2.9276 | 2.9276 | 2.9276 | 2.9276 | 2.9276 | 2.9276 | 2.9276 | 2.9276
165 | Upper Harbour | Northwest | Whenuapai | 2080 | 60.6354 | 58.2211 | 55.903 | 53.6772 | 51.5401 | 51.5401 | 51.5401 | 51.5401 | 51.5401 | 51.5401 | 53.2159 | 54.9462 | 56.7327 | 58.5774 | 60.482 | 67.246 | 74.7665 | 83.1281 | 92.4247 | 102.7611 | 128.4968 | 160.6777 | 200.9181 | 251.2364 | 314.1565 | 348.2089 | 385.9525 | 427.7871 | 474.1564 | 525.5518 | 545.1709 | 565.5223 | 586.6335 | 608.5327 | 631.2495 | 651.3835 | 671.5174 | 691.6513 | 711.7853 | 731.9192 | 752.0532 | 772.1871 | 792.3211 | 812.455 | 832.589 | 852.7229 | 872.8569 | 892.9908 | 913.1248 | 933.2587 | 953.3926 | 973.5266 | 993.6605 | 1013.7945 | 1033.9284 | 1054.0624 | 1074.1963 | 1094.3303 | 1114.4642 | 1134.5982 | 1154.7321 | 1174.8661 | 1195 |  | 200 | 192.0369 | 184.3909 | 177.0493 | 170 | 169.7889 | 169.578 | 169.3674 | 169.157 | 168.9469 | 174.2222 | 179.6622 | 185.272 | 191.057 | 197.0226 | 214.8911 | 234.3801 | 255.6366 | 278.8208 | 304.1078 | 375.7384 | 464.2411 | 573.5901 | 708.6955 | 875.6241 | 966.0239 | 1065.7567 | 1175.7859 | 1297.1746 | 1431.0955 | 1484.5033 | 1539.9041 | 1597.3726 | 1656.9857 | 1718.8235 | 1763.2941 | 1807.7647 | 1852.2353 | 1896.7059 | 1941.1765 | 1985.6471 | 2030.1177 | 2074.5882 | 2119.0588 | 2163.5294 | 2208 | 2252.4706 | 2296.9412 | 2341.4118 | 2385.8824 | 2430.3529 | 2474.8235 | 2519.2941 | 2563.7647 | 2608.2353 | 2652.7059 | 2697.1765 | 2741.6471 | 2786.1176 | 2830.5882 | 2875.0588 | 2919.5294 | 2964 | [6 empty] | 241 | 1515 | 2789 | 4063 | 5336.3 | 5002 | 4668 | 4334 | 4000 | 3666 | 3329.9 | 3600 | 3870 | 4140 | 4410 | 4680 | 4950 | 5220 | 5490 | 5760 | 6030 | 6300 | 6570 | 6840 | 7110 | 7380 | 7650 | 7920 | 8190 | 8460 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | 8728.2 | [6 empty] | 3.2984 | 3.2984 | 3.2984 | 3.2984 | 3.2984 | 3.2943 | 3.2902 | 3.2861 | 3.282 | 3.278 | 3.2739 | 3.2698 | 3.2657 | 3.2616 | 3.2575 | 3.1956 | 3.1348 | 3.0752 | 3.0167 | 2.9594 | 2.9241 | 2.8893 | 2.8548 | 2.8208 | 2.7872 | 2.7743 | 2.7614 | 2.7485 | 2.7358 | 2.723 | 2.723 | 2.723 | 2.7229 | 2.7229 | 2.7229 | 2.707 | 2.6921 | 2.678 | 2.6647 | 2.6522 | 2.6403 | 2.629 | 2.6184 | 2.6082 | 2.5986 | 2.5894 | 2.5806 | 2.5722 | 2.5642 | 2.5565 | 2.5492 | 2.5421 | 2.5354 | 2.5289 | 2.5226 | 2.5166 | 2.5109 | 2.5053 | 2.5 | 2.4948 | 2.4898 | 2.485 | 2.4803
166 | Upper Harbour | Northwest | Whenuapai | 2080 | 37.5128 | 35.4774 | 33.5525 | 31.732 | 30.0102 | 30.0102 | 30.0102 | 30.0102 | 30.0102 | 30.0102 | 30.0102 | 30.0102 | 30.0102 | 30.0102 | 30.0102 | 35.2598 | 41.4277 | 48.6745 | 57.189 | 67.1929 | 75.6202 | 85.1044 | 95.7781 | 107.7905 | 121.3096 | 125.9365 | 130.7399 | 135.7266 | 140.9034 | 146.2777 | 146.2777 | 146.2777 | 146.2777 | 146.2777 | 146.2777 | 149.9821 | 153.6864 | 157.3908 | 161.0952 | 164.7995 | 168.5039 | 172.2083 | 175.9126 | 179.617 | 183.3214 | 187.0257 | 190.7301 | 194.4345 | 198.1388 | 201.8432 | 205.5476 | 209.2519 | 212.9563 | 216.6607 | 220.3651 | 224.0694 | 227.7738 | 231.4782 | 235.1825 | 238.8869 | 242.5913 | 246.2956 | 250 |  | 50 | 47.2871 | 44.7214 | 42.2949 | 40 | 41.1666 | 42.3673 | 43.603 | 44.8748 | 46.1836 | 47.3589 | 48.5642 | 49.8001 | 51.0675 | 52.3672 | 64.0844 | 78.4233 | 95.9707 | 117.4442 | 143.7225 | 163.4638 | 185.9168 | 211.4538 | 240.4985 | 273.5327 | 283.4345 | 293.6947 | 304.3264 | 315.3429 | 326.7582 | 326.7582 | 326.7582 | 326.7582 | 326.7582 | 326.7582 | 336.4097 | 346.0612 | 355.7127 | 365.3642 | 375.0157 | 384.6672 | 394.3187 | 403.9702 | 413.6217 | 423.2731 | 432.9246 | 442.5761 | 452.2276 | 461.8791 | 471.5306 | 481.1821 | 490.8336 | 500.4851 | 510.1366 | 519.7881 | 529.4396 | 539.091 | 548.7425 | 558.394 | 568.0455 | 577.697 | 587.3485 | 597 | [6 empty] | 1 | 22 | 43 | 64 | 84 | 98 | 112 | 126 | 140 | 154 | 168.2 | 280 | 392 | 504 | 616 | 728 | 840 | 952 | 1064 | 1176 | 1288 | 1400 | 1512 | 1624 | 1736 | 1848 | 1960 | 2072 | 2184 | 2296 | 2409.3 | 2416.9679 | 2424.6357 | 2432.3036 | 2439.9714 | 2447.6393 | 2455.3071 | 2462.975 | 2470.6429 | 2478.3107 | 2485.9786 | 2493.6464 | 2501.3143 | 2508.9821 | 2516.65 | 2524.3179 | 2531.9857 | 2539.6536 | 2547.3214 | 2554.9893 | 2562.6571 | 2570.325 | 2577.9929 | 2585.6607 | 2593.3286 | 2600.9964 | 2608.6643 | 2616.3321 | 2624 | [6 empty] | 1.3329 | 1.3329 | 1.3329 | 1.3329 | 1.3329 | 1.3718 | 1.4118 | 1.4529 | 1.4953 | 1.5389 | 1.5781 | 1.6183 | 1.6594 | 1.7017 | 1.745 | 1.8175 | 1.893 | 1.9717 | 2.0536 | 2.139 | 2.1616 | 2.1846 | 2.2077 | 2.2312 | 2.2548 | 2.2506 | 2.2464 | 2.2422 | 2.238 | 2.2338 | 2.2338 | 2.2338 | 2.2338 | 2.2338 | 2.2338 | 2.243 | 2.2517 | 2.2601 | 2.268 | 2.2756 | 2.2828 | 2.2898 | 2.2964 | 2.3028 | 2.3089 | 2.3148 | 2.3204 | 2.3259 | 2.3311 | 2.3361 | 2.341 | 2.3457 | 2.3502 | 2.3545 | 2.3588 | 2.3628 | 2.3668 | 2.3706 | 2.3743 | 2.3779 | 2.3814 | 2.3847 | 2.388
167 | Upper Harbour | Northwest | Whenuapai | 2080 | 263.7636 | 252.011 | 240.7821 | 230.0535 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 219.803 | 223.2386 | 226.6742 | 230.1098 | 233.5454 | 236.981 | 240.4166 | 243.8522 | 247.2878 | 250.7234 | 254.1591 | 257.5947 | 261.0303 | 264.4659 | 267.9015 | 271.3371 | 274.7727 | 278.2083 | 281.6439 | 285.0795 | 288.5151 | 291.9507 | 295.3864 | 298.822 | 302.2576 | 305.6932 | 309.1288 | 312.5644 | 316 |  | 720 | 687.9188 | 657.2671 | 627.9811 | 600 | 600.4802 | 600.9607 | 601.4417 | 601.923 | 602.4047 | 602.8849 | 603.3655 | 603.8464 | 604.3277 | 604.8095 | 604.3569 | 603.9046 | 603.4527 | 603.0012 | 602.5499 | 602.0973 | 601.6451 | 601.1932 | 600.7416 | 600.2904 | 599.8378 | 599.3855 | 598.9336 | 598.482 | 598.0308 | 598.0308 | 598.0308 | 598.0309 | 598.0309 | 598.0309 | 604.6726 | 611.3144 | 617.9562 | 624.5979 | 631.2397 | 637.8814 | 644.5232 | 651.1649 | 657.8067 | 664.4484 | 671.0902 | 677.7319 | 684.3737 | 691.0154 | 697.6572 | 704.299 | 710.9407 | 717.5825 | 724.2242 | 730.866 | 737.5077 | 744.1495 | 750.7912 | 757.433 | 764.0747 | 770.7165 | 777.3582 | 784 | [6 empty] | 181 | 182 | 183 | 184 | 183.9 | 186 | 188 | 190 | 192 | 194 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | 214.2 | [6 empty] | 2.7297 | 2.7297 | 2.7297 | 2.7297 | 2.7297 | 2.7319 | 2.7341 | 2.7363 | 2.7385 | 2.7407 | 2.7428 | 2.745 | 2.7472 | 2.7494 | 2.7516 | 2.7495 | 2.7475 | 2.7454 | 2.7434 | 2.7413 | 2.7393 | 2.7372 | 2.7351 | 2.7331 | 2.731 | 2.729 | 2.7269 | 2.7249 | 2.7228 | 2.7208 | 2.7208 | 2.7208 | 2.7208 | 2.7208 | 2.7208 | 2.7086 | 2.6969 | 2.6855 | 2.6744 | 2.6637 | 2.6532 | 2.6431 | 2.6332 | 2.6236 | 2.6143 | 2.6052 | 2.5964 | 2.5878 | 2.5794 | 2.5712 | 2.5632 | 2.5554 | 2.5478 | 2.5404 | 2.5332 | 2.5261 | 2.5192 | 2.5125 | 2.5059 | 2.4995 | 2.4932 | 2.487 | 2.481
168 | Upper Harbour | Northwest | Whenuapai | 2080 | 110.6989 | 147.2094 | 195.7619 | 260.3278 | 346.1888 | 373.8984 | 403.8259 | 436.149 | 471.0592 | 508.7637 | 508.7637 | 508.7637 | 508.7637 | 508.7637 | 508.7637 | 586.6644 | 676.4931 | 780.0762 | 899.5197 | 1037.2521 | 1161.9754 | 1301.696 | 1458.2172 | 1633.559 | 1829.9847 | 1880.0214 | 1931.4263 | 1984.2367 | 2038.4911 | 2094.2289 | 2144.5961 | 2196.1746 | 2248.9936 | 2303.0829 | 2358.4731 | 2393.6705 | 2428.8679 | 2464.0653 | 2499.2627 | 2534.4601 | 2569.6574 | 2604.8548 | 2640.0522 | 2675.2496 | 2710.447 | 2745.6444 | 2780.8418 | 2816.0392 | 2851.2366 | 2886.4339 | 2921.6313 | 2956.8287 | 2992.0261 | 3027.2235 | 3062.4209 | 3097.6183 | 3132.8157 | 3168.0131 | 3203.2104 | 3238.4078 | 3273.6052 | 3308.8026 | 3344 |  | 260 | 350.6345 | 472.8636 | 637.7011 | 860 | 929.0552 | 1003.6553 | 1084.2455 | 1171.3069 | 1265.359 | 1265.6572 | 1265.9554 | 1266.2537 | 1266.552 | 1266.8504 | 1464.0599 | 1691.9688 | 1955.3561 | 2259.7447 | 2611.5171 | 2926.4888 | 3279.4487 | 3674.9787 | 4118.213 | 4614.9052 | 4738.9766 | 4866.3837 | 4997.2161 | 5131.5659 | 5269.5278 | 5396.0728 | 5525.6567 | 5658.3526 | 5794.235 | 5933.3806 | 6019.7599 | 6106.1392 | 6192.5184 | 6278.8977 | 6365.277 | 6451.6562 | 6538.0355 | 6624.4147 | 6710.794 | 6797.1733 | 6883.5525 | 6969.9318 | 7056.3111 | 7142.6903 | 7229.0696 | 7315.4488 | 7401.8281 | 7488.2074 | 7574.5866 | 7660.9659 | 7747.3452 | 7833.7244 | 7920.1037 | 8006.4829 | 8092.8622 | 8179.2415 | 8265.6207 | 8352 | [6 empty] | 45 | 45 | 45 | 45 | 45.7 | 46 | 46 | 46 | 46 | 46 | 47.9 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 53.6 | 78.9714 | 104.3429 | 129.7143 | 155.0857 | 180.4571 | 205.8286 | 231.2 | 256.5714 | 281.9429 | 307.3143 | 332.6857 | 358.0571 | 383.4286 | 408.8 | 434.1714 | 459.5429 | 484.9143 | 510.2857 | 535.6571 | 561.0286 | 586.4 | 611.7714 | 637.1429 | 662.5143 | 687.8857 | 713.2571 | 738.6286 | 764 | [6 empty] | 2.3487 | 2.3819 | 2.4155 | 2.4496 | 2.4842 | 2.4848 | 2.4854 | 2.486 | 2.4865 | 2.4871 | 2.4877 | 2.4883 | 2.4889 | 2.4895 | 2.4901 | 2.4956 | 2.5011 | 2.5066 | 2.5122 | 2.5177 | 2.5185 | 2.5194 | 2.5202 | 2.521 | 2.5218 | 2.5207 | 2.5196 | 2.5185 | 2.5173 | 2.5162 | 2.5161 | 2.516 | 2.5159 | 2.5159 | 2.5158 | 2.5149 | 2.514 | 2.5131 | 2.5123 | 2.5115 | 2.5107 | 2.5099 | 2.5092 | 2.5085 | 2.5078 | 2.5071 | 2.5064 | 2.5058 | 2.5051 | 2.5045 | 2.5039 | 2.5033 | 2.5027 | 2.5022 | 2.5016 | 2.5011 | 2.5005 | 2.5 | 2.4995 | 2.499 | 2.4985 | 2.4981 | 2.4976
169 | Upper Harbour | Northwest | Whenuapai | 2080 | 118.2389 | 111.3975 | 104.9519 | 98.8792 | 93.158 | 93.158 | 93.158 | 93.158 | 93.158 | 93.158 | 93.158 | 93.158 | 93.158 | 93.158 | 93.158 | 116.6006 | 145.9424 | 182.6679 | 228.6351 | 286.1697 | 328.1168 | 376.2126 | 431.3582 | 494.5873 | 567.0845 | 590.9168 | 615.7507 | 641.6283 | 668.5934 | 696.6917 | 696.6917 | 696.6917 | 696.6917 | 696.6917 | 696.6917 | 830.8099 | 964.928 | 1099.0462 | 1233.1643 | 1367.2825 | 1501.4006 | 1635.5188 | 1769.6369 | 1903.7551 | 2037.8732 | 2171.9914 | 2306.1096 | 2440.2277 | 2574.3459 | 2708.464 | 2842.5822 | 2976.7003 | 3110.8185 | 3244.9366 | 3379.0548 | 3513.1729 | 3647.2911 | 3781.4092 | 3915.5274 | 4049.6455 | 4183.7637 | 4317.8818 | 4452 |  | 330 | 310.9058 | 292.9164 | 275.9679 | 260 | 260.3052 | 260.6107 | 260.9165 | 261.2228 | 261.5294 | 261.8345 | 262.14 | 262.4459 | 262.7521 | 263.0587 | 324.2082 | 399.5721 | 492.4548 | 606.9287 | 748.0125 | 854.1801 | 975.4164 | 1113.86 | 1271.9534 | 1452.4855 | 1512.3359 | 1574.6526 | 1639.537 | 1707.0951 | 1777.4369 | 1777.4369 | 1777.4369 | 1777.4369 | 1777.4369 | 1777.4369 | 2108.0998 | 2438.7628 | 2769.4258 | 3100.0887 | 3430.7517 | 3761.4147 | 4092.0776 | 4422.7406 | 4753.4036 | 5084.0665 | 5414.7295 | 5745.3925 | 6076.0555 | 6406.7184 | 6737.3814 | 7068.0444 | 7398.7073 | 7729.3703 | 8060.0333 | 8390.6962 | 8721.3592 | 9052.0222 | 9382.6852 | 9713.3481 | 10044.0111 | 10374.6741 | 10705.337 | 11036 | [6 empty] | 135 | 136 | 137 | 138 | 138.1 | 139 | 140 | 141 | 142 | 143 | 146.3 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 159.7 | 195.0321 | 230.3643 | 265.6964 | 301.0286 | 336.3607 | 371.6929 | 407.025 | 442.3571 | 477.6893 | 513.0214 | 548.3536 | 583.6857 | 619.0179 | 654.35 | 689.6821 | 725.0143 | 760.3464 | 795.6786 | 831.0107 | 866.3429 | 901.675 | 937.0071 | 972.3393 | 1007.6714 | 1043.0036 | 1078.3357 | 1113.6679 | 1149 | [6 empty] | 2.791 | 2.791 | 2.791 | 2.791 | 2.791 | 2.7942 | 2.7975 | 2.8008 | 2.8041 | 2.8074 | 2.8107 | 2.8139 | 2.8172 | 2.8205 | 2.8238 | 2.7805 | 2.7379 | 2.6959 | 2.6546 | 2.6139 | 2.6033 | 2.5927 | 2.5822 | 2.5717 | 2.5613 | 2.5593 | 2.5573 | 2.5553 | 2.5533 | 2.5513 | 2.5513 | 2.5513 | 2.5513 | 2.5513 | 2.5513 | 2.5374 | 2.5274 | 2.5198 | 2.5139 | 2.5092 | 2.5053 | 2.502 | 2.4992 | 2.4969 | 2.4948 | 2.493 | 2.4914 | 2.49 | 2.4887 | 2.4875 | 2.4865 | 2.4855 | 2.4847 | 2.4839 | 2.4831 | 2.4825 | 2.4818 | 2.4813 | 2.4807 | 2.4802 | 2.4797 | 2.4793 | 2.4789
170 | Upper Harbour | Northwest | Whenuapai | 2080 | 72.7624 | 70.1439 | 67.6196 | 65.1862 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 62.8403 | 114.2389 | 165.6374 | 217.036 | 268.4345 | 319.8331 | 371.2317 | 422.6302 | 474.0288 | 525.4273 | 576.8259 | 628.2245 | 679.623 | 731.0216 | 782.4201 | 833.8187 | 885.2173 | 936.6158 | 988.0144 | 1039.413 | 1090.8115 | 1142.2101 | 1193.6086 | 1245.0072 | 1296.4058 | 1347.8043 | 1399.2029 | 1450.6014 | 1502 |  | 220 | 212.0828 | 204.4505 | 197.0929 | 190 | 188.8765 | 187.7596 | 186.6493 | 185.5455 | 184.4483 | 183.3244 | 182.2073 | 181.097 | 179.9935 | 178.8967 | 178.0015 | 177.1108 | 176.2245 | 175.3426 | 174.4652 | 173.8356 | 173.2082 | 172.583 | 171.9602 | 171.3395 | 170.859 | 170.3798 | 169.902 | 169.4255 | 168.9504 | 168.9091 | 168.8679 | 168.8267 | 168.7855 | 168.7443 | 295.8963 | 423.0483 | 550.2003 | 677.3523 | 804.5042 | 931.6562 | 1058.8082 | 1185.9602 | 1313.1122 | 1440.2642 | 1567.4162 | 1694.5682 | 1821.7202 | 1948.8721 | 2076.0241 | 2203.1761 | 2330.3281 | 2457.4801 | 2584.6321 | 2711.7841 | 2838.9361 | 2966.0881 | 3093.2401 | 3220.392 | 3347.544 | 3474.696 | 3601.848 | 3729 | [6 empty] | 19 | 19 | 19 | 19 | 19.5 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21.9 | 33.5464 | 45.1929 | 56.8393 | 68.4857 | 80.1321 | 91.7786 | 103.425 | 115.0714 | 126.7179 | 138.3643 | 150.0107 | 161.6571 | 173.3036 | 184.95 | 196.5964 | 208.2429 | 219.8893 | 231.5357 | 243.1821 | 254.8286 | 266.475 | 278.1214 | 289.7679 | 301.4143 | 313.0607 | 324.7071 | 336.3536 | 348 | [6 empty] | 3.0235 | 3.0235 | 3.0235 | 3.0235 | 3.0235 | 3.0057 | 2.9879 | 2.9702 | 2.9527 | 2.9352 | 2.9173 | 2.8995 | 2.8819 | 2.8643 | 2.8468 | 2.8326 | 2.8184 | 2.8043 | 2.7903 | 2.7763 | 2.7663 | 2.7563 | 2.7464 | 2.7365 | 2.7266 | 2.7189 | 2.7113 | 2.7037 | 2.6961 | 2.6886 | 2.6879 | 2.6873 | 2.6866 | 2.6859 | 2.6853 | 2.5902 | 2.5541 | 2.5351 | 2.5233 | 2.5154 | 2.5096 | 2.5053 | 2.5019 | 2.4991 | 2.4969 | 2.495 | 2.4934 | 2.492 | 2.4908 | 2.4898 | 2.4889 | 2.488 | 2.4873 | 2.4866 | 2.486 | 2.4855 | 2.485 | 2.4845 | 2.4841 | 2.4837 | 2.4833 | 2.483 | 2.4827
171 | Upper Harbour | Northwest | Whenuapai | 2080 | 278.9225 | 265.5376 | 252.795 | 240.6639 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 229.1149 | 289.3966 | 349.6782 | 409.9598 | 470.2414 | 530.523 | 590.8046 | 651.0862 | 711.3678 | 771.6494 | 831.931 | 892.2126 | 952.4943 | 1012.7759 | 1073.0575 | 1133.3391 | 1193.6207 | 1253.9023 | 1314.1839 | 1374.4655 | 1434.7471 | 1495.0287 | 1555.3103 | 1615.592 | 1675.8736 | 1736.1552 | 1796.4368 | 1856.7184 | 1917 |  | 840 | 799.6901 | 761.3147 | 724.7807 | 690 | 686.8978 | 683.8095 | 680.7351 | 677.6746 | 674.6277 | 671.5249 | 668.4363 | 665.3619 | 662.3017 | 659.2555 | 656.6673 | 654.0894 | 651.5215 | 648.9637 | 646.416 | 644.0425 | 641.6777 | 639.3216 | 636.9741 | 634.6353 | 632.0188 | 629.413 | 626.818 | 624.2337 | 621.6601 | 621.7803 | 621.9006 | 622.0209 | 622.1412 | 622.2615 | 769.7164 | 917.1714 | 1064.6263 | 1212.0813 | 1359.5362 | 1506.9912 | 1654.4461 | 1801.901 | 1949.356 | 2096.8109 | 2244.2659 | 2391.7208 | 2539.1758 | 2686.6307 | 2834.0857 | 2981.5406 | 3128.9956 | 3276.4505 | 3423.9055 | 3571.3604 | 3718.8154 | 3866.2703 | 4013.7253 | 4161.1802 | 4308.6352 | 4456.0901 | 4603.5451 | 4751 | [6 empty] | 148 | 177 | 206 | 235 | 264.9 | 288 | 312 | 336 | 360 | 384 | 406.1 | 429 | 452 | 475 | 498 | 521 | 544 | 567 | 590 | 613 | 636 | 659 | 682 | 705 | 728 | 751 | 774 | 797 | 820 | 843 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | 873.4 | [6 empty] | 3.0116 | 3.0116 | 3.0116 | 3.0116 | 3.0116 | 2.998 | 2.9846 | 2.9712 | 2.9578 | 2.9445 | 2.931 | 2.9175 | 2.9041 | 2.8907 | 2.8774 | 2.8661 | 2.8549 | 2.8436 | 2.8325 | 2.8214 | 2.811 | 2.8007 | 2.7904 | 2.7802 | 2.7699 | 2.7585 | 2.7471 | 2.7358 | 2.7245 | 2.7133 | 2.7138 | 2.7144 | 2.7149 | 2.7154 | 2.7159 | 2.6597 | 2.6229 | 2.5969 | 2.5776 | 2.5626 | 2.5507 | 2.5411 | 2.533 | 2.5262 | 2.5204 | 2.5154 | 2.511 | 2.5071 | 2.5037 | 2.5007 | 2.4979 | 2.4954 | 2.4931 | 2.4911 | 2.4892 | 2.4875 | 2.4859 | 2.4844 | 2.483 | 2.4817 | 2.4805 | 2.4794 | 2.4784
172 | Upper Harbour | Northwest | Whenuapai | 2080 | 181.3614 | 209.2444 | 241.4142 | 278.5299 | 321.3518 | 321.3518 | 321.3518 | 321.3518 | 321.3518 | 321.3518 | 321.3518 | 321.3518 | 321.3518 | 321.3518 | 321.3518 | 353.0984 | 387.9812 | 426.3101 | 468.4255 | 514.7016 | 561.6152 | 612.8048 | 668.6602 | 729.6067 | 796.1083 | 820.5301 | 845.7011 | 871.6443 | 898.3833 | 925.9426 | 925.9426 | 925.9426 | 925.9426 | 925.9426 | 925.9426 | 933.8375 | 941.7324 | 949.6273 | 957.5222 | 965.4171 | 973.312 | 981.2069 | 989.1018 | 996.9967 | 1004.8916 | 1012.7866 | 1020.6815 | 1028.5764 | 1036.4713 | 1044.3662 | 1052.2611 | 1060.156 | 1068.0509 | 1075.9458 | 1083.8407 | 1091.7356 | 1099.6305 | 1107.5255 | 1115.4204 | 1123.3153 | 1131.2102 | 1139.1051 | 1147 |  | 600 | 681.7316 | 774.5967 | 880.1117 | 1000 | 996.7623 | 993.5351 | 990.3183 | 987.112 | 983.916 | 980.6779 | 977.4505 | 974.2338 | 971.0276 | 967.832 | 1052.4953 | 1144.5649 | 1244.6884 | 1353.5704 | 1471.9772 | 1592.6267 | 1723.1651 | 1864.4031 | 2017.2175 | 2182.5572 | 2237.4601 | 2293.744 | 2351.4438 | 2410.5951 | 2471.2344 | 2469.9431 | 2468.6526 | 2467.3627 | 2466.0735 | 2464.7849 | 2480.8283 | 2496.8717 | 2512.9151 | 2528.9585 | 2545.0019 | 2561.0453 | 2577.0887 | 2593.1321 | 2609.1755 | 2625.2189 | 2641.2623 | 2657.3057 | 2673.3491 | 2689.3925 | 2705.4359 | 2721.4793 | 2737.5227 | 2753.5661 | 2769.6094 | 2785.6528 | 2801.6962 | 2817.7396 | 2833.783 | 2849.8264 | 2865.8698 | 2881.9132 | 2897.9566 | 2914 | [6 empty] | 1666 | 1687 | 1708 | 1729 | 1751.9 | 1773 | 1795 | 1817 | 1839 | 1861 | 1881 | 1917 | 1953 | 1989 | 2025 | 2061 | 2097 | 2133 | 2169 | 2205 | 2241 | 2277 | 2313 | 2349 | 2385 | 2421 | 2457 | 2493 | 2529 | 2565 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | 2591.6 | [6 empty] | 3.3083 | 3.2581 | 3.2086 | 3.1598 | 3.1119 | 3.1018 | 3.0917 | 3.0817 | 3.0717 | 3.0618 | 3.0517 | 3.0417 | 3.0317 | 3.0217 | 3.0118 | 2.9807 | 2.9501 | 2.9197 | 2.8896 | 2.8599 | 2.8358 | 2.8119 | 2.7883 | 2.7648 | 2.7415 | 2.7268 | 2.7122 | 2.6977 | 2.6833 | 2.6689 | 2.6675 | 2.6661 | 2.6647 | 2.6633 | 2.6619 | 2.6566 | 2.6514 | 2.6462 | 2.6411 | 2.6362 | 2.6313 | 2.6264 | 2.6217 | 2.617 | 2.6124 | 2.6079 | 2.6035 | 2.5991 | 2.5948 | 2.5905 | 2.5863 | 2.5822 | 2.5781 | 2.5741 | 2.5702 | 2.5663 | 2.5624 | 2.5587 | 2.5549 | 2.5513 | 2.5476 | 2.5441 | 2.5405
173 | Upper Harbour | Northwest | Whenuapai | 2080 | 9.0953 | 8.5734 | 8.0814 | 7.6176 | 7.1805 | 8.6973 | 10.5345 | 12.7597 | 15.4551 | 18.7198 | 20.6374 | 22.7515 | 25.0822 | 27.6516 | 30.4842 | 32.4121 | 34.4619 | 36.6413 | 38.9586 | 41.4224 | 43.2262 | 45.1085 | 47.0728 | 49.1227 | 51.2618 | 53.6743 | 56.2004 | 58.8454 | 61.6149 | 64.5147 | 66.828 | 69.2242 | 71.7064 | 74.2776 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 | 76.941 |  | 190 | 179.0969 | 168.8194 | 159.1318 | 150 | 156.1871 | 162.6294 | 169.3375 | 176.3222 | 183.595 | 189.4392 | 195.4694 | 201.6916 | 208.1118 | 214.7364 | 220.0821 | 225.5608 | 231.1759 | 236.9308 | 242.829 | 247.6527 | 252.5721 | 257.5893 | 262.7062 | 267.9247 | 274.345 | 280.9192 | 287.6508 | 294.5438 | 301.602 | 307.6554 | 313.8303 | 320.1292 | 326.5544 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | 333.1087 | [6 empty] | 7 | 12 | 17 | 22 | 27.3 | 32 | 36 | 40 | 44 | 48 | 52.8 | 57 | 61 | 65 | 69 | 73 | 77 | 81 | 85 | 89 | 93 | 97 | 101 | 105 | 109 | 113 | 117 | 121 | 125 | 129 | 135 | 172.8214 | 210.6429 | 248.4643 | 286.2857 | 324.1071 | 361.9286 | 399.75 | 437.5714 | 475.3929 | 513.2143 | 551.0357 | 588.8571 | 626.6786 | 664.5 | 702.3214 | 740.1429 | 777.9643 | 815.7857 | 853.6071 | 891.4286 | 929.25 | 967.0714 | 1004.8929 | 1042.7143 | 1080.5357 | 1118.3571 | 1156.1786 | 1194 | [6 empty] | 20.8899 | 20.8899 | 20.8899 | 20.8899 | 20.8899 | 17.9581 | 15.4378 | 13.2712 | 11.4087 | 9.8076 | 9.1794 | 8.5915 | 8.0412 | 7.5262 | 7.0442 | 6.7901 | 6.5452 | 6.3092 | 6.0816 | 5.8623 | 5.7292 | 5.5992 | 5.4721 | 5.348 | 5.2266 | 5.1113 | 4.9985 | 4.8882 | 4.7804 | 4.6749 | 4.6037 | 4.5335 | 4.4644 | 4.3964 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294 | 4.3294
174 | Henderson - Massey | Northwest | Whenuapai | 2080 | 66.6988 | 64.2985 | 61.9846 | 59.7539 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 57.6036 | 87.2993 | 132.3037 | 200.5088 | 303.8749 | 460.5282 | 542.7386 | 639.6246 | 753.8061 | 888.3704 | 1046.9563 | 1096.2113 | 1147.7836 | 1201.7821 | 1258.3211 | 1317.5199 | 1317.5199 | 1317.5199 | 1317.5199 | 1317.5199 | 1317.5199 | 1401.2156 | 1484.9114 | 1568.6071 | 1652.3028 | 1735.9985 | 1819.6942 | 1903.3899 | 1987.0857 | 2070.7814 | 2154.4771 | 2238.1728 | 2321.8685 | 2405.5642 | 2489.26 | 2572.9557 | 2656.6514 | 2740.3471 | 2824.0428 | 2907.7385 | 2991.4343 | 3075.13 | 3158.8257 | 3242.5214 | 3326.2171 | 3409.9128 | 3493.6086 | 3577.3043 | 3661 |  | 220 | 212.0828 | 204.4505 | 197.0929 | 190 | 189.3235 | 188.6494 | 187.9777 | 187.3084 | 186.6415 | 185.9649 | 185.2907 | 184.619 | 183.9498 | 183.2829 | 270.5377 | 399.3314 | 589.4394 | 870.0514 | 1284.2531 | 1504.0259 | 1761.4082 | 2062.836 | 2415.8469 | 2829.2681 | 2948.5204 | 3072.7992 | 3202.3163 | 3337.2924 | 3477.9578 | 3477.9584 | 3477.9589 | 3477.9595 | 3477.96 | 3477.9606 | 3692.0692 | 3906.1777 | 4120.2863 | 4334.3948 | 4548.5034 | 4762.6119 | 4976.7205 | 5190.829 | 5404.9376 | 5619.0461 | 5833.1547 | 6047.2632 | 6261.3718 | 6475.4803 | 6689.5889 | 6903.6974 | 7117.806 | 7331.9145 | 7546.0231 | 7760.1316 | 7974.2402 | 8188.3487 | 8402.4573 | 8616.5658 | 8830.6744 | 9044.7829 | 9258.8915 | 9473 | [6 empty] | 62 | 62 | 62 | 62 | 63.8 | 65 | 66 | 67 | 68 | 69 | 69.9 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 83.3 | 112.075 | 140.85 | 169.625 | 198.4 | 227.175 | 255.95 | 284.725 | 313.5 | 342.275 | 371.05 | 399.825 | 428.6 | 457.375 | 486.15 | 514.925 | 543.7 | 572.475 | 601.25 | 630.025 | 658.8 | 687.575 | 716.35 | 745.125 | 773.9 | 802.675 | 831.45 | 860.225 | 889 | [6 empty] | 3.2984 | 3.2984 | 3.2984 | 3.2984 | 3.2984 | 3.2867 | 3.275 | 3.2633 | 3.2517 | 3.2401 | 3.2284 | 3.2167 | 3.205 | 3.1934 | 3.1818 | 3.099 | 3.0183 | 2.9397 | 2.8632 | 2.7887 | 2.7712 | 2.7538 | 2.7366 | 2.7194 | 2.7024 | 2.6897 | 2.6772 | 2.6646 | 2.6522 | 2.6398 | 2.6398 | 2.6398 | 2.6398 | 2.6398 | 2.6398 | 2.6349 | 2.6306 | 2.6267 | 2.6232 | 2.6201 | 2.6173 | 2.6147 | 2.6123 | 2.6101 | 2.6081 | 2.6062 | 2.6045 | 2.6029 | 2.6014 | 2.6 | 2.5986 | 2.5974 | 2.5962 | 2.5952 | 2.5941 | 2.5931 | 2.5922 | 2.5913 | 2.5905 | 2.5897 | 2.589 | 2.5882 | 2.5875
175 | Upper Harbour | Northwest | Whenuapai | 2080 | 100.0483 | 101.8042 | 103.591 | 105.4091 | 107.2592 | 107.2592 | 107.2592 | 107.2592 | 107.2592 | 107.2592 | 107.2592 | 107.2592 | 107.2592 | 107.2592 | 107.2592 | 118.8172 | 131.6208 | 145.804 | 161.5156 | 178.9203 | 196.1335 | 215.0027 | 235.6873 | 258.3619 | 283.2179 | 292.2475 | 301.5651 | 311.1797 | 321.1008 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 | 331.3383 |  | 310 | 314.8834 | 319.8437 | 324.8822 | 330 | 329.5628 | 329.1262 | 328.6902 | 328.2548 | 327.82 | 327.3828 | 326.9462 | 326.5102 | 326.0748 | 325.6399 | 356.9675 | 391.3089 | 428.9541 | 470.2208 | 515.4575 | 560.8686 | 610.2803 | 664.0452 | 722.5467 | 786.202 | 808.0295 | 830.463 | 853.5193 | 877.2158 | 901.5701 | 901.5702 | 901.5703 | 901.5704 | 901.5705 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | 901.5706 | [6 empty] | 1799 | 1816 | 1833 | 1850 | 1865.4 | 1887 | 1908 | 1929 | 1950 | 1971 | 1993.5 | 1933 | 1873 | 1813 | 1753 | 1693 | 1633 | 1573 | 1513 | 1453 | 1393 | 1333 | 1273 | 1213 | 1153 | 1093 | 1033 | 973 | 913 | 853 | 783.6 | 827.3286 | 871.0571 | 914.7857 | 958.5143 | 1002.2429 | 1045.9714 | 1089.7 | 1133.4286 | 1177.1571 | 1220.8857 | 1264.6143 | 1308.3429 | 1352.0714 | 1395.8 | 1439.5286 | 1483.2571 | 1526.9857 | 1570.7143 | 1614.4429 | 1658.1714 | 1701.9 | 1745.6286 | 1789.3571 | 1833.0857 | 1876.8143 | 1920.5429 | 1964.2714 | 2008 | [6 empty] | 3.0985 | 3.093 | 3.0876 | 3.0821 | 3.0767 | 3.0726 | 3.0685 | 3.0644 | 3.0604 | 3.0563 | 3.0523 | 3.0482 | 3.0441 | 3.0401 | 3.036 | 3.0043 | 2.973 | 2.942 | 2.9113 | 2.8809 | 2.8596 | 2.8385 | 2.8175 | 2.7966 | 2.776 | 2.7649 | 2.7538 | 2.7429 | 2.7319 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721 | 2.721
176 | Upper Harbour | Northwest | Whenuapai | 2080 | 66.0982 | 62.7546 | 59.5801 | 56.5663 | 53.7048 | 53.7048 | 53.7048 | 53.7048 | 53.7048 | 53.7048 | 53.7048 | 53.7048 | 53.7048 | 53.7048 | 53.7048 | 71.0053 | 93.8789 | 124.1211 | 164.1055 | 216.9704 | 251.5619 | 291.6682 | 338.1686 | 392.0825 | 454.5919 | 474.6656 | 495.6257 | 517.5114 | 540.3634 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 | 564.2246 |  | 160 | 151.9063 | 144.2221 | 136.9265 | 130 | 130.5556 | 131.1136 | 131.674 | 132.2368 | 132.802 | 133.3577 | 133.9157 | 134.4761 | 135.0388 | 135.6039 | 182.8654 | 246.5988 | 332.545 | 448.4456 | 604.7407 | 700.7482 | 811.9976 | 940.9088 | 1090.2857 | 1263.3774 | 1313.8561 | 1366.3518 | 1420.9449 | 1477.7193 | 1536.7621 | 1536.7624 | 1536.7626 | 1536.7629 | 1536.7631 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | 1536.7634 | [6 empty] | 39 | 39 | 39 | 39 | 40.1 | 41 | 42 | 43 | 44 | 45 | 46.9 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 64.5 | 91.0179 | 117.5357 | 144.0536 | 170.5714 | 197.0893 | 223.6071 | 250.125 | 276.6429 | 303.1607 | 329.6786 | 356.1964 | 382.7143 | 409.2321 | 435.75 | 462.2679 | 488.7857 | 515.3036 | 541.8214 | 568.3393 | 594.8571 | 621.375 | 647.8929 | 674.4107 | 700.9286 | 727.4464 | 753.9643 | 780.4821 | 807 | [6 empty] | 2.4206 | 2.4206 | 2.4206 | 2.4206 | 2.4206 | 2.431 | 2.4414 | 2.4518 | 2.4623 | 2.4728 | 2.4832 | 2.4936 | 2.504 | 2.5145 | 2.525 | 2.5754 | 2.6268 | 2.6792 | 2.7327 | 2.7872 | 2.7856 | 2.784 | 2.7824 | 2.7808 | 2.7791 | 2.768 | 2.7568 | 2.7457 | 2.7347 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237 | 2.7237
177 | Upper Harbour | Northwest | Whenuapai | 2080 | 33.3494 | 42.8603 | 55.0835 | 70.7927 | 90.982 | 90.982 | 90.982 | 90.982 | 90.982 | 90.982 | 90.982 | 90.982 | 90.982 | 90.982 | 90.982 | 117.2602 | 151.1283 | 194.7785 | 251.0361 | 323.5425 | 373.3525 | 430.8307 | 497.1579 | 573.6962 | 662.0178 | 690.6622 | 720.5461 | 751.723 | 784.2488 | 818.182 | 847.8721 | 878.6396 | 910.5236 | 943.5646 | 977.8046 | 1003.5973 | 1029.39 | 1055.1827 | 1080.9754 | 1106.768 | 1132.5607 | 1158.3534 | 1184.1461 | 1209.9388 | 1235.7315 | 1261.5242 | 1287.3169 | 1313.1096 | 1338.9023 | 1364.695 | 1390.4877 | 1416.2804 | 1442.0731 | 1467.8658 | 1493.6585 | 1519.4511 | 1545.2438 | 1571.0365 | 1596.8292 | 1622.6219 | 1648.4146 | 1674.2073 | 1700 |  | 110 | 141.3594 | 181.659 | 233.4474 | 300 | 296.1434 | 292.3363 | 288.5782 | 284.8684 | 281.2063 | 277.3428 | 273.5324 | 269.7744 | 266.068 | 262.4125 | 336.8572 | 432.4214 | 555.0965 | 712.5737 | 914.7262 | 1051.6017 | 1208.9585 | 1389.8616 | 1597.8342 | 1836.9268 | 1909.1131 | 1984.1361 | 2062.1073 | 2143.1425 | 2227.3623 | 2308.1889 | 2391.9485 | 2478.7476 | 2568.6965 | 2661.9095 | 2729.9484 | 2797.9874 | 2866.0263 | 2934.0653 | 3002.1042 | 3070.1431 | 3138.1821 | 3206.221 | 3274.26 | 3342.2989 | 3410.3379 | 3478.3768 | 3546.4158 | 3614.4547 | 3682.4937 | 3750.5326 | 3818.5716 | 3886.6105 | 3954.6495 | 4022.6884 | 4090.7274 | 4158.7663 | 4226.8053 | 4294.8442 | 4362.8832 | 4430.9221 | 4498.9611 | 4567 | [6 empty] | 30 | 30 | 30 | 30 | 31.2 | 31 | 31 | 31 | 31 | 31 | 31.9 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 35.8 | 49.0571 | 62.3143 | 75.5714 | 88.8286 | 102.0857 | 115.3429 | 128.6 | 141.8571 | 155.1143 | 168.3714 | 181.6286 | 194.8857 | 208.1429 | 221.4 | 234.6571 | 247.9143 | 261.1714 | 274.4286 | 287.6857 | 300.9429 | 314.2 | 327.4571 | 340.7143 | 353.9714 | 367.2286 | 380.4857 | 393.7429 | 407 | [6 empty] | 3.2984 | 3.2981 | 3.2979 | 3.2976 | 3.2974 | 3.255 | 3.2131 | 3.1718 | 3.131 | 3.0908 | 3.0483 | 3.0064 | 2.9651 | 2.9244 | 2.8842 | 2.8727 | 2.8613 | 2.8499 | 2.8385 | 2.8272 | 2.8166 | 2.8061 | 2.7956 | 2.7852 | 2.7747 | 2.7642 | 2.7537 | 2.7432 | 2.7327 | 2.7223 | 2.7223 | 2.7223 | 2.7223 | 2.7223 | 2.7223 | 2.7202 | 2.7181 | 2.7161 | 2.7143 | 2.7125 | 2.7108 | 2.7092 | 2.7076 | 2.7061 | 2.7047 | 2.7033 | 2.702 | 2.7008 | 2.6996 | 2.6984 | 2.6973 | 2.6962 | 2.6952 | 2.6941 | 2.6932 | 2.6922 | 2.6913 | 2.6905 | 2.6896 | 2.6888 | 2.688 | 2.6872 | 2.6865
178 | Upper Harbour |  |  | 2052 | 465.1876 | 500.395 | 538.2671 | 579.0055 | 622.8272 | 639.6466 | 656.9202 | 674.6603 | 692.8795 | 711.5907 | 728.8337 | 746.4945 | 764.5833 | 783.1104 | 802.0864 | 811.6625 | 821.3528 | 831.1589 | 841.0821 | 851.1237 | 855.9875 | 860.8791 | 865.7986 | 870.7463 | 875.7222 | 882.2506 | 888.8276 | 895.4537 | 902.1292 | 908.8544 | 914.9843 | 921.1556 | 927.3684 | 933.6232 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 | 939.9202 |  | 1080 | 1158.5154 | 1242.7389 | 1333.0854 | 1430 | 1469.3502 | 1509.7831 | 1551.3287 | 1594.0176 | 1637.8811 | 1678.6648 | 1720.4641 | 1763.3042 | 1807.2111 | 1852.2112 | 1873.7899 | 1895.6201 | 1917.7045 | 1940.0463 | 1962.6484 | 1973.6041 | 1984.621 | 1995.6993 | 2006.8396 | 2018.042 | 2032.7474 | 2047.5599 | 2062.4804 | 2077.5096 | 2092.6483 | 2106.4547 | 2120.3522 | 2134.3414 | 2148.4229 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | 2162.5974 | [6 empty] | 636 | 644 | 652 | 660 | 668.1 | 677 | 686 | 695 | 704 | 713 | 723.7 | 729 | 734 | 739 | 744 | 749 | 754 | 759 | 764 | 769 | 774 | 779 | 784 | 789 | 794 | 799 | 804 | 809 | 814 | 819 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | 833.4 | [6 empty] | 2.3216 | 2.3152 | 2.3088 | 2.3024 | 2.296 | 2.2971 | 2.2983 | 2.2994 | 2.3006 | 2.3017 | 2.3032 | 2.3047 | 2.3062 | 2.3077 | 2.3092 | 2.3086 | 2.3079 | 2.3073 | 2.3066 | 2.3059 | 2.3056 | 2.3053 | 2.305 | 2.3047 | 2.3044 | 2.304 | 2.3037 | 2.3033 | 2.3029 | 2.3025 | 2.3022 | 2.3018 | 2.3015 | 2.3012 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008 | 2.3008
179 | Upper Harbour |  |  | 2052 | 1204.9169 | 1340.8699 | 1492.1627 | 1660.5261 | 1847.8863 | 1883.4189 | 1919.6348 | 1956.547 | 1994.169 | 2032.5145 | 2068.8389 | 2105.8125 | 2143.4469 | 2181.7539 | 2220.7455 | 2251.1835 | 2282.0387 | 2313.3168 | 2345.0236 | 2377.165 | 2402.6856 | 2428.4801 | 2454.5515 | 2480.9028 | 2507.5371 | 2528.6199 | 2549.88 | 2571.3189 | 2592.938 | 2614.7389 | 2628.0236 | 2641.3759 | 2654.796 | 2668.2842 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 | 2681.841 |  | 3360 | 3744.0091 | 4171.906 | 4648.7066 | 5180 | 5281.4356 | 5384.8574 | 5490.3045 | 5597.8165 | 5707.4338 | 5811.3051 | 5917.0668 | 6024.7533 | 6134.3995 | 6246.0413 | 6325.6781 | 6406.3302 | 6488.0107 | 6570.7326 | 6654.5091 | 6719.3943 | 6784.912 | 6851.0686 | 6917.8703 | 6985.3234 | 7037.0188 | 7089.0967 | 7141.5601 | 7194.4118 | 7247.6546 | 7284.7283 | 7321.9916 | 7359.4455 | 7397.0911 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | 7434.9291 | [6 empty] | 715 | 720 | 725 | 730 | 733.1 | 743 | 753 | 763 | 773 | 783 | 791.1 | 796 | 801 | 806 | 811 | 816 | 821 | 826 | 831 | 836 | 841 | 846 | 851 | 856 | 861 | 866 | 871 | 876 | 881 | 886 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | 890.6 | [6 empty] | 2.7886 | 2.7922 | 2.7959 | 2.7995 | 2.8032 | 2.8042 | 2.8051 | 2.8061 | 2.8071 | 2.8081 | 2.809 | 2.8099 | 2.8108 | 2.8117 | 2.8126 | 2.8099 | 2.8073 | 2.8046 | 2.802 | 2.7993 | 2.7966 | 2.7939 | 2.7912 | 2.7884 | 2.7857 | 2.7829 | 2.7802 | 2.7774 | 2.7746 | 2.7718 | 2.7719 | 2.772 | 2.7721 | 2.7722 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723 | 2.7723
180 | Upper Harbour |  |  | 2052 | 50.9256 | 102.3674 | 205.7726 | 413.6311 | 831.4552 | 865.8575 | 901.6833 | 938.9914 | 977.8431 | 1018.3024 | 1053.8335 | 1090.6044 | 1128.6583 | 1168.04 | 1208.7959 | 1241.8325 | 1275.772 | 1310.6391 | 1346.4591 | 1383.258 | 1413.0402 | 1443.4635 | 1474.5419 | 1506.2894 | 1538.7205 | 1578.4113 | 1619.126 | 1660.8908 | 1703.733 | 1747.6803 | 1785.1791 | 1823.4825 | 1862.6078 | 1902.5725 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 | 1943.3948 |  | 160 | 328.7011 | 675.2777 | 1387.2785 | 2850 | 2960.7641 | 3075.833 | 3195.3739 | 3319.5608 | 3448.5742 | 3559.9918 | 3675.0092 | 3793.7426 | 3916.312 | 4042.8415 | 4137.2903 | 4233.9455 | 4332.8588 | 4434.083 | 4537.6719 | 4616.9778 | 4697.6698 | 4779.7721 | 4863.3093 | 4948.3065 | 5055.4243 | 5164.8609 | 5276.6665 | 5390.8925 | 5507.5911 | 5626.0852 | 5747.1287 | 5870.7765 | 5997.0844 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | 6126.1098 | [6 empty] | 365 | 368 | 371 | 374 | 375.4 | 381 | 387 | 393 | 399 | 405 | 410.1 | 415 | 420 | 425 | 430 | 435 | 440 | 445 | 450 | 455 | 460 | 465 | 470 | 475 | 480 | 485 | 490 | 495 | 500 | 505 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | 502.5 | [6 empty] | 3.1418 | 3.211 | 3.2817 | 3.3539 | 3.4277 | 3.4195 | 3.4112 | 3.403 | 3.3948 | 3.3866 | 3.3781 | 3.3697 | 3.3613 | 3.3529 | 3.3445 | 3.3316 | 3.3187 | 3.3059 | 3.2931 | 3.2804 | 3.2674 | 3.2544 | 3.2415 | 3.2287 | 3.2159 | 3.2029 | 3.1899 | 3.177 | 3.1642 | 3.1514 | 3.1516 | 3.1517 | 3.1519 | 3.1521 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523 | 3.1523
181 | Upper Harbour |  |  | 2052 | 1086.0422 | 1076.2127 | 1066.4722 | 1056.8199 | 1047.255 | 1051.656 | 1056.0755 | 1060.5136 | 1064.9704 | 1069.4458 | 1073.9328 | 1078.4386 | 1082.9633 | 1087.507 | 1092.0698 | 1095.6808 | 1099.3037 | 1102.9386 | 1106.5855 | 1110.2445 | 1113.1808 | 1116.1248 | 1119.0766 | 1122.0362 | 1125.0036 | 1128.0912 | 1131.1872 | 1134.2917 | 1137.4047 | 1140.5263 | 1143.0008 | 1145.4807 | 1147.9659 | 1150.4566 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 | 1152.9526 |  | 3080 | 3052.1238 | 3024.5 | 2997.1261 | 2970 | 2973.922 | 2977.8492 | 2981.7816 | 2985.7192 | 2989.662 | 2993.4694 | 2997.2816 | 3001.0987 | 3004.9206 | 3008.7474 | 3008.474 | 3008.2006 | 3007.9272 | 3007.6539 | 3007.3806 | 3004.9902 | 3002.6017 | 3000.215 | 2997.8303 | 2995.4475 | 2993.1804 | 2990.9151 | 2988.6514 | 2986.3895 | 2984.1293 | 2990.4742 | 2996.8327 | 3003.2046 | 3009.5901 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | 3015.9891 | [6 empty] | 584 | 587 | 590 | 593 | 597.3 | 604 | 611 | 618 | 625 | 632 | 639.2 | 642 | 645 | 648 | 651 | 654 | 657 | 660 | 663 | 666 | 669 | 672 | 675 | 678 | 681 | 684 | 687 | 690 | 693 | 696 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | 696.2 | [6 empty] | 2.836 | 2.836 | 2.836 | 2.836 | 2.836 | 2.8278 | 2.8197 | 2.8116 | 2.8036 | 2.7955 | 2.7874 | 2.7793 | 2.7712 | 2.7631 | 2.7551 | 2.7458 | 2.7365 | 2.7272 | 2.718 | 2.7088 | 2.6995 | 2.6902 | 2.681 | 2.6718 | 2.6626 | 2.6533 | 2.644 | 2.6348 | 2.6256 | 2.6164 | 2.6163 | 2.6162 | 2.6161 | 2.616 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159 | 2.6159
182 | Upper Harbour |  |  | 2052 | 1461.1287 | 1437.3884 | 1414.0337 | 1391.0586 | 1368.4567 | 1368.4567 | 1368.4567 | 1368.4567 | 1368.4567 | 1368.4567 | 1368.4567 | 1368.4567 | 1368.4567 | 1368.4567 | 1368.4567 | 1368.9296 | 1369.4027 | 1369.8759 | 1370.3493 | 1370.8229 | 1371.5109 | 1372.1993 | 1372.8881 | 1373.5772 | 1374.2667 | 1374.5843 | 1374.902 | 1375.2198 | 1375.5376 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 | 1375.8555 |  | 4730 | 4653.1472 | 4577.543 | 4503.1673 | 4430 | 4410.0471 | 4390.1841 | 4370.4106 | 4350.7261 | 4331.1303 | 4311.1733 | 4291.3082 | 4271.5347 | 4251.8523 | 4232.2606 | 4212.9252 | 4193.6782 | 4174.5191 | 4155.4476 | 4136.4631 | 4117.6908 | 4099.0038 | 4080.4015 | 4061.8837 | 4043.4498 | 4023.494 | 4003.6367 | 3983.8774 | 3964.2156 | 3944.6509 | 3944.6515 | 3944.652 | 3944.6526 | 3944.6532 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | 3944.6538 | [6 empty] | 912 | 917 | 922 | 927 | 933.5 | 945 | 957 | 969 | 981 | 993 | 1002.9 | 1008 | 1014 | 1020 | 1026 | 1032 | 1038 | 1044 | 1050 | 1056 | 1062 | 1068 | 1074 | 1080 | 1086 | 1092 | 1098 | 1104 | 1110 | 1116 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | 1113.4 | [6 empty] | 3.2372 | 3.2372 | 3.2372 | 3.2372 | 3.2372 | 3.2226 | 3.2081 | 3.1937 | 3.1793 | 3.165 | 3.1504 | 3.1359 | 3.1214 | 3.107 | 3.0927 | 3.0775 | 3.0624 | 3.0474 | 3.0324 | 3.0175 | 3.0023 | 2.9872 | 2.9721 | 2.9572 | 2.9423 | 2.9271 | 2.9119 | 2.8969 | 2.8819 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671 | 2.8671
183 | Henderson - Massey |  |  | 2052 | 1342.9475 | 1344.6074 | 1346.2694 | 1347.9334 | 1349.5995 | 1349.5995 | 1349.5995 | 1349.5995 | 1349.5995 | 1349.5995 | 1349.5995 | 1349.5995 | 1349.5995 | 1349.5995 | 1349.5995 | 1350.4098 | 1351.2205 | 1352.0318 | 1352.8435 | 1353.6558 | 1354.8344 | 1356.0141 | 1357.1949 | 1358.3766 | 1359.5594 | 1360.1037 | 1360.6483 | 1361.193 | 1361.738 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 | 1362.2832 |  | 4040 | 4044.9907 | 4049.9877 | 4054.9907 | 4060 | 4065.3711 | 4070.7493 | 4076.1346 | 4081.5271 | 4086.9267 | 4092.2979 | 4097.6761 | 4103.0615 | 4108.4539 | 4113.8533 | 4116.322 | 4118.7921 | 4121.2637 | 4123.7367 | 4126.2113 | 4129.8023 | 4133.3964 | 4136.9936 | 4140.5939 | 4144.1974 | 4145.8557 | 4147.5148 | 4149.1744 | 4150.8348 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | 4152.4958 | [6 empty] | 406 | 409 | 412 | 415 | 417.4 | 423 | 429 | 435 | 441 | 447 | 451.5 | 456 | 461 | 466 | 471 | 476 | 481 | 486 | 491 | 496 | 501 | 506 | 511 | 516 | 521 | 526 | 531 | 536 | 541 | 546 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | 544.1 | [6 empty] | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0123 | 3.0163 | 3.0203 | 3.0243 | 3.0283 | 3.0322 | 3.0362 | 3.0402 | 3.0442 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482
184 | Henderson - Massey |  |  | 2052 | 1015.7682 | 1035.2491 | 1055.1035 | 1075.3387 | 1095.9621 | 1099.3008 | 1102.6497 | 1106.0088 | 1109.3782 | 1112.7578 | 1116.1616 | 1119.5758 | 1123.0005 | 1126.4356 | 1129.8813 | 1132.7459 | 1135.6177 | 1138.4968 | 1141.3832 | 1144.2769 | 1146.6871 | 1149.1023 | 1151.5227 | 1153.9481 | 1156.3786 | 1158.6405 | 1160.9069 | 1163.1776 | 1165.4529 | 1167.7325 | 1169.3738 | 1171.0174 | 1172.6633 | 1174.3115 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 | 1175.9621 |  | 3110 | 3168.3379 | 3227.7701 | 3288.3172 | 3350 | 3353.4975 | 3356.9987 | 3360.5035 | 3364.012 | 3367.5241 | 3371.0163 | 3374.5121 | 3378.0116 | 3381.5147 | 3385.0214 | 3384.5729 | 3384.1244 | 3383.676 | 3383.2276 | 3382.7794 | 3380.7946 | 3378.8109 | 3376.8285 | 3374.8472 | 3372.867 | 3370.2707 | 3367.6763 | 3365.084 | 3362.4936 | 3359.9052 | 3364.5295 | 3369.1601 | 3373.7971 | 3378.4405 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | 3383.0903 | [6 empty] | 391 | 394 | 397 | 400 | 401.6 | 407 | 412 | 417 | 422 | 427 | 434.2 | 438 | 442 | 446 | 450 | 454 | 458 | 462 | 466 | 470 | 474 | 478 | 482 | 486 | 490 | 494 | 498 | 502 | 506 | 510 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | 513 | [6 empty] | 3.0617 | 3.0605 | 3.0592 | 3.0579 | 3.0567 | 3.0506 | 3.0445 | 3.0384 | 3.0323 | 3.0263 | 3.0202 | 3.0141 | 3.008 | 3.002 | 2.9959 | 2.9879 | 2.98 | 2.9721 | 2.9641 | 2.9563 | 2.9483 | 2.9404 | 2.9325 | 2.9246 | 2.9167 | 2.9088 | 2.9009 | 2.893 | 2.8851 | 2.8773 | 2.8772 | 2.8771 | 2.877 | 2.877 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769 | 2.8769
185 | Henderson - Massey |  |  | 2052 | 1532.4399 | 1535.6962 | 1538.9594 | 1542.2296 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 | 1545.5067 |  | 4720 | 4729.9684 | 4739.9578 | 4749.9683 | 4760 | 4744.2769 | 4728.6056 | 4712.9862 | 4697.4184 | 4681.9019 | 4666.177 | 4650.505 | 4634.8855 | 4619.3185 | 4603.8039 | 4586.4741 | 4569.2096 | 4552.0101 | 4534.8754 | 4517.8051 | 4500.4731 | 4483.2076 | 4466.0083 | 4448.875 | 4431.8075 | 4414.4723 | 4397.2048 | 4380.005 | 4362.8724 | 4345.8068 | 4345.8068 | 4345.8068 | 4345.8068 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | 4345.8069 | [6 empty] | 451 | 453 | 455 | 457 | 458.2 | 464 | 470 | 476 | 482 | 488 | 491.8 | 495 | 498 | 501 | 504 | 507 | 510 | 513 | 516 | 519 | 522 | 525 | 528 | 531 | 534 | 537 | 540 | 543 | 546 | 549 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | 558.2 | [6 empty] | 3.0801 | 3.08 | 3.08 | 3.0799 | 3.0799 | 3.0697 | 3.0596 | 3.0495 | 3.0394 | 3.0294 | 3.0192 | 3.009 | 2.9989 | 2.9889 | 2.9788 | 2.9676 | 2.9564 | 2.9453 | 2.9342 | 2.9232 | 2.912 | 2.9008 | 2.8897 | 2.8786 | 2.8675 | 2.8563 | 2.8452 | 2.834 | 2.8229 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119 | 2.8119
186 | Henderson - Massey |  |  | 2052 | 557.4791 | 567.4611 | 577.6218 | 587.9644 | 598.4922 | 619.3546 | 640.9441 | 663.2863 | 686.4073 | 710.3342 | 731.8018 | 753.9181 | 776.7028 | 800.1761 | 824.3588 | 844.3124 | 864.749 | 885.6802 | 907.1181 | 929.0749 | 947.0599 | 965.3929 | 984.0809 | 1003.1307 | 1022.5492 | 1046.4945 | 1071.0005 | 1096.0804 | 1121.7476 | 1148.0158 | 1170.5957 | 1193.6197 | 1217.0965 | 1241.0351 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 | 1265.4446 |  | 1650 | 1676.8381 | 1704.1127 | 1731.8309 | 1760 | 1818.7341 | 1879.4283 | 1942.1479 | 2006.9606 | 2073.9362 | 2134.9437 | 2197.7458 | 2262.3952 | 2328.9465 | 2397.4554 | 2451.9766 | 2507.7378 | 2564.767 | 2623.0932 | 2682.7457 | 2731.8257 | 2781.8036 | 2832.6958 | 2884.519 | 2937.2904 | 3002.6259 | 3069.4147 | 3137.6891 | 3207.4822 | 3278.8277 | 3340.3844 | 3403.0967 | 3466.9864 | 3532.0756 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | 3598.3867 | [6 empty] | 1408 | 1421 | 1434 | 1447 | 1459.7 | 1479 | 1498 | 1517 | 1536 | 1555 | 1575.2 | 1591 | 1607 | 1623 | 1639 | 1655 | 1671 | 1687 | 1703 | 1719 | 1735 | 1751 | 1767 | 1783 | 1799 | 1815 | 1831 | 1847 | 1863 | 1879 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | 1886.5 | [6 empty] | 2.9598 | 2.955 | 2.9502 | 2.9455 | 2.9407 | 2.9365 | 2.9323 | 2.9281 | 2.9239 | 2.9197 | 2.9174 | 2.9151 | 2.9128 | 2.9105 | 2.9083 | 2.9041 | 2.9 | 2.8958 | 2.8917 | 2.8875 | 2.8845 | 2.8815 | 2.8785 | 2.8755 | 2.8725 | 2.8692 | 2.8659 | 2.8626 | 2.8594 | 2.8561 | 2.8536 | 2.8511 | 2.8486 | 2.8461 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436 | 2.8436
187 | Henderson - Massey |  |  | 2052 | 1924.3627 | 1927.6331 | 1930.9091 | 1934.1907 | 1937.4778 | 1939.8235 | 1942.1721 | 1944.5235 | 1946.8777 | 1949.2348 | 1951.6262 | 1954.0206 | 1956.4179 | 1958.8181 | 1961.2213 | 1963.4108 | 1965.6029 | 1967.7973 | 1969.9943 | 1972.1937 | 1974.1447 | 1976.0976 | 1978.0525 | 1980.0093 | 1981.9681 | 1984.5942 | 1987.2238 | 1989.8569 | 1992.4934 | 1995.1335 | 1997.5963 | 2000.0621 | 2002.5309 | 2005.0028 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 | 2007.4778 |  | 5850 | 5859.9745 | 5869.9659 | 5879.9744 | 5890 | 5892.4372 | 5894.8754 | 5897.3146 | 5899.7549 | 5902.1961 | 5904.7149 | 5907.2348 | 5909.7558 | 5912.2779 | 5914.801 | 5911.4025 | 5908.0061 | 5904.6115 | 5901.2189 | 5897.8283 | 5893.6035 | 5889.3817 | 5885.163 | 5880.9472 | 5876.7345 | 5874.4142 | 5872.0949 | 5869.7764 | 5867.4589 | 5865.1422 | 5872.4057 | 5879.6782 | 5886.9596 | 5894.2501 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | 5901.5496 | [6 empty] | 515 | 517 | 519 | 521 | 523.6 | 530 | 536 | 542 | 548 | 554 | 562.4 | 567 | 571 | 575 | 579 | 583 | 587 | 591 | 595 | 599 | 603 | 607 | 611 | 615 | 619 | 623 | 627 | 631 | 635 | 639 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | 644.5 | [6 empty] | 3.04 | 3.04 | 3.04 | 3.04 | 3.04 | 3.0376 | 3.0352 | 3.0328 | 3.0304 | 3.028 | 3.0255 | 3.0231 | 3.0207 | 3.0183 | 3.0159 | 3.0108 | 3.0057 | 3.0006 | 2.9956 | 2.9905 | 2.9854 | 2.9803 | 2.9752 | 2.9702 | 2.9651 | 2.96 | 2.9549 | 2.9498 | 2.9448 | 2.9397 | 2.9397 | 2.9397 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398 | 2.9398
188 | Henderson - Massey |  |  | 2052 | 1732.4461 | 1741.1173 | 1749.8319 | 1758.5901 | 1767.3922 | 1770.0714 | 1772.7546 | 1775.4419 | 1778.1333 | 1780.8288 | 1783.5601 | 1786.2957 | 1789.0355 | 1791.7794 | 1794.5276 | 1797.0286 | 1799.5331 | 1802.041 | 1804.5525 | 1807.0675 | 1809.2961 | 1811.5275 | 1813.7617 | 1815.9986 | 1818.2383 | 1821.2376 | 1824.2418 | 1827.2511 | 1830.2653 | 1833.2844 | 1836.0973 | 1838.9146 | 1841.7361 | 1844.562 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 | 1847.3922 |  | 5500 | 5527.2961 | 5554.7277 | 5582.2954 | 5610 | 5617.0905 | 5624.19 | 5631.2984 | 5638.4158 | 5645.5422 | 5652.7764 | 5660.0199 | 5667.2726 | 5674.5346 | 5681.806 | 5682.6646 | 5683.5233 | 5684.3822 | 5685.2413 | 5686.1004 | 5686.0128 | 5685.9253 | 5685.8377 | 5685.7501 | 5685.6625 | 5687.8749 | 5690.0881 | 5692.3022 | 5694.5172 | 5696.733 | 5705.4023 | 5714.0847 | 5722.7804 | 5731.4893 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | 5740.2115 | [6 empty] | 600 | 604 | 608 | 612 | 616.3 | 625 | 634 | 643 | 652 | 661 | 668.1 | 675 | 681 | 687 | 693 | 699 | 705 | 711 | 717 | 723 | 729 | 735 | 741 | 747 | 753 | 759 | 765 | 771 | 777 | 783 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | 796.2 | [6 empty] | 3.1747 | 3.1746 | 3.1744 | 3.1743 | 3.1742 | 3.1734 | 3.1726 | 3.1718 | 3.171 | 3.1702 | 3.1694 | 3.1686 | 3.1678 | 3.167 | 3.1662 | 3.1623 | 3.1583 | 3.1544 | 3.1505 | 3.1466 | 3.1427 | 3.1387 | 3.1348 | 3.1309 | 3.127 | 3.1231 | 3.1192 | 3.1152 | 3.1113 | 3.1074 | 3.1074 | 3.1073 | 3.1073 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072 | 3.1072
189 | Henderson - Massey |  |  | 2052 | 1217.0195 | 1220.3953 | 1223.7805 | 1227.175 | 1230.579 | 1232.0034 | 1233.4294 | 1234.857 | 1236.2863 | 1237.7172 | 1239.1693 | 1240.6231 | 1242.0786 | 1243.5358 | 1244.9947 | 1246.3402 | 1247.6871 | 1249.0354 | 1250.3852 | 1251.7365 | 1252.9443 | 1254.1533 | 1255.3635 | 1256.5748 | 1257.7873 | 1259.4131 | 1261.041 | 1262.671 | 1264.3031 | 1265.9373 | 1267.462 | 1268.9885 | 1270.5168 | 1272.047 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 | 1273.579 |  | 3600 | 3609.9586 | 3619.9448 | 3629.9585 | 3640 | 3649.0125 | 3658.0473 | 3667.1045 | 3676.1841 | 3685.2862 | 3694.437 | 3703.6106 | 3712.8069 | 3722.0261 | 3731.2682 | 3735.2899 | 3739.3159 | 3743.3462 | 3747.3809 | 3751.42 | 3755.0303 | 3758.6441 | 3762.2615 | 3765.8822 | 3769.5065 | 3774.3662 | 3779.2321 | 3784.1044 | 3788.9829 | 3793.8677 | 3798.4251 | 3802.9879 | 3807.5563 | 3812.1301 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | 3816.7094 | [6 empty] | 284 | 285 | 286 | 287 | 287.9 | 291 | 294 | 297 | 300 | 303 | 306.5 | 309 | 311 | 313 | 315 | 317 | 319 | 321 | 323 | 325 | 327 | 329 | 331 | 333 | 335 | 337 | 339 | 341 | 343 | 345 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | 348.8 | [6 empty] | 2.958 | 2.958 | 2.958 | 2.958 | 2.958 | 2.9619 | 2.9658 | 2.9697 | 2.9736 | 2.9775 | 2.9814 | 2.9853 | 2.9892 | 2.9931 | 2.997 | 2.997 | 2.997 | 2.997 | 2.997 | 2.997 | 2.997 | 2.997 | 2.9969 | 2.9969 | 2.9969 | 2.9969 | 2.9969 | 2.9969 | 2.9969 | 2.9969 | 2.9969 | 2.9969 | 2.9969 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968 | 2.9968
190 | Henderson - Massey |  |  | 2052 | 596.8203 | 622.5218 | 649.3302 | 677.293 | 706.4601 | 728.5489 | 751.3284 | 774.8202 | 799.0465 | 824.0302 | 846.7189 | 870.0322 | 893.9874 | 918.6022 | 943.8947 | 964.885 | 986.342 | 1008.2761 | 1030.6981 | 1053.6186 | 1072.48 | 1091.6791 | 1111.2218 | 1131.1144 | 1151.3631 | 1176.5661 | 1202.3208 | 1228.6393 | 1255.5338 | 1283.0171 | 1306.807 | 1331.0379 | 1355.7182 | 1380.8561 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 | 1406.4601 |  | 1930 | 2009.9 | 2093.1077 | 2179.7602 | 2270 | 2331.0061 | 2393.6517 | 2457.9809 | 2524.039 | 2591.8724 | 2652.3 | 2714.1365 | 2777.4147 | 2842.1681 | 2908.4312 | 2959.7641 | 3012.0029 | 3065.1638 | 3119.2629 | 3174.3168 | 3216.8213 | 3259.895 | 3303.5454 | 3347.7803 | 3392.6075 | 3450.9945 | 3510.3862 | 3570.8001 | 3632.2537 | 3694.765 | 3761.8563 | 3830.1658 | 3899.7158 | 3970.5287 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | 4042.6274 | [6 empty] | 602 | 607 | 612 | 617 | 621.2 | 629 | 637 | 645 | 653 | 661 | 666.5 | 672 | 678 | 684 | 690 | 696 | 702 | 708 | 714 | 720 | 726 | 732 | 738 | 744 | 750 | 756 | 762 | 768 | 774 | 780 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | 784.4 | [6 empty] | 3.2338 | 3.2286 | 3.2235 | 3.2183 | 3.2132 | 3.1995 | 3.1859 | 3.1723 | 3.1588 | 3.1454 | 3.1324 | 3.1196 | 3.1068 | 3.094 | 3.0813 | 3.0675 | 3.0537 | 3.04 | 3.0264 | 3.0128 | 2.9994 | 2.9861 | 2.9729 | 2.9597 | 2.9466 | 2.9331 | 2.9197 | 2.9063 | 2.893 | 2.8797 | 2.8787 | 2.8776 | 2.8765 | 2.8754 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743 | 2.8743
191 | Waitakere Ranges |  |  | 2052 | 601.859 | 640.8495 | 682.3661 | 726.5722 | 773.6422 | 787.4191 | 801.4413 | 815.7132 | 830.2393 | 845.0241 | 859.1021 | 873.4146 | 887.9656 | 902.7591 | 917.7989 | 930.7215 | 943.826 | 957.1151 | 970.5912 | 984.2571 | 995.8054 | 1007.4891 | 1019.3099 | 1031.2694 | 1043.3693 | 1058.8282 | 1074.5162 | 1090.4366 | 1106.5929 | 1122.9886 | 1137.5374 | 1152.2747 | 1167.203 | 1182.3246 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 | 1197.6422 |  | 1730 | 1841.2927 | 1959.7449 | 2085.8173 | 2220 | 2255.6767 | 2291.9268 | 2328.7594 | 2366.1839 | 2404.2099 | 2440.0911 | 2476.5078 | 2513.4679 | 2550.9797 | 2589.0513 | 2618.9999 | 2649.295 | 2679.9404 | 2710.9404 | 2742.2989 | 2767.5564 | 2793.0464 | 2818.7712 | 2844.733 | 2870.9339 | 2906.0851 | 2941.6667 | 2977.684 | 3014.1423 | 3051.0469 | 3090.4074 | 3130.2757 | 3170.6583 | 3211.5619 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | 3252.9932 | [6 empty] | 394 | 396 | 398 | 400 | 403.7 | 408 | 413 | 418 | 423 | 428 | 431.9 | 435 | 438 | 441 | 444 | 447 | 450 | 453 | 456 | 459 | 462 | 465 | 468 | 471 | 474 | 477 | 480 | 483 | 486 | 489 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | 501.1 | [6 empty] | 2.8744 | 2.8732 | 2.872 | 2.8708 | 2.8695 | 2.8646 | 2.8598 | 2.8549 | 2.85 | 2.8451 | 2.8403 | 2.8354 | 2.8306 | 2.8258 | 2.8209 | 2.8139 | 2.807 | 2.8 | 2.7931 | 2.7862 | 2.7792 | 2.7723 | 2.7654 | 2.7585 | 2.7516 | 2.7446 | 2.7377 | 2.7307 | 2.7238 | 2.7169 | 2.7168 | 2.7166 | 2.7165 | 2.7163 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162 | 2.7162
192 | Henderson - Massey |  |  | 2052 | 1157.7002 | 1157.7002 | 1157.7002 | 1157.7002 | 1157.7002 | 1159.0408 | 1160.3829 | 1161.7265 | 1163.0717 | 1164.4185 | 1165.7852 | 1167.1535 | 1168.5233 | 1169.8948 | 1171.2679 | 1172.5829 | 1173.8994 | 1175.2173 | 1176.5367 | 1177.8577 | 1179.0653 | 1180.2743 | 1181.4844 | 1182.6959 | 1183.9085 | 1185.452 | 1186.9976 | 1188.5452 | 1190.0947 | 1191.6463 | 1193.0538 | 1194.4629 | 1195.8737 | 1197.2861 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 | 1198.7002 |  | 3460 | 3460 | 3460 | 3460 | 3460 | 3461.1859 | 3462.3722 | 3463.5589 | 3464.746 | 3465.9336 | 3467.1636 | 3468.394 | 3469.6249 | 3470.8563 | 3472.088 | 3470.1551 | 3468.2233 | 3466.2925 | 3464.3628 | 3462.4342 | 3460.1313 | 3457.83 | 3455.5302 | 3453.2319 | 3450.9351 | 3449.5218 | 3448.1091 | 3446.6969 | 3445.2853 | 3443.8743 | 3447.8246 | 3451.7793 | 3455.7386 | 3459.7025 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | 3463.6708 | [6 empty] | 1245 | 1248 | 1251 | 1254 | 1255.5 | 1272 | 1289 | 1306 | 1323 | 1340 | 1356 | 1363 | 1370 | 1377 | 1384 | 1391 | 1398 | 1405 | 1412 | 1419 | 1426 | 1433 | 1440 | 1447 | 1454 | 1461 | 1468 | 1475 | 1482 | 1489 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | 1495.8 | [6 empty] | 2.9887 | 2.9887 | 2.9887 | 2.9887 | 2.9887 | 2.9863 | 2.9838 | 2.9814 | 2.979 | 2.9765 | 2.9741 | 2.9717 | 2.9692 | 2.9668 | 2.9644 | 2.9594 | 2.9544 | 2.9495 | 2.9445 | 2.9396 | 2.9346 | 2.9297 | 2.9247 | 2.9198 | 2.9149 | 2.9099 | 2.9049 | 2.8999 | 2.895 | 2.89 | 2.8899 | 2.8898 | 2.8897 | 2.8896 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895 | 2.8895
193 | Henderson - Massey |  |  | 2052 | 1755.9953 | 1752.8735 | 1749.7573 | 1746.6466 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 | 1743.5414 |  | 5640 | 5629.9733 | 5619.9644 | 5609.9733 | 5600 | 5607.3216 | 5614.6528 | 5621.9935 | 5629.3439 | 5636.7038 | 5644.0256 | 5651.3568 | 5658.6975 | 5666.0478 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | 5673.4077 | [6 empty] | 386 | 389 | 392 | 395 | 396.1 | 402 | 408 | 414 | 420 | 426 | 430.2 | 435 | 440 | 445 | 450 | 455 | 460 | 465 | 470 | 475 | 480 | 485 | 490 | 495 | 500 | 505 | 510 | 515 | 520 | 525 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | 526.7 | [6 empty] | 3.2119 | 3.2119 | 3.2119 | 3.2119 | 3.2119 | 3.2161 | 3.2203 | 3.2245 | 3.2287 | 3.2329 | 3.2371 | 3.2413 | 3.2455 | 3.2497 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254 | 3.254
194 | Henderson - Massey |  |  | 2052 | 1985.2801 | 2015.8115 | 2046.8125 | 2078.2902 | 2110.252 | 2118.997 | 2127.7782 | 2136.5958 | 2145.4499 | 2154.3408 | 2163.2565 | 2172.2092 | 2181.1988 | 2190.2257 | 2199.29 | 2207.4741 | 2215.6887 | 2223.9339 | 2232.2097 | 2240.5164 | 2247.8227 | 2255.1528 | 2262.5068 | 2269.8849 | 2277.2869 | 2287.1073 | 2296.9699 | 2306.8752 | 2316.8231 | 2326.8139 | 2336.0282 | 2345.2791 | 2354.5666 | 2363.8908 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 | 2373.252 |  | 6690 | 6792.6148 | 6896.8036 | 7002.5905 | 7110 | 7110.2104 | 7110.4209 | 7110.6313 | 7110.8418 | 7111.0523 | 7110.6131 | 7110.174 | 7109.735 | 7109.2959 | 7108.8569 | 7103.4394 | 7098.0261 | 7092.617 | 7087.2119 | 7081.811 | 7072.4541 | 7063.1096 | 7053.7774 | 7044.4576 | 7035.1501 | 7032.4439 | 7029.7387 | 7027.0345 | 7024.3314 | 7021.6293 | 7049.3649 | 7077.2101 | 7105.1653 | 7133.2308 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | 7161.4073 | [6 empty] | 955 | 963 | 971 | 979 | 986.2 | 998 | 1010 | 1022 | 1034 | 1046 | 1057.4 | 1068 | 1078 | 1088 | 1098 | 1108 | 1118 | 1128 | 1138 | 1148 | 1158 | 1168 | 1178 | 1188 | 1198 | 1208 | 1218 | 1228 | 1238 | 1248 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | 1261.6 | [6 empty] | 3.3698 | 3.3697 | 3.3695 | 3.3694 | 3.3693 | 3.3555 | 3.3417 | 3.328 | 3.3144 | 3.3008 | 3.287 | 3.2732 | 3.2596 | 3.2459 | 3.2323 | 3.2179 | 3.2035 | 3.1892 | 3.175 | 3.1608 | 3.1464 | 3.132 | 3.1177 | 3.1034 | 3.0893 | 3.0748 | 3.0604 | 3.0461 | 3.0319 | 3.0177 | 3.0177 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176 | 3.0176
195 | Waitakere Ranges |  |  | 2052 | 1354.7395 | 1391.8496 | 1429.9762 | 1469.1473 | 1509.3914 | 1512.0692 | 1514.7517 | 1517.439 | 1520.1311 | 1522.8279 | 1525.5579 | 1528.2927 | 1531.0325 | 1533.7772 | 1536.5267 | 1539.0266 | 1541.5305 | 1544.0384 | 1546.5505 | 1549.0666 | 1551.2944 | 1553.5253 | 1555.7595 | 1557.9968 | 1560.2374 | 1563.1533 | 1566.0746 | 1569.0014 | 1571.9337 | 1574.8714 | 1577.5662 | 1580.2655 | 1582.9695 | 1585.6781 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 | 1588.3914 |  | 3750 | 3853.1642 | 3959.1666 | 4068.0851 | 4180 | 4182.3147 | 4184.6307 | 4186.948 | 4189.2666 | 4191.5865 | 4193.9542 | 4196.3232 | 4198.6936 | 4201.0653 | 4203.4383 | 4201.67 | 4199.9025 | 4198.1357 | 4196.3697 | 4194.6044 | 4191.9573 | 4189.312 | 4186.6683 | 4184.0263 | 4181.386 | 4180.4614 | 4179.537 | 4178.6129 | 4177.6889 | 4176.7651 | 4183.9406 | 4191.1283 | 4198.3284 | 4205.5409 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | 4212.7658 | [6 empty] | 806 | 810 | 814 | 818 | 823.8 | 835 | 847 | 859 | 871 | 883 | 892.8 | 900 | 908 | 916 | 924 | 932 | 940 | 948 | 956 | 964 | 972 | 980 | 988 | 996 | 1004 | 1012 | 1020 | 1028 | 1036 | 1044 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | 1043.1 | [6 empty] | 2.7681 | 2.7684 | 2.7687 | 2.769 | 2.7693 | 2.766 | 2.7626 | 2.7592 | 2.7559 | 2.7525 | 2.7491 | 2.7458 | 2.7424 | 2.739 | 2.7357 | 2.7301 | 2.7245 | 2.7189 | 2.7134 | 2.7078 | 2.7022 | 2.6966 | 2.6911 | 2.6855 | 2.68 | 2.6744 | 2.6688 | 2.6632 | 2.6577 | 2.6521 | 2.6521 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522 | 2.6522
196 | Henderson - Massey |  |  | 2052 | 1486.466 | 1487.1895 | 1487.9132 | 1488.6374 | 1489.3618 | 1500.862 | 1512.451 | 1524.1295 | 1535.8982 | 1547.7577 | 1559.4857 | 1571.3025 | 1583.2089 | 1595.2056 | 1607.2931 | 1618.0776 | 1628.9345 | 1639.8642 | 1650.8672 | 1661.9441 | 1671.5856 | 1681.2831 | 1691.0369 | 1700.8472 | 1710.7144 | 1723.6043 | 1736.5913 | 1749.6761 | 1762.8596 | 1776.1424 | 1788.2209 | 1800.3815 | 1812.6248 | 1824.9514 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 | 1837.3618 |  | 5070 | 5072.4982 | 5074.9975 | 5077.4982 | 5080 | 5098.7966 | 5117.6627 | 5136.5986 | 5155.6046 | 5174.681 | 5192.5882 | 5210.5573 | 5228.5887 | 5246.6824 | 5264.8388 | 5276.6048 | 5288.3971 | 5300.2158 | 5312.0609 | 5323.9325 | 5330.3581 | 5336.7915 | 5343.2327 | 5349.6816 | 5356.1383 | 5371.3822 | 5386.6694 | 5402.0001 | 5417.3745 | 5432.7926 | 5470.2886 | 5508.0434 | 5546.0588 | 5584.3366 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | 5622.8786 | [6 empty] | 698 | 701 | 704 | 707 | 710.5 | 719 | 727 | 735 | 743 | 751 | 759.7 | 765 | 770 | 775 | 780 | 785 | 790 | 795 | 800 | 805 | 810 | 815 | 820 | 825 | 830 | 835 | 840 | 845 | 850 | 855 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | 868.7 | [6 empty] | 3.4108 | 3.4108 | 3.4108 | 3.4108 | 3.4109 | 3.3972 | 3.3837 | 3.3702 | 3.3567 | 3.3433 | 3.3297 | 3.3161 | 3.3025 | 3.289 | 3.2756 | 3.261 | 3.2465 | 3.2321 | 3.2177 | 3.2034 | 3.1888 | 3.1742 | 3.1597 | 3.1453 | 3.1309 | 3.1164 | 3.1019 | 3.0874 | 3.0731 | 3.0588 | 3.0591 | 3.0594 | 3.0597 | 3.06 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603 | 3.0603
197 | Henderson - Massey |  |  | 2052 | 2220.8804 | 2219.2456 | 2217.612 | 2215.9796 | 2214.3484 | 2219.7866 | 2225.2382 | 2230.7032 | 2236.1816 | 2241.6734 | 2247.2176 | 2252.7754 | 2258.347 | 2263.9324 | 2269.5316 | 2274.619 | 2279.7177 | 2284.8279 | 2289.9495 | 2295.0826 | 2299.6225 | 2304.1713 | 2308.7292 | 2313.2961 | 2317.872 | 2323.9788 | 2330.1017 | 2336.2407 | 2342.396 | 2348.5674 | 2354.2956 | 2360.0377 | 2365.7939 | 2371.5641 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 | 2377.3484 |  | 6800 | 6794.9945 | 6789.9926 | 6784.9945 | 6780 | 6784.758 | 6789.5194 | 6794.2841 | 6799.0522 | 6803.8236 | 6808.6091 | 6813.398 | 6818.1903 | 6822.9859 | 6827.7849 | 6826.1668 | 6824.5491 | 6822.9317 | 6821.3147 | 6819.6981 | 6816.0689 | 6812.4417 | 6808.8164 | 6805.193 | 6801.5715 | 6802.2063 | 6802.8412 | 6803.4761 | 6804.1112 | 6804.7462 | 6821.412 | 6838.1186 | 6854.8661 | 6871.6546 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | 6888.4843 | [6 empty] | 973 | 980 | 987 | 994 | 1002.9 | 1015 | 1028 | 1041 | 1054 | 1067 | 1078 | 1088 | 1098 | 1108 | 1118 | 1128 | 1138 | 1148 | 1158 | 1168 | 1178 | 1188 | 1198 | 1208 | 1218 | 1228 | 1238 | 1248 | 1258 | 1268 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | 1275.6 | [6 empty] | 3.0618 | 3.0618 | 3.0618 | 3.0618 | 3.0618 | 3.0565 | 3.0511 | 3.0458 | 3.0405 | 3.0352 | 3.0298 | 3.0244 | 3.0191 | 3.0138 | 3.0085 | 3.001 | 2.9936 | 2.9862 | 2.9788 | 2.9714 | 2.964 | 2.9566 | 2.9492 | 2.9418 | 2.9344 | 2.927 | 2.9195 | 2.9121 | 2.9048 | 2.8974 | 2.8974 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975 | 2.8975
198 | Henderson - Massey |  |  | 2052 | 915.5695 | 919.6634 | 923.7756 | 927.9061 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 | 932.0552 |  | 2840 | 2852.4183 | 2864.8909 | 2877.4181 | 2890 | 2893.742 | 2897.4889 | 2901.2407 | 2904.9973 | 2908.7587 | 2912.5009 | 2916.2478 | 2919.9995 | 2923.7561 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | 2927.5175 | [6 empty] | 1788 | 1796 | 1804 | 1812 | 1820.3 | 1844 | 1868 | 1892 | 1916 | 1940 | 1962.8 | 1976 | 1989 | 2002 | 2015 | 2028 | 2041 | 2054 | 2067 | 2080 | 2093 | 2106 | 2119 | 2132 | 2145 | 2158 | 2171 | 2184 | 2197 | 2210 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | 2224.6 | [6 empty] | 3.1019 | 3.1016 | 3.1013 | 3.101 | 3.1007 | 3.1047 | 3.1087 | 3.1127 | 3.1168 | 3.1208 | 3.1248 | 3.1288 | 3.1329 | 3.1369 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409 | 3.1409
199 | Henderson - Massey |  |  | 2052 | 1285.421 | 1287.0022 | 1288.5853 | 1290.1704 | 1291.7575 | 1294.4337 | 1297.1154 | 1299.8028 | 1302.4956 | 1305.1941 | 1307.9224 | 1310.6564 | 1313.3962 | 1316.1417 | 1318.8929 | 1321.3914 | 1323.8946 | 1326.4026 | 1328.9153 | 1331.4328 | 1333.6595 | 1335.8899 | 1338.124 | 1340.3619 | 1342.6036 | 1345.5994 | 1348.6019 | 1351.6111 | 1354.6271 | 1357.6497 | 1360.4596 | 1363.2753 | 1366.0969 | 1368.9243 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 | 1371.7575 |  | 4080 | 4084.9908 | 4089.9878 | 4094.9908 | 4100 | 4113.8555 | 4127.7579 | 4141.7072 | 4155.7037 | 4169.7475 | 4183.8811 | 4198.0627 | 4212.2923 | 4226.5702 | 4240.8964 | 4248.8873 | 4256.8932 | 4264.9142 | 4272.9503 | 4281.0016 | 4288.1232 | 4295.2566 | 4302.4019 | 4309.5591 | 4316.7282 | 4326.3097 | 4335.9125 | 4345.5367 | 4355.1821 | 4364.849 | 4373.8359 | 4382.8412 | 4391.8651 | 4400.9076 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | 4409.9687 | [6 empty] | 917 | 924 | 931 | 938 | 944.8 | 957 | 969 | 981 | 993 | 1005 | 1017.4 | 1027 | 1036 | 1045 | 1054 | 1063 | 1072 | 1081 | 1090 | 1099 | 1108 | 1117 | 1126 | 1135 | 1144 | 1153 | 1162 | 1171 | 1180 | 1189 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | 1205 | [6 empty] | 3.1741 | 3.174 | 3.174 | 3.174 | 3.174 | 3.1781 | 3.1823 | 3.1864 | 3.1906 | 3.1947 | 3.1989 | 3.203 | 3.2072 | 3.2113 | 3.2155 | 3.2155 | 3.2154 | 3.2154 | 3.2154 | 3.2153 | 3.2153 | 3.2153 | 3.2152 | 3.2152 | 3.2152 | 3.2152 | 3.2151 | 3.2151 | 3.215 | 3.215 | 3.215 | 3.2149 | 3.2149 | 3.2149 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148 | 3.2148
200 | Henderson - Massey |  |  | 2052 | 1150.6163 | 1174.8812 | 1199.6578 | 1224.9568 | 1250.7894 | 1253.4653 | 1256.1469 | 1258.8342 | 1261.5272 | 1264.226 | 1266.954 | 1269.6878 | 1272.4276 | 1275.1732 | 1277.9248 | 1280.423 | 1282.9261 | 1285.4341 | 1287.9469 | 1290.4647 | 1292.6912 | 1294.9215 | 1297.1556 | 1299.3936 | 1301.6355 | 1304.6309 | 1307.6332 | 1310.6424 | 1313.6586 | 1316.6817 | 1319.4912 | 1322.3067 | 1325.1283 | 1327.9558 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 | 1330.7894 |  | 3500 | 3572.7031 | 3646.9165 | 3722.6714 | 3800 | 3812.9839 | 3826.0121 | 3839.0848 | 3852.2022 | 3865.3644 | 3878.6121 | 3891.9052 | 3905.2439 | 3918.6283 | 3932.0586 | 3939.6399 | 3947.2358 | 3954.8464 | 3962.4716 | 3970.1116 | 3976.8682 | 3983.6364 | 3990.4161 | 3997.2073 | 4004.0101 | 4013.1004 | 4022.2114 | 4031.343 | 4040.4954 | 4049.6686 | 4058.1948 | 4066.739 | 4075.3011 | 4083.8813 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | 4092.4795 | [6 empty] | 892 | 903 | 914 | 925 | 935.3 | 948 | 961 | 974 | 987 | 1000 | 1010.3 | 1022 | 1033 | 1044 | 1055 | 1066 | 1077 | 1088 | 1099 | 1110 | 1121 | 1132 | 1143 | 1154 | 1165 | 1176 | 1187 | 1198 | 1209 | 1220 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | 1239.9 | [6 empty] | 3.0418 | 3.0409 | 3.04 | 3.039 | 3.0381 | 3.042 | 3.0458 | 3.0497 | 3.0536 | 3.0575 | 3.0614 | 3.0652 | 3.0691 | 3.073 | 3.0769 | 3.0768 | 3.0767 | 3.0767 | 3.0766 | 3.0765 | 3.0764 | 3.0764 | 3.0763 | 3.0762 | 3.0761 | 3.076 | 3.0759 | 3.0759 | 3.0758 | 3.0757 | 3.0756 | 3.0755 | 3.0754 | 3.0753 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752 | 3.0752
201 | Henderson - Massey |  |  | 2052 | 397.8865 | 397.8865 | 397.8865 | 397.8865 | 397.8865 | 402.3214 | 406.8057 | 411.34 | 415.9248 | 420.5608 | 425.0857 | 429.6593 | 434.2821 | 438.9547 | 443.6775 | 447.8004 | 451.9616 | 456.1614 | 460.4003 | 464.6786 | 468.3439 | 472.0382 | 475.7615 | 479.5143 | 483.2966 | 488.211 | 493.1754 | 498.1903 | 503.2562 | 508.3736 | 512.9915 | 517.6514 | 522.3536 | 527.0985 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 | 531.8865 |  | 1210 | 1210 | 1210 | 1210 | 1210 | 1225.3487 | 1240.8921 | 1256.6326 | 1272.5728 | 1288.7152 | 1304.6339 | 1320.7492 | 1337.0636 | 1353.5795 | 1370.2994 | 1383.4014 | 1396.6287 | 1409.9825 | 1423.4639 | 1437.0742 | 1448.9501 | 1460.9241 | 1472.9971 | 1485.1698 | 1497.4432 | 1513.0697 | 1528.8594 | 1544.8138 | 1560.9347 | 1577.2239 | 1590.7705 | 1604.4335 | 1618.2138 | 1632.1125 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | 1646.1306 | [6 empty] | 3907 | 3946 | 3985 | 4024 | 4063.8 | 4113 | 4162 | 4211 | 4260 | 4309 | 4360.1 | 4402 | 4443 | 4484 | 4525 | 4566 | 4607 | 4648 | 4689 | 4730 | 4771 | 4812 | 4853 | 4894 | 4935 | 4976 | 5017 | 5058 | 5099 | 5140 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | 5189 | [6 empty] | 3.0411 | 3.0411 | 3.0411 | 3.0411 | 3.0411 | 3.0457 | 3.0503 | 3.055 | 3.0596 | 3.0643 | 3.0691 | 3.0739 | 3.0788 | 3.0836 | 3.0885 | 3.0893 | 3.0901 | 3.091 | 3.0918 | 3.0926 | 3.0938 | 3.0949 | 3.0961 | 3.0972 | 3.0984 | 3.0992 | 3.1 | 3.1009 | 3.1017 | 3.1025 | 3.101 | 3.0994 | 3.0979 | 3.0964 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949 | 3.0949
202 | Henderson - Massey |  |  | 2052 | 15.1588 | 14.7648 | 14.3809 | 14.0071 | 13.6429 | 15.6479 | 17.9474 | 20.5849 | 23.6099 | 27.0795 | 29.39 | 31.8975 | 34.619 | 37.5727 | 40.7783 | 43.0248 | 45.395 | 47.8958 | 50.5343 | 53.3182 | 55.3857 | 57.5333 | 59.7643 | 62.0817 | 64.489 | 67.2513 | 70.1318 | 73.1358 | 76.2684 | 79.5352 | 82.1755 | 84.9035 | 87.722 | 90.6342 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 | 93.6429 |  | 100 | 97.4004 | 94.8683 | 92.4021 | 90 | 97.4979 | 105.6205 | 114.4198 | 123.9522 | 134.2787 | 143.4926 | 153.3387 | 163.8604 | 175.1041 | 187.1193 | 194.575 | 202.3277 | 210.3893 | 218.7721 | 227.4889 | 234.1809 | 241.0697 | 248.1612 | 255.4613 | 262.9762 | 271.8854 | 281.0964 | 290.6194 | 300.4651 | 310.6443 | 319.2922 | 328.1808 | 337.3169 | 346.7073 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | 356.3592 | [6 empty] | 2766 | 2787 | 2808 | 2829 | 2850.9 | 2886 | 2921 | 2956 | 2991 | 3026 | 3061.2 | 3086 | 3111 | 3136 | 3161 | 3186 | 3211 | 3236 | 3261 | 3286 | 3311 | 3336 | 3361 | 3386 | 3411 | 3436 | 3461 | 3486 | 3511 | 3536 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | 3556.4 | [6 empty] | 6.5968 | 6.5968 | 6.5968 | 6.5968 | 6.5968 | 6.2308 | 5.885 | 5.5584 | 5.25 | 4.9587 | 4.8824 | 4.8072 | 4.7333 | 4.6604 | 4.5887 | 4.5224 | 4.457 | 4.3926 | 4.3292 | 4.2666 | 4.2282 | 4.1901 | 4.1523 | 4.1149 | 4.0778 | 4.0428 | 4.0081 | 3.9737 | 3.9396 | 3.9057 | 3.8855 | 3.8653 | 3.8453 | 3.8253 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055 | 3.8055
203 | Henderson - Massey |  |  | 2052 | 3.0318 | 5.0925 | 8.5539 | 14.3681 | 24.1342 | 26.3679 | 28.8084 | 31.4748 | 34.388 | 37.5708 | 39.9808 | 42.5455 | 45.2747 | 48.179 | 51.2696 | 53.563 | 55.959 | 58.4621 | 61.0773 | 63.8094 | 65.9018 | 68.0628 | 70.2946 | 72.5996 | 74.9802 | 77.7735 | 80.6707 | 83.6759 | 86.7931 | 90.0264 | 92.6861 | 95.4243 | 98.2435 | 101.146 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 | 104.1342 |  | 20 | 28.2843 | 40 | 56.5685 | 80 | 87.9616 | 96.7155 | 106.3405 | 116.9235 | 128.5597 | 138.3291 | 148.8409 | 160.1515 | 172.3216 | 185.4166 | 192.7102 | 200.2909 | 208.1697 | 216.3584 | 224.8692 | 231.2408 | 237.7928 | 244.5305 | 251.4592 | 258.5841 | 267.0532 | 275.7998 | 284.8327 | 294.1616 | 303.7959 | 312.453 | 321.3568 | 330.5143 | 339.9327 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | 349.6196 | [6 empty] | 2435 | 2451 | 2467 | 2483 | 2497.5 | 2528 | 2559 | 2590 | 2621 | 2652 | 2681.3 | 2701 | 2721 | 2741 | 2761 | 2781 | 2801 | 2821 | 2841 | 2861 | 2881 | 2901 | 2921 | 2941 | 2961 | 2981 | 3001 | 3021 | 3041 | 3061 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | 3079.4 | [6 empty] | 6.5968 | 5.5541 | 4.6762 | 3.9371 | 3.3148 | 3.3359 | 3.3572 | 3.3786 | 3.4001 | 3.4218 | 3.4599 | 3.4984 | 3.5373 | 3.5767 | 3.6165 | 3.5978 | 3.5792 | 3.5608 | 3.5424 | 3.5241 | 3.5089 | 3.4937 | 3.4787 | 3.4636 | 3.4487 | 3.4337 | 3.4188 | 3.404 | 3.3892 | 3.3745 | 3.3711 | 3.3677 | 3.3642 | 3.3608 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574 | 3.3574
204 | Henderson - Massey |  |  | 2052 | 1852.964 | 1865.0999 | 1877.3153 | 1889.6107 | 1901.9866 | 1903.7469 | 1905.5088 | 1907.2724 | 1909.0376 | 1910.8044 | 1912.599 | 1914.3952 | 1916.1932 | 1917.9929 | 1919.7942 | 1921.4532 | 1923.1136 | 1924.7754 | 1926.4387 | 1928.1035 | 1929.5906 | 1931.0789 | 1932.5683 | 1934.0589 | 1935.5507 | 1937.5527 | 1939.5567 | 1941.5629 | 1943.5711 | 1945.5814 | 1947.4588 | 1949.3381 | 1951.2191 | 1953.1019 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 | 1954.9866 |  | 5310 | 5344.6592 | 5379.5446 | 5414.6577 | 5450 | 5438.8235 | 5427.6698 | 5416.5391 | 5405.4312 | 5394.3461 | 5383.1148 | 5371.9068 | 5360.7222 | 5349.561 | 5338.4229 | 5324.3845 | 5310.3831 | 5296.4185 | 5282.4906 | 5268.5993 | 5253.9322 | 5239.3059 | 5224.7203 | 5210.1753 | 5195.6708 | 5182.2289 | 5168.8218 | 5155.4493 | 5142.1114 | 5128.8081 | 5133.7396 | 5138.6759 | 5143.6169 | 5148.5627 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | 5153.5132 | [6 empty] | 1056 | 1061 | 1066 | 1071 | 1076.7 | 1090 | 1103 | 1116 | 1129 | 1142 | 1156.7 | 1165 | 1173 | 1181 | 1189 | 1197 | 1205 | 1213 | 1221 | 1229 | 1237 | 1245 | 1253 | 1261 | 1269 | 1277 | 1285 | 1293 | 1301 | 1309 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | 1319.8 | [6 empty] | 2.8657 | 2.8656 | 2.8656 | 2.8655 | 2.8654 | 2.8569 | 2.8484 | 2.8399 | 2.8315 | 2.8231 | 2.8146 | 2.8061 | 2.7976 | 2.7891 | 2.7807 | 2.771 | 2.7613 | 2.7517 | 2.7421 | 2.7325 | 2.7228 | 2.7131 | 2.7035 | 2.6939 | 2.6843 | 2.6746 | 2.665 | 2.6553 | 2.6457 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361 | 2.6361
205 | Henderson - Massey |  |  | 2052 | 2162.135 | 2173.9902 | 2185.9105 | 2197.8961 | 2209.9474 | 2227.9588 | 2246.117 | 2264.4231 | 2282.8784 | 2301.4842 | 2319.8533 | 2338.3689 | 2357.0323 | 2375.8447 | 2394.8073 | 2411.6826 | 2428.6769 | 2445.7909 | 2463.0256 | 2480.3816 | 2495.46 | 2510.6301 | 2525.8924 | 2541.2475 | 2556.6959 | 2576.8577 | 2597.1785 | 2617.6596 | 2638.3021 | 2659.1075 | 2678.005 | 2697.0367 | 2716.2038 | 2735.507 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 | 2754.9474 |  | 5930 | 5962.2362 | 5994.6476 | 6027.2352 | 6060 | 6087.1445 | 6114.4106 | 6141.7988 | 6169.3097 | 6196.9438 | 6223.2691 | 6249.7063 | 6276.2558 | 6302.918 | 6329.6936 | 6348.1677 | 6366.6958 | 6385.278 | 6403.9144 | 6422.6051 | 6434.6757 | 6446.7689 | 6458.8849 | 6471.0237 | 6483.1852 | 6506.3677 | 6529.633 | 6552.9816 | 6576.4136 | 6599.9295 | 6646.454 | 6693.3064 | 6740.4891 | 6788.0045 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | 6835.8547 | [6 empty] | 1469 | 1485 | 1501 | 1517 | 1531.5 | 1550 | 1569 | 1588 | 1607 | 1626 | 1645.1 | 1661 | 1677 | 1693 | 1709 | 1725 | 1741 | 1757 | 1773 | 1789 | 1805 | 1821 | 1837 | 1853 | 1869 | 1885 | 1901 | 1917 | 1933 | 1949 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | 1960.2 | [6 empty] | 2.7427 | 2.7425 | 2.7424 | 2.7423 | 2.7421 | 2.7322 | 2.7222 | 2.7123 | 2.7024 | 2.6926 | 2.6826 | 2.6727 | 2.6628 | 2.6529 | 2.6431 | 2.6323 | 2.6215 | 2.6107 | 2.6 | 2.5894 | 2.5786 | 2.5678 | 2.5571 | 2.5464 | 2.5358 | 2.5249 | 2.5141 | 2.5034 | 2.4927 | 2.482 | 2.4819 | 2.4817 | 2.4816 | 2.4814 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813 | 2.4813
206 | Henderson - Massey |  |  | 2052 | 838.5027 | 839.3304 | 840.159 | 840.9883 | 841.8185 | 847.9736 | 854.1736 | 860.419 | 866.7101 | 873.0471 | 879.3238 | 885.6456 | 892.0129 | 898.426 | 904.8851 | 910.563 | 916.2766 | 922.0259 | 927.8114 | 933.6332 | 938.656 | 943.7058 | 948.7827 | 953.887 | 959.0188 | 964.1168 | 969.2418 | 974.3942 | 979.5739 | 984.7811 | 988.7564 | 992.7477 | 996.7551 | 1000.7787 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 | 1004.8185 |  | 2640 | 2642.4965 | 2644.9953 | 2647.4965 | 2650 | 2659.5586 | 2669.1517 | 2678.7794 | 2688.4418 | 2698.139 | 2707.476 | 2716.8453 | 2726.247 | 2735.6813 | 2745.1482 | 2751.1994 | 2757.2639 | 2763.3418 | 2769.4331 | 2775.5378 | 2779.1515 | 2782.7699 | 2786.393 | 2790.0208 | 2793.6533 | 2796.9317 | 2800.2139 | 2803.4999 | 2806.7899 | 2810.0836 | 2820.8266 | 2831.6106 | 2842.4359 | 2853.3025 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | 2864.2107 | [6 empty] | 618 | 624 | 630 | 636 | 642.2 | 649 | 656 | 663 | 670 | 677 | 682.8 | 689 | 695 | 701 | 707 | 713 | 719 | 725 | 731 | 737 | 743 | 749 | 755 | 761 | 767 | 773 | 779 | 785 | 791 | 797 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | 797.8 | [6 empty] | 3.1485 | 3.1483 | 3.1482 | 3.1481 | 3.1479 | 3.1364 | 3.1248 | 3.1133 | 3.1019 | 3.0905 | 3.079 | 3.0676 | 3.0563 | 3.045 | 3.0337 | 3.0214 | 3.0092 | 2.997 | 2.9849 | 2.9728 | 2.9608 | 2.9488 | 2.9368 | 2.9249 | 2.913 | 2.901 | 2.8891 | 2.8772 | 2.8653 | 2.8535 | 2.8529 | 2.8523 | 2.8517 | 2.8511 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505 | 2.8505
207 | Henderson - Massey |  |  | 2052 | 1304.9932 | 1315.4047 | 1325.8991 | 1336.4774 | 1347.14 | 1353.3286 | 1359.5456 | 1365.7912 | 1372.0655 | 1378.3686 | 1384.6781 | 1391.0166 | 1397.384 | 1403.7806 | 1410.2065 | 1415.9098 | 1421.6362 | 1427.3857 | 1433.1585 | 1438.9546 | 1443.9963 | 1449.0556 | 1454.1327 | 1459.2275 | 1464.3402 | 1469.4568 | 1474.5913 | 1479.7437 | 1484.9141 | 1490.1026 | 1494.0887 | 1498.0854 | 1502.0929 | 1506.111 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 | 1510.14 |  | 3730 | 3759.6447 | 3789.525 | 3819.6428 | 3850 | 3870.6371 | 3891.3849 | 3912.2438 | 3933.2146 | 3954.2977 | 3975.4234 | 3996.6619 | 4018.0139 | 4039.4799 | 4061.0607 | 4075.7075 | 4090.4072 | 4105.1599 | 4119.9658 | 4134.8251 | 4147.5148 | 4160.2434 | 4173.011 | 4185.8179 | 4198.664 | 4211.5081 | 4224.3916 | 4237.3144 | 4250.2768 | 4263.2789 | 4274.6285 | 4286.0083 | 4297.4184 | 4308.8589 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | 4320.3299 | [6 empty] | 729 | 734 | 739 | 744 | 749.2 | 759 | 768 | 777 | 786 | 795 | 805.9 | 813 | 820 | 827 | 834 | 841 | 848 | 855 | 862 | 869 | 876 | 883 | 890 | 897 | 904 | 911 | 918 | 925 | 932 | 939 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | 953.9 | [6 empty] | 2.8583 | 2.8582 | 2.8581 | 2.858 | 2.8579 | 2.8601 | 2.8623 | 2.8645 | 2.8666 | 2.8688 | 2.871 | 2.8732 | 2.8754 | 2.8776 | 2.8798 | 2.8785 | 2.8773 | 2.876 | 2.8747 | 2.8735 | 2.8722 | 2.871 | 2.8698 | 2.8685 | 2.8673 | 2.866 | 2.8648 | 2.8635 | 2.8623 | 2.8611 | 2.861 | 2.861 | 2.861 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609 | 2.8609
208 | Henderson - Massey |  |  | 2052 | 1609.0904 | 1610.8149 | 1612.5412 | 1614.2694 | 1615.9994 | 1623.0785 | 1630.1886 | 1637.3299 | 1644.5024 | 1651.7063 | 1658.9237 | 1666.1727 | 1673.4533 | 1680.7657 | 1688.1101 | 1694.7356 | 1701.3871 | 1708.0647 | 1714.7686 | 1721.4987 | 1727.4139 | 1733.3495 | 1739.3054 | 1745.2818 | 1751.2787 | 1759.2284 | 1767.2143 | 1775.2363 | 1783.2948 | 1791.3899 | 1798.8494 | 1806.34 | 1813.8618 | 1821.4149 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 | 1828.9994 |  | 4700 | 4704.992 | 4709.9894 | 4714.992 | 4720 | 4730.6928 | 4741.4098 | 4752.1511 | 4762.9167 | 4773.7067 | 4784.3693 | 4795.0556 | 4805.7659 | 4816.5 | 4827.2582 | 4832.7792 | 4838.3065 | 4843.8402 | 4849.3802 | 4854.9265 | 4857.9536 | 4860.9826 | 4864.0135 | 4867.0462 | 4870.0809 | 4878.2297 | 4886.3922 | 4894.5683 | 4902.7581 | 4910.9617 | 4931.2073 | 4951.5364 | 4971.9493 | 4992.4463 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | 5013.0279 | [6 empty] | 896 | 904 | 912 | 920 | 926.2 | 937 | 948 | 959 | 970 | 981 | 992.3 | 1002 | 1011 | 1020 | 1029 | 1038 | 1047 | 1056 | 1065 | 1074 | 1083 | 1092 | 1101 | 1110 | 1119 | 1128 | 1137 | 1146 | 1155 | 1164 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | 1181.3 | [6 empty] | 2.9209 | 2.9209 | 2.9208 | 2.9208 | 2.9208 | 2.9146 | 2.9085 | 2.9024 | 2.8963 | 2.8902 | 2.884 | 2.8779 | 2.8718 | 2.8657 | 2.8596 | 2.8516 | 2.8437 | 2.8359 | 2.828 | 2.8202 | 2.8123 | 2.8044 | 2.7965 | 2.7887 | 2.7809 | 2.7729 | 2.765 | 2.7571 | 2.7493 | 2.7414 | 2.7413 | 2.7412 | 2.7411 | 2.741 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409 | 2.7409
209 | Henderson - Massey |  |  | 2052 | 1516.1947 | 1533.7373 | 1551.4829 | 1569.4338 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 | 1587.5924 |  | 4220 | 4266.7184 | 4313.9541 | 4361.7127 | 4410 | 4428.5908 | 4447.26 | 4466.0079 | 4484.8348 | 4503.7411 | 4522.3352 | 4541.006 | 4559.7539 | 4578.5792 | 4597.4823 | 4607.8006 | 4618.1421 | 4628.5068 | 4638.8948 | 4649.306 | 4659.6251 | 4669.967 | 4680.3319 | 4690.7198 | 4701.1307 | 4711.4494 | 4721.7908 | 4732.1548 | 4742.5416 | 4752.9512 | 4752.9512 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | 4752.9513 | [6 empty] | 576 | 580 | 584 | 588 | 592.1 | 600 | 608 | 616 | 624 | 632 | 641.6 | 648 | 655 | 662 | 669 | 676 | 683 | 690 | 697 | 704 | 711 | 718 | 725 | 732 | 739 | 746 | 753 | 760 | 767 | 774 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | 778.2 | [6 empty] | 2.7833 | 2.7819 | 2.7805 | 2.7792 | 2.7778 | 2.7895 | 2.8013 | 2.8131 | 2.8249 | 2.8368 | 2.8485 | 2.8603 | 2.8721 | 2.884 | 2.8959 | 2.9024 | 2.9089 | 2.9154 | 2.922 | 2.9285 | 2.935 | 2.9415 | 2.9481 | 2.9546 | 2.9612 | 2.9677 | 2.9742 | 2.9807 | 2.9873 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938 | 2.9938
210 | Henderson - Massey |  |  | 2052 | 577.1178 | 574.7181 | 572.3284 | 569.9486 | 567.5787 | 581.1925 | 595.1329 | 609.4077 | 624.0248 | 638.9925 | 652.9324 | 667.1764 | 681.7311 | 696.6033 | 711.7999 | 724.6807 | 737.7946 | 751.1458 | 764.7386 | 778.5773 | 790.1407 | 801.8758 | 813.7852 | 825.8715 | 838.1372 | 853.6005 | 869.3491 | 885.3882 | 901.7232 | 918.3596 | 932.9335 | 947.7386 | 962.7787 | 978.0575 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 | 993.5787 |  | 1210 | 1204.9687 | 1199.9583 | 1194.9688 | 1190 | 1240.3871 | 1292.9077 | 1347.6522 | 1404.7146 | 1464.1932 | 1521.9461 | 1581.9769 | 1644.3755 | 1709.2354 | 1776.6536 | 1831.5101 | 1888.0603 | 1946.3566 | 2006.4529 | 2068.4047 | 2124.894 | 2182.9261 | 2242.543 | 2303.7881 | 2366.7058 | 2437.9086 | 2511.2536 | 2586.8052 | 2664.6298 | 2744.7957 | 2785.4206 | 2826.6467 | 2868.483 | 2910.9386 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | 2954.0225 | [6 empty] | 2128 | 2156 | 2184 | 2212 | 2238.9 | 2268 | 2297 | 2326 | 2355 | 2384 | 2411.6 | 2441 | 2470 | 2499 | 2528 | 2557 | 2586 | 2615 | 2644 | 2673 | 2702 | 2731 | 2760 | 2789 | 2818 | 2847 | 2876 | 2905 | 2934 | 2963 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | 2997.3 | [6 empty] | 2.0966 | 2.0966 | 2.0966 | 2.0966 | 2.0966 | 2.1342 | 2.1725 | 2.2114 | 2.2511 | 2.2914 | 2.3309 | 2.3712 | 2.4121 | 2.4537 | 2.496 | 2.5273 | 2.5591 | 2.5912 | 2.6237 | 2.6566 | 2.6893 | 2.7223 | 2.7557 | 2.7895 | 2.8238 | 2.856 | 2.8887 | 2.9217 | 2.955 | 2.9888 | 2.9857 | 2.9825 | 2.9794 | 2.9762 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731 | 2.9731
211 | Henderson - Massey |  |  | 2052 | 292.6467 | 302.7675 | 313.2382 | 324.071 | 335.2785 | 358.3994 | 383.1146 | 409.5342 | 437.7758 | 467.9649 | 492.344 | 517.9933 | 544.9788 | 573.3701 | 603.2405 | 626.1925 | 650.0177 | 674.7495 | 700.4222 | 727.0717 | 747.9054 | 769.3361 | 791.3808 | 814.0572 | 837.3834 | 865.1181 | 893.7714 | 923.3737 | 953.9564 | 985.5521 | 1011.8554 | 1038.8607 | 1066.5867 | 1095.0528 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 | 1124.2785 |  | 880 | 908.5776 | 938.0832 | 968.5469 | 1000 | 1066.8807 | 1138.2345 | 1214.3604 | 1295.5777 | 1382.2269 | 1453.4195 | 1528.2789 | 1606.994 | 1689.7633 | 1776.7957 | 1842.4054 | 1910.4378 | 1980.9824 | 2054.1318 | 2129.9824 | 2189.4886 | 2250.6573 | 2313.5348 | 2378.169 | 2444.6089 | 2523.826 | 2605.6101 | 2690.0444 | 2777.2148 | 2867.2099 | 2942.3058 | 3019.3686 | 3098.4497 | 3179.602 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | 3262.8799 | [6 empty] | 3076 | 3118 | 3160 | 3202 | 3243.2 | 3287 | 3330 | 3373 | 3416 | 3459 | 3503.8 | 3547 | 3590 | 3633 | 3676 | 3719 | 3762 | 3805 | 3848 | 3891 | 3934 | 3977 | 4020 | 4063 | 4106 | 4149 | 4192 | 4235 | 4278 | 4321 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | 4365.9 | [6 empty] | 3.007 | 3.0009 | 2.9948 | 2.9887 | 2.9826 | 2.9768 | 2.971 | 2.9652 | 2.9595 | 2.9537 | 2.952 | 2.9504 | 2.9487 | 2.9471 | 2.9454 | 2.9422 | 2.9391 | 2.9359 | 2.9327 | 2.9295 | 2.9275 | 2.9255 | 2.9234 | 2.9214 | 2.9193 | 2.9173 | 2.9153 | 2.9133 | 2.9113 | 2.9092 | 2.9078 | 2.9064 | 2.905 | 2.9036 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022 | 2.9022
212 | Henderson - Massey |  |  | 2052 | 1608.6837 | 1619.7377 | 1630.8677 | 1642.0742 | 1653.3576 | 1656.3699 | 1659.3876 | 1662.4108 | 1665.4395 | 1668.4738 | 1671.5447 | 1674.6212 | 1677.7035 | 1680.7914 | 1683.8849 | 1686.697 | 1689.5138 | 1692.3352 | 1695.1614 | 1697.9923 | 1700.4983 | 1703.008 | 1705.5215 | 1708.0386 | 1710.5594 | 1713.9315 | 1717.3102 | 1720.6956 | 1724.0876 | 1727.4864 | 1730.649 | 1733.8175 | 1736.9917 | 1740.1717 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 | 1743.3576 |  | 5130 | 5164.6474 | 5199.5288 | 5234.6458 | 5270 | 5286.3124 | 5302.6752 | 5319.0888 | 5335.5531 | 5352.0684 | 5368.6915 | 5385.3663 | 5402.0929 | 5418.8715 | 5435.7021 | 5444.6321 | 5453.5767 | 5462.536 | 5471.51 | 5480.4988 | 5488.4568 | 5496.4264 | 5504.4076 | 5512.4003 | 5520.4047 | 5531.113 | 5541.8422 | 5552.5921 | 5563.363 | 5574.1547 | 5584.1979 | 5594.2593 | 5604.3388 | 5614.4365 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | 5624.5524 | [6 empty] | 393 | 396 | 399 | 402 | 403.3 | 408 | 413 | 418 | 423 | 428 | 432.3 | 436 | 440 | 444 | 448 | 452 | 456 | 460 | 464 | 468 | 472 | 476 | 480 | 484 | 488 | 492 | 496 | 500 | 504 | 508 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | 506.1 | [6 empty] | 3.1889 | 3.1886 | 3.1882 | 3.1878 | 3.1875 | 3.1915 | 3.1956 | 3.1996 | 3.2037 | 3.2078 | 3.2118 | 3.2159 | 3.2199 | 3.224 | 3.2281 | 3.228 | 3.2279 | 3.2278 | 3.2277 | 3.2276 | 3.2276 | 3.2275 | 3.2274 | 3.2273 | 3.2273 | 3.2271 | 3.227 | 3.2269 | 3.2268 | 3.2267 | 3.2266 | 3.2266 | 3.2265 | 3.2264 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263 | 3.2263
213 | Henderson - Massey |  |  | 2052 | 354.1941 | 363.1131 | 372.2566 | 381.6305 | 391.2403 | 404.4196 | 418.0428 | 432.1249 | 446.6814 | 461.7282 | 475.2815 | 489.2326 | 503.5933 | 518.3754 | 533.5915 | 546.1437 | 558.9911 | 572.1407 | 585.5997 | 599.3752 | 610.6624 | 622.162 | 633.8783 | 645.8152 | 657.9768 | 673.005 | 688.3764 | 704.0989 | 720.1805 | 736.6294 | 750.7961 | 765.2353 | 779.9521 | 794.952 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 | 810.2403 |  | 990 | 1014.1052 | 1038.7974 | 1064.0908 | 1090 | 1126.6925 | 1164.6202 | 1203.8247 | 1244.3488 | 1286.2372 | 1324.5463 | 1363.9965 | 1404.6216 | 1446.4567 | 1489.5379 | 1523.7201 | 1558.6867 | 1594.4557 | 1631.0456 | 1668.4752 | 1699.241 | 1730.5742 | 1762.4852 | 1794.9845 | 1828.0832 | 1869.0867 | 1911.01 | 1953.8735 | 1997.6985 | 2042.5065 | 2081.1791 | 2120.584 | 2160.7349 | 2201.6461 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | 2243.3318 | [6 empty] | 3516 | 3530 | 3544 | 3558 | 3571.8 | 3618 | 3665 | 3712 | 3759 | 3806 | 3851.9 | 3875 | 3898 | 3921 | 3944 | 3967 | 3990 | 4013 | 4036 | 4059 | 4082 | 4105 | 4128 | 4151 | 4174 | 4197 | 4220 | 4243 | 4266 | 4289 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | 4319.3 | [6 empty] | 2.7951 | 2.7928 | 2.7905 | 2.7883 | 2.786 | 2.7859 | 2.7859 | 2.7858 | 2.7858 | 2.7857 | 2.7869 | 2.788 | 2.7892 | 2.7904 | 2.7915 | 2.79 | 2.7884 | 2.7868 | 2.7853 | 2.7837 | 2.7826 | 2.7815 | 2.7805 | 2.7794 | 2.7783 | 2.7772 | 2.7761 | 2.775 | 2.7739 | 2.7728 | 2.772 | 2.7712 | 2.7703 | 2.7695 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687 | 2.7687
214 | Waitakere Ranges |  |  | 2052 | 1271.7457 | 1272.5488 | 1273.3523 | 1274.1564 | 1274.961 | 1277.3871 | 1279.8179 | 1282.2533 | 1284.6933 | 1287.1379 | 1289.6113 | 1292.0894 | 1294.5723 | 1297.06 | 1299.5524 | 1301.8333 | 1304.1181 | 1306.4069 | 1308.6998 | 1310.9967 | 1313.0383 | 1315.0831 | 1317.131 | 1319.1822 | 1321.2366 | 1323.9836 | 1326.7363 | 1329.4948 | 1332.2589 | 1335.0289 | 1337.6053 | 1340.1868 | 1342.7732 | 1345.3646 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 | 1347.961 |  | 4010 | 4012.4977 | 4014.9969 | 4017.4977 | 4020 | 4032.8054 | 4045.6516 | 4058.5387 | 4071.4669 | 4084.4363 | 4097.4901 | 4110.5857 | 4123.7231 | 4136.9025 | 4150.124 | 4157.3122 | 4164.5127 | 4171.7258 | 4178.9513 | 4186.1894 | 4192.6236 | 4199.0677 | 4205.5217 | 4211.9856 | 4218.4594 | 4227.1169 | 4235.7921 | 4244.485 | 4253.1959 | 4261.9246 | 4270.0445 | 4278.1798 | 4286.3306 | 4294.497 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | 4302.6789 | [6 empty] | 431 | 434 | 437 | 440 | 442.5 | 450 | 457 | 464 | 471 | 478 | 484.8 | 490 | 495 | 500 | 505 | 510 | 515 | 520 | 525 | 530 | 535 | 540 | 545 | 550 | 555 | 560 | 565 | 570 | 575 | 580 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | 581.1 | [6 empty] | 3.1531 | 3.1531 | 3.1531 | 3.1531 | 3.153 | 3.1571 | 3.1611 | 3.1652 | 3.1692 | 3.1733 | 3.1773 | 3.1813 | 3.1854 | 3.1894 | 3.1935 | 3.1934 | 3.1934 | 3.1933 | 3.1932 | 3.1931 | 3.1931 | 3.193 | 3.1929 | 3.1929 | 3.1928 | 3.1927 | 3.1926 | 3.1926 | 3.1925 | 3.1924 | 3.1923 | 3.1922 | 3.1921 | 3.1921 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192 | 3.192
215 | Henderson - Massey |  |  | 2052 | 1158.2358 | 1171.6933 | 1185.3071 | 1199.0791 | 1213.0111 | 1221.7034 | 1230.4579 | 1239.2753 | 1248.1558 | 1257.0999 | 1265.9638 | 1274.8903 | 1283.8797 | 1292.9325 | 1302.0491 | 1310.1919 | 1318.3856 | 1326.6306 | 1334.9271 | 1343.2755 | 1350.5504 | 1357.8647 | 1365.2186 | 1372.6123 | 1380.046 | 1389.8122 | 1399.6475 | 1409.5524 | 1419.5274 | 1429.573 | 1438.7422 | 1447.9703 | 1457.2575 | 1466.6043 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 | 1476.0111 |  | 3390 | 3429.3109 | 3469.0777 | 3509.3056 | 3550 | 3573.7719 | 3597.703 | 3621.7943 | 3646.0469 | 3670.4619 | 3694.6179 | 3718.9328 | 3743.4077 | 3768.0437 | 3792.8419 | 3811.1069 | 3829.4599 | 3847.9012 | 3866.4314 | 3885.0508 | 3900.4754 | 3915.9613 | 3931.5087 | 3947.1178 | 3962.7888 | 3985.0426 | 4007.4214 | 4029.9258 | 4052.5566 | 4075.3145 | 4101.4106 | 4127.6739 | 4154.1053 | 4180.7059 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | 4207.4769 | [6 empty] | 313 | 316 | 319 | 322 | 324.3 | 328 | 332 | 336 | 340 | 344 | 348.7 | 352 | 355 | 358 | 361 | 364 | 367 | 370 | 373 | 376 | 379 | 382 | 385 | 388 | 391 | 394 | 397 | 400 | 403 | 406 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | 412.8 | [6 empty] | 2.9269 | 2.9268 | 2.9267 | 2.9267 | 2.9266 | 2.9252 | 2.9239 | 2.9225 | 2.9211 | 2.9198 | 2.9184 | 2.9171 | 2.9157 | 2.9143 | 2.913 | 2.9088 | 2.9047 | 2.9005 | 2.8964 | 2.8922 | 2.8881 | 2.8839 | 2.8798 | 2.8756 | 2.8715 | 2.8673 | 2.8632 | 2.859 | 2.8549 | 2.8507 | 2.8507 | 2.8507 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506 | 2.8506
216 | Henderson - Massey |  |  | 2052 | 1507.1626 | 1519.9616 | 1532.8694 | 1545.8867 | 1559.0146 | 1568.1603 | 1577.3597 | 1586.613 | 1595.9206 | 1605.2828 | 1614.608 | 1623.9874 | 1633.4213 | 1642.91 | 1652.4538 | 1661.0174 | 1669.6254 | 1678.278 | 1686.9755 | 1695.718 | 1703.3663 | 1711.0491 | 1718.7666 | 1726.5189 | 1734.3061 | 1744.5787 | 1754.9121 | 1765.3068 | 1775.763 | 1786.2812 | 1795.9232 | 1805.6173 | 1815.3637 | 1825.1627 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 | 1835.0146 |  | 4400 | 4437.0299 | 4474.3715 | 4512.0273 | 4550 | 4586.3983 | 4623.0879 | 4660.0709 | 4697.3498 | 4734.9269 | 4772.4644 | 4810.2995 | 4848.4345 | 4886.8719 | 4925.614 | 4954.2638 | 4983.0804 | 5012.0645 | 5041.2172 | 5070.5395 | 5096.6773 | 5122.9498 | 5149.3578 | 5175.9019 | 5202.5829 | 5236.6761 | 5270.9928 | 5305.5344 | 5340.3023 | 5375.2981 | 5403.9917 | 5432.8384 | 5461.8391 | 5490.9947 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | 5520.3059 | [6 empty] | 537 | 540 | 543 | 546 | 549 | 557 | 565 | 573 | 581 | 589 | 595.5 | 601 | 607 | 613 | 619 | 625 | 631 | 637 | 643 | 649 | 655 | 661 | 667 | 673 | 679 | 685 | 691 | 697 | 703 | 709 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | 707.3 | [6 empty] | 2.9194 | 2.9192 | 2.919 | 2.9187 | 2.9185 | 2.9247 | 2.9309 | 2.9371 | 2.9433 | 2.9496 | 2.9558 | 2.962 | 2.9683 | 2.9745 | 2.9808 | 2.9827 | 2.9845 | 2.9864 | 2.9883 | 2.9902 | 2.9921 | 2.994 | 2.996 | 2.9979 | 2.9998 | 3.0017 | 3.0036 | 3.0054 | 3.0073 | 3.0092 | 3.009 | 3.0089 | 3.0087 | 3.0085 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083 | 3.0083
217 | Henderson - Massey |  |  | 2052 | 2126.8943 | 2122.6413 | 2118.3969 | 2114.1609 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 | 2109.9334 |  | 6270 | 6257.4624 | 6244.95 | 6232.4625 | 6220 | 6205.0334 | 6190.1027 | 6175.208 | 6160.3492 | 6145.5261 | 6130.5586 | 6115.6275 | 6100.7328 | 6085.8744 | 6071.0521 | 6052.7898 | 6034.5823 | 6016.4296 | 5998.3315 | 5980.2879 | 5962.0241 | 5943.8162 | 5925.6639 | 5907.5669 | 5889.5253 | 5871.2588 | 5853.049 | 5834.8956 | 5816.7986 | 5798.7576 | 5798.7577 | 5798.7577 | 5798.7577 | 5798.7577 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | 5798.7578 | [6 empty] | 1182 | 1192 | 1202 | 1212 | 1222.6 | 1239 | 1255 | 1271 | 1287 | 1303 | 1320.4 | 1332 | 1344 | 1356 | 1368 | 1380 | 1392 | 1404 | 1416 | 1428 | 1440 | 1452 | 1464 | 1476 | 1488 | 1500 | 1512 | 1524 | 1536 | 1548 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | 1560.5 | [6 empty] | 2.948 | 2.948 | 2.948 | 2.948 | 2.948 | 2.9409 | 2.9338 | 2.9267 | 2.9197 | 2.9127 | 2.9056 | 2.8985 | 2.8914 | 2.8844 | 2.8774 | 2.8687 | 2.8601 | 2.8515 | 2.8429 | 2.8343 | 2.8257 | 2.8171 | 2.8085 | 2.7999 | 2.7913 | 2.7827 | 2.774 | 2.7654 | 2.7569 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483 | 2.7483
218 | Henderson - Massey |  |  | 2052 | 433.7618 | 435.2597 | 436.7627 | 438.2709 | 439.7843 | 443.7434 | 447.738 | 451.7687 | 455.8356 | 459.9392 | 463.9773 | 468.0509 | 472.1602 | 476.3056 | 480.4874 | 484.1918 | 487.9247 | 491.6865 | 495.4772 | 499.2972 | 502.6043 | 505.9334 | 509.2845 | 512.6578 | 516.0534 | 520.4106 | 524.8046 | 529.2357 | 533.7042 | 538.2105 | 542.2637 | 546.3475 | 550.462 | 554.6076 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 | 558.7843 |  | 1480 | 1484.9749 | 1489.9664 | 1494.9748 | 1500 | 1509.7224 | 1519.5078 | 1529.3566 | 1539.2692 | 1549.2461 | 1558.919 | 1568.6522 | 1578.4462 | 1588.3014 | 1598.2181 | 1605.5611 | 1612.9379 | 1620.3486 | 1627.7933 | 1635.2723 | 1640.989 | 1646.7257 | 1652.4825 | 1658.2594 | 1664.0565 | 1672.7487 | 1681.4863 | 1690.2696 | 1699.0987 | 1707.974 | 1720.5434 | 1733.2053 | 1745.9604 | 1758.8094 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | 1771.753 | [6 empty] | 1266 | 1277 | 1288 | 1299 | 1310.1 | 1333 | 1356 | 1379 | 1402 | 1425 | 1447.9 | 1463 | 1478 | 1493 | 1508 | 1523 | 1538 | 1553 | 1568 | 1583 | 1598 | 1613 | 1628 | 1643 | 1658 | 1673 | 1688 | 1703 | 1718 | 1733 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | 1742.3 | [6 empty] | 3.412 | 3.4117 | 3.4114 | 3.4111 | 3.4108 | 3.4022 | 3.3937 | 3.3853 | 3.3768 | 3.3684 | 3.3599 | 3.3515 | 3.343 | 3.3346 | 3.3262 | 3.316 | 3.3057 | 3.2955 | 3.2853 | 3.2751 | 3.265 | 3.2548 | 3.2447 | 3.2346 | 3.2246 | 3.2143 | 3.204 | 3.1938 | 3.1836 | 3.1734 | 3.1729 | 3.1723 | 3.1718 | 3.1713 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707 | 3.1707
219 | Whau |  |  | 2052 | 1983.1768 | 1989.7955 | 1996.4363 | 2003.0992 | 2009.7844 | 2010.6235 | 2011.4629 | 2012.3027 | 2013.1428 | 2013.9833 | 2014.8388 | 2015.6946 | 2016.5507 | 2017.4073 | 2018.2642 | 2019.0792 | 2019.8946 | 2020.7104 | 2021.5264 | 2022.3428 | 2023.087 | 2023.8314 | 2024.5761 | 2025.3211 | 2026.0664 | 2026.9862 | 2027.9064 | 2028.8271 | 2029.7481 | 2030.6696 | 2031.4919 | 2032.3145 | 2033.1375 | 2033.9608 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 | 2034.7844 |  | 6000 | 6019.9008 | 6039.8675 | 6059.9006 | 6080 | 6090.3885 | 6100.7948 | 6111.2189 | 6121.6608 | 6132.1205 | 6142.5917 | 6153.0807 | 6163.5876 | 6174.1125 | 6184.6553 | 6187.0297 | 6189.4051 | 6191.7813 | 6194.1584 | 6196.5365 | 6198.6945 | 6200.8533 | 6203.0129 | 6205.1732 | 6207.3343 | 6210.0268 | 6212.7205 | 6215.4154 | 6218.1114 | 6220.8086 | 6223.3125 | 6225.8175 | 6228.3235 | 6230.8304 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | 6233.3384 | [6 empty] | 558 | 560 | 562 | 564 | 566.5 | 573 | 580 | 587 | 594 | 601 | 607.3 | 612 | 617 | 622 | 627 | 632 | 637 | 642 | 647 | 652 | 657 | 662 | 667 | 672 | 677 | 682 | 687 | 692 | 697 | 702 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | 704 | [6 empty] | 3.0254 | 3.0254 | 3.0253 | 3.0253 | 3.0252 | 3.0291 | 3.033 | 3.0369 | 3.0408 | 3.0448 | 3.0487 | 3.0526 | 3.0565 | 3.0604 | 3.0643 | 3.0643 | 3.0642 | 3.0642 | 3.0641 | 3.064 | 3.064 | 3.0639 | 3.0639 | 3.0638 | 3.0637 | 3.0637 | 3.0636 | 3.0636 | 3.0635 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634 | 3.0634
220 | Whau |  |  | 2052 | 1665.4497 | 1663.174 | 1660.9014 | 1658.6318 | 1656.3654 | 1662.5337 | 1668.725 | 1674.9394 | 1681.1768 | 1687.4375 | 1693.7262 | 1700.0383 | 1706.3739 | 1712.7331 | 1719.116 | 1724.8454 | 1730.5939 | 1736.3616 | 1742.1484 | 1747.9546 | 1753.0448 | 1758.1498 | 1763.2697 | 1768.4046 | 1773.5543 | 1780.3975 | 1787.267 | 1794.1631 | 1801.0858 | 1808.0351 | 1814.4554 | 1820.8985 | 1827.3645 | 1833.8534 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 | 1840.3654 |  | 5500 | 5492.4846 | 5484.9795 | 5477.4846 | 5470 | 5494.7386 | 5519.5891 | 5544.5519 | 5569.6277 | 5594.8168 | 5620.1231 | 5645.5439 | 5671.0796 | 5696.7309 | 5722.4982 | 5739.2524 | 5756.0557 | 5772.9082 | 5789.8101 | 5806.7614 | 5821.3555 | 5835.9863 | 5850.6538 | 5865.3582 | 5880.0996 | 5900.3608 | 5920.6919 | 5941.093 | 5961.5644 | 5982.1064 | 6003.0521 | 6024.0712 | 6045.1639 | 6066.3305 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | 6087.5711 | [6 empty] | 1447 | 1459 | 1471 | 1483 | 1495.4 | 1518 | 1541 | 1564 | 1587 | 1610 | 1630.8 | 1647 | 1663 | 1679 | 1695 | 1711 | 1727 | 1743 | 1759 | 1775 | 1791 | 1807 | 1823 | 1839 | 1855 | 1871 | 1887 | 1903 | 1919 | 1935 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | 1954.7 | [6 empty] | 3.3024 | 3.3024 | 3.3024 | 3.3024 | 3.3024 | 3.305 | 3.3077 | 3.3103 | 3.3129 | 3.3156 | 3.3182 | 3.3208 | 3.3235 | 3.3261 | 3.3287 | 3.3274 | 3.3261 | 3.3247 | 3.3234 | 3.322 | 3.3207 | 3.3194 | 3.3181 | 3.3168 | 3.3154 | 3.3141 | 3.3127 | 3.3113 | 3.31 | 3.3086 | 3.3085 | 3.3083 | 3.3081 | 3.308 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078 | 3.3078
221 | Waitakere Ranges |  |  | 2052 | 987.4103 | 1005.6315 | 1024.1889 | 1043.0887 | 1062.3373 | 1065.6754 | 1069.024 | 1072.3831 | 1075.7528 | 1079.133 | 1082.5362 | 1085.9501 | 1089.3748 | 1092.8102 | 1096.2565 | 1099.3737 | 1102.4998 | 1105.6347 | 1108.7786 | 1111.9314 | 1114.7102 | 1117.4959 | 1120.2886 | 1123.0882 | 1125.8949 | 1129.6315 | 1133.3806 | 1137.1421 | 1140.9161 | 1144.7026 | 1148.208 | 1151.7241 | 1155.251 | 1158.7888 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 | 1162.3373 |  | 2670 | 2718.6539 | 2768.1944 | 2818.6376 | 2870 | 2893.23 | 2916.648 | 2940.2555 | 2964.0541 | 2988.0454 | 3011.9099 | 3035.965 | 3060.2122 | 3084.6531 | 3109.2891 | 3126.6792 | 3144.1666 | 3161.7517 | 3179.4352 | 3197.2176 | 3213.8893 | 3230.648 | 3247.494 | 3264.4279 | 3281.45 | 3301.1127 | 3320.8933 | 3340.7923 | 3360.8106 | 3380.9489 | 3391.1978 | 3401.4778 | 3411.7889 | 3422.1313 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | 3432.505 | [6 empty] | 669 | 677 | 685 | 693 | 701.8 | 712 | 723 | 734 | 745 | 756 | 765.8 | 776 | 786 | 796 | 806 | 816 | 826 | 836 | 846 | 856 | 866 | 876 | 886 | 896 | 906 | 916 | 926 | 936 | 946 | 956 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | 961.6 | [6 empty] | 2.704 | 2.7034 | 2.7028 | 2.7022 | 2.7016 | 2.7149 | 2.7283 | 2.7418 | 2.7553 | 2.7689 | 2.7823 | 2.7957 | 2.8091 | 2.8227 | 2.8363 | 2.8441 | 2.8519 | 2.8597 | 2.8675 | 2.8754 | 2.8832 | 2.891 | 2.8988 | 2.9067 | 2.9145 | 2.9223 | 2.9301 | 2.9379 | 2.9457 | 2.9536 | 2.9535 | 2.9534 | 2.9533 | 2.9532 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531 | 2.9531
222 | Whau |  |  | 2052 | 1383.9894 | 1386.9058 | 1389.8284 | 1392.7571 | 1395.692 | 1401.6042 | 1407.5414 | 1413.5038 | 1419.4915 | 1425.5045 | 1431.5321 | 1437.5852 | 1443.664 | 1449.7684 | 1455.8987 | 1461.4054 | 1466.933 | 1472.4815 | 1478.051 | 1483.6416 | 1488.5428 | 1493.4603 | 1498.394 | 1503.344 | 1508.3104 | 1514.898 | 1521.5144 | 1528.1596 | 1534.8339 | 1541.5374 | 1547.7185 | 1553.9245 | 1560.1553 | 1566.4111 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 | 1572.692 |  | 3590 | 3597.4766 | 3604.9688 | 3612.4766 | 3620 | 3641.3101 | 3662.7456 | 3684.3072 | 3705.9959 | 3727.8122 | 3749.6824 | 3771.681 | 3793.8087 | 3816.0661 | 3838.4542 | 3853.971 | 3869.5505 | 3885.193 | 3900.8987 | 3916.668 | 3930.6465 | 3944.6749 | 3958.7534 | 3972.8821 | 3987.0613 | 4005.4913 | 4024.0065 | 4042.6073 | 4061.2941 | 4080.0673 | 4096.2598 | 4112.5165 | 4128.8378 | 4145.2239 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | 4161.6749 | [6 empty] | 447 | 449 | 451 | 453 | 456.3 | 463 | 470 | 477 | 484 | 491 | 497.7 | 503 | 508 | 513 | 518 | 523 | 528 | 533 | 538 | 543 | 548 | 553 | 558 | 563 | 568 | 573 | 578 | 583 | 588 | 593 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | 596 | [6 empty] | 2.594 | 2.5939 | 2.5938 | 2.5938 | 2.5937 | 2.598 | 2.6022 | 2.6065 | 2.6108 | 2.6151 | 2.6193 | 2.6236 | 2.6279 | 2.6322 | 2.6365 | 2.6372 | 2.6379 | 2.6385 | 2.6392 | 2.6399 | 2.6406 | 2.6413 | 2.642 | 2.6427 | 2.6434 | 2.6441 | 2.6447 | 2.6454 | 2.6461 | 2.6468 | 2.6466 | 2.6465 | 2.6464 | 2.6463 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462 | 2.6462
223 | Waitakere Ranges |  |  | 2052 | 874.554 | 876.4963 | 878.443 | 880.3939 | 882.3492 | 885.683 | 889.0295 | 892.3886 | 895.7604 | 899.1449 | 902.5438 | 905.9556 | 909.3802 | 912.8178 | 916.2684 | 919.3822 | 922.5065 | 925.6414 | 928.787 | 931.9433 | 934.7194 | 937.5038 | 940.2964 | 943.0974 | 945.9068 | 949.6387 | 953.3854 | 957.1469 | 960.9233 | 964.7145 | 968.2159 | 971.7301 | 975.2569 | 978.7966 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 | 982.3492 |  | 2310 | 2314.9838 | 2319.9784 | 2324.9838 | 2330 | 2340.2689 | 2350.5832 | 2360.9428 | 2371.3481 | 2381.7993 | 2392.3007 | 2402.8483 | 2413.4425 | 2424.0834 | 2434.7712 | 2441.733 | 2448.7146 | 2455.7163 | 2462.7379 | 2469.7797 | 2475.8338 | 2481.9028 | 2487.9866 | 2494.0854 | 2500.1991 | 2508.6795 | 2517.1887 | 2525.7268 | 2534.2938 | 2542.8899 | 2551.8809 | 2560.9036 | 2569.9583 | 2579.0449 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | 2588.1637 | [6 empty] | 1141 | 1155 | 1169 | 1183 | 1196.2 | 1212 | 1228 | 1244 | 1260 | 1276 | 1289.7 | 1304 | 1318 | 1332 | 1346 | 1360 | 1374 | 1388 | 1402 | 1416 | 1430 | 1444 | 1458 | 1472 | 1486 | 1500 | 1514 | 1528 | 1542 | 1556 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | 1579.3 | [6 empty] | 2.6413 | 2.6412 | 2.641 | 2.6408 | 2.6407 | 2.6423 | 2.644 | 2.6456 | 2.6473 | 2.649 | 2.6506 | 2.6523 | 2.6539 | 2.6556 | 2.6573 | 2.6558 | 2.6544 | 2.653 | 2.6516 | 2.6501 | 2.6487 | 2.6474 | 2.646 | 2.6446 | 2.6432 | 2.6417 | 2.6403 | 2.6388 | 2.6374 | 2.6359 | 2.6357 | 2.6354 | 2.6352 | 2.6349 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347 | 2.6347
224 | Waitakere Ranges |  |  | 2052 | 1562.1098 | 1548.8666 | 1535.7358 | 1522.7162 | 1509.807 | 1513.1513 | 1516.503 | 1519.8622 | 1523.2287 | 1526.6028 | 1530.0122 | 1533.4292 | 1536.8539 | 1540.2863 | 1543.7263 | 1546.8486 | 1549.9772 | 1553.1122 | 1556.2534 | 1559.4011 | 1562.1838 | 1564.9716 | 1567.7643 | 1570.5619 | 1573.3646 | 1577.1083 | 1580.8609 | 1584.6224 | 1588.3929 | 1592.1723 | 1595.6837 | 1599.2029 | 1602.7298 | 1606.2645 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 | 1609.807 |  | 4480 | 4442.0197 | 4404.3615 | 4367.0225 | 4330 | 4342.6357 | 4355.3082 | 4368.0177 | 4380.7644 | 4393.5482 | 4406.4388 | 4419.3673 | 4432.3337 | 4445.3382 | 4458.3808 | 4465.2062 | 4472.0421 | 4478.8885 | 4485.7453 | 4492.6126 | 4498.4118 | 4504.2185 | 4510.0326 | 4515.8543 | 4521.6834 | 4530.2126 | 4538.7578 | 4547.3192 | 4555.8967 | 4564.4904 | 4574.5926 | 4584.7171 | 4594.8641 | 4605.0335 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | 4615.2254 | [6 empty] | 425 | 429 | 433 | 437 | 440.5 | 446 | 451 | 456 | 461 | 466 | 472.2 | 477 | 481 | 485 | 489 | 493 | 497 | 501 | 505 | 509 | 513 | 517 | 521 | 525 | 529 | 533 | 537 | 541 | 545 | 549 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | 560.9 | [6 empty] | 2.8679 | 2.8679 | 2.8679 | 2.8679 | 2.8679 | 2.8699 | 2.8719 | 2.874 | 2.876 | 2.878 | 2.88 | 2.882 | 2.884 | 2.886 | 2.8881 | 2.8866 | 2.8852 | 2.8838 | 2.8824 | 2.881 | 2.8796 | 2.8781 | 2.8767 | 2.8753 | 2.8739 | 2.8725 | 2.8711 | 2.8697 | 2.8682 | 2.8668 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669 | 2.8669
225 | Waitakere Ranges |  |  | 2052 | 1332.7974 | 1342.163 | 1351.5944 | 1361.0921 | 1370.6565 | 1375.9068 | 1381.1772 | 1386.4678 | 1391.7786 | 1397.1098 | 1402.4626 | 1407.8358 | 1413.2296 | 1418.6441 | 1424.0793 | 1429.0303 | 1433.9985 | 1438.984 | 1443.9869 | 1449.0071 | 1453.4481 | 1457.9027 | 1462.371 | 1466.853 | 1471.3487 | 1477.1562 | 1482.9867 | 1488.8402 | 1494.7168 | 1500.6166 | 1505.9861 | 1511.3747 | 1516.7826 | 1522.2099 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 | 1527.6565 |  | 3900 | 3927.2138 | 3954.6176 | 3982.2125 | 4010 | 4023.5414 | 4037.1285 | 4050.7614 | 4064.4404 | 4078.1656 | 4091.9383 | 4105.7574 | 4119.6232 | 4133.5359 | 4147.4955 | 4156.0688 | 4164.6599 | 4173.2687 | 4181.8954 | 4190.5398 | 4197.4502 | 4204.3719 | 4211.3051 | 4218.2497 | 4225.2058 | 4235.8304 | 4246.4817 | 4257.1598 | 4267.8648 | 4278.5967 | 4293.8082 | 4309.0738 | 4324.3937 | 4339.7681 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | 4355.1971 | [6 empty] | 329 | 331 | 333 | 335 | 337.7 | 342 | 346 | 350 | 354 | 358 | 362.7 | 366 | 369 | 372 | 375 | 378 | 381 | 384 | 387 | 390 | 393 | 396 | 399 | 402 | 405 | 408 | 411 | 414 | 417 | 420 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | 428.9 | [6 empty] | 2.9262 | 2.926 | 2.9259 | 2.9257 | 2.9256 | 2.9243 | 2.923 | 2.9216 | 2.9203 | 2.919 | 2.9177 | 2.9164 | 2.915 | 2.9137 | 2.9124 | 2.9083 | 2.9042 | 2.9001 | 2.8961 | 2.892 | 2.8879 | 2.8838 | 2.8798 | 2.8757 | 2.8717 | 2.8676 | 2.8635 | 2.8594 | 2.8553 | 2.8512 | 2.8512 | 2.8511 | 2.851 | 2.851 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509 | 2.8509
226 | Waitakere Ranges |  |  | 2052 | 1006.479 | 998.9204 | 991.4186 | 983.9731 | 976.5836 | 977.1707 | 977.7582 | 978.346 | 978.9343 | 979.5228 | 980.1214 | 980.7204 | 981.3197 | 981.9194 | 982.5194 | 983.0515 | 983.5838 | 984.1164 | 984.6494 | 985.1826 | 985.6476 | 986.1128 | 986.5783 | 987.0439 | 987.5098 | 988.1359 | 988.7625 | 989.3894 | 990.0167 | 990.6444 | 991.2316 | 991.819 | 992.4069 | 992.995 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 | 993.5836 |  | 3030 | 3007.2449 | 2984.6608 | 2962.2462 | 2940 | 2939.8384 | 2939.6769 | 2939.5153 | 2939.3538 | 2939.1922 | 2939.0528 | 2938.9133 | 2938.7739 | 2938.6345 | 2938.4951 | 2935.5301 | 2932.5681 | 2929.6092 | 2926.6532 | 2923.7001 | 2920.517 | 2917.3374 | 2914.1612 | 2910.9885 | 2907.8192 | 2905.0762 | 2902.3359 | 2899.5981 | 2896.863 | 2894.1304 | 2895.8021 | 2897.4747 | 2899.1484 | 2900.823 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | 2902.4985 | [6 empty] | 299 | 300 | 301 | 302 | 304.5 | 309 | 313 | 317 | 321 | 325 | 328.6 | 331 | 334 | 337 | 340 | 343 | 346 | 349 | 352 | 355 | 358 | 361 | 364 | 367 | 370 | 373 | 376 | 379 | 382 | 385 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | 381 | [6 empty] | 3.0105 | 3.0105 | 3.0105 | 3.0105 | 3.0105 | 3.0085 | 3.0065 | 3.0046 | 3.0026 | 3.0006 | 2.9987 | 2.9967 | 2.9947 | 2.9927 | 2.9908 | 2.9861 | 2.9815 | 2.9769 | 2.9723 | 2.9677 | 2.963 | 2.9584 | 2.9538 | 2.9492 | 2.9446 | 2.94 | 2.9353 | 2.9307 | 2.9261 | 2.9215 | 2.9214 | 2.9214 | 2.9213 | 2.9213 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212 | 2.9212
227 | Waitakere Ranges |  |  | 2052 | 1394.8392 | 1385.9487 | 1377.115 | 1368.3375 | 1359.616 | 1363.6232 | 1367.6423 | 1371.6733 | 1375.7161 | 1379.7708 | 1383.8562 | 1387.9537 | 1392.0633 | 1396.1851 | 1400.319 | 1404.061 | 1407.8129 | 1411.5748 | 1415.3468 | 1419.1289 | 1422.4644 | 1425.8077 | 1429.159 | 1432.5181 | 1435.8851 | 1440.3708 | 1444.8705 | 1449.3843 | 1453.9123 | 1458.4543 | 1462.6623 | 1466.8824 | 1471.1147 | 1475.3592 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 | 1479.616 |  | 3960 | 3934.7597 | 3909.6803 | 3884.7607 | 3860 | 3865.0032 | 3870.013 | 3875.0292 | 3880.0519 | 3885.0811 | 3890.1151 | 3895.1555 | 3900.2025 | 3905.256 | 3910.3161 | 3911.3835 | 3912.4513 | 3913.5193 | 3914.5876 | 3915.6562 | 3915.3416 | 3915.027 | 3914.7124 | 3914.3979 | 3914.0834 | 3916.6994 | 3919.3171 | 3921.9365 | 3924.5577 | 3927.1806 | 3938.6142 | 3950.081 | 3961.5812 | 3973.1149 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | 3984.6822 | [6 empty] | 573 | 576 | 579 | 582 | 585.6 | 592 | 599 | 606 | 613 | 620 | 625.4 | 630 | 635 | 640 | 645 | 650 | 655 | 660 | 665 | 670 | 675 | 680 | 685 | 690 | 695 | 700 | 705 | 710 | 715 | 720 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | 721.5 | [6 empty] | 2.839 | 2.839 | 2.839 | 2.839 | 2.839 | 2.8344 | 2.8297 | 2.825 | 2.8204 | 2.8157 | 2.8111 | 2.8064 | 2.8017 | 2.7971 | 2.7924 | 2.7858 | 2.7791 | 2.7724 | 2.7658 | 2.7592 | 2.7525 | 2.7458 | 2.7392 | 2.7325 | 2.7259 | 2.7192 | 2.7126 | 2.7059 | 2.6993 | 2.6927 | 2.6928 | 2.6928 | 2.6929 | 2.693 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931 | 2.6931
228 | Waitakere Ranges |  |  | 2052 | 2291.2587 | 2294.9743 | 2298.6959 | 2302.4235 | 2306.1572 | 2308.8383 | 2311.5225 | 2314.2098 | 2316.9002 | 2319.5938 | 2322.3271 | 2325.0636 | 2327.8034 | 2330.5464 | 2333.2926 | 2335.7952 | 2338.3005 | 2340.8085 | 2343.3191 | 2345.8325 | 2348.0624 | 2350.2944 | 2352.5286 | 2354.7649 | 2357.0033 | 2360.0049 | 2363.0103 | 2366.0195 | 2369.0325 | 2372.0494 | 2374.8643 | 2377.6825 | 2380.5041 | 2383.329 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 | 2386.1572 |  | 6220 | 6229.976 | 6239.9679 | 6249.9759 | 6260 | 6259.7107 | 6259.4214 | 6259.1321 | 6258.8428 | 6258.5535 | 6258.3164 | 6258.0793 | 6257.8421 | 6257.605 | 6257.3679 | 6251.4765 | 6245.5906 | 6239.7102 | 6233.8354 | 6227.9662 | 6221.2256 | 6214.4923 | 6207.7663 | 6201.0476 | 6194.3362 | 6189.477 | 6184.6216 | 6179.77 | 6174.9222 | 6170.0782 | 6177.3192 | 6184.5687 | 6191.8267 | 6199.0932 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | 6206.3683 | [6 empty] | 1306 | 1312 | 1318 | 1324 | 1329.2 | 1343 | 1357 | 1371 | 1385 | 1399 | 1414.5 | 1424 | 1433 | 1442 | 1451 | 1460 | 1469 | 1478 | 1487 | 1496 | 1505 | 1514 | 1523 | 1532 | 1541 | 1550 | 1559 | 1568 | 1577 | 1586 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | 1599.7 | [6 empty] | 2.7147 | 2.7146 | 2.7146 | 2.7145 | 2.7145 | 2.7112 | 2.7079 | 2.7047 | 2.7014 | 2.6981 | 2.6948 | 2.6916 | 2.6883 | 2.685 | 2.6818 | 2.6764 | 2.671 | 2.6656 | 2.6603 | 2.6549 | 2.6495 | 2.6441 | 2.6388 | 2.6334 | 2.6281 | 2.6227 | 2.6173 | 2.6119 | 2.6065 | 2.6012 | 2.6011 | 2.6011 | 2.6011 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601 | 2.601
229 | Waitakere Ranges |  |  | 2052 | 704.7144 | 706.6407 | 708.5722 | 710.509 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 | 712.4511 |  | 1860 | 1864.98 | 1869.9733 | 1874.9799 | 1880 | 1877.4685 | 1874.9403 | 1872.4156 | 1869.8942 | 1867.3763 | 1864.8447 | 1862.3165 | 1859.7918 | 1857.2705 | 1854.7526 | 1850.8307 | 1846.9171 | 1843.0117 | 1839.1147 | 1835.2258 | 1831.3037 | 1827.39 | 1823.4847 | 1819.5877 | 1815.6991 | 1811.7768 | 1807.863 | 1803.9577 | 1800.0608 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | 1796.1723 | [6 empty] | 273 | 274 | 275 | 276 | 278.2 | 281 | 284 | 287 | 290 | 293 | 295.8 | 298 | 300 | 302 | 304 | 306 | 308 | 310 | 312 | 314 | 316 | 318 | 320 | 322 | 324 | 326 | 328 | 330 | 332 | 334 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | 338.2 | [6 empty] | 2.6394 | 2.6392 | 2.6391 | 2.6389 | 2.6388 | 2.6352 | 2.6317 | 2.6281 | 2.6246 | 2.6211 | 2.6175 | 2.614 | 2.6104 | 2.6069 | 2.6033 | 2.5978 | 2.5923 | 2.5869 | 2.5814 | 2.5759 | 2.5704 | 2.5649 | 2.5595 | 2.554 | 2.5485 | 2.543 | 2.5375 | 2.532 | 2.5266 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211 | 2.5211
230 | Waitakere Ranges |  |  | 2052 | 1088.3149 | 1083.9703 | 1079.643 | 1075.3329 | 1071.0401 | 1071.8786 | 1072.7177 | 1073.5575 | 1074.3979 | 1075.239 | 1076.0938 | 1076.9493 | 1077.8055 | 1078.6624 | 1079.5199 | 1080.3344 | 1081.1495 | 1081.9652 | 1082.7816 | 1083.5985 | 1084.3422 | 1085.0864 | 1085.8311 | 1086.5764 | 1087.3221 | 1088.2412 | 1089.1611 | 1090.0817 | 1091.0031 | 1091.9253 | 1092.747 | 1093.5694 | 1094.3923 | 1095.2159 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 | 1096.0401 |  | 3150 | 3137.4249 | 3124.9 | 3112.4251 | 3100 | 3095.3735 | 3090.7539 | 3086.1412 | 3081.5353 | 3076.9364 | 3072.3 | 3067.6707 | 3063.0483 | 3058.4329 | 3053.8244 | 3047.3623 | 3040.9138 | 3034.4789 | 3028.0577 | 3021.65 | 3014.9323 | 3008.2295 | 3001.5416 | 2994.8686 | 2988.2104 | 2981.8948 | 2975.5925 | 2969.3036 | 2963.0279 | 2956.7655 | 2958.9069 | 2961.05 | 2963.1945 | 2965.3406 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | 2967.4883 | [6 empty] | 443 | 447 | 451 | 455 | 457.8 | 463 | 468 | 473 | 478 | 483 | 487.2 | 491 | 495 | 499 | 503 | 507 | 511 | 515 | 519 | 523 | 527 | 531 | 535 | 539 | 543 | 547 | 551 | 555 | 559 | 563 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | [6 empty] | 2.8944 | 2.8944 | 2.8944 | 2.8944 | 2.8944 | 2.8878 | 2.8812 | 2.8747 | 2.8682 | 2.8616 | 2.855 | 2.8485 | 2.8419 | 2.8354 | 2.8289 | 2.8208 | 2.8127 | 2.8046 | 2.7966 | 2.7885 | 2.7804 | 2.7723 | 2.7643 | 2.7562 | 2.7482 | 2.7401 | 2.732 | 2.7239 | 2.7159 | 2.7078 | 2.7078 | 2.7077 | 2.7076 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075 | 2.7075
231 | Waitakere Ranges |  |  | 2052 | 877.8388 | 877.8388 | 877.8388 | 877.8388 | 877.8389 | 878.677 | 879.516 | 880.3558 | 881.1964 | 882.0378 | 882.8923 | 883.7476 | 884.6038 | 885.4608 | 886.3187 | 887.1329 | 887.9479 | 888.7636 | 889.5801 | 890.3973 | 891.1407 | 891.8848 | 892.6296 | 893.3749 | 894.1209 | 895.0396 | 895.9593 | 896.88 | 897.8015 | 898.7241 | 899.5455 | 900.3677 | 901.1907 | 902.0144 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 | 902.8389 |  | 2660 | 2660 | 2660 | 2660 | 2660 | 2656.5608 | 2653.126 | 2649.6957 | 2646.2698 | 2642.8483 | 2639.4004 | 2635.9571 | 2632.5182 | 2629.0838 | 2625.6538 | 2620.521 | 2615.3982 | 2610.2854 | 2605.1825 | 2600.0897 | 2594.6832 | 2589.2879 | 2583.9038 | 2578.5309 | 2573.1692 | 2568.1975 | 2563.2353 | 2558.2827 | 2553.3397 | 2548.4062 | 2550.7142 | 2553.0243 | 2555.3366 | 2557.6509 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | 2559.9673 | [6 empty] | 431 | 434 | 437 | 440 | 442.3 | 447 | 452 | 457 | 462 | 467 | 472.1 | 476 | 479 | 482 | 485 | 488 | 491 | 494 | 497 | 500 | 503 | 506 | 509 | 512 | 515 | 518 | 521 | 524 | 527 | 530 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | 540.8 | [6 empty] | 3.0302 | 3.0302 | 3.0302 | 3.0302 | 3.0302 | 3.0234 | 3.0166 | 3.0098 | 3.003 | 2.9963 | 2.9895 | 2.9827 | 2.9759 | 2.9692 | 2.9624 | 2.9539 | 2.9454 | 2.937 | 2.9286 | 2.9201 | 2.9116 | 2.9032 | 2.8947 | 2.8863 | 2.8779 | 2.8694 | 2.8609 | 2.8524 | 2.844 | 2.8356 | 2.8356 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355 | 2.8355
232 | Waitakere Ranges |  |  | 2052 | 560.8765 | 557.4248 | 553.9943 | 550.5849 | 547.1966 | 548.0338 | 548.8723 | 549.7121 | 550.5531 | 551.3955 | 552.249 | 553.1039 | 553.96 | 554.8175 | 555.6764 | 556.4897 | 557.3042 | 558.12 | 558.9369 | 559.755 | 560.4977 | 561.2415 | 561.9862 | 562.7319 | 563.4786 | 564.3962 | 565.3154 | 566.236 | 567.1581 | 568.0818 | 568.9024 | 569.7241 | 570.5471 | 571.3712 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 | 572.1966 |  | 1640 | 1629.9072 | 1619.8765 | 1609.9076 | 1600 | 1598.8557 | 1597.7123 | 1596.5696 | 1595.4278 | 1594.2868 | 1593.1342 | 1591.9824 | 1590.8314 | 1589.6813 | 1588.532 | 1586.3337 | 1584.1384 | 1581.9462 | 1579.757 | 1577.5709 | 1575.117 | 1572.6669 | 1570.2207 | 1567.7783 | 1565.3397 | 1563.2914 | 1561.2459 | 1559.203 | 1557.1628 | 1555.1253 | 1557.2821 | 1559.4419 | 1561.6047 | 1563.7704 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | 1565.9392 | [6 empty] | 282 | 284 | 286 | 288 | 290 | 293 | 296 | 299 | 302 | 305 | 308.8 | 311 | 314 | 317 | 320 | 323 | 326 | 329 | 332 | 335 | 338 | 341 | 344 | 347 | 350 | 353 | 356 | 359 | 362 | 365 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | 359.2 | [6 empty] | 2.924 | 2.924 | 2.924 | 2.924 | 2.924 | 2.9174 | 2.9109 | 2.9044 | 2.8979 | 2.8914 | 2.8848 | 2.8783 | 2.8717 | 2.8652 | 2.8587 | 2.8506 | 2.8425 | 2.8344 | 2.8264 | 2.8183 | 2.8102 | 2.8021 | 2.7941 | 2.786 | 2.778 | 2.7698 | 2.7617 | 2.7536 | 2.7456 | 2.7375 | 2.7373 | 2.7372 | 2.737 | 2.7369 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367 | 2.7367
233 | Waitakere Ranges |  |  | 2052 | 863.7795 | 857.3295 | 850.9276 | 844.5736 | 838.267 | 838.9378 | 839.609 | 840.2809 | 840.9532 | 841.6261 | 842.31 | 842.9944 | 843.6793 | 844.3648 | 845.0508 | 845.7407 | 846.4311 | 847.122 | 847.8135 | 848.5056 | 849.1562 | 849.8074 | 850.459 | 851.1111 | 851.7638 | 852.5575 | 853.3521 | 854.1473 | 854.9433 | 855.7401 | 856.4443 | 857.1491 | 857.8545 | 858.5604 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 | 859.267 |  | 2370 | 2352.3028 | 2334.7377 | 2317.3037 | 2300 | 2296.4485 | 2292.9025 | 2289.362 | 2285.827 | 2282.2974 | 2278.7383 | 2275.1847 | 2271.6367 | 2268.0943 | 2264.5573 | 2259.645 | 2254.7434 | 2249.8524 | 2244.972 | 2240.1022 | 2235.0291 | 2229.9674 | 2224.9172 | 2219.8784 | 2214.851 | 2210.1028 | 2205.3647 | 2200.6368 | 2195.919 | 2191.2114 | 2193.047 | 2194.8841 | 2196.7227 | 2198.5629 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | 2200.4047 | [6 empty] | 403 | 406 | 409 | 412 | 415.2 | 420 | 425 | 430 | 435 | 440 | 443.2 | 447 | 451 | 455 | 459 | 463 | 467 | 471 | 475 | 479 | 483 | 487 | 491 | 495 | 499 | 503 | 507 | 511 | 515 | 519 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | 516 | [6 empty] | 2.7438 | 2.7438 | 2.7438 | 2.7438 | 2.7438 | 2.7373 | 2.7309 | 2.7245 | 2.7181 | 2.7118 | 2.7053 | 2.6989 | 2.6925 | 2.6862 | 2.6798 | 2.6718 | 2.6638 | 2.6559 | 2.648 | 2.6401 | 2.6321 | 2.6241 | 2.6161 | 2.6082 | 2.6003 | 2.5923 | 2.5844 | 2.5764 | 2.5685 | 2.5606 | 2.5606 | 2.5607 | 2.5607 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608 | 2.5608
234 | Waitakere Ranges |  |  | 2052 | 1139.6873 | 1135.511 | 1131.35 | 1127.2043 | 1123.0737 | 1126.8276 | 1130.594 | 1134.373 | 1138.1646 | 1141.969 | 1145.796 | 1149.6359 | 1153.4886 | 1157.3543 | 1161.2329 | 1164.7543 | 1168.2864 | 1171.8292 | 1175.3827 | 1178.947 | 1182.0952 | 1185.2518 | 1188.4169 | 1191.5904 | 1194.7723 | 1198.924 | 1203.0901 | 1207.2707 | 1211.4659 | 1215.6756 | 1219.5307 | 1223.398 | 1227.2776 | 1231.1695 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 | 1235.0737 |  | 3430 | 3417.4311 | 3404.9082 | 3392.4313 | 3380 | 3383.3427 | 3386.6886 | 3390.0379 | 3393.3905 | 3396.7464 | 3400.0449 | 3403.3466 | 3406.6515 | 3409.9596 | 3413.2709 | 3413.525 | 3413.7791 | 3414.0332 | 3414.2873 | 3414.5415 | 3413.4491 | 3412.357 | 3411.2653 | 3410.1739 | 3409.0829 | 3410.5021 | 3411.922 | 3413.3424 | 3414.7635 | 3416.1851 | 3426.7298 | 3437.307 | 3447.9169 | 3458.5595 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | 3469.235 | [6 empty] | 719 | 726 | 733 | 740 | 746 | 755 | 764 | 773 | 782 | 791 | 798.6 | 806 | 813 | 820 | 827 | 834 | 841 | 848 | 855 | 862 | 869 | 876 | 883 | 890 | 897 | 904 | 911 | 918 | 925 | 932 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | [6 empty] | 3.0096 | 3.0096 | 3.0096 | 3.0096 | 3.0096 | 3.0025 | 2.9955 | 2.9885 | 2.9815 | 2.9745 | 2.9674 | 2.9604 | 2.9533 | 2.9463 | 2.9394 | 2.9307 | 2.922 | 2.9134 | 2.9048 | 2.8963 | 2.8876 | 2.879 | 2.8704 | 2.8619 | 2.8533 | 2.8446 | 2.836 | 2.8273 | 2.8187 | 2.8101 | 2.8099 | 2.8096 | 2.8094 | 2.8092 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089 | 2.8089
235 | Whau |  |  | 2052 | 1851.3216 | 1848.4341 | 1845.5512 | 1842.6728 | 1839.7988 | 1847.8736 | 1855.9837 | 1864.1295 | 1872.311 | 1880.5285 | 1888.761 | 1897.0295 | 1905.3343 | 1913.6754 | 1922.053 | 1929.6116 | 1937.1999 | 1944.8181 | 1952.4662 | 1960.1444 | 1966.8933 | 1973.6655 | 1980.461 | 1987.2799 | 1994.1223 | 2003.1925 | 2012.3039 | 2021.4568 | 2030.6513 | 2039.8877 | 2048.3986 | 2056.945 | 2065.5271 | 2074.145 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 | 2082.7988 |  | 4820 | 4812.4824 | 4804.9766 | 4797.4824 | 4790 | 4794.5386 | 4799.0814 | 4803.6286 | 4808.1801 | 4812.7359 | 4816.9567 | 4821.1812 | 4825.4094 | 4829.6414 | 4833.877 | 4834.0878 | 4834.2986 | 4834.5094 | 4834.7202 | 4834.931 | 4832.4286 | 4829.9275 | 4827.4277 | 4824.9292 | 4822.432 | 4824.8323 | 4827.2337 | 4829.6364 | 4832.0402 | 4834.4453 | 4854.5027 | 4874.6433 | 4894.8675 | 4915.1756 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | 4935.5679 | [6 empty] | 897 | 905 | 913 | 921 | 930.1 | 942 | 954 | 966 | 978 | 990 | 1000 | 1011 | 1022 | 1033 | 1044 | 1055 | 1066 | 1077 | 1088 | 1099 | 1110 | 1121 | 1132 | 1143 | 1154 | 1165 | 1176 | 1187 | 1198 | 1209 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | 1213.4 | [6 empty] | 2.6035 | 2.6035 | 2.6035 | 2.6035 | 2.6035 | 2.5946 | 2.5857 | 2.5769 | 2.568 | 2.5592 | 2.5503 | 2.5414 | 2.5326 | 2.5238 | 2.515 | 2.5052 | 2.4955 | 2.4858 | 2.4762 | 2.4666 | 2.4569 | 2.4472 | 2.4375 | 2.4279 | 2.4183 | 2.4086 | 2.3989 | 2.3892 | 2.3796 | 2.37 | 2.3699 | 2.3698 | 2.3698 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697 | 2.3697
236 | Whau |  |  | 2052 | 1092.7363 | 1096.2067 | 1099.6881 | 1103.1806 | 1106.6842 | 1110.8516 | 1115.0347 | 1119.2336 | 1123.4483 | 1127.6788 | 1131.9276 | 1136.1923 | 1140.4731 | 1144.7701 | 1149.0832 | 1152.9439 | 1156.8176 | 1160.7043 | 1164.604 | 1168.5169 | 1171.9411 | 1175.3753 | 1178.8196 | 1182.274 | 1185.7385 | 1190.3419 | 1194.9631 | 1199.6023 | 1204.2594 | 1208.9347 | 1213.2536 | 1217.588 | 1221.9378 | 1226.3032 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 | 1230.6842 |  | 3220 | 3229.9538 | 3239.9383 | 3249.9537 | 3260 | 3269.9864 | 3280.0034 | 3290.0512 | 3300.1296 | 3310.239 | 3320.3837 | 3330.5595 | 3340.7665 | 3351.0048 | 3361.2745 | 3367.1951 | 3373.1262 | 3379.0677 | 3385.0197 | 3390.9822 | 3395.4994 | 3400.0227 | 3404.5519 | 3409.0872 | 3413.6285 | 3421.2987 | 3428.9861 | 3436.6908 | 3444.4128 | 3452.1522 | 3464.179 | 3476.2478 | 3488.3587 | 3500.5117 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | 3512.707 | [6 empty] | 520 | 524 | 528 | 532 | 537.2 | 544 | 551 | 558 | 565 | 572 | 576.9 | 583 | 589 | 595 | 601 | 607 | 613 | 619 | 625 | 631 | 637 | 643 | 649 | 655 | 661 | 667 | 673 | 679 | 685 | 691 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | 694 | [6 empty] | 2.9467 | 2.9465 | 2.9462 | 2.946 | 2.9457 | 2.9437 | 2.9416 | 2.9396 | 2.9375 | 2.9354 | 2.9334 | 2.9313 | 2.9293 | 2.9272 | 2.9252 | 2.9205 | 2.9159 | 2.9112 | 2.9066 | 2.902 | 2.8973 | 2.8927 | 2.8881 | 2.8835 | 2.8789 | 2.8742 | 2.8695 | 2.8649 | 2.8602 | 2.8555 | 2.8553 | 2.855 | 2.8548 | 2.8545 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543 | 2.8543
237 | Whau |  |  | 2052 | 1183.8179 | 1181.9925 | 1180.1698 | 1178.35 | 1176.5329 | 1181.7766 | 1187.0437 | 1192.3342 | 1197.6484 | 1202.9862 | 1208.3324 | 1213.7023 | 1219.0961 | 1224.5139 | 1229.9557 | 1234.9013 | 1239.8668 | 1244.8523 | 1249.8578 | 1254.8834 | 1259.3203 | 1263.7728 | 1268.2411 | 1272.7251 | 1277.225 | 1283.1066 | 1289.0153 | 1294.9513 | 1300.9145 | 1306.9052 | 1312.3846 | 1317.887 | 1323.4124 | 1328.961 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 | 1334.5329 |  | 3250 | 3244.9884 | 3239.9846 | 3234.9884 | 3230 | 3250.8326 | 3271.7996 | 3292.9019 | 3314.1402 | 3335.5155 | 3356.9205 | 3378.4628 | 3400.1433 | 3421.9629 | 3443.9226 | 3459.5536 | 3475.2555 | 3491.0286 | 3506.8734 | 3522.79 | 3537.0633 | 3551.3944 | 3565.7835 | 3580.231 | 3594.7369 | 3613.1436 | 3631.6446 | 3650.2403 | 3668.9312 | 3687.7178 | 3703.1822 | 3718.7115 | 3734.3059 | 3749.9657 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | 3765.6912 | [6 empty] | 444 | 447 | 450 | 453 | 456 | 462 | 468 | 474 | 480 | 486 | 489.8 | 495 | 500 | 505 | 510 | 515 | 520 | 525 | 530 | 535 | 540 | 545 | 550 | 555 | 560 | 565 | 570 | 575 | 580 | 585 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | 584.3 | [6 empty] | 2.7454 | 2.7454 | 2.7454 | 2.7454 | 2.7454 | 2.7508 | 2.7563 | 2.7617 | 2.7672 | 2.7727 | 2.7781 | 2.7836 | 2.7891 | 2.7945 | 2.8 | 2.8015 | 2.8029 | 2.8044 | 2.8058 | 2.8073 | 2.8087 | 2.8102 | 2.8116 | 2.813 | 2.8145 | 2.8159 | 2.8174 | 2.8188 | 2.8203 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217 | 2.8217
238 | Whau |  |  | 2052 | 2260.2308 | 2270.1275 | 2280.0676 | 2290.0512 | 2300.0785 | 2306.2596 | 2312.4573 | 2318.6717 | 2324.9028 | 2331.1506 | 2337.4521 | 2343.7707 | 2350.1064 | 2356.4591 | 2362.8291 | 2368.5688 | 2374.3225 | 2380.0902 | 2385.8719 | 2391.6676 | 2396.7658 | 2401.8748 | 2406.9948 | 2412.1256 | 2417.2674 | 2424.1245 | 2431.0011 | 2437.8972 | 2444.8129 | 2451.7482 | 2458.1804 | 2464.6295 | 2471.0955 | 2477.5785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 | 2484.0785 |  | 6200 | 6227.3189 | 6254.7582 | 6282.3184 | 6310 | 6328.5924 | 6347.2395 | 6365.9417 | 6384.6989 | 6403.5114 | 6422.4778 | 6441.5003 | 6460.5793 | 6479.7147 | 6498.9068 | 6509.1743 | 6519.458 | 6529.758 | 6540.0742 | 6550.4068 | 6558.7718 | 6567.1474 | 6575.5338 | 6583.9308 | 6592.3386 | 6605.4039 | 6618.4951 | 6631.6122 | 6644.7554 | 6657.9245 | 6675.4946 | 6693.111 | 6710.7739 | 6728.4834 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | 6746.2396 | [6 empty] | 753 | 758 | 763 | 768 | 773.2 | 784 | 795 | 806 | 817 | 828 | 837.5 | 846 | 855 | 864 | 873 | 882 | 891 | 900 | 909 | 918 | 927 | 936 | 945 | 954 | 963 | 972 | 981 | 990 | 999 | 1008 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | 1017.1 | [6 empty] | 2.7431 | 2.7432 | 2.7432 | 2.7433 | 2.7434 | 2.7441 | 2.7448 | 2.7455 | 2.7462 | 2.7469 | 2.7476 | 2.7483 | 2.7491 | 2.7498 | 2.7505 | 2.7481 | 2.7458 | 2.7435 | 2.7412 | 2.7388 | 2.7365 | 2.7342 | 2.7318 | 2.7295 | 2.7272 | 2.7249 | 2.7225 | 2.7202 | 2.7179 | 2.7156 | 2.7156 | 2.7157 | 2.7157 | 2.7157 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158 | 2.7158
239 | Whau |  |  | 2052 | 449.3527 | 460.254 | 471.4198 | 482.8565 | 494.5706 | 539.4137 | 588.3227 | 641.6664 | 699.8468 | 763.3024 | 811.5894 | 862.9311 | 917.5207 | 975.5636 | 1037.2784 | 1083.1898 | 1131.1333 | 1181.1988 | 1233.4803 | 1288.0759 | 1329.947 | 1373.1792 | 1417.8167 | 1463.9052 | 1511.4919 | 1567.3869 | 1625.3488 | 1685.4542 | 1747.7823 | 1812.4153 | 1865.6285 | 1920.4041 | 1976.788 | 2034.8273 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 | 2094.5706 |  | 1100 | 1126.5251 | 1153.6897 | 1181.5094 | 1210 | 1320.9229 | 1442.0143 | 1574.2064 | 1718.5168 | 1876.0563 | 1996.966 | 2125.6681 | 2262.6649 | 2408.491 | 2563.7154 | 2676.9094 | 2795.1011 | 2918.5113 | 3047.3704 | 3181.9188 | 3285.1426 | 3391.715 | 3501.7447 | 3615.3438 | 3732.6282 | 3870.424 | 4013.3067 | 4161.4641 | 4315.091 | 4474.3893 | 4605.5685 | 4740.5936 | 4879.5773 | 5022.6357 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | 5169.8883 | [6 empty] | 4039 | 4083 | 4127 | 4171 | 4214.2 | 4272 | 4330 | 4388 | 4446 | 4504 | 4563.6 | 4613 | 4662 | 4711 | 4760 | 4809 | 4858 | 4907 | 4956 | 5005 | 5054 | 5103 | 5152 | 5201 | 5250 | 5299 | 5348 | 5397 | 5446 | 5495 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | 5550.9 | [6 empty] | 2.448 | 2.4476 | 2.4473 | 2.4469 | 2.4466 | 2.4488 | 2.4511 | 2.4533 | 2.4556 | 2.4578 | 2.4606 | 2.4633 | 2.4661 | 2.4688 | 2.4716 | 2.4713 | 2.4711 | 2.4708 | 2.4705 | 2.4703 | 2.4701 | 2.47 | 2.4698 | 2.4697 | 2.4695 | 2.4693 | 2.4692 | 2.469 | 2.4689 | 2.4687 | 2.4686 | 2.4685 | 2.4684 | 2.4683 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682 | 2.4682
240 | Whau |  |  | 2052 | 733.7167 | 729.3098 | 724.9293 | 720.5752 | 716.2472 | 752.1786 | 789.9126 | 829.5395 | 871.1543 | 914.8568 | 952.1815 | 991.029 | 1031.4614 | 1073.5434 | 1117.3422 | 1152.2436 | 1188.2352 | 1225.3511 | 1263.6262 | 1303.097 | 1334.6696 | 1367.0071 | 1400.1282 | 1434.0517 | 1468.7972 | 1510.7976 | 1553.999 | 1598.4358 | 1644.1432 | 1691.1577 | 1730.8665 | 1771.5078 | 1813.1033 | 1855.6754 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 | 1899.2472 |  | 2100 | 2087.3868 | 2074.8494 | 2062.3873 | 2050 | 2142.431 | 2239.0295 | 2339.9835 | 2445.4893 | 2555.7522 | 2648.4302 | 2744.4689 | 2843.9903 | 2947.1205 | 3053.9905 | 3134.811 | 3217.7704 | 3302.9251 | 3390.3334 | 3480.0549 | 3548.3565 | 3617.9986 | 3689.0076 | 3761.4103 | 3835.234 | 3926.6987 | 4020.3448 | 4116.2241 | 4214.3901 | 4314.8971 | 4414.4625 | 4516.3253 | 4620.5386 | 4727.1566 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | 4836.2348 | [6 empty] | 2256 | 2284 | 2312 | 2340 | 2368.5 | 2403 | 2438 | 2473 | 2508 | 2543 | 2577.3 | 2608 | 2639 | 2670 | 2701 | 2732 | 2763 | 2794 | 2825 | 2856 | 2887 | 2918 | 2949 | 2980 | 3011 | 3042 | 3073 | 3104 | 3135 | 3166 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | 3191.8 | [6 empty] | 2.8621 | 2.8621 | 2.8621 | 2.8621 | 2.8621 | 2.8483 | 2.8345 | 2.8208 | 2.8072 | 2.7936 | 2.7814 | 2.7693 | 2.7572 | 2.7452 | 2.7333 | 2.7206 | 2.708 | 2.6955 | 2.683 | 2.6706 | 2.6586 | 2.6467 | 2.6348 | 2.6229 | 2.6111 | 2.5991 | 2.5871 | 2.5752 | 2.5633 | 2.5514 | 2.5504 | 2.5494 | 2.5484 | 2.5474 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464 | 2.5464
241 | Whau |  |  | 2052 | 1376.4458 | 1376.4458 | 1376.4458 | 1376.4458 | 1376.4458 | 1385.1527 | 1393.9147 | 1402.7321 | 1411.6053 | 1420.5346 | 1429.4128 | 1438.3464 | 1447.3359 | 1456.3816 | 1465.4838 | 1473.6378 | 1481.8373 | 1490.0823 | 1498.3732 | 1506.7102 | 1513.9936 | 1521.3121 | 1528.6661 | 1536.0556 | 1543.4808 | 1553.2614 | 1563.1041 | 1573.0091 | 1582.9768 | 1593.0077 | 1602.1889 | 1611.423 | 1620.7103 | 1630.0511 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 | 1639.4458 |  | 3820 | 3820 | 3820 | 3820 | 3820 | 3858.4087 | 3897.2036 | 3936.3886 | 3975.9676 | 4015.9445 | 4055.7802 | 4096.0111 | 4136.6411 | 4177.674 | 4219.114 | 4250.4688 | 4282.0565 | 4313.8791 | 4345.9381 | 4378.2353 | 4407.6055 | 4437.1726 | 4466.9382 | 4496.9034 | 4527.0696 | 4564.0037 | 4601.2392 | 4638.7784 | 4676.6239 | 4714.7782 | 4741.218 | 4767.8061 | 4794.5433 | 4821.4304 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | 4848.4683 | [6 empty] | 772 | 779 | 786 | 793 | 799 | 810 | 821 | 832 | 843 | 854 | 864.1 | 873 | 882 | 891 | 900 | 909 | 918 | 927 | 936 | 945 | 954 | 963 | 972 | 981 | 990 | 999 | 1008 | 1017 | 1026 | 1035 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | 1045.9 | [6 empty] | 2.7753 | 2.7753 | 2.7753 | 2.7753 | 2.7753 | 2.7855 | 2.7959 | 2.8062 | 2.8166 | 2.8271 | 2.8374 | 2.8477 | 2.8581 | 2.8685 | 2.879 | 2.8843 | 2.8897 | 2.8951 | 2.9004 | 2.9058 | 2.9112 | 2.9167 | 2.9221 | 2.9276 | 2.933 | 2.9383 | 2.9437 | 2.949 | 2.9543 | 2.9597 | 2.9592 | 2.9588 | 2.9583 | 2.9578 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574 | 2.9574
242 | Whau |  |  | 2052 | 1249.6644 | 1247.7434 | 1245.8252 | 1243.91 | 1241.9978 | 1248.8089 | 1255.6574 | 1262.5435 | 1269.4673 | 1276.4291 | 1283.3737 | 1290.3562 | 1297.3766 | 1304.4352 | 1311.5322 | 1317.9282 | 1324.3554 | 1330.8139 | 1337.3039 | 1343.8256 | 1349.5482 | 1355.2952 | 1361.0667 | 1366.8627 | 1372.6835 | 1380.2901 | 1387.9389 | 1395.6301 | 1403.3639 | 1411.1406 | 1418.2402 | 1425.3756 | 1432.5468 | 1439.7542 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 | 1446.9978 |  | 3260 | 3254.9885 | 3249.9846 | 3244.9885 | 3240 | 3274.3345 | 3309.0328 | 3344.0988 | 3379.5364 | 3415.3495 | 3450.9756 | 3486.9733 | 3523.3465 | 3560.0991 | 3597.2351 | 3625.1555 | 3653.2926 | 3681.6481 | 3710.2237 | 3739.0211 | 3765.6285 | 3792.4253 | 3819.4127 | 3846.5922 | 3873.9651 | 3906.2694 | 3938.8431 | 3971.6884 | 4004.8075 | 4038.2029 | 4058.1196 | 4078.1345 | 4098.2482 | 4118.461 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | 4138.7736 | [6 empty] | 650 | 655 | 660 | 665 | 671 | 679 | 687 | 695 | 703 | 711 | 717.4 | 724 | 731 | 738 | 745 | 752 | 759 | 766 | 773 | 780 | 787 | 794 | 801 | 808 | 815 | 822 | 829 | 836 | 843 | 850 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | 857 | [6 empty] | 2.6087 | 2.6087 | 2.6087 | 2.6087 | 2.6087 | 2.622 | 2.6353 | 2.6487 | 2.6622 | 2.6757 | 2.689 | 2.7023 | 2.7157 | 2.7292 | 2.7428 | 2.7506 | 2.7585 | 2.7665 | 2.7744 | 2.7824 | 2.7903 | 2.7982 | 2.8062 | 2.8142 | 2.8222 | 2.83 | 2.8379 | 2.8458 | 2.8537 | 2.8617 | 2.8614 | 2.8611 | 2.8608 | 2.8605 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602 | 2.8602
243 | Waitemata |  |  | 2052 | 593.6422 | 607.7392 | 622.1708 | 636.9452 | 652.0705 | 718.6439 | 792.0142 | 872.8753 | 961.9919 | 1060.2069 | 1132.7861 | 1210.3338 | 1293.1903 | 1381.7189 | 1476.3079 | 1545.6587 | 1618.2673 | 1694.2868 | 1773.8773 | 1857.2066 | 1920.5924 | 1986.1415 | 2053.9277 | 2124.0275 | 2196.5197 | 2281.077 | 2368.8894 | 2460.0823 | 2554.7857 | 2653.1348 | 2733.6807 | 2816.6718 | 2902.1824 | 2990.289 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 | 3081.0705 |  | 1020 | 1041.7917 | 1064.0489 | 1086.7816 | 1110 | 1215.7428 | 1331.559 | 1458.4083 | 1597.3417 | 1749.5105 | 1865.2167 | 1988.5752 | 2120.0922 | 2260.3072 | 2409.7956 | 2518.4471 | 2631.9974 | 2750.6674 | 2874.6879 | 3004.3002 | 3103.455 | 3205.8825 | 3311.6905 | 3420.9906 | 3533.898 | 3666.1572 | 3803.3663 | 3945.7105 | 4093.3821 | 4246.5804 | 4372.4751 | 4502.1021 | 4635.5721 | 4772.9989 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | 4914.4999 | [6 empty] | 21838 | 22134 | 22430 | 22726 | 23021.6 | 23348 | 23675 | 24002 | 24329 | 24656 | 24982.9 | 25274 | 25565 | 25856 | 26147 | 26438 | 26729 | 27020 | 27311 | 27602 | 27893 | 28184 | 28475 | 28766 | 29057 | 29348 | 29639 | 29930 | 30221 | 30512 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | 30804.7 | [6 empty] | 1.7182 | 1.7142 | 1.7102 | 1.7062 | 1.7023 | 1.6917 | 1.6812 | 1.6708 | 1.6605 | 1.6502 | 1.6466 | 1.643 | 1.6394 | 1.6359 | 1.6323 | 1.6294 | 1.6264 | 1.6235 | 1.6206 | 1.6176 | 1.6159 | 1.6141 | 1.6124 | 1.6106 | 1.6089 | 1.6072 | 1.6055 | 1.6039 | 1.6022 | 1.6006 | 1.5995 | 1.5984 | 1.5973 | 1.5962 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951 | 1.5951
244 | Waitemata |  |  | 2052 | 3861.6186 | 3909.1225 | 3957.2108 | 4005.8907 | 4055.1694 | 4142.8332 | 4232.392 | 4323.887 | 4417.3598 | 4512.8533 | 4602.54 | 4694.0091 | 4787.2961 | 4882.437 | 4979.4686 | 5062.1376 | 5146.1791 | 5231.6158 | 5318.4709 | 5406.768 | 5480.8571 | 5555.9615 | 5632.095 | 5709.2718 | 5787.5061 | 5886.6176 | 5987.4264 | 6089.9615 | 6194.2526 | 6300.3297 | 6393.6895 | 6488.4327 | 6584.5798 | 6682.1517 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 | 6781.1694 |  | 7630 | 7723.2756 | 7817.6915 | 7913.2616 | 8010 | 8192.9259 | 8380.0293 | 8571.4056 | 8767.1525 | 8967.3696 | 9156.6235 | 9349.8716 | 9547.1982 | 9748.6892 | 9954.4327 | 10118.9173 | 10286.1197 | 10456.085 | 10628.8587 | 10804.4873 | 10951.8952 | 11101.3143 | 11252.7719 | 11406.2959 | 11561.9145 | 11759.1108 | 11959.6704 | 12163.6508 | 12371.1101 | 12582.1078 | 12767.8551 | 12956.3446 | 13147.6167 | 13341.7125 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | 13538.6737 | [6 empty] | 16387 | 16609 | 16831 | 17053 | 17274.6 | 17520 | 17765 | 18010 | 18255 | 18500 | 18747.2 | 18966 | 19184 | 19402 | 19620 | 19838 | 20056 | 20274 | 20492 | 20710 | 20928 | 21146 | 21364 | 21582 | 21800 | 22018 | 22236 | 22454 | 22672 | 22890 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | 23116.3 | [6 empty] | 1.9759 | 1.9757 | 1.9756 | 1.9754 | 1.9753 | 1.9776 | 1.98 | 1.9823 | 1.9847 | 1.9871 | 1.9895 | 1.9919 | 1.9943 | 1.9967 | 1.9991 | 1.9989 | 1.9988 | 1.9986 | 1.9985 | 1.9983 | 1.9982 | 1.9981 | 1.998 | 1.9979 | 1.9977 | 1.9976 | 1.9975 | 1.9973 | 1.9972 | 1.9971 | 1.9969 | 1.9968 | 1.9967 | 1.9966 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965 | 1.9965
245 | Waitemata |  |  | 2052 | 2065.2191 | 2083.7022 | 2102.3509 | 2121.1664 | 2140.1503 | 2204.8916 | 2271.5914 | 2340.3089 | 2411.1051 | 2484.043 | 2550.5103 | 2618.756 | 2688.8279 | 2760.7747 | 2834.6467 | 2896.1552 | 2958.9985 | 3023.2053 | 3088.8054 | 3155.8289 | 3211.1084 | 3267.3563 | 3324.5893 | 3382.825 | 3442.0807 | 3515.877 | 3591.2554 | 3668.25 | 3746.8952 | 3827.2265 | 3896.8329 | 3967.7053 | 4039.8666 | 4113.3403 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 | 4188.1503 |  | 2780 | 2804.6697 | 2829.5583 | 2854.6677 | 2880 | 2970.3404 | 3063.5147 | 3159.6116 | 3258.7229 | 3360.9432 | 3454.7772 | 3551.2309 | 3650.3776 | 3752.2922 | 3857.0523 | 3940.2498 | 4025.242 | 4112.0674 | 4200.7657 | 4291.3772 | 4366.144 | 4442.2135 | 4519.6083 | 4598.3515 | 4678.4666 | 4778.28 | 4880.2228 | 4984.3406 | 5090.6797 | 5199.2875 | 5293.4292 | 5389.2755 | 5486.8573 | 5586.206 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | 5687.3535 | [6 empty] | 32836 | 33291 | 33746 | 34201 | 34657.7 | 35159 | 35660 | 36161 | 36662 | 37163 | 37665.5 | 38113 | 38561 | 39009 | 39457 | 39905 | 40353 | 40801 | 41249 | 41697 | 42145 | 42593 | 43041 | 43489 | 43937 | 44385 | 44833 | 45281 | 45729 | 46177 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | 46622.2 | [6 empty] | 1.3461 | 1.346 | 1.3459 | 1.3458 | 1.3457 | 1.3472 | 1.3486 | 1.3501 | 1.3515 | 1.353 | 1.3545 | 1.3561 | 1.3576 | 1.3591 | 1.3607 | 1.3605 | 1.3603 | 1.3602 | 1.36 | 1.3598 | 1.3597 | 1.3596 | 1.3594 | 1.3593 | 1.3592 | 1.3591 | 1.3589 | 1.3588 | 1.3586 | 1.3585 | 1.3584 | 1.3583 | 1.3582 | 1.3581 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.358
246 | Waitemata |  |  | 2052 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.030614 | 0.035166 | 0.040395 | 0.046402 | 0.053302 | 0.061228 | 0.061228 | 0.061228 | 0.061228 | 0.061228 | 0.061228 | 0.11651 | 0.2217 | 0.42186 | 0.80273 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | 1.5275 | [6 empty] | 3459 | 3534 | 3609 | 3684 | 3757.4 | 3834 | 3911 | 3988 | 4065 | 4142 | 4219.4 | 4292 | 4365 | 4438 | 4511 | 4584 | 4657 | 4730 | 4803 | 4876 | 4949 | 5022 | 5095 | 5168 | 5241 | 5314 | 5387 | 5460 | 5533 | 5606 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | 5674.5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.010098 | 0.011599 | 0.013324 | 0.015305 | 0.017581 | 0.020195 | 0.020195 | 0.020195 | 0.020195 | 0.020195 | 0.020195 | 0.038429 | 0.073125 | 0.13915 | 0.26477 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383 | 0.50383
247 | Waitemata |  |  | 2052 | 3441.8699 | 3403.1235 | 3364.8133 | 3326.9343 | 3289.4818 | 3345.6442 | 3402.7656 | 3460.8622 | 3519.9507 | 3580.0481 | 3637.4264 | 3695.7244 | 3754.9567 | 3815.1384 | 3876.2846 | 3929.0626 | 3982.5593 | 4036.7843 | 4091.7477 | 4147.4594 | 4194.6853 | 4242.4489 | 4290.7564 | 4339.614 | 4389.0279 | 4452.2545 | 4516.392 | 4581.4533 | 4647.4519 | 4714.4013 | 4773.8967 | 4834.1429 | 4895.1494 | 4956.9258 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 | 5019.4818 |  | 6550 | 6476.2642 | 6403.3585 | 6331.2735 | 6260 | 6368.3725 | 6478.6211 | 6590.7784 | 6704.8772 | 6820.9514 | 6932.8375 | 7046.5589 | 7162.1457 | 7279.6286 | 7399.0385 | 7494.6114 | 7591.4189 | 7689.4768 | 7788.8014 | 7889.4089 | 7974.9023 | 8061.3223 | 8148.6787 | 8236.9818 | 8326.2417 | 8440.7256 | 8556.7836 | 8674.4374 | 8793.7089 | 8914.6203 | 9022.3228 | 9131.3265 | 9241.6471 | 9353.3006 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | 9466.303 | [6 empty] | 8138 | 8248 | 8358 | 8468 | 8578.2 | 8700 | 8822 | 8944 | 9066 | 9188 | 9310.8 | 9419 | 9527 | 9635 | 9743 | 9851 | 9959 | 10067 | 10175 | 10283 | 10391 | 10499 | 10607 | 10715 | 10823 | 10931 | 11039 | 11147 | 11255 | 11363 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | 11480 | [6 empty] | 1.903 | 1.903 | 1.903 | 1.903 | 1.903 | 1.9035 | 1.9039 | 1.9044 | 1.9048 | 1.9053 | 1.906 | 1.9067 | 1.9074 | 1.9081 | 1.9088 | 1.9075 | 1.9062 | 1.9049 | 1.9035 | 1.9022 | 1.9012 | 1.9002 | 1.8991 | 1.8981 | 1.8971 | 1.8958 | 1.8946 | 1.8934 | 1.8922 | 1.8909 | 1.8899 | 1.8889 | 1.8879 | 1.8869 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859 | 1.8859
248 | Waitemata |  |  | 2052 | 1989.5834 | 1931.2883 | 1874.7012 | 1819.7721 | 1766.4525 | 1823.1578 | 1881.6834 | 1942.0878 | 2004.4311 | 2068.7758 | 2127.0443 | 2186.954 | 2248.5511 | 2311.883 | 2376.9988 | 2430.9253 | 2486.0751 | 2542.4762 | 2600.1568 | 2659.146 | 2707.6152 | 2756.9678 | 2807.22 | 2858.3882 | 2910.489 | 2975.2499 | 3041.4518 | 3109.1268 | 3178.3076 | 3249.0278 | 3310.1679 | 3372.4586 | 3435.9215 | 3500.5787 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 | 3566.4525 |  | 3210 | 3115.9465 | 3024.6487 | 2936.026 | 2850 | 2941.1058 | 3035.124 | 3132.1476 | 3232.2728 | 3335.5987 | 3430.2608 | 3527.6094 | 3627.7206 | 3730.673 | 3836.547 | 3920.6316 | 4006.559 | 4094.3697 | 4184.1049 | 4275.8067 | 4351.3503 | 4428.2285 | 4506.4649 | 4586.0837 | 4667.109 | 4768.0572 | 4871.1887 | 4976.551 | 5084.1923 | 5194.1617 | 5289.438 | 5386.462 | 5485.2656 | 5585.8816 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | 5688.3432 | [6 empty] | 24912 | 25250 | 25588 | 25926 | 26263.8 | 26637 | 27010 | 27383 | 27756 | 28129 | 28500.7 | 28833 | 29165 | 29497 | 29829 | 30161 | 30493 | 30825 | 31157 | 31489 | 31821 | 32153 | 32485 | 32817 | 33149 | 33481 | 33813 | 34145 | 34477 | 34809 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | 35141.6 | [6 empty] | 1.6134 | 1.6134 | 1.6134 | 1.6134 | 1.6134 | 1.6132 | 1.613 | 1.6128 | 1.6126 | 1.6124 | 1.6127 | 1.613 | 1.6134 | 1.6137 | 1.614 | 1.6128 | 1.6116 | 1.6104 | 1.6092 | 1.608 | 1.6071 | 1.6062 | 1.6053 | 1.6044 | 1.6035 | 1.6026 | 1.6016 | 1.6006 | 1.5997 | 1.5987 | 1.5979 | 1.5972 | 1.5964 | 1.5957 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595 | 1.595
249 | Waitemata |  |  | 2052 | 1808.5513 | 1808.5513 | 1808.5513 | 1808.5513 | 1808.5513 | 1844.6996 | 1881.5704 | 1919.1781 | 1957.5375 | 1996.6636 | 2033.6262 | 2071.273 | 2109.6167 | 2148.6703 | 2188.4468 | 2222.5433 | 2257.171 | 2292.3382 | 2328.0533 | 2364.3249 | 2394.8953 | 2425.8611 | 2457.2273 | 2488.999 | 2521.1815 | 2562.0098 | 2603.4992 | 2645.6606 | 2688.5047 | 2732.0426 | 2770.4492 | 2809.3958 | 2848.8898 | 2888.9391 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 | 2929.5513 |  | 3740 | 3740 | 3740 | 3740 | 3740 | 3798.5633 | 3858.0436 | 3918.4553 | 3979.813 | 4042.1315 | 4102.5875 | 4163.9477 | 4226.2257 | 4289.4351 | 4353.59 | 4405.8019 | 4458.6399 | 4512.1117 | 4566.2247 | 4620.9867 | 4667.7271 | 4714.9402 | 4762.6309 | 4810.804 | 4859.4643 | 4921.9531 | 4985.2454 | 5049.3516 | 5114.2822 | 5180.0477 | 5238.7583 | 5298.1343 | 5358.1833 | 5418.9129 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | 5480.3308 | [6 empty] | 8311 | 8424 | 8537 | 8650 | 8762.5 | 8887 | 9011 | 9135 | 9259 | 9383 | 9507.1 | 9618 | 9729 | 9840 | 9951 | 10062 | 10173 | 10284 | 10395 | 10506 | 10617 | 10728 | 10839 | 10950 | 11061 | 11172 | 11283 | 11394 | 11505 | 11616 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | 11724.4 | [6 empty] | 2.068 | 2.068 | 2.068 | 2.068 | 2.068 | 2.0592 | 2.0504 | 2.0417 | 2.0331 | 2.0244 | 2.0174 | 2.0103 | 2.0033 | 1.9963 | 1.9894 | 1.9823 | 1.9753 | 1.9683 | 1.9614 | 1.9545 | 1.949 | 1.9436 | 1.9382 | 1.9328 | 1.9275 | 1.9211 | 1.9148 | 1.9085 | 1.9023 | 1.896 | 1.8909 | 1.8859 | 1.8808 | 1.8757 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707 | 1.8707
250 | Waitemata |  |  | 2052 | 2809.455 | 2889.8006 | 2972.444 | 3057.4509 | 3144.8888 | 3207.3569 | 3271.0658 | 3336.0402 | 3402.3052 | 3469.8864 | 3533.7591 | 3598.8076 | 3665.0535 | 3732.5189 | 3801.2261 | 3860.0695 | 3919.8238 | 3980.5031 | 4042.1217 | 4104.6942 | 4157.408 | 4210.7989 | 4264.8753 | 4319.6463 | 4375.1206 | 4445.6578 | 4517.3321 | 4590.162 | 4664.1661 | 4739.3633 | 4805.7806 | 4873.1286 | 4941.4205 | 5010.6694 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 | 5080.8888 |  | 5740 | 5891.4036 | 6046.8008 | 6206.2969 | 6370 | 6495.6716 | 6623.8225 | 6754.5016 | 6887.7589 | 7023.6452 | 7153.516 | 7285.7882 | 7420.5061 | 7557.7151 | 7697.4611 | 7809.6484 | 7923.4709 | 8038.9522 | 8156.1166 | 8274.9887 | 8375.4489 | 8477.1288 | 8580.043 | 8684.2067 | 8789.6349 | 8924.0951 | 9060.6122 | 9199.2176 | 9339.9434 | 9482.822 | 9609.3889 | 9737.6451 | 9867.6131 | 9999.3158 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | 10132.7763 | [6 empty] | 7750 | 7855 | 7960 | 8065 | 8170 | 8286 | 8402 | 8518 | 8634 | 8750 | 8865.3 | 8969 | 9072 | 9175 | 9278 | 9381 | 9484 | 9587 | 9690 | 9793 | 9896 | 9999 | 10102 | 10205 | 10308 | 10411 | 10514 | 10617 | 10720 | 10823 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | 10931.9 | [6 empty] | 2.0431 | 2.0387 | 2.0343 | 2.0299 | 2.0255 | 2.0252 | 2.025 | 2.0247 | 2.0244 | 2.0242 | 2.0243 | 2.0245 | 2.0247 | 2.0248 | 2.025 | 2.0232 | 2.0214 | 2.0196 | 2.0178 | 2.016 | 2.0146 | 2.0132 | 2.0118 | 2.0104 | 2.009 | 2.0074 | 2.0057 | 2.0041 | 2.0025 | 2.0009 | 1.9995 | 1.9982 | 1.9969 | 1.9956 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943 | 1.9943
251 | Waitemata |  |  | 2052 | 2509.6659 | 2428.2883 | 2349.5494 | 2273.3637 | 2199.6483 | 2251.711 | 2305.0059 | 2359.5622 | 2415.4097 | 2472.5791 | 2525.8822 | 2580.3344 | 2635.9605 | 2692.7857 | 2750.836 | 2800.0206 | 2850.0847 | 2901.0439 | 2952.9143 | 3005.7121 | 3049.826 | 3094.5873 | 3140.0056 | 3186.0904 | 3232.8517 | 3291.7699 | 3351.762 | 3412.8474 | 3475.046 | 3538.3782 | 3593.8646 | 3650.221 | 3707.4611 | 3765.5989 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 | 3824.6483 |  | 5100 | 4934.6291 | 4774.6204 | 4619.8001 | 4470 | 4568.3166 | 4668.7956 | 4771.4846 | 4876.4323 | 4983.6882 | 5085.3918 | 5189.1708 | 5295.0677 | 5403.1256 | 5513.3887 | 5602.1841 | 5692.4094 | 5784.088 | 5877.243 | 5971.8983 | 6051.4719 | 6132.1057 | 6213.814 | 6296.611 | 6380.5113 | 6486.8338 | 6594.928 | 6704.8234 | 6816.5501 | 6930.1386 | 7030.204 | 7131.7143 | 7234.6903 | 7339.1532 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | 7445.1244 | [6 empty] | 5879 | 5959 | 6039 | 6119 | 6198.5 | 6286 | 6374 | 6462 | 6550 | 6638 | 6726.2 | 6805 | 6883 | 6961 | 7039 | 7117 | 7195 | 7273 | 7351 | 7429 | 7507 | 7585 | 7663 | 7741 | 7819 | 7897 | 7975 | 8053 | 8131 | 8209 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | 8292.5 | [6 empty] | 2.0321 | 2.0321 | 2.0321 | 2.0321 | 2.0321 | 2.0288 | 2.0255 | 2.0222 | 2.0189 | 2.0156 | 2.0133 | 2.011 | 2.0088 | 2.0065 | 2.0043 | 2.0008 | 1.9973 | 1.9938 | 1.9903 | 1.9868 | 1.9842 | 1.9816 | 1.9789 | 1.9763 | 1.9736 | 1.9706 | 1.9676 | 1.9646 | 1.9616 | 1.9586 | 1.9562 | 1.9538 | 1.9514 | 1.949 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466 | 1.9466
252 | Waitemata |  |  | 2052 | 1118.5763 | 1088.6592 | 1059.5422 | 1031.204 | 1003.6238 | 1022.8487 | 1042.4418 | 1062.4103 | 1082.7613 | 1103.5021 | 1123.1549 | 1143.1578 | 1163.5169 | 1184.2387 | 1205.3294 | 1223.4007 | 1241.7428 | 1260.36 | 1279.2563 | 1298.4359 | 1314.6044 | 1330.9743 | 1347.5481 | 1364.3282 | 1381.3172 | 1402.9555 | 1424.9327 | 1447.2542 | 1469.9254 | 1492.9517 | 1513.3226 | 1533.9714 | 1554.902 | 1576.1181 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 | 1597.6238 |  | 2530 | 2462.3334 | 2396.4766 | 2332.3812 | 2270 | 2314.9964 | 2360.8847 | 2407.6827 | 2455.4082 | 2504.0799 | 2550.724 | 2598.237 | 2646.635 | 2695.9345 | 2746.1524 | 2786.3592 | 2827.1548 | 2868.5477 | 2910.5466 | 2953.1604 | 2989.2059 | 3025.6913 | 3062.6221 | 3100.0037 | 3137.8415 | 3186.1053 | 3235.1115 | 3284.8715 | 3335.3968 | 3386.6993 | 3432.0275 | 3477.9625 | 3524.5122 | 3571.6849 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | 3619.489 | [6 empty] | 1975 | 2001 | 2027 | 2053 | 2080.6 | 2115 | 2149 | 2183 | 2217 | 2251 | 2285.2 | 2316 | 2347 | 2378 | 2409 | 2440 | 2471 | 2502 | 2533 | 2564 | 2595 | 2626 | 2657 | 2688 | 2719 | 2750 | 2781 | 2812 | 2843 | 2874 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | 2905.2 | [6 empty] | 2.2618 | 2.2618 | 2.2618 | 2.2618 | 2.2618 | 2.2633 | 2.2648 | 2.2662 | 2.2677 | 2.2692 | 2.271 | 2.2729 | 2.2747 | 2.2765 | 2.2783 | 2.2776 | 2.2768 | 2.276 | 2.2752 | 2.2744 | 2.2738 | 2.2733 | 2.2727 | 2.2722 | 2.2716 | 2.271 | 2.2704 | 2.2697 | 2.2691 | 2.2685 | 2.2679 | 2.2673 | 2.2667 | 2.2661 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655 | 2.2655
253 | Waitemata |  |  | 2052 | 1012.2935 | 985.7142 | 959.8328 | 934.6309 | 910.0908 | 935.5564 | 961.7345 | 988.6452 | 1016.3088 | 1044.7465 | 1070.8643 | 1097.635 | 1125.075 | 1153.2009 | 1182.03 | 1206.1371 | 1230.7358 | 1255.8362 | 1281.4485 | 1307.5832 | 1329.2118 | 1351.1981 | 1373.5481 | 1396.2678 | 1419.3633 | 1448.2731 | 1477.7718 | 1507.8713 | 1538.5839 | 1569.9221 | 1597.1919 | 1624.9353 | 1653.1607 | 1681.8763 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 | 1711.0908 |  | 2080 | 2025.3865 | 1972.2069 | 1920.4236 | 1870 | 1946.6963 | 2026.5383 | 2109.6549 | 2196.1804 | 2286.2547 | 2371.9793 | 2460.9182 | 2553.1919 | 2648.9254 | 2748.2486 | 2827.8992 | 2909.8584 | 2994.1929 | 3080.9716 | 3170.2653 | 3249.1446 | 3329.9864 | 3412.8397 | 3497.7544 | 3584.7819 | 3686.5374 | 3791.1811 | 3898.7953 | 4009.4641 | 4123.2743 | 4193.8805 | 4265.6958 | 4338.7409 | 4413.0368 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | 4488.6049 | [6 empty] | 5773 | 5849 | 5925 | 6001 | 6075.9 | 6167 | 6258 | 6349 | 6440 | 6531 | 6620.2 | 6699 | 6777 | 6855 | 6933 | 7011 | 7089 | 7167 | 7245 | 7323 | 7401 | 7479 | 7557 | 7635 | 7713 | 7791 | 7869 | 7947 | 8025 | 8103 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | 8186.4 | [6 empty] | 2.0547 | 2.0547 | 2.0547 | 2.0547 | 2.0547 | 2.0808 | 2.1072 | 2.1339 | 2.1609 | 2.1883 | 2.215 | 2.242 | 2.2694 | 2.297 | 2.325 | 2.3446 | 2.3643 | 2.3842 | 2.4043 | 2.4245 | 2.4444 | 2.4645 | 2.4847 | 2.5051 | 2.5256 | 2.5455 | 2.5655 | 2.5856 | 2.6059 | 2.6264 | 2.6258 | 2.6251 | 2.6245 | 2.6239 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232 | 2.6232
254 | Waitemata |  |  | 2052 | 1385.5431 | 1341.6801 | 1299.2058 | 1258.0761 | 1218.2484 | 1239.0933 | 1260.2949 | 1281.8592 | 1303.7925 | 1326.1011 | 1347.3975 | 1369.0359 | 1391.0218 | 1413.3608 | 1436.0585 | 1455.6131 | 1475.434 | 1495.5247 | 1515.889 | 1536.5307 | 1554.0084 | 1571.685 | 1589.5626 | 1607.6436 | 1625.9303 | 1649.3298 | 1673.0661 | 1697.144 | 1721.5684 | 1746.3443 | 1768.3629 | 1790.659 | 1813.2363 | 1836.0982 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 | 1859.2484 |  | 3230 | 3127.746 | 3028.7291 | 2932.8469 | 2840 | 2912.2716 | 2986.3824 | 3062.3792 | 3140.3099 | 3220.2238 | 3298.317 | 3378.3041 | 3460.231 | 3544.1446 | 3630.0932 | 3698.9882 | 3769.1906 | 3840.7255 | 3913.6179 | 3987.8938 | 4054.6518 | 4122.5274 | 4191.5392 | 4261.7062 | 4333.0479 | 4417.8022 | 4504.2143 | 4592.3166 | 4682.1423 | 4773.7249 | 4831.8061 | 4890.5939 | 4950.0971 | 5010.3242 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | 5071.284 | [6 empty] | 2320 | 2349 | 2378 | 2407 | 2436 | 2476 | 2516 | 2556 | 2596 | 2636 | 2675.2 | 2711 | 2747 | 2783 | 2819 | 2855 | 2891 | 2927 | 2963 | 2999 | 3035 | 3071 | 3107 | 3143 | 3179 | 3215 | 3251 | 3287 | 3323 | 3359 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | 3394.9 | [6 empty] | 2.3312 | 2.3312 | 2.3312 | 2.3312 | 2.3312 | 2.3503 | 2.3696 | 2.389 | 2.4086 | 2.4283 | 2.4479 | 2.4677 | 2.4875 | 2.5076 | 2.5278 | 2.5412 | 2.5546 | 2.5681 | 2.5817 | 2.5954 | 2.6092 | 2.623 | 2.6369 | 2.6509 | 2.665 | 2.6785 | 2.6922 | 2.7059 | 2.7197 | 2.7336 | 2.7324 | 2.7312 | 2.73 | 2.7288 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276 | 2.7276
255 | Waitemata |  |  | 2052 | 1266.9211 | 1234.2056 | 1202.3348 | 1171.2871 | 1141.0411 | 1144.3153 | 1147.5989 | 1150.8919 | 1154.1944 | 1157.5063 | 1160.8443 | 1164.1919 | 1167.5492 | 1170.9161 | 1174.2928 | 1177.3174 | 1180.3499 | 1183.3901 | 1186.4382 | 1189.4941 | 1192.1718 | 1194.8554 | 1197.5451 | 1200.2409 | 1202.9427 | 1206.5439 | 1210.1558 | 1213.7786 | 1217.4122 | 1221.0568 | 1224.4349 | 1227.8224 | 1231.2192 | 1234.6254 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 | 1238.0411 |  | 3120 | 3039.4327 | 2960.9458 | 2884.4857 | 2810 | 2826.6125 | 2843.3231 | 2860.1326 | 2877.0414 | 2894.0502 | 2911.0689 | 2928.1877 | 2945.4071 | 2962.7278 | 2980.1504 | 2991.8278 | 3003.551 | 3015.3201 | 3027.1354 | 3038.9969 | 3049.9029 | 3060.848 | 3071.8323 | 3082.8561 | 3093.9195 | 3107.2655 | 3120.669 | 3134.1304 | 3147.6498 | 3161.2276 | 3169.8584 | 3178.5127 | 3187.1907 | 3195.8924 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | 3204.6179 | [6 empty] | 885 | 893 | 901 | 909 | 918 | 933 | 948 | 963 | 978 | 993 | 1005.4 | 1018 | 1031 | 1044 | 1057 | 1070 | 1083 | 1096 | 1109 | 1122 | 1135 | 1148 | 1161 | 1174 | 1187 | 1200 | 1213 | 1226 | 1239 | 1252 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | 1257.1 | [6 empty] | 2.4627 | 2.4627 | 2.4627 | 2.4627 | 2.4627 | 2.4701 | 2.4776 | 2.4851 | 2.4927 | 2.5002 | 2.5077 | 2.5152 | 2.5227 | 2.5303 | 2.5378 | 2.5412 | 2.5446 | 2.548 | 2.5514 | 2.5549 | 2.5583 | 2.5617 | 2.5651 | 2.5685 | 2.572 | 2.5753 | 2.5787 | 2.5821 | 2.5855 | 2.5889 | 2.5888 | 2.5887 | 2.5886 | 2.5886 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885 | 2.5885
256 | Waitemata |  |  | 2052 | 1284.2123 | 1246.949 | 1210.7669 | 1175.6348 | 1141.522 | 1162.3207 | 1183.4984 | 1205.0619 | 1227.0183 | 1249.3747 | 1270.6305 | 1292.248 | 1314.2332 | 1336.5925 | 1359.3321 | 1378.8575 | 1398.6634 | 1418.7537 | 1439.1326 | 1459.8043 | 1477.2616 | 1494.9278 | 1512.8051 | 1530.8963 | 1549.2039 | 1572.5711 | 1596.2907 | 1620.3681 | 1644.8087 | 1669.6179 | 1691.6116 | 1713.895 | 1736.472 | 1759.3463 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 | 1782.522 |  | 3150 | 3058.5982 | 2969.8485 | 2883.674 | 2800 | 2866.9834 | 2935.5691 | 3005.7957 | 3077.7022 | 3151.3289 | 3222.3503 | 3294.9723 | 3369.231 | 3445.1632 | 3522.8067 | 3584.8889 | 3648.0652 | 3712.3548 | 3777.7774 | 3844.353 | 3902.5779 | 3961.6846 | 4021.6866 | 4082.5973 | 4144.4306 | 4220.0097 | 4296.9671 | 4375.3279 | 4455.1177 | 4536.3625 | 4596.2837 | 4656.9964 | 4718.511 | 4780.8382 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | 4843.9887 | [6 empty] | 3742 | 3791 | 3840 | 3889 | 3937.1 | 3998 | 4059 | 4120 | 4181 | 4242 | 4303.7 | 4359 | 4415 | 4471 | 4527 | 4583 | 4639 | 4695 | 4751 | 4807 | 4863 | 4919 | 4975 | 5031 | 5087 | 5143 | 5199 | 5255 | 5311 | 5367 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | 5418.7 | [6 empty] | 2.4529 | 2.4529 | 2.4529 | 2.4529 | 2.4529 | 2.4666 | 2.4804 | 2.4943 | 2.5083 | 2.5223 | 2.536 | 2.5498 | 2.5636 | 2.5776 | 2.5916 | 2.5999 | 2.6083 | 2.6166 | 2.625 | 2.6335 | 2.6418 | 2.6501 | 2.6584 | 2.6668 | 2.6752 | 2.6835 | 2.6918 | 2.7002 | 2.7086 | 2.717 | 2.7171 | 2.7172 | 2.7173 | 2.7174 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175 | 2.7175
257 | Waitemata |  |  | 2052 | 1049.5025 | 1026.2794 | 1003.5701 | 981.3633 | 959.6479 | 963.0825 | 966.5294 | 969.9886 | 973.4602 | 976.9442 | 980.4458 | 983.96 | 987.4867 | 991.0261 | 994.5782 | 997.8168 | 1001.0659 | 1004.3257 | 1007.596 | 1010.8771 | 1013.7819 | 1016.6951 | 1019.6167 | 1022.5466 | 1025.485 | 1029.231 | 1032.9907 | 1036.7641 | 1040.5513 | 1044.3523 | 1047.7887 | 1051.2364 | 1054.6955 | 1058.166 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 | 1061.6479 |  | 2920 | 2855.3868 | 2792.2034 | 2730.4181 | 2670 | 2682.8572 | 2695.7762 | 2708.7575 | 2721.8013 | 2734.9079 | 2748.071 | 2761.2975 | 2774.5876 | 2787.9418 | 2801.3601 | 2810.3476 | 2819.3639 | 2828.4091 | 2837.4834 | 2846.5868 | 2854.6462 | 2862.7284 | 2870.8334 | 2878.9615 | 2887.1125 | 2897.5034 | 2907.9318 | 2918.3976 | 2928.9011 | 2939.4424 | 2948.9723 | 2958.533 | 2968.1247 | 2977.7475 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | 2987.4015 | [6 empty] | 1303 | 1319 | 1335 | 1351 | 1367.3 | 1391 | 1415 | 1439 | 1463 | 1487 | 1510.3 | 1532 | 1554 | 1576 | 1598 | 1620 | 1642 | 1664 | 1686 | 1708 | 1730 | 1752 | 1774 | 1796 | 1818 | 1840 | 1862 | 1884 | 1906 | 1928 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | 1945.9 | [6 empty] | 2.7823 | 2.7823 | 2.7823 | 2.7823 | 2.7823 | 2.7857 | 2.7891 | 2.7926 | 2.796 | 2.7995 | 2.8029 | 2.8063 | 2.8097 | 2.8132 | 2.8166 | 2.8165 | 2.8164 | 2.8162 | 2.8161 | 2.816 | 2.8158 | 2.8157 | 2.8156 | 2.8155 | 2.8154 | 2.8152 | 2.8151 | 2.8149 | 2.8148 | 2.8146 | 2.8145 | 2.8143 | 2.8142 | 2.8141 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139 | 2.8139
258 | Waitemata |  |  | 2052 | 1080.9681 | 1054.7996 | 1029.2647 | 1004.3479 | 980.0343 | 984.9482 | 989.8867 | 994.85 | 999.8381 | 1004.8513 | 1009.8613 | 1014.8964 | 1019.9565 | 1025.0419 | 1030.1526 | 1034.7198 | 1039.3073 | 1043.9152 | 1048.5434 | 1053.1922 | 1057.252 | 1061.3274 | 1065.4185 | 1069.5253 | 1073.648 | 1079.1028 | 1084.5853 | 1090.0956 | 1095.6339 | 1101.2004 | 1106.3193 | 1111.4621 | 1116.6288 | 1121.8195 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 | 1127.0343 |  | 3320 | 3239.6283 | 3161.2023 | 3084.6749 | 3010 | 3023.5191 | 3037.099 | 3050.7398 | 3064.4419 | 3078.2055 | 3091.9446 | 3105.7451 | 3119.6071 | 3133.531 | 3147.517 | 3156.9028 | 3166.3165 | 3175.7583 | 3185.2282 | 3194.7264 | 3202.4122 | 3210.1165 | 3217.8393 | 3225.5807 | 3233.3407 | 3244.9649 | 3256.6308 | 3268.3386 | 3280.0885 | 3291.8807 | 3306.8742 | 3321.936 | 3337.0664 | 3352.2657 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | 3367.5343 | [6 empty] | 657 | 662 | 667 | 672 | 678.3 | 690 | 702 | 714 | 726 | 738 | 750.4 | 761 | 772 | 783 | 794 | 805 | 816 | 827 | 838 | 849 | 860 | 871 | 882 | 893 | 904 | 915 | 926 | 937 | 948 | 959 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | 970 | [6 empty] | 3.0713 | 3.0713 | 3.0713 | 3.0713 | 3.0713 | 3.0697 | 3.0681 | 3.0665 | 3.0649 | 3.0633 | 3.0618 | 3.0602 | 3.0586 | 3.057 | 3.0554 | 3.051 | 3.0466 | 3.0422 | 3.0378 | 3.0334 | 3.029 | 3.0246 | 3.0203 | 3.0159 | 3.0115 | 3.0071 | 3.0027 | 2.9982 | 2.9938 | 2.9894 | 2.9891 | 2.9888 | 2.9885 | 2.9882 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988 | 2.988
259 | Waitemata |  |  | 2052 | 1224.3861 | 1187.0131 | 1150.7809 | 1115.6546 | 1081.6005 | 1086.7578 | 1091.9396 | 1097.1462 | 1102.3776 | 1107.6339 | 1112.892 | 1118.1751 | 1123.4833 | 1128.8167 | 1134.1753 | 1138.9934 | 1143.832 | 1148.6911 | 1153.5709 | 1158.4713 | 1162.768 | 1167.0807 | 1171.4093 | 1175.754 | 1180.1148 | 1185.8884 | 1191.6903 | 1197.5205 | 1203.3793 | 1209.2667 | 1214.6847 | 1220.127 | 1225.5936 | 1231.0848 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 | 1236.6005 |  | 3430 | 3325.3032 | 3223.8021 | 3125.3992 | 3030 | 3052.3208 | 3074.8061 | 3097.457 | 3120.2747 | 3143.2606 | 3166.2453 | 3189.3981 | 3212.7202 | 3236.2128 | 3259.8773 | 3276.9162 | 3294.0442 | 3311.2618 | 3328.5693 | 3345.9673 | 3361.6351 | 3377.3762 | 3393.191 | 3409.0799 | 3425.0432 | 3445.1215 | 3465.3175 | 3485.6318 | 3506.0653 | 3526.6185 | 3542.415 | 3558.2823 | 3574.2206 | 3590.2304 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | 3606.3118 | [6 empty] | 1926 | 1955 | 1984 | 2013 | 2043.9 | 2081 | 2118 | 2155 | 2192 | 2229 | 2268 | 2305 | 2342 | 2379 | 2416 | 2453 | 2490 | 2527 | 2564 | 2601 | 2638 | 2675 | 2712 | 2749 | 2786 | 2823 | 2860 | 2897 | 2934 | 2971 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | 3002.9 | [6 empty] | 2.8014 | 2.8014 | 2.8014 | 2.8014 | 2.8014 | 2.8086 | 2.8159 | 2.8232 | 2.8305 | 2.8378 | 2.8451 | 2.8523 | 2.8596 | 2.8669 | 2.8742 | 2.877 | 2.8798 | 2.8826 | 2.8854 | 2.8883 | 2.8911 | 2.8939 | 2.8967 | 2.8995 | 2.9023 | 2.9051 | 2.9079 | 2.9107 | 2.9135 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163 | 2.9163
260 | Waitemata |  |  | 2052 | 1557.1181 | 1518.2566 | 1480.365 | 1443.4191 | 1407.3952 | 1420.5716 | 1433.8713 | 1447.2956 | 1460.8456 | 1474.5224 | 1487.9625 | 1501.5252 | 1515.2115 | 1529.0225 | 1542.9595 | 1555.3728 | 1567.886 | 1580.4998 | 1593.2152 | 1606.0328 | 1617.163 | 1628.3703 | 1639.6553 | 1651.0186 | 1662.4605 | 1677.2847 | 1692.241 | 1707.3307 | 1722.5549 | 1737.915 | 1751.7878 | 1765.7713 | 1779.8664 | 1794.0741 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 | 1808.3952 |  | 4160 | 4056.1776 | 3954.9463 | 3856.2414 | 3760 | 3805.8107 | 3852.1795 | 3899.1133 | 3946.6189 | 3994.7033 | 4042.2362 | 4090.3347 | 4139.0055 | 4188.2555 | 4238.0915 | 4277.076 | 4316.4191 | 4356.1241 | 4396.1943 | 4436.6332 | 4472.4877 | 4508.6319 | 4545.0683 | 4581.7991 | 4618.8268 | 4665.2744 | 4712.1891 | 4759.5755 | 4807.4385 | 4855.7829 | 4894.3828 | 4933.2896 | 4972.5056 | 5012.0334 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | 5051.8754 | [6 empty] | 2402 | 2431 | 2460 | 2489 | 2519.8 | 2563 | 2606 | 2649 | 2692 | 2735 | 2778.6 | 2818 | 2858 | 2898 | 2938 | 2978 | 3018 | 3058 | 3098 | 3138 | 3178 | 3218 | 3258 | 3298 | 3338 | 3378 | 3418 | 3458 | 3498 | 3538 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | 3575.9 | [6 empty] | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6791 | 2.6866 | 2.6941 | 2.7016 | 2.7092 | 2.7166 | 2.7241 | 2.7316 | 2.7392 | 2.7467 | 2.7499 | 2.753 | 2.7562 | 2.7593 | 2.7625 | 2.7656 | 2.7688 | 2.772 | 2.7751 | 2.7783 | 2.7814 | 2.7846 | 2.7877 | 2.7909 | 2.794 | 2.7939 | 2.7938 | 2.7938 | 2.7937 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936 | 2.7936
261 | Waitemata |  |  | 2052 | 1482.3186 | 1437.3891 | 1393.8215 | 1351.5745 | 1310.6079 | 1320.5339 | 1330.535 | 1340.6119 | 1350.7651 | 1360.9951 | 1371.1175 | 1381.3152 | 1391.5888 | 1401.9387 | 1412.3656 | 1421.6477 | 1430.9908 | 1440.3953 | 1449.8616 | 1459.3902 | 1467.6737 | 1476.0042 | 1484.3821 | 1492.8075 | 1501.2807 | 1512.3994 | 1523.6004 | 1534.8844 | 1546.252 | 1557.7038 | 1568.1437 | 1578.6536 | 1589.234 | 1599.8853 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 | 1610.6079 |  | 4230 | 4101.7877 | 3977.4615 | 3856.9037 | 3740 | 3773.1232 | 3806.5397 | 3840.2522 | 3874.2633 | 3908.5755 | 3942.6366 | 3976.9944 | 4011.6517 | 4046.611 | 4081.875 | 4108.5604 | 4135.4202 | 4162.4557 | 4189.6679 | 4217.058 | 4240.8724 | 4264.8212 | 4288.9052 | 4313.1253 | 4337.4821 | 4369.4478 | 4401.6491 | 4434.0876 | 4466.7652 | 4499.6837 | 4529.6977 | 4559.9119 | 4590.3276 | 4620.9462 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | 4651.7691 | [6 empty] | 1470 | 1484 | 1498 | 1512 | 1527.3 | 1556 | 1585 | 1614 | 1643 | 1672 | 1698.5 | 1725 | 1752 | 1779 | 1806 | 1833 | 1860 | 1887 | 1914 | 1941 | 1968 | 1995 | 2022 | 2049 | 2076 | 2103 | 2130 | 2157 | 2184 | 2211 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | 2237.5 | [6 empty] | 2.8536 | 2.8536 | 2.8536 | 2.8536 | 2.8536 | 2.8573 | 2.8609 | 2.8646 | 2.8682 | 2.8719 | 2.8755 | 2.8791 | 2.8828 | 2.8864 | 2.8901 | 2.89 | 2.8899 | 2.8898 | 2.8897 | 2.8896 | 2.8895 | 2.8894 | 2.8894 | 2.8893 | 2.8892 | 2.8891 | 2.889 | 2.8889 | 2.8888 | 2.8887 | 2.8886 | 2.8885 | 2.8884 | 2.8883 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882 | 2.8882
262 | Waitemata |  |  | 2052 | 1050.0634 | 1035.7735 | 1021.678 | 1007.7744 | 994.06 | 1029.9327 | 1067.0999 | 1105.6083 | 1145.5064 | 1186.8444 | 1223.7818 | 1261.8688 | 1301.1412 | 1341.6359 | 1383.3908 | 1417.6189 | 1452.694 | 1488.6368 | 1525.469 | 1563.2125 | 1594.0023 | 1625.3987 | 1657.4134 | 1690.0587 | 1723.347 | 1764.3833 | 1806.3969 | 1849.4108 | 1893.449 | 1938.5359 | 1977.2622 | 2016.7622 | 2057.0512 | 2098.1451 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 | 2140.06 |  | 2250 | 2219.3806 | 2189.1779 | 2159.3863 | 2130 | 2206.3825 | 2285.5041 | 2367.4631 | 2452.3611 | 2540.3036 | 2619.6783 | 2701.5332 | 2785.9457 | 2872.9958 | 2962.7658 | 3033.5793 | 3106.0854 | 3180.3244 | 3256.3378 | 3334.168 | 3397.784 | 3462.6138 | 3528.6805 | 3596.0078 | 3664.6197 | 3749.358 | 3836.0556 | 3924.758 | 4015.5115 | 4108.3635 | 4188.2583 | 4269.7067 | 4352.7392 | 4437.3863 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | 4523.6795 | [6 empty] | 7176 | 7266 | 7356 | 7446 | 7536.6 | 7648 | 7760 | 7872 | 7984 | 8096 | 8207.3 | 8305 | 8403 | 8501 | 8599 | 8697 | 8795 | 8893 | 8991 | 9089 | 9187 | 9285 | 9383 | 9481 | 9579 | 9677 | 9775 | 9873 | 9971 | 10069 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | 10161 | [6 empty] | 2.1427 | 2.1427 | 2.1427 | 2.1427 | 2.1427 | 2.1423 | 2.1418 | 2.1413 | 2.1409 | 2.1404 | 2.1406 | 2.1409 | 2.1412 | 2.1414 | 2.1417 | 2.1399 | 2.1382 | 2.1364 | 2.1346 | 2.1329 | 2.1316 | 2.1303 | 2.129 | 2.1277 | 2.1265 | 2.125 | 2.1236 | 2.1222 | 2.1207 | 2.1193 | 2.1182 | 2.1171 | 2.116 | 2.1149 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138 | 2.1138
263 | Waitemata |  |  | 2052 | 837.8781 | 839.207 | 840.5379 | 841.871 | 843.2062 | 880.9836 | 920.4535 | 961.6918 | 1004.7776 | 1049.7938 | 1088.8944 | 1129.4513 | 1171.5189 | 1215.1532 | 1260.4128 | 1296.8664 | 1334.3743 | 1372.967 | 1412.6759 | 1453.5332 | 1486.4514 | 1520.115 | 1554.541 | 1589.7467 | 1625.7497 | 1669.6265 | 1714.6874 | 1760.9645 | 1808.4906 | 1857.2993 | 1898.7855 | 1941.1983 | 1984.5585 | 2028.8873 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 | 2074.2062 |  | 1590 | 1592.4941 | 1594.9922 | 1597.4941 | 1600 | 1673.1587 | 1749.6626 | 1829.6646 | 1913.3246 | 2000.8098 | 2077.436 | 2156.9968 | 2239.6046 | 2325.3761 | 2414.4324 | 2483.7859 | 2555.1316 | 2628.5266 | 2704.0299 | 2781.7019 | 2844.3215 | 2908.3507 | 2973.8213 | 3040.7657 | 3109.2172 | 3192.6844 | 3278.3924 | 3366.4012 | 3456.7725 | 3549.57 | 3628.4835 | 3709.1514 | 3791.6127 | 3875.9073 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | 3962.0759 | [6 empty] | 2639 | 2672 | 2705 | 2738 | 2772.7 | 2815 | 2857 | 2899 | 2941 | 2983 | 3025.6 | 3062 | 3099 | 3136 | 3173 | 3210 | 3247 | 3284 | 3321 | 3358 | 3395 | 3432 | 3469 | 3506 | 3543 | 3580 | 3617 | 3654 | 3691 | 3728 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | 3761.8 | [6 empty] | 1.8977 | 1.8976 | 1.8976 | 1.8976 | 1.8975 | 1.8992 | 1.9009 | 1.9025 | 1.9042 | 1.9059 | 1.9078 | 1.9098 | 1.9117 | 1.9136 | 1.9156 | 1.9152 | 1.9149 | 1.9145 | 1.9141 | 1.9138 | 1.9135 | 1.9132 | 1.913 | 1.9127 | 1.9125 | 1.9122 | 1.9119 | 1.9117 | 1.9114 | 1.9111 | 1.9109 | 1.9108 | 1.9106 | 1.9104 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102 | 1.9102
264 | Waitemata |  |  | 2052 | 859.0854 | 869.481 | 880.0023 | 890.651 | 901.4286 | 952.8316 | 1007.1659 | 1064.5985 | 1125.3061 | 1189.4755 | 1243.1429 | 1299.2316 | 1357.851 | 1419.1152 | 1483.1435 | 1533.4148 | 1585.3901 | 1639.127 | 1694.6854 | 1752.127 | 1797.6415 | 1844.3383 | 1892.2481 | 1941.4025 | 1991.8337 | 2052.5861 | 2115.1915 | 2179.7064 | 2246.189 | 2314.6994 | 2372.3057 | 2431.3456 | 2491.8549 | 2553.87 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 | 2617.4286 |  | 1900 | 1922.111 | 1944.4794 | 1967.108 | 1990 | 2103.2165 | 2222.8742 | 2349.3395 | 2482.9998 | 2624.2644 | 2744.2054 | 2869.6283 | 3000.7835 | 3137.9331 | 3281.3511 | 3391.3154 | 3504.9647 | 3622.4227 | 3743.8169 | 3869.2792 | 3969.2439 | 4071.7912 | 4176.9879 | 4284.9023 | 4395.6048 | 4529.0092 | 4666.4623 | 4808.087 | 4954.0099 | 5104.3616 | 5229.6385 | 5357.9902 | 5489.4919 | 5624.2212 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | 5762.2571 | [6 empty] | 5999 | 6084 | 6169 | 6254 | 6338.2 | 6435 | 6532 | 6629 | 6726 | 6823 | 6921.9 | 7014 | 7106 | 7198 | 7290 | 7382 | 7474 | 7566 | 7658 | 7750 | 7842 | 7934 | 8026 | 8118 | 8210 | 8302 | 8394 | 8486 | 8578 | 8670 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | 8761.4 | [6 empty] | 2.2117 | 2.2106 | 2.2096 | 2.2086 | 2.2076 | 2.2073 | 2.2071 | 2.2068 | 2.2065 | 2.2062 | 2.2075 | 2.2087 | 2.21 | 2.2112 | 2.2124 | 2.2116 | 2.2108 | 2.21 | 2.2092 | 2.2083 | 2.208 | 2.2077 | 2.2074 | 2.2071 | 2.2068 | 2.2065 | 2.2062 | 2.2058 | 2.2055 | 2.2052 | 2.2045 | 2.2037 | 2.203 | 2.2022 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015 | 2.2015
265 | Albert - Eden |  |  | 2052 | 982.8551 | 975.7325 | 968.6615 | 961.6418 | 954.6729 | 990.0019 | 1026.6382 | 1064.6304 | 1104.0285 | 1144.8846 | 1181.2806 | 1218.8335 | 1257.5803 | 1297.5588 | 1338.8082 | 1372.5804 | 1407.2045 | 1442.7019 | 1479.0948 | 1516.4058 | 1546.8123 | 1577.8285 | 1609.4666 | 1641.7392 | 1674.6588 | 1715.1965 | 1756.7155 | 1799.2396 | 1842.793 | 1887.4007 | 1925.6713 | 1964.7179 | 2004.5563 | 2045.2025 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 | 2086.6729 |  | 2790 | 2769.7813 | 2749.7091 | 2729.7823 | 2710 | 2794.6597 | 2881.9642 | 2971.9961 | 3064.8405 | 3160.5854 | 3248.5333 | 3338.9286 | 3431.8392 | 3527.3352 | 3625.4885 | 3703.9969 | 3784.2054 | 3866.1508 | 3949.8707 | 4035.4035 | 4105.9468 | 4177.7232 | 4250.7544 | 4325.0622 | 4400.6691 | 4494.7646 | 4590.872 | 4689.0345 | 4789.2959 | 4891.701 | 4980.413 | 5070.7338 | 5162.6926 | 5256.3191 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | 5351.6435 | [6 empty] | 5296 | 5367 | 5438 | 5509 | 5581.2 | 5661 | 5741 | 5821 | 5901 | 5981 | 6062.3 | 6137 | 6212 | 6287 | 6362 | 6437 | 6512 | 6587 | 6662 | 6737 | 6812 | 6887 | 6962 | 7037 | 7112 | 7187 | 7262 | 7337 | 7412 | 7487 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | 7563.9 | [6 empty] | 2.8387 | 2.8387 | 2.8387 | 2.8387 | 2.8387 | 2.8229 | 2.8072 | 2.7916 | 2.7761 | 2.7606 | 2.75 | 2.7394 | 2.7289 | 2.7184 | 2.708 | 2.6986 | 2.6892 | 2.6798 | 2.6705 | 2.6612 | 2.6545 | 2.6478 | 2.6411 | 2.6344 | 2.6278 | 2.6206 | 2.6133 | 2.6061 | 2.5989 | 2.5918 | 2.5863 | 2.5809 | 2.5755 | 2.5701 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647 | 2.5647
266 | Waitemata |  |  | 2052 | 997.8324 | 961.9231 | 927.306 | 893.9347 | 861.7644 | 900.5966 | 941.1787 | 983.5895 | 1027.9114 | 1074.2305 | 1114.4296 | 1156.133 | 1199.3971 | 1244.2801 | 1290.8427 | 1328.2378 | 1366.7162 | 1406.3092 | 1447.0493 | 1488.9696 | 1522.6885 | 1557.1711 | 1592.4345 | 1628.4965 | 1665.3751 | 1710.3952 | 1756.6323 | 1804.1193 | 1852.8901 | 1902.9792 | 1945.5852 | 1989.1452 | 2033.6803 | 2079.2126 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 | 2125.7644 |  | 2200 | 2120.8278 | 2044.5048 | 1970.9285 | 1900 | 1991.7167 | 2087.8607 | 2188.6457 | 2294.2959 | 2405.046 | 2503.385 | 2605.7449 | 2712.2903 | 2823.1921 | 2938.6285 | 3029.0134 | 3122.1783 | 3218.2088 | 3317.1929 | 3419.2215 | 3503.1492 | 3589.137 | 3677.2354 | 3767.4963 | 3859.9727 | 3971.5533 | 4086.3593 | 4204.4841 | 4326.0235 | 4451.0763 | 4549.6822 | 4650.4725 | 4753.4957 | 4858.8012 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | 4966.4395 | [6 empty] | 3362 | 3406 | 3450 | 3494 | 3536.2 | 3588 | 3639 | 3690 | 3741 | 3792 | 3845 | 3893 | 3941 | 3989 | 4037 | 4085 | 4133 | 4181 | 4229 | 4277 | 4325 | 4373 | 4421 | 4469 | 4517 | 4565 | 4613 | 4661 | 4709 | 4757 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | 4798.1 | [6 empty] | 2.2048 | 2.2048 | 2.2048 | 2.2048 | 2.2048 | 2.2116 | 2.2183 | 2.2252 | 2.232 | 2.2389 | 2.2463 | 2.2538 | 2.2614 | 2.2689 | 2.2765 | 2.2805 | 2.2844 | 2.2884 | 2.2924 | 2.2964 | 2.3006 | 2.3049 | 2.3092 | 2.3135 | 2.3178 | 2.322 | 2.3262 | 2.3305 | 2.3347 | 2.339 | 2.3385 | 2.3379 | 2.3374 | 2.3368 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363 | 2.3363
267 | Albert - Eden |  |  | 2052 | 1037.4553 | 1020.2715 | 1003.3722 | 986.7529 | 970.4089 | 1002.3335 | 1035.3083 | 1069.368 | 1104.5481 | 1140.8856 | 1173.7032 | 1207.4648 | 1242.1976 | 1277.9295 | 1314.6891 | 1345.0963 | 1376.2068 | 1408.0368 | 1440.603 | 1473.9224 | 1501.2731 | 1529.1313 | 1557.5065 | 1586.4083 | 1615.8463 | 1652.3248 | 1689.6269 | 1727.771 | 1766.7763 | 1806.6621 | 1841.0752 | 1876.1439 | 1911.8805 | 1948.2979 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 | 1985.4089 |  | 2940 | 2891.3034 | 2843.4134 | 2796.3167 | 2750 | 2842.8742 | 2938.885 | 3038.1383 | 3140.7437 | 3246.8143 | 3344.7307 | 3445.6002 | 3549.5116 | 3656.5567 | 3766.8301 | 3854.8219 | 3944.8692 | 4037.0199 | 4131.3233 | 4227.8295 | 4308.3574 | 4390.419 | 4474.0438 | 4559.2613 | 4646.102 | 4753.0597 | 4862.4798 | 4974.4188 | 5088.9347 | 5206.0869 | 5302.6277 | 5400.9588 | 5501.1133 | 5603.125 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | 5707.0284 | [6 empty] | 2272 | 2303 | 2334 | 2365 | 2394.9 | 2435 | 2475 | 2515 | 2555 | 2595 | 2636.3 | 2675 | 2713 | 2751 | 2789 | 2827 | 2865 | 2903 | 2941 | 2979 | 3017 | 3055 | 3093 | 3131 | 3169 | 3207 | 3245 | 3283 | 3321 | 3359 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | 3400.4 | [6 empty] | 2.8339 | 2.8339 | 2.8339 | 2.8339 | 2.8339 | 2.8363 | 2.8387 | 2.8411 | 2.8435 | 2.8459 | 2.8497 | 2.8536 | 2.8574 | 2.8613 | 2.8652 | 2.8658 | 2.8665 | 2.8671 | 2.8678 | 2.8684 | 2.8698 | 2.8712 | 2.8726 | 2.874 | 2.8753 | 2.8766 | 2.8778 | 2.8791 | 2.8804 | 2.8816 | 2.8802 | 2.8788 | 2.8773 | 2.8759 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745 | 2.8745
268 | Albert - Eden |  |  | 2052 | 814.6815 | 794.0399 | 773.9213 | 754.3125 | 735.2004 | 751.2775 | 767.7061 | 784.494 | 801.649 | 819.1791 | 835.6286 | 852.4084 | 869.5251 | 886.9855 | 904.7966 | 919.955 | 935.3673 | 951.0378 | 966.9708 | 983.1708 | 996.7538 | 1010.5244 | 1024.4853 | 1038.639 | 1052.9883 | 1071.1581 | 1089.6413 | 1108.4435 | 1127.5702 | 1147.0269 | 1164.1431 | 1181.5147 | 1199.1455 | 1217.0395 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 | 1235.2004 |  | 2460 | 2397.6709 | 2336.9211 | 2277.7104 | 2220 | 2268.5317 | 2318.1244 | 2368.8012 | 2420.5859 | 2473.5026 | 2523.7258 | 2574.9687 | 2627.2521 | 2680.5971 | 2735.0252 | 2778.6827 | 2823.037 | 2868.0993 | 2913.8809 | 2960.3933 | 2999.5378 | 3039.1999 | 3079.3864 | 3120.1043 | 3161.3606 | 3213.7062 | 3266.9185 | 3321.0119 | 3376.001 | 3431.9006 | 3481.043 | 3530.889 | 3581.4488 | 3632.7326 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | 3684.7507 | [6 empty] | 832 | 843 | 854 | 865 | 876.6 | 894 | 912 | 930 | 948 | 966 | 982.9 | 999 | 1015 | 1031 | 1047 | 1063 | 1079 | 1095 | 1111 | 1127 | 1143 | 1159 | 1175 | 1191 | 1207 | 1223 | 1239 | 1255 | 1271 | 1287 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | 1304.8 | [6 empty] | 3.0196 | 3.0196 | 3.0196 | 3.0196 | 3.0196 | 3.0196 | 3.0195 | 3.0195 | 3.0195 | 3.0195 | 3.0202 | 3.0208 | 3.0215 | 3.0221 | 3.0228 | 3.0205 | 3.0181 | 3.0158 | 3.0134 | 3.0111 | 3.0093 | 3.0075 | 3.0058 | 3.004 | 3.0023 | 3.0002 | 2.9982 | 2.9961 | 2.994 | 2.992 | 2.9902 | 2.9884 | 2.9867 | 2.9849 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831 | 2.9831
269 | Albert - Eden |  |  | 2052 | 920.4808 | 909.1523 | 897.9632 | 886.9119 | 875.9966 | 896.4349 | 917.3501 | 938.7533 | 960.6558 | 983.0694 | 1003.9921 | 1025.3601 | 1047.1829 | 1069.4701 | 1092.2317 | 1111.5682 | 1131.2471 | 1151.2743 | 1171.6561 | 1192.3987 | 1209.759 | 1227.3722 | 1245.2417 | 1263.3714 | 1281.7651 | 1304.9057 | 1328.4642 | 1352.4479 | 1376.8647 | 1401.7222 | 1423.4904 | 1445.5967 | 1468.0462 | 1490.8443 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 | 1513.9966 |  | 2690 | 2656.8938 | 2624.1951 | 2591.8988 | 2560 | 2634.3696 | 2710.8997 | 2789.6531 | 2870.6943 | 2954.0898 | 3033.6296 | 3115.3111 | 3199.1919 | 3285.3313 | 3373.7899 | 3444.9767 | 3517.6656 | 3591.8882 | 3667.6768 | 3745.0646 | 3812.3239 | 3880.7911 | 3950.4879 | 4021.4365 | 4093.6592 | 4181.1751 | 4270.5618 | 4361.8595 | 4455.109 | 4550.352 | 4620.1195 | 4690.9567 | 4762.88 | 4835.9061 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | 4910.0518 | [6 empty] | 358 | 365 | 372 | 379 | 384.6 | 396 | 407 | 418 | 429 | 440 | 452.3 | 464 | 476 | 488 | 500 | 512 | 524 | 536 | 548 | 560 | 572 | 584 | 596 | 608 | 620 | 632 | 644 | 656 | 668 | 680 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | [6 empty] | 2.9224 | 2.9224 | 2.9224 | 2.9224 | 2.9224 | 2.9387 | 2.9551 | 2.9717 | 2.9883 | 3.005 | 3.0216 | 3.0383 | 3.055 | 3.0719 | 3.0889 | 3.0992 | 3.1095 | 3.1199 | 3.1303 | 3.1408 | 3.1513 | 3.1619 | 3.1725 | 3.1831 | 3.1938 | 3.2042 | 3.2147 | 3.2252 | 3.2357 | 3.2463 | 3.2456 | 3.245 | 3.2444 | 3.2437 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431 | 3.2431
270 | Albert - Eden |  |  | 2052 | 812.1876 | 795.7125 | 779.5716 | 763.7581 | 748.2654 | 774.8594 | 802.3986 | 830.9166 | 860.4481 | 891.0292 | 918.4046 | 946.621 | 975.7043 | 1005.6811 | 1036.5789 | 1061.9531 | 1087.9485 | 1114.5801 | 1141.8637 | 1169.8151 | 1192.6445 | 1215.9193 | 1239.6484 | 1263.8406 | 1288.5049 | 1318.9999 | 1350.2167 | 1382.1724 | 1414.8843 | 1448.3704 | 1477.1802 | 1506.5632 | 1536.5305 | 1567.094 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 | 1598.2654 |  | 2160 | 2116.1848 | 2073.2583 | 2031.2026 | 1990 | 2076.0617 | 2165.8453 | 2259.5117 | 2357.229 | 2459.1723 | 2553.23 | 2650.8853 | 2752.2757 | 2857.544 | 2966.8386 | 3053.8169 | 3143.3451 | 3235.498 | 3330.3526 | 3427.988 | 3511.2398 | 3596.5134 | 3683.858 | 3773.3239 | 3864.9625 | 3974.468 | 4087.0762 | 4202.8749 | 4321.9545 | 4444.408 | 4532.2096 | 4621.7458 | 4713.0508 | 4806.1597 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | 4901.1079 | [6 empty] | 2074 | 2097 | 2120 | 2143 | 2167.3 | 2205 | 2243 | 2281 | 2319 | 2357 | 2392.3 | 2425 | 2458 | 2491 | 2524 | 2557 | 2590 | 2623 | 2656 | 2689 | 2722 | 2755 | 2788 | 2821 | 2854 | 2887 | 2920 | 2953 | 2986 | 3019 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | 3052.3 | [6 empty] | 2.6595 | 2.6595 | 2.6595 | 2.6595 | 2.6595 | 2.6793 | 2.6992 | 2.7193 | 2.7395 | 2.7599 | 2.7801 | 2.8004 | 2.8208 | 2.8414 | 2.8621 | 2.8757 | 2.8892 | 2.9029 | 2.9166 | 2.9304 | 2.9441 | 2.9579 | 2.9717 | 2.9856 | 2.9996 | 3.0132 | 3.027 | 3.0408 | 3.0546 | 3.0686 | 3.0681 | 3.0677 | 3.0673 | 3.0669 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665
271 | Albert - Eden |  |  | 2052 | 770.3451 | 750.8717 | 731.8906 | 713.3893 | 695.3557 | 719.5604 | 744.6076 | 770.5266 | 797.3479 | 825.1028 | 850.0089 | 875.6669 | 902.0993 | 929.3296 | 957.3818 | 980.4743 | 1004.1237 | 1028.3436 | 1053.1476 | 1078.55 | 1099.3305 | 1120.5114 | 1142.1004 | 1164.1054 | 1186.5344 | 1214.2188 | 1242.5492 | 1271.5406 | 1301.2084 | 1331.5685 | 1357.6815 | 1384.3065 | 1411.4537 | 1439.1333 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 | 1467.3557 |  | 2260 | 2202.87 | 2147.1842 | 2092.9061 | 2040 | 2114.6123 | 2191.9535 | 2272.1235 | 2355.2257 | 2441.3672 | 2519.9833 | 2601.1309 | 2684.8916 | 2771.3496 | 2860.5916 | 2931.4064 | 3003.9743 | 3078.3386 | 3154.5438 | 3232.6355 | 3297.4423 | 3363.5483 | 3430.9797 | 3499.7628 | 3569.9249 | 3655.8851 | 3743.9151 | 3834.0649 | 3926.3853 | 4020.9287 | 4098.5099 | 4177.588 | 4258.1918 | 4340.3509 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | 4424.0951 | [6 empty] | 1454 | 1471 | 1488 | 1505 | 1521 | 1545 | 1569 | 1593 | 1617 | 1641 | 1664.7 | 1687 | 1709 | 1731 | 1753 | 1775 | 1797 | 1819 | 1841 | 1863 | 1885 | 1907 | 1929 | 1951 | 1973 | 1995 | 2017 | 2039 | 2061 | 2083 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | 2111.6 | [6 empty] | 2.9338 | 2.9338 | 2.9338 | 2.9338 | 2.9338 | 2.9388 | 2.9438 | 2.9488 | 2.9538 | 2.9589 | 2.9647 | 2.9705 | 2.9763 | 2.9821 | 2.9879 | 2.9898 | 2.9916 | 2.9935 | 2.9953 | 2.9972 | 2.9995 | 3.0018 | 3.0041 | 3.0064 | 3.0087 | 3.0109 | 3.0131 | 3.0153 | 3.0175 | 3.0197 | 3.0188 | 3.0178 | 3.0169 | 3.0159 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015
272 | Albert - Eden |  |  | 2052 | 1045.3275 | 1043.5692 | 1041.8138 | 1040.0614 | 1038.3119 | 1060.5967 | 1083.3597 | 1106.6114 | 1130.362 | 1154.6224 | 1177.4202 | 1200.6682 | 1224.3752 | 1248.5502 | 1273.2026 | 1294.2227 | 1315.5897 | 1337.3095 | 1359.388 | 1381.8309 | 1400.6727 | 1419.7715 | 1439.1306 | 1458.7538 | 1478.6445 | 1503.8504 | 1529.4859 | 1555.5585 | 1582.0755 | 1609.0446 | 1632.787 | 1656.8797 | 1681.3279 | 1706.1369 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 | 1731.3119 |  | 2980 | 2974.9874 | 2969.9832 | 2964.9874 | 2960 | 3033.5828 | 3108.9949 | 3186.2816 | 3265.4896 | 3346.6666 | 3423.8612 | 3502.8365 | 3583.6333 | 3666.2939 | 3750.8611 | 3818.6239 | 3887.6109 | 3957.8443 | 4029.3464 | 4102.1404 | 4164.3431 | 4227.4891 | 4291.5927 | 4356.6682 | 4422.7305 | 4504.881 | 4588.5574 | 4673.788 | 4760.6018 | 4849.0281 | 4920.7561 | 4993.545 | 5067.4107 | 5142.369 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | 5218.4362 | [6 empty] | 939 | 952 | 965 | 978 | 991.5 | 1007 | 1023 | 1039 | 1055 | 1071 | 1086.5 | 1103 | 1120 | 1137 | 1154 | 1171 | 1188 | 1205 | 1222 | 1239 | 1256 | 1273 | 1290 | 1307 | 1324 | 1341 | 1358 | 1375 | 1392 | 1409 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | 1420.6 | [6 empty] | 2.8508 | 2.8508 | 2.8508 | 2.8508 | 2.8508 | 2.8603 | 2.8698 | 2.8793 | 2.8889 | 2.8985 | 2.9079 | 2.9174 | 2.9269 | 2.9364 | 2.946 | 2.9505 | 2.955 | 2.9596 | 2.9641 | 2.9686 | 2.9731 | 2.9776 | 2.9821 | 2.9866 | 2.9911 | 2.9956 | 3.0001 | 3.0046 | 3.0091 | 3.0136 | 3.0137 | 3.0138 | 3.0139 | 3.014 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142 | 3.0142
273 | Albert - Eden |  |  | 2052 | 1108.5258 | 1087.9139 | 1067.6853 | 1047.8328 | 1028.3494 | 1049.2342 | 1070.5431 | 1092.2848 | 1114.4681 | 1137.1018 | 1158.4593 | 1180.2178 | 1202.3851 | 1224.9687 | 1247.9765 | 1267.6305 | 1287.5941 | 1307.8721 | 1328.4694 | 1349.3911 | 1366.9857 | 1384.8098 | 1402.8662 | 1421.1581 | 1439.6884 | 1463.2305 | 1487.1574 | 1511.4757 | 1536.1916 | 1561.3116 | 1583.4806 | 1605.9644 | 1628.7674 | 1651.8942 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 | 1675.3494 |  | 3180 | 3120.8712 | 3062.8418 | 3005.8914 | 2950 | 3017.3981 | 3086.3361 | 3156.8491 | 3228.9731 | 3302.7449 | 3373.2737 | 3445.3086 | 3518.8818 | 3594.0262 | 3670.7752 | 3732.2782 | 3794.8117 | 3858.3929 | 3923.0394 | 3988.769 | 4045.012 | 4102.0481 | 4159.8885 | 4218.5443 | 4278.0273 | 4352.3649 | 4427.9942 | 4504.9377 | 4583.2182 | 4662.859 | 4728.1388 | 4794.3325 | 4861.4529 | 4929.5131 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | 4998.526 | [6 empty] | 1306 | 1321 | 1336 | 1351 | 1367 | 1394 | 1421 | 1448 | 1475 | 1502 | 1526 | 1550 | 1574 | 1598 | 1622 | 1646 | 1670 | 1694 | 1718 | 1742 | 1766 | 1790 | 1814 | 1838 | 1862 | 1886 | 1910 | 1934 | 1958 | 1982 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | 1998.3 | [6 empty] | 2.8687 | 2.8687 | 2.8687 | 2.8687 | 2.8687 | 2.8758 | 2.883 | 2.8901 | 2.8973 | 2.9045 | 2.9119 | 2.9192 | 2.9266 | 2.934 | 2.9414 | 2.9443 | 2.9472 | 2.9501 | 2.9531 | 2.956 | 2.9591 | 2.9622 | 2.9653 | 2.9684 | 2.9715 | 2.9745 | 2.9775 | 2.9805 | 2.9835 | 2.9865 | 2.9859 | 2.9853 | 2.9847 | 2.9842 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836 | 2.9836
274 | Albert - Eden |  |  | 2052 | 1042.2299 | 1019.4622 | 997.1919 | 975.4081 | 954.1001 | 971.1177 | 988.4388 | 1006.0688 | 1024.0133 | 1042.2778 | 1059.6674 | 1077.3472 | 1095.322 | 1113.5966 | 1132.1761 | 1148.2063 | 1164.4634 | 1180.9507 | 1197.6715 | 1214.629 | 1228.9934 | 1243.5277 | 1258.2339 | 1273.114 | 1288.1701 | 1307.3982 | 1326.9133 | 1346.7198 | 1366.8219 | 1387.224 | 1405.3209 | 1423.6538 | 1442.2259 | 1461.0403 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 | 1480.1001 |  | 2720 | 2660.5812 | 2602.4604 | 2545.6092 | 2490 | 2531.243 | 2573.169 | 2615.7895 | 2659.116 | 2703.1601 | 2745.3331 | 2788.164 | 2831.6632 | 2875.841 | 2920.708 | 2956.6565 | 2993.0474 | 3029.8862 | 3067.1784 | 3104.9297 | 3136.5041 | 3168.3995 | 3200.6193 | 3233.1668 | 3266.0453 | 3308.8799 | 3352.2763 | 3396.2418 | 3440.784 | 3485.9104 | 3528.8428 | 3572.304 | 3616.3005 | 3660.8388 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | 3705.9257 | [6 empty] | 772 | 789 | 806 | 823 | 838.1 | 859 | 880 | 901 | 922 | 943 | 965.2 | 987 | 1009 | 1031 | 1053 | 1075 | 1097 | 1119 | 1141 | 1163 | 1185 | 1207 | 1229 | 1251 | 1273 | 1295 | 1317 | 1339 | 1361 | 1383 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | 1404.2 | [6 empty] | 2.6098 | 2.6098 | 2.6098 | 2.6098 | 2.6098 | 2.6065 | 2.6033 | 2.6 | 2.5968 | 2.5935 | 2.5907 | 2.588 | 2.5852 | 2.5825 | 2.5797 | 2.575 | 2.5703 | 2.5656 | 2.561 | 2.5563 | 2.5521 | 2.5479 | 2.5437 | 2.5396 | 2.5354 | 2.5309 | 2.5264 | 2.5219 | 2.5174 | 2.5129 | 2.5111 | 2.5093 | 2.5074 | 2.5056 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038 | 2.5038
275 | Albert - Eden |  |  | 2052 | 286.3461 | 283.9019 | 281.4787 | 279.0761 | 276.694 | 294.2173 | 312.8505 | 332.6636 | 353.7316 | 376.1338 | 394.522 | 413.809 | 434.039 | 455.2579 | 477.5142 | 494.7511 | 512.6101 | 531.1139 | 550.2855 | 570.1492 | 585.7563 | 601.7906 | 618.2638 | 635.1879 | 652.5754 | 673.4066 | 694.9028 | 717.0851 | 739.9756 | 763.5968 | 783.3658 | 803.6465 | 824.4524 | 845.7969 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 | 867.694 |  | 890 | 882.4033 | 874.8714 | 867.4038 | 860 | 912.4451 | 968.0884 | 1027.125 | 1089.7618 | 1156.2184 | 1212.6453 | 1271.8259 | 1333.8947 | 1398.9927 | 1467.2676 | 1519.4365 | 1573.4602 | 1629.4047 | 1687.3383 | 1747.3318 | 1795.0412 | 1844.0533 | 1894.4037 | 1946.1288 | 1999.2662 | 2063.0001 | 2128.7657 | 2196.6278 | 2266.6532 | 2338.911 | 2398.3055 | 2459.2082 | 2521.6574 | 2585.6926 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | 2651.3538 | [6 empty] | 1893 | 1920 | 1947 | 1974 | 2000.1 | 2032 | 2064 | 2096 | 2128 | 2160 | 2189.7 | 2221 | 2253 | 2285 | 2317 | 2349 | 2381 | 2413 | 2445 | 2477 | 2509 | 2541 | 2573 | 2605 | 2637 | 2669 | 2701 | 2733 | 2765 | 2797 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | 2820.4 | [6 empty] | 3.1081 | 3.1081 | 3.1081 | 3.1081 | 3.1081 | 3.1013 | 3.0944 | 3.0876 | 3.0808 | 3.074 | 3.0737 | 3.0735 | 3.0732 | 3.073 | 3.0727 | 3.0711 | 3.0695 | 3.0679 | 3.0663 | 3.0647 | 3.0645 | 3.0643 | 3.0641 | 3.0639 | 3.0637 | 3.0635 | 3.0634 | 3.0633 | 3.0631 | 3.063 | 3.0615 | 3.0601 | 3.0586 | 3.0571 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556 | 3.0556
276 | Waitemata |  |  | 2052 | 364.7292 | 363.3398 | 361.9556 | 360.5767 | 359.203 | 417.723 | 485.7769 | 564.9179 | 656.9522 | 763.9804 | 832.9054 | 908.0489 | 989.9716 | 1079.2852 | 1176.6566 | 1244.0376 | 1315.2771 | 1390.596 | 1470.2282 | 1554.4204 | 1616.5546 | 1681.1724 | 1748.3732 | 1818.2602 | 1890.9407 | 1973.9049 | 2060.5092 | 2150.9131 | 2245.2835 | 2343.7943 | 2423.1215 | 2505.1335 | 2589.9213 | 2677.5787 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 | 2768.203 |  | 1320 | 1314.9713 | 1309.9618 | 1304.9714 | 1300 | 1476.2024 | 1676.2872 | 1903.4917 | 2161.4914 | 2454.4606 | 2654.1465 | 2870.0782 | 3103.5773 | 3356.073 | 3629.1109 | 3817.8524 | 4016.4098 | 4225.2938 | 4445.0413 | 4676.2174 | 4846.6213 | 5023.2348 | 5206.2842 | 5396.004 | 5592.6373 | 5819.1893 | 6054.9186 | 6300.1971 | 6555.4116 | 6820.9646 | 7043.1306 | 7272.5328 | 7509.4069 | 7753.9962 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | 8006.5521 | [6 empty] | 7785 | 7884 | 7983 | 8082 | 8181 | 8304 | 8427 | 8550 | 8673 | 8796 | 8921.6 | 9028 | 9135 | 9242 | 9349 | 9456 | 9563 | 9670 | 9777 | 9884 | 9991 | 10098 | 10205 | 10312 | 10419 | 10526 | 10633 | 10740 | 10847 | 10954 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | 11056.7 | [6 empty] | 3.6191 | 3.6191 | 3.6191 | 3.6191 | 3.6191 | 3.5339 | 3.4507 | 3.3695 | 3.2902 | 3.2127 | 3.1866 | 3.1607 | 3.135 | 3.1095 | 3.0843 | 3.0689 | 3.0537 | 3.0385 | 3.0234 | 3.0083 | 2.9981 | 2.9879 | 2.9778 | 2.9677 | 2.9576 | 2.9481 | 2.9386 | 2.9291 | 2.9196 | 2.9102 | 2.9066 | 2.9031 | 2.8995 | 2.8959 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923 | 2.8923
277 | Albert - Eden |  |  | 2052 | 1172.8705 | 1156.8657 | 1141.0794 | 1125.5085 | 1110.1501 | 1114.4831 | 1118.8329 | 1123.1997 | 1127.5836 | 1131.9846 | 1136.4021 | 1140.8368 | 1145.2889 | 1149.7583 | 1154.2451 | 1158.2921 | 1162.3533 | 1166.4287 | 1170.5184 | 1174.6224 | 1178.2307 | 1181.8501 | 1185.4805 | 1189.1222 | 1192.775 | 1197.5442 | 1202.3326 | 1207.1401 | 1211.9668 | 1216.8128 | 1221.2478 | 1225.699 | 1230.1664 | 1234.6501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 | 1239.1501 |  | 3740 | 3688.9649 | 3638.6261 | 3588.9743 | 3540 | 3557.0225 | 3574.1269 | 3591.3135 | 3608.5828 | 3625.9351 | 3643.377 | 3660.9028 | 3678.5129 | 3696.2078 | 3713.9877 | 3726.0121 | 3738.0754 | 3750.1777 | 3762.3192 | 3774.5001 | 3785.2275 | 3795.9854 | 3806.7739 | 3817.593 | 3828.4429 | 3842.6088 | 3856.8271 | 3871.098 | 3885.4217 | 3899.7984 | 3912.9213 | 3926.0883 | 3939.2996 | 3952.5554 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | 3965.8558 | [6 empty] | 1936 | 1959 | 1982 | 2005 | 2027.6 | 2056 | 2085 | 2114 | 2143 | 2172 | 2198.9 | 2226 | 2253 | 2280 | 2307 | 2334 | 2361 | 2388 | 2415 | 2442 | 2469 | 2496 | 2523 | 2550 | 2577 | 2604 | 2631 | 2658 | 2685 | 2712 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | [6 empty] | 3.1888 | 3.1888 | 3.1888 | 3.1888 | 3.1888 | 3.1916 | 3.1945 | 3.1974 | 3.2003 | 3.2032 | 3.2061 | 3.209 | 3.2119 | 3.2148 | 3.2177 | 3.2168 | 3.216 | 3.2151 | 3.2142 | 3.2134 | 3.2126 | 3.2119 | 3.2112 | 3.2104 | 3.2097 | 3.2087 | 3.2078 | 3.2068 | 3.2059 | 3.2049 | 3.204 | 3.2031 | 3.2022 | 3.2014 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005 | 3.2005
278 | Albert - Eden |  |  | 2052 | 840.8528 | 826.474 | 812.341 | 798.4497 | 784.796 | 786.6348 | 788.4781 | 790.3256 | 792.1774 | 794.0336 | 795.9083 | 797.7875 | 799.671 | 801.5591 | 803.4515 | 805.2001 | 806.9525 | 808.7087 | 810.4687 | 812.2326 | 813.809 | 815.3885 | 816.971 | 818.5566 | 820.1453 | 822.2658 | 824.3918 | 826.5234 | 828.6604 | 830.803 | 832.792 | 834.7858 | 836.7844 | 838.7878 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 | 840.796 |  | 2850 | 2801.2641 | 2753.3616 | 2706.2782 | 2660 | 2662.6589 | 2665.3204 | 2667.9846 | 2670.6514 | 2673.3209 | 2676.0168 | 2678.7153 | 2681.4166 | 2684.1206 | 2686.8273 | 2686.9392 | 2687.0511 | 2687.163 | 2687.2749 | 2687.3868 | 2686.8115 | 2686.2363 | 2685.6612 | 2685.0863 | 2684.5115 | 2685.5863 | 2686.6615 | 2687.7372 | 2688.8132 | 2689.8898 | 2696.2736 | 2702.6726 | 2709.0868 | 2715.5162 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | 2721.9609 | [6 empty] | 874 | 885 | 896 | 907 | 918.4 | 930 | 942 | 954 | 966 | 978 | 989.7 | 1001 | 1012 | 1023 | 1034 | 1045 | 1056 | 1067 | 1078 | 1089 | 1100 | 1111 | 1122 | 1133 | 1144 | 1155 | 1166 | 1177 | 1188 | 1199 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | 1219.6 | [6 empty] | 3.3894 | 3.3894 | 3.3894 | 3.3894 | 3.3894 | 3.3849 | 3.3803 | 3.3758 | 3.3713 | 3.3668 | 3.3622 | 3.3577 | 3.3531 | 3.3486 | 3.3441 | 3.337 | 3.3299 | 3.3228 | 3.3157 | 3.3086 | 3.3015 | 3.2944 | 3.2873 | 3.2803 | 3.2732 | 3.2661 | 3.259 | 3.2519 | 3.2448 | 3.2377 | 3.2376 | 3.2376 | 3.2375 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374 | 3.2374
279 | Albert - Eden |  |  | 2052 | 523.876 | 503.2072 | 483.3539 | 464.2839 | 445.9662 | 448.6217 | 451.293 | 453.9803 | 456.6835 | 459.4028 | 462.1105 | 464.8341 | 467.5737 | 470.3296 | 473.1016 | 475.5834 | 478.0782 | 480.5861 | 483.1072 | 485.6415 | 487.8554 | 490.0793 | 492.3135 | 494.5578 | 496.8123 | 499.7857 | 502.7769 | 505.7861 | 508.8132 | 511.8585 | 514.6494 | 517.4556 | 520.277 | 523.1139 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 | 525.9662 |  | 1950 | 1873.0656 | 1799.1665 | 1728.183 | 1660 | 1669.99 | 1680.0401 | 1690.1507 | 1700.3221 | 1710.5548 | 1720.8143 | 1731.1353 | 1741.5182 | 1751.9634 | 1762.4712 | 1770.1964 | 1777.9555 | 1785.7486 | 1793.5759 | 1801.4375 | 1808.327 | 1815.2428 | 1822.1851 | 1829.154 | 1836.1495 | 1845.4065 | 1854.7103 | 1864.0609 | 1873.4587 | 1882.9038 | 1891.5909 | 1900.3181 | 1909.0856 | 1917.8936 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | 1926.7421 | [6 empty] | 1565 | 1586 | 1607 | 1628 | 1648.8 | 1672 | 1696 | 1720 | 1744 | 1768 | 1790.3 | 1812 | 1834 | 1856 | 1878 | 1900 | 1922 | 1944 | 1966 | 1988 | 2010 | 2032 | 2054 | 2076 | 2098 | 2120 | 2142 | 2164 | 2186 | 2208 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | 2228.3 | [6 empty] | 3.7223 | 3.7223 | 3.7223 | 3.7223 | 3.7223 | 3.7225 | 3.7227 | 3.723 | 3.7232 | 3.7234 | 3.7238 | 3.7242 | 3.7246 | 3.725 | 3.7254 | 3.7222 | 3.719 | 3.7158 | 3.7126 | 3.7094 | 3.7067 | 3.704 | 3.7013 | 3.6986 | 3.6959 | 3.6924 | 3.6889 | 3.6855 | 3.682 | 3.6786 | 3.6755 | 3.6724 | 3.6694 | 3.6663 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632 | 3.6632
280 | Albert - Eden |  |  | 2052 | 1057.8437 | 1029.7106 | 1002.3258 | 975.6692 | 949.7215 | 960.7171 | 971.84 | 983.0916 | 994.4736 | 1005.9873 | 1017.2069 | 1028.5517 | 1040.0231 | 1051.6223 | 1063.351 | 1073.6208 | 1083.9899 | 1094.4591 | 1105.0294 | 1115.7018 | 1124.8592 | 1134.0918 | 1143.4002 | 1152.785 | 1162.2468 | 1174.5232 | 1186.9292 | 1199.4663 | 1212.1358 | 1224.9392 | 1236.4763 | 1248.122 | 1259.8775 | 1271.7436 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 | 1283.7215 |  | 3620 | 3523.7271 | 3430.0146 | 3338.7943 | 3250 | 3282.3338 | 3314.9892 | 3347.9695 | 3381.278 | 3414.9178 | 3447.6083 | 3480.6118 | 3513.9312 | 3547.5696 | 3581.53 | 3607.8791 | 3634.422 | 3661.1603 | 3688.0952 | 3715.2283 | 3737.4498 | 3759.8043 | 3782.2925 | 3804.9152 | 3827.6732 | 3859.0908 | 3890.7662 | 3922.7017 | 3954.8993 | 3987.3611 | 4023.1191 | 4059.1977 | 4095.5998 | 4132.3285 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | 4169.3864 | [6 empty] | 2497 | 2531 | 2565 | 2599 | 2633.4 | 2674 | 2715 | 2756 | 2797 | 2838 | 2878 | 2916 | 2954 | 2992 | 3030 | 3068 | 3106 | 3144 | 3182 | 3220 | 3258 | 3296 | 3334 | 3372 | 3410 | 3448 | 3486 | 3524 | 3562 | 3600 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | 3643.5 | [6 empty] | 3.4221 | 3.4221 | 3.4221 | 3.4221 | 3.4221 | 3.4165 | 3.411 | 3.4056 | 3.4001 | 3.3946 | 3.3893 | 3.384 | 3.3787 | 3.3734 | 3.3682 | 3.3605 | 3.3528 | 3.3452 | 3.3376 | 3.3299 | 3.3226 | 3.3153 | 3.3079 | 3.3006 | 3.2933 | 3.2857 | 3.278 | 3.2704 | 3.2628 | 3.2552 | 3.2537 | 3.2522 | 3.2508 | 3.2493 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479 | 3.2479
281 | Waitemata |  |  | 2052 | 3.0318 | 2.9024 | 2.7787 | 2.6601 | 2.5467 | 5.2562 | 10.8485 | 22.3906 | 46.2129 | 95.3808 | 109.4792 | 125.6615 | 144.2358 | 165.5555 | 190.0266 | 204.8595 | 220.8503 | 238.0894 | 256.674 | 276.7093 | 290.6753 | 305.3462 | 320.7576 | 336.9468 | 353.9531 | 372.6736 | 392.3842 | 413.1373 | 434.988 | 457.9943 | 476.0277 | 494.7711 | 514.2525 | 534.5009 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 | 555.5467 |  | 250 | 239.337 | 229.1288 | 219.356 | 210 | 236.2211 | 265.7162 | 298.8941 | 336.2147 | 378.1953 | 419.9767 | 466.374 | 517.897 | 575.1121 | 638.648 | 680.5639 | 725.2309 | 772.8295 | 823.5521 | 877.6037 | 916.588 | 957.304 | 999.8287 | 1044.2424 | 1090.6289 | 1142.7915 | 1197.4488 | 1254.7203 | 1314.731 | 1377.6119 | 1427.663 | 1479.5326 | 1533.2867 | 1588.9938 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | 1646.7248 | [6 empty] | 9828 | 10001 | 10174 | 10347 | 10520.1 | 10666 | 10812 | 10958 | 11104 | 11250 | 11395.7 | 11549 | 11702 | 11855 | 12008 | 12161 | 12314 | 12467 | 12620 | 12773 | 12926 | 13079 | 13232 | 13385 | 13538 | 13691 | 13844 | 13997 | 14150 | 14303 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | 14452.4 | [6 empty] | 82.4604 | 82.4604 | 82.4604 | 82.4604 | 82.4604 | 44.9415 | 24.4934 | 13.3491 | 7.2753 | 3.9651 | 3.8361 | 3.7114 | 3.5906 | 3.4738 | 3.3608 | 3.3221 | 3.2838 | 3.246 | 3.2086 | 3.1716 | 3.1533 | 3.1351 | 3.1171 | 3.0991 | 3.0813 | 3.0665 | 3.0517 | 3.0371 | 3.0225 | 3.0079 | 2.9991 | 2.9903 | 2.9816 | 2.9729 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642 | 2.9642
282 | Waitemata |  |  | 2052 | 1756.9178 | 1717.1127 | 1678.2095 | 1640.1876 | 1603.0272 | 1643.7356 | 1685.4778 | 1728.28 | 1772.1692 | 1817.1729 | 1858.879 | 1901.5422 | 1945.1847 | 1989.8288 | 2035.4975 | 2074.0148 | 2113.2609 | 2153.2497 | 2193.9952 | 2235.5116 | 2270.0794 | 2305.1817 | 2340.8268 | 2377.023 | 2413.779 | 2459.9972 | 2507.1004 | 2555.1054 | 2604.0297 | 2653.8907 | 2697.4636 | 2741.7518 | 2786.7671 | 2832.5216 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 | 2879.0272 |  | 4110 | 4016.883 | 3925.8757 | 3836.9303 | 3750 | 3843.0872 | 3938.4852 | 4036.2512 | 4136.4441 | 4239.1241 | 4335.8798 | 4434.844 | 4536.0669 | 4639.6002 | 4745.4966 | 4830.616 | 4917.2622 | 5005.4625 | 5095.2449 | 5186.6377 | 5263.4574 | 5341.4148 | 5420.5269 | 5500.8107 | 5582.2836 | 5684.7396 | 5789.076 | 5895.3274 | 6003.5289 | 6113.7164 | 6208.5242 | 6304.8022 | 6402.5733 | 6501.8606 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | 6602.6875 | [6 empty] | 13441 | 13602 | 13763 | 13924 | 14085.3 | 14292 | 14499 | 14706 | 14913 | 15120 | 15325.1 | 15499 | 15673 | 15847 | 16021 | 16195 | 16369 | 16543 | 16717 | 16891 | 17065 | 17239 | 17413 | 17587 | 17761 | 17935 | 18109 | 18283 | 18457 | 18631 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | 18803.5 | [6 empty] | 2.3393 | 2.3393 | 2.3393 | 2.3393 | 2.3393 | 2.338 | 2.3367 | 2.3354 | 2.3341 | 2.3328 | 2.3325 | 2.3322 | 2.3319 | 2.3317 | 2.3314 | 2.3291 | 2.3269 | 2.3246 | 2.3224 | 2.3201 | 2.3186 | 2.3171 | 2.3156 | 2.3142 | 2.3127 | 2.3109 | 2.3091 | 2.3073 | 2.3055 | 2.3037 | 2.3016 | 2.2996 | 2.2975 | 2.2954 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934 | 2.2934
283 | Waitemata |  |  | 2052 | 1336.3504 | 1301.946 | 1268.4273 | 1235.7716 | 1203.9566 | 1221.7904 | 1239.8883 | 1258.2544 | 1276.8925 | 1295.8067 | 1314.0162 | 1332.4816 | 1351.2064 | 1370.1944 | 1389.4492 | 1406.1765 | 1423.105 | 1440.2374 | 1457.5761 | 1475.1235 | 1490.0761 | 1505.1803 | 1520.4377 | 1535.8497 | 1551.4179 | 1571.4013 | 1591.6422 | 1612.1437 | 1632.9093 | 1653.9425 | 1672.7143 | 1691.6992 | 1710.8996 | 1730.3179 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 | 1749.9566 |  | 3230 | 3146.8435 | 3065.8278 | 2986.8979 | 2910 | 2959.4653 | 3009.7714 | 3060.9326 | 3112.9635 | 3165.8788 | 3217.4304 | 3269.8214 | 3323.0656 | 3377.1767 | 3432.169 | 3476.0162 | 3520.4236 | 3565.3983 | 3610.9476 | 3657.0787 | 3697.0205 | 3737.3986 | 3778.2176 | 3819.4825 | 3861.198 | 3913.879 | 3967.2788 | 4021.4072 | 4076.274 | 4131.8895 | 4178.1985 | 4225.0265 | 4272.3793 | 4320.2628 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | 4368.683 | [6 empty] | 1035 | 1045 | 1055 | 1065 | 1073.4 | 1088 | 1103 | 1118 | 1133 | 1148 | 1161.9 | 1175 | 1188 | 1201 | 1214 | 1227 | 1240 | 1253 | 1266 | 1279 | 1292 | 1305 | 1318 | 1331 | 1344 | 1357 | 1370 | 1383 | 1396 | 1409 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | 1415.1 | [6 empty] | 2.417 | 2.417 | 2.417 | 2.417 | 2.417 | 2.4222 | 2.4275 | 2.4327 | 2.4379 | 2.4432 | 2.4485 | 2.4539 | 2.4593 | 2.4647 | 2.4702 | 2.472 | 2.4738 | 2.4756 | 2.4774 | 2.4792 | 2.4811 | 2.483 | 2.485 | 2.4869 | 2.4888 | 2.4907 | 2.4926 | 2.4944 | 2.4963 | 2.4982 | 2.4979 | 2.4975 | 2.4972 | 2.4968 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965 | 2.4965
284 | Waitemata |  |  | 2052 | 1000.5854 | 976.9195 | 953.8133 | 931.2537 | 909.2276 | 953.7022 | 1000.3522 | 1049.2841 | 1100.6095 | 1154.4454 | 1200.6043 | 1248.6087 | 1298.5326 | 1350.4525 | 1404.4485 | 1447.4978 | 1491.8666 | 1537.5955 | 1584.726 | 1633.3012 | 1672.1792 | 1711.9826 | 1752.7334 | 1794.4543 | 1837.1683 | 1889.0702 | 1942.4384 | 1997.3143 | 2053.7405 | 2111.7608 | 2160.9123 | 2211.2078 | 2262.6739 | 2315.3379 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 | 2369.2276 |  | 2300 | 2245.6003 | 2192.4872 | 2140.6303 | 2090 | 2192.4195 | 2299.858 | 2412.5615 | 2530.788 | 2654.8081 | 2762.3215 | 2874.189 | 2990.5869 | 3111.6985 | 3237.715 | 3335.2454 | 3435.7137 | 3539.2085 | 3645.8209 | 3755.6448 | 3843.6949 | 3933.8093 | 4026.0365 | 4120.4259 | 4217.0282 | 4334.5787 | 4455.406 | 4579.6013 | 4707.2587 | 4838.4745 | 4949.7726 | 5063.6309 | 5180.1082 | 5299.2648 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | 5421.1624 | [6 empty] | 9804 | 9925 | 10046 | 10167 | 10289.9 | 10444 | 10598 | 10752 | 10906 | 11060 | 11214.9 | 11351 | 11487 | 11623 | 11759 | 11895 | 12031 | 12167 | 12303 | 12439 | 12575 | 12711 | 12847 | 12983 | 13119 | 13255 | 13391 | 13527 | 13663 | 13799 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | 13935.6 | [6 empty] | 2.2987 | 2.2987 | 2.2987 | 2.2987 | 2.2987 | 2.2989 | 2.299 | 2.2992 | 2.2994 | 2.2996 | 2.3008 | 2.3019 | 2.3031 | 2.3042 | 2.3053 | 2.3041 | 2.303 | 2.3018 | 2.3006 | 2.2994 | 2.2986 | 2.2978 | 2.297 | 2.2962 | 2.2954 | 2.2946 | 2.2937 | 2.2929 | 2.292 | 2.2912 | 2.2906 | 2.29 | 2.2894 | 2.2888 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882 | 2.2882
285 | Waitemata |  |  | 2052 | 752.9094 | 739.3028 | 725.9422 | 712.823 | 699.9409 | 743.2759 | 789.2938 | 838.1609 | 890.0534 | 945.1587 | 990.579 | 1038.182 | 1088.0727 | 1140.3608 | 1195.1618 | 1237.7822 | 1281.9225 | 1327.6369 | 1374.9815 | 1424.0145 | 1462.6354 | 1502.3038 | 1543.048 | 1584.8973 | 1627.8816 | 1679.4303 | 1732.6115 | 1787.4766 | 1844.0792 | 1902.4741 | 1951.3869 | 2001.5572 | 2053.0174 | 2105.8006 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 | 2159.9409 |  | 1990 | 1954.0368 | 1918.7235 | 1884.0484 | 1850 | 1964.4616 | 2086.005 | 2215.0684 | 2352.1172 | 2497.6453 | 2618.9737 | 2746.1959 | 2879.5981 | 3019.4807 | 3166.1584 | 3277.4838 | 3392.7236 | 3512.0154 | 3635.5016 | 3763.3296 | 3864.1731 | 3967.7188 | 4074.0391 | 4183.2084 | 4295.3031 | 4429.9038 | 4568.7224 | 4711.8911 | 4859.5463 | 5011.8285 | 5139.5213 | 5270.4674 | 5404.7498 | 5542.4535 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | 5683.6657 | [6 empty] | 7868 | 7962 | 8056 | 8150 | 8244.4 | 8363 | 8481 | 8599 | 8717 | 8835 | 8955.2 | 9058 | 9161 | 9264 | 9367 | 9470 | 9573 | 9676 | 9779 | 9882 | 9985 | 10088 | 10191 | 10294 | 10397 | 10500 | 10603 | 10706 | 10809 | 10912 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | 11006.3 | [6 empty] | 2.6431 | 2.6431 | 2.6431 | 2.6431 | 2.6431 | 2.643 | 2.6429 | 2.6428 | 2.6427 | 2.6426 | 2.6439 | 2.6452 | 2.6465 | 2.6478 | 2.6491 | 2.6479 | 2.6466 | 2.6453 | 2.644 | 2.6428 | 2.6419 | 2.6411 | 2.6403 | 2.6394 | 2.6386 | 2.6377 | 2.6369 | 2.6361 | 2.6352 | 2.6344 | 2.6338 | 2.6332 | 2.6326 | 2.632 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314 | 2.6314
286 | Orakei |  |  | 2052 | 1033.0612 | 1009.786 | 987.0351 | 964.7969 | 943.0597 | 965.4818 | 988.4371 | 1011.9382 | 1035.998 | 1060.6298 | 1083.5872 | 1107.0414 | 1131.0033 | 1155.4839 | 1180.4943 | 1201.666 | 1223.2173 | 1245.1551 | 1267.4864 | 1290.2182 | 1309.2003 | 1328.4617 | 1348.0064 | 1367.8387 | 1387.9627 | 1413.3478 | 1439.1972 | 1465.5193 | 1492.3229 | 1519.6167 | 1543.5401 | 1567.8401 | 1592.5227 | 1617.5938 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 | 1643.0597 |  | 2640 | 2580.5199 | 2522.3798 | 2465.5497 | 2410 | 2477.868 | 2547.6473 | 2619.3916 | 2693.1563 | 2768.9983 | 2841.6715 | 2916.252 | 2992.7899 | 3071.3365 | 3151.9446 | 3216.9867 | 3283.371 | 3351.1252 | 3420.2775 | 3490.8567 | 3552.1146 | 3614.4473 | 3677.8739 | 3742.4135 | 3808.0857 | 3888.2501 | 3970.1021 | 4053.6772 | 4139.0116 | 4226.1424 | 4291.0482 | 4356.9509 | 4423.8657 | 4491.8081 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | 4560.7941 | [6 empty] | 868 | 877 | 886 | 895 | 903 | 920 | 937 | 954 | 971 | 988 | 1002.5 | 1017 | 1032 | 1047 | 1062 | 1077 | 1092 | 1107 | 1122 | 1137 | 1152 | 1167 | 1182 | 1197 | 1212 | 1227 | 1242 | 1257 | 1272 | 1287 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | 1295.8 | [6 empty] | 2.5555 | 2.5555 | 2.5555 | 2.5555 | 2.5555 | 2.5665 | 2.5775 | 2.5885 | 2.5996 | 2.6107 | 2.6225 | 2.6343 | 2.6461 | 2.6581 | 2.67 | 2.6771 | 2.6842 | 2.6913 | 2.6985 | 2.7056 | 2.7132 | 2.7208 | 2.7284 | 2.736 | 2.7437 | 2.7511 | 2.7586 | 2.766 | 2.7735 | 2.7811 | 2.78 | 2.779 | 2.7779 | 2.7768 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758 | 2.7758
287 | Orakei |  |  | 2052 | 978.5277 | 966.3264 | 954.2773 | 942.3783 | 930.6278 | 937.4959 | 944.4147 | 951.3845 | 958.4058 | 965.4789 | 972.4828 | 979.5375 | 986.6434 | 993.8008 | 1001.0102 | 1007.4167 | 1013.8643 | 1020.3531 | 1026.8834 | 1033.4555 | 1039.1637 | 1044.9034 | 1050.6748 | 1056.4781 | 1062.3134 | 1069.976 | 1077.6937 | 1085.4672 | 1093.2967 | 1101.1827 | 1108.3771 | 1115.6185 | 1122.9072 | 1130.2435 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 | 1137.6278 |  | 2860 | 2824.3385 | 2789.1217 | 2754.344 | 2720 | 2743.5435 | 2767.2907 | 2791.2435 | 2815.4036 | 2839.7729 | 2863.9509 | 2888.3348 | 2912.9264 | 2937.7272 | 2962.7393 | 2981.5118 | 3000.4033 | 3019.4146 | 3038.5462 | 3057.7991 | 3074.4347 | 3091.1607 | 3107.9778 | 3124.8864 | 3141.8869 | 3164.3707 | 3187.0154 | 3209.8222 | 3232.7922 | 3255.9265 | 3277.5571 | 3299.3313 | 3321.2503 | 3343.3148 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | 3365.5259 | [6 empty] | 528 | 533 | 538 | 543 | 548.9 | 557 | 566 | 575 | 584 | 593 | 599.9 | 608 | 616 | 624 | 632 | 640 | 648 | 656 | 664 | 672 | 680 | 688 | 696 | 704 | 712 | 720 | 728 | 736 | 744 | 752 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | 755.9 | [6 empty] | 2.9228 | 2.9228 | 2.9228 | 2.9228 | 2.9228 | 2.9265 | 2.9302 | 2.9339 | 2.9376 | 2.9413 | 2.945 | 2.9487 | 2.9524 | 2.9561 | 2.9597 | 2.9596 | 2.9594 | 2.9592 | 2.959 | 2.9588 | 2.9586 | 2.9583 | 2.9581 | 2.9578 | 2.9576 | 2.9574 | 2.9573 | 2.9571 | 2.9569 | 2.9568 | 2.9571 | 2.9574 | 2.9577 | 2.958 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584 | 2.9584
288 | Orakei |  |  | 2052 | 1392.4538 | 1373.9483 | 1355.6887 | 1337.6717 | 1319.8942 | 1336.447 | 1353.2074 | 1370.178 | 1387.3614 | 1404.7603 | 1421.6535 | 1438.7499 | 1456.0518 | 1473.5618 | 1491.2824 | 1506.8187 | 1522.5169 | 1538.3786 | 1554.4055 | 1570.5994 | 1584.4957 | 1598.515 | 1612.6583 | 1626.9268 | 1641.3214 | 1659.9454 | 1678.7806 | 1697.8295 | 1717.0946 | 1736.5783 | 1754.0849 | 1771.7681 | 1789.6294 | 1807.6709 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 | 1825.8942 |  | 4030 | 3976.4418 | 3923.5953 | 3871.4512 | 3820 | 3872.8723 | 3926.4764 | 3980.8224 | 4035.9206 | 4091.7815 | 4146.2911 | 4201.5268 | 4257.4985 | 4314.2157 | 4371.6885 | 4417.1229 | 4463.0294 | 4509.4131 | 4556.2788 | 4603.6315 | 4644.2723 | 4685.2719 | 4726.6335 | 4768.3601 | 4810.4552 | 4864.926 | 4920.0136 | 4975.7251 | 5032.0673 | 5089.0476 | 5140.2532 | 5191.974 | 5244.2152 | 5296.9821 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | 5350.2799 | [6 empty] | 1260 | 1271 | 1282 | 1293 | 1305.3 | 1323 | 1341 | 1359 | 1377 | 1395 | 1413 | 1428 | 1443 | 1458 | 1473 | 1488 | 1503 | 1518 | 1533 | 1548 | 1563 | 1578 | 1593 | 1608 | 1623 | 1638 | 1653 | 1668 | 1683 | 1698 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | 1719.1 | [6 empty] | 2.8942 | 2.8942 | 2.8942 | 2.8942 | 2.8942 | 2.8979 | 2.9016 | 2.9053 | 2.9091 | 2.9128 | 2.9165 | 2.9203 | 2.924 | 2.9277 | 2.9315 | 2.9314 | 2.9313 | 2.9313 | 2.9312 | 2.9311 | 2.9311 | 2.931 | 2.931 | 2.9309 | 2.9308 | 2.9308 | 2.9307 | 2.9306 | 2.9306 | 2.9305 | 2.9304 | 2.9304 | 2.9303 | 2.9303 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302 | 2.9302
289 | Orakei |  |  | 2052 | 921.3926 | 911.6034 | 901.9181 | 892.3358 | 882.8553 | 895.0278 | 907.3681 | 919.8786 | 932.5616 | 945.4194 | 957.8454 | 970.4348 | 983.1896 | 996.1121 | 1009.2044 | 1020.6362 | 1032.1975 | 1043.8898 | 1055.7145 | 1067.6732 | 1077.9014 | 1088.2276 | 1098.6527 | 1109.1777 | 1119.8036 | 1133.5071 | 1147.3784 | 1161.4194 | 1175.6323 | 1190.019 | 1202.9042 | 1215.9289 | 1229.0946 | 1242.4029 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 | 1255.8553 |  | 2630 | 2602.0578 | 2574.4126 | 2547.061 | 2520 | 2554.8716 | 2590.2257 | 2626.0691 | 2662.4085 | 2699.2507 | 2734.9354 | 2771.0919 | 2807.7263 | 2844.8451 | 2882.4546 | 2912.2436 | 2942.3404 | 2972.7482 | 3003.4703 | 3034.5099 | 3060.6641 | 3087.0437 | 3113.6507 | 3140.487 | 3167.5546 | 3203.1552 | 3239.156 | 3275.5613 | 3312.3759 | 3349.6042 | 3385.3827 | 3421.5434 | 3458.0904 | 3495.0277 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | 3532.3595 | [6 empty] | 1055 | 1066 | 1077 | 1088 | 1098.3 | 1114 | 1130 | 1146 | 1162 | 1178 | 1193.2 | 1207 | 1221 | 1235 | 1249 | 1263 | 1277 | 1291 | 1305 | 1319 | 1333 | 1347 | 1361 | 1375 | 1389 | 1403 | 1417 | 1431 | 1445 | 1459 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | 1469.3 | [6 empty] | 2.8544 | 2.8544 | 2.8544 | 2.8544 | 2.8544 | 2.8545 | 2.8547 | 2.8548 | 2.8549 | 2.8551 | 2.8553 | 2.8555 | 2.8557 | 2.8559 | 2.8562 | 2.8534 | 2.8506 | 2.8478 | 2.845 | 2.8422 | 2.8395 | 2.8368 | 2.8341 | 2.8314 | 2.8287 | 2.8259 | 2.8231 | 2.8203 | 2.8175 | 2.8147 | 2.8143 | 2.8139 | 2.8135 | 2.8131 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127 | 2.8127
290 | Orakei |  |  | 2052 | 1395.435 | 1380.776 | 1366.2709 | 1351.9182 | 1337.7163 | 1353.9455 | 1370.3716 | 1386.9969 | 1403.824 | 1420.8552 | 1437.4169 | 1454.1716 | 1471.1215 | 1488.2691 | 1505.6165 | 1520.8628 | 1536.2634 | 1551.82 | 1567.5341 | 1583.4074 | 1597.0524 | 1610.815 | 1624.6961 | 1638.6969 | 1652.8184 | 1671.0084 | 1689.3987 | 1707.9914 | 1726.7887 | 1745.7928 | 1762.8413 | 1780.0562 | 1797.4393 | 1814.9921 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 | 1832.7163 |  | 4110 | 4066.8244 | 4024.1024 | 3981.8292 | 3940 | 3992.7092 | 4046.1236 | 4100.2525 | 4155.1055 | 4210.6924 | 4265.0097 | 4320.0277 | 4375.7555 | 4432.2021 | 4489.3768 | 4534.5526 | 4580.183 | 4626.2725 | 4672.8258 | 4719.8476 | 4760.2737 | 4801.046 | 4842.1676 | 4883.6414 | 4925.4704 | 4979.3582 | 5033.8357 | 5088.9091 | 5144.5851 | 5200.8702 | 5251.3702 | 5302.3605 | 5353.8459 | 5405.8313 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | 5458.3214 | [6 empty] | 1707 | 1729 | 1751 | 1773 | 1796.6 | 1823 | 1850 | 1877 | 1904 | 1931 | 1955.7 | 1981 | 2006 | 2031 | 2056 | 2081 | 2106 | 2131 | 2156 | 2181 | 2206 | 2231 | 2256 | 2281 | 2306 | 2331 | 2356 | 2381 | 2406 | 2431 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | 2461.9 | [6 empty] | 2.9453 | 2.9453 | 2.9453 | 2.9453 | 2.9453 | 2.9489 | 2.9526 | 2.9562 | 2.9598 | 2.9635 | 2.9671 | 2.9708 | 2.9744 | 2.9781 | 2.9818 | 2.9816 | 2.9814 | 2.9812 | 2.981 | 2.9808 | 2.9807 | 2.9805 | 2.9804 | 2.9802 | 2.98 | 2.9799 | 2.9797 | 2.9795 | 2.9793 | 2.9791 | 2.9789 | 2.9788 | 2.9786 | 2.9784 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783 | 2.9783
291 | Orakei |  |  | 2052 | 1255.041 | 1243.3565 | 1231.7809 | 1220.313 | 1208.9519 | 1216.6629 | 1224.4231 | 1232.2328 | 1240.0923 | 1248.002 | 1255.8647 | 1263.777 | 1271.7391 | 1279.7514 | 1287.8141 | 1295.0374 | 1302.3012 | 1309.6058 | 1316.9513 | 1324.3381 | 1330.7912 | 1337.2757 | 1343.7919 | 1350.3398 | 1356.9196 | 1365.5851 | 1374.306 | 1383.0826 | 1391.9152 | 1400.8042 | 1408.9387 | 1417.1205 | 1425.3497 | 1433.6268 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 | 1441.9519 |  | 3540 | 3507.0426 | 3474.392 | 3442.0454 | 3410 | 3436.0466 | 3462.2921 | 3488.7381 | 3515.3862 | 3542.2377 | 3568.9989 | 3595.9622 | 3623.1293 | 3650.5016 | 3678.0807 | 3698.5313 | 3719.0957 | 3739.7744 | 3760.5681 | 3781.4775 | 3799.7473 | 3818.1053 | 3836.5521 | 3855.088 | 3873.7134 | 3898.2475 | 3922.9371 | 3947.783 | 3972.7862 | 3997.9478 | 4020.9782 | 4044.1412 | 4067.4377 | 4090.8683 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | 4114.434 | [6 empty] | 706 | 712 | 718 | 724 | 729 | 739 | 749 | 759 | 769 | 779 | 787.2 | 795 | 802 | 809 | 816 | 823 | 830 | 837 | 844 | 851 | 858 | 865 | 872 | 879 | 886 | 893 | 900 | 907 | 914 | 921 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | 934.5 | [6 empty] | 2.8206 | 2.8206 | 2.8206 | 2.8206 | 2.8206 | 2.8242 | 2.8277 | 2.8312 | 2.8348 | 2.8383 | 2.8419 | 2.8454 | 2.849 | 2.8525 | 2.8561 | 2.8559 | 2.8558 | 2.8556 | 2.8555 | 2.8554 | 2.8553 | 2.8551 | 2.855 | 2.8549 | 2.8548 | 2.8546 | 2.8545 | 2.8543 | 2.8542 | 2.854 | 2.8539 | 2.8538 | 2.8536 | 2.8535 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534 | 2.8534
292 | Albert - Eden |  |  | 2052 | 1199.4426 | 1178.9984 | 1158.9026 | 1139.1494 | 1119.7328 | 1124.066 | 1128.416 | 1132.7829 | 1137.1666 | 1141.5673 | 1145.9851 | 1150.42 | 1154.872 | 1159.3413 | 1163.8278 | 1167.9381 | 1172.0629 | 1176.2023 | 1180.3563 | 1184.5249 | 1188.2253 | 1191.9373 | 1195.6609 | 1199.3961 | 1203.1429 | 1208.0359 | 1212.9488 | 1217.8817 | 1222.8346 | 1227.8077 | 1232.3589 | 1236.9269 | 1241.5119 | 1246.1138 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 | 1250.7328 |  | 3160 | 3106.1385 | 3053.195 | 3001.154 | 2950 | 2971.5953 | 2993.3486 | 3015.2612 | 3037.3342 | 3059.5688 | 3081.793 | 3104.1785 | 3126.7267 | 3149.4387 | 3172.3157 | 3188.7556 | 3205.2807 | 3221.8915 | 3238.5883 | 3255.3717 | 3270.8999 | 3286.5021 | 3302.1788 | 3317.9303 | 3333.7569 | 3352.7037 | 3371.7582 | 3390.9211 | 3410.1928 | 3429.574 | 3442.0373 | 3454.5459 | 3467.1 | 3479.6996 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | 3492.3451 | [6 empty] | 884 | 891 | 898 | 905 | 913.8 | 925 | 936 | 947 | 958 | 969 | 980.8 | 991 | 1001 | 1011 | 1021 | 1031 | 1041 | 1051 | 1061 | 1071 | 1081 | 1091 | 1101 | 1111 | 1121 | 1131 | 1141 | 1151 | 1161 | 1171 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | 1181.1 | [6 empty] | 2.6346 | 2.6346 | 2.6346 | 2.6346 | 2.6346 | 2.6436 | 2.6527 | 2.6618 | 2.671 | 2.6801 | 2.6892 | 2.6983 | 2.7074 | 2.7166 | 2.7258 | 2.7302 | 2.7347 | 2.7392 | 2.7437 | 2.7483 | 2.7528 | 2.7573 | 2.7618 | 2.7663 | 2.7709 | 2.7753 | 2.7798 | 2.7843 | 2.7888 | 2.7933 | 2.793 | 2.7928 | 2.7926 | 2.7924 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922 | 2.7922
293 | Waitemata |  |  | 2052 | 1117.7422 | 1116.0133 | 1114.2871 | 1112.5635 | 1110.8426 | 1126.2795 | 1141.931 | 1157.7999 | 1173.8894 | 1190.2025 | 1205.9613 | 1221.9288 | 1238.1077 | 1254.5008 | 1271.111 | 1285.6054 | 1300.265 | 1315.0918 | 1330.0877 | 1345.2546 | 1358.221 | 1371.3124 | 1384.5299 | 1397.8749 | 1411.3485 | 1428.7202 | 1446.3057 | 1464.1077 | 1482.1287 | 1500.3716 | 1516.7063 | 1533.2187 | 1549.911 | 1566.7849 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 | 1583.8426 |  | 3240 | 3234.9884 | 3229.9845 | 3224.9884 | 3220 | 3268.2305 | 3317.1834 | 3366.8696 | 3417.3 | 3468.4857 | 3518.2824 | 3568.7939 | 3620.0307 | 3672.0031 | 3724.7216 | 3766.6492 | 3809.0488 | 3851.9256 | 3895.2851 | 3939.1327 | 3976.735 | 4014.6962 | 4053.0199 | 4091.7093 | 4130.7681 | 4181.0404 | 4231.9245 | 4283.4279 | 4335.5581 | 4388.3227 | 4435.1333 | 4482.4433 | 4530.258 | 4578.5827 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | 4627.4229 | [6 empty] | 1116 | 1133 | 1150 | 1167 | 1182.2 | 1204 | 1226 | 1248 | 1270 | 1292 | 1311.3 | 1332 | 1353 | 1374 | 1395 | 1416 | 1437 | 1458 | 1479 | 1500 | 1521 | 1542 | 1563 | 1584 | 1605 | 1626 | 1647 | 1668 | 1689 | 1710 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | 1728.7 | [6 empty] | 2.8987 | 2.8987 | 2.8987 | 2.8987 | 2.8987 | 2.9018 | 2.9049 | 2.908 | 2.9111 | 2.9142 | 2.9174 | 2.9206 | 2.9238 | 2.9271 | 2.9303 | 2.9299 | 2.9294 | 2.929 | 2.9286 | 2.9282 | 2.9279 | 2.9276 | 2.9274 | 2.9271 | 2.9268 | 2.9264 | 2.926 | 2.9256 | 2.9252 | 2.9248 | 2.9242 | 2.9236 | 2.9229 | 2.9223 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216 | 2.9216
294 | Albert - Eden |  |  | 2052 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 8.3339 | 22.9086 | 62.9725 | 173.102 | 475.8318 | 547.297 | 629.4955 | 724.0393 | 832.7827 | 957.8583 | 1070.3478 | 1196.048 | 1336.5101 | 1493.468 | 1668.8587 | 1802.7256 | 1947.3305 | 2103.5349 | 2272.2691 | 2454.5383 | 2523.0985 | 2593.5737 | 2666.0174 | 2740.4846 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 | 2817.0318 |  | 110 | 110 | 110 | 110 | 110 | 188.0115 | 321.3483 | 549.247 | 938.7705 | 1604.542 | 1828.4594 | 2083.6249 | 2374.3994 | 2705.7521 | 3083.3457 | 3424.3959 | 3803.1698 | 4223.8401 | 4691.0408 | 5209.9189 | 5601.7065 | 6022.9567 | 6475.8851 | 6962.8738 | 7486.4842 | 7666.2001 | 7850.2302 | 8038.6779 | 8231.6495 | 8429.2534 | 8399.4335 | 8369.7191 | 8340.1098 | 8310.6053 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | 8281.2051 | [6 empty] | 1849 | 1880 | 1911 | 1942 | 1974.3 | 2000 | 2026 | 2052 | 2078 | 2104 | 2129.5 | 2160 | 2190 | 2220 | 2250 | 2280 | 2310 | 2340 | 2370 | 2400 | 2430 | 2460 | 2490 | 2520 | 2550 | 2580 | 2610 | 2640 | 2670 | 2700 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | 2736.8 | [6 empty] | 36.2824 | 36.2824 | 36.2824 | 36.2824 | 36.2824 | 22.5599 | 14.0274 | 8.722 | 5.4232 | 3.3721 | 3.3409 | 3.31 | 3.2794 | 3.249 | 3.219 | 3.1993 | 3.1798 | 3.1604 | 3.141 | 3.1218 | 3.1074 | 3.0929 | 3.0786 | 3.0643 | 3.0501 | 3.0384 | 3.0268 | 3.0152 | 3.0037 | 2.9922 | 2.9817 | 2.9711 | 2.9606 | 2.9501 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397 | 2.9397
295 | Albert - Eden |  |  | 2052 | 1337.7016 | 1342.3555 | 1347.0256 | 1351.7119 | 1356.4145 | 1359.0913 | 1361.7733 | 1364.4606 | 1367.1532 | 1369.8511 | 1372.58 | 1375.3143 | 1378.0541 | 1380.7993 | 1383.5499 | 1386.0489 | 1388.5523 | 1391.0603 | 1393.5728 | 1396.0898 | 1398.3169 | 1400.5475 | 1402.7816 | 1405.0193 | 1407.2606 | 1410.2571 | 1413.2599 | 1416.2691 | 1419.2847 | 1422.3068 | 1425.1172 | 1427.9332 | 1430.7547 | 1433.5818 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 | 1436.4145 |  | 3590 | 3602.4352 | 3614.9136 | 3627.4351 | 3640 | 3653.3873 | 3666.8239 | 3680.3099 | 3693.8455 | 3707.4309 | 3721.0824 | 3734.7842 | 3748.5364 | 3762.3393 | 3776.193 | 3784.1508 | 3792.1254 | 3800.1167 | 3808.125 | 3816.1501 | 3823.3886 | 3830.6408 | 3837.9067 | 3845.1865 | 3852.4801 | 3861.8357 | 3871.2141 | 3880.6153 | 3890.0393 | 3899.4862 | 3907.1604 | 3914.8498 | 3922.5543 | 3930.274 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | 3938.0089 | [6 empty] | 471 | 474 | 477 | 480 | 483.2 | 490 | 497 | 504 | 511 | 518 | 522.7 | 528 | 533 | 538 | 543 | 548 | 553 | 558 | 563 | 568 | 573 | 578 | 583 | 588 | 593 | 598 | 603 | 608 | 613 | 618 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | 627.9 | [6 empty] | 2.6837 | 2.6837 | 2.6836 | 2.6836 | 2.6835 | 2.6881 | 2.6927 | 2.6973 | 2.7019 | 2.7064 | 2.711 | 2.7156 | 2.7202 | 2.7248 | 2.7294 | 2.7302 | 2.731 | 2.7318 | 2.7326 | 2.7335 | 2.7343 | 2.7351 | 2.7359 | 2.7367 | 2.7376 | 2.7384 | 2.7392 | 2.74 | 2.7408 | 2.7417 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416 | 2.7416
296 | Albert - Eden |  |  | 2052 | 915.2068 | 908.2238 | 901.2941 | 894.4172 | 887.5928 | 892.8215 | 898.081 | 903.3715 | 908.6931 | 914.0461 | 919.3774 | 924.7399 | 930.1336 | 935.5588 | 941.0156 | 945.8865 | 950.7826 | 955.7041 | 960.651 | 965.6235 | 969.9596 | 974.3152 | 978.6904 | 983.0852 | 987.4997 | 993.3237 | 999.182 | 1005.0749 | 1011.0025 | 1016.9651 | 1022.4315 | 1027.9274 | 1033.4528 | 1039.0079 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 | 1044.5928 |  | 2320 | 2302.2984 | 2284.7319 | 2267.2995 | 2250 | 2269.5885 | 2289.3476 | 2309.2787 | 2329.3833 | 2349.663 | 2369.8949 | 2390.301 | 2410.8828 | 2431.6418 | 2452.5796 | 2468.1096 | 2483.7379 | 2499.4651 | 2515.292 | 2531.219 | 2545.5067 | 2559.8751 | 2574.3245 | 2588.8556 | 2603.4686 | 2621.7923 | 2640.2449 | 2658.8274 | 2677.5407 | 2696.3857 | 2710.7847 | 2725.2606 | 2739.8138 | 2754.4448 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | 2769.1538 | [6 empty] | 232 | 234 | 236 | 238 | 239.6 | 243 | 246 | 249 | 252 | 255 | 257.2 | 260 | 262 | 264 | 266 | 268 | 270 | 272 | 274 | 276 | 278 | 280 | 282 | 284 | 286 | 288 | 290 | 292 | 294 | 296 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | 303.9 | [6 empty] | 2.5349 | 2.5349 | 2.5349 | 2.5349 | 2.5349 | 2.542 | 2.5492 | 2.5563 | 2.5634 | 2.5706 | 2.5777 | 2.5848 | 2.592 | 2.5991 | 2.6063 | 2.6093 | 2.6123 | 2.6153 | 2.6183 | 2.6213 | 2.6243 | 2.6274 | 2.6304 | 2.6334 | 2.6364 | 2.6394 | 2.6424 | 2.6454 | 2.6484 | 2.6514 | 2.6513 | 2.6512 | 2.6511 | 2.651 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509 | 2.6509
297 | Albert - Eden |  |  | 2052 | 1055.6909 | 1049.7764 | 1043.8951 | 1038.0467 | 1032.2311 | 1037.6329 | 1043.0629 | 1048.5214 | 1054.0084 | 1059.5242 | 1065.0317 | 1070.5679 | 1076.1329 | 1081.7268 | 1087.3498 | 1092.4128 | 1097.4993 | 1102.6095 | 1107.7435 | 1112.9014 | 1117.4259 | 1121.9687 | 1126.5301 | 1131.11 | 1135.7085 | 1141.7869 | 1147.8979 | 1154.0415 | 1160.2181 | 1166.4277 | 1172.1323 | 1177.8648 | 1183.6253 | 1189.4141 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 | 1195.2311 |  | 3150 | 3132.3522 | 3114.8034 | 3097.3528 | 3080 | 3105.3683 | 3130.9456 | 3156.7335 | 3182.7339 | 3208.9483 | 3235.1418 | 3261.549 | 3288.1718 | 3315.012 | 3342.0712 | 3362.0385 | 3382.1252 | 3402.3319 | 3422.6592 | 3443.1081 | 3461.6831 | 3480.3582 | 3499.1341 | 3518.0114 | 3536.9904 | 3560.4775 | 3584.1206 | 3607.9207 | 3631.8788 | 3655.996 | 3673.378 | 3690.8425 | 3708.3902 | 3726.0212 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | 3743.7361 | [6 empty] | 1095 | 1106 | 1117 | 1128 | 1139.9 | 1158 | 1176 | 1194 | 1212 | 1230 | 1248.3 | 1264 | 1280 | 1296 | 1312 | 1328 | 1344 | 1360 | 1376 | 1392 | 1408 | 1424 | 1440 | 1456 | 1472 | 1488 | 1504 | 1520 | 1536 | 1552 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | 1569.8 | [6 empty] | 2.9838 | 2.9838 | 2.9838 | 2.9838 | 2.9838 | 2.9927 | 3.0017 | 3.0107 | 3.0196 | 3.0287 | 3.0376 | 3.0466 | 3.0555 | 3.0646 | 3.0736 | 3.0776 | 3.0817 | 3.0857 | 3.0898 | 3.0938 | 3.0979 | 3.102 | 3.1061 | 3.1102 | 3.1143 | 3.1183 | 3.1223 | 3.1263 | 3.1303 | 3.1344 | 3.1339 | 3.1335 | 3.1331 | 3.1327 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322 | 3.1322
298 | Albert - Eden |  |  | 2052 | 1327.8678 | 1304.323 | 1281.1958 | 1258.4786 | 1236.1642 | 1268.5208 | 1301.7243 | 1335.7969 | 1370.7613 | 1406.641 | 1439.801 | 1473.7427 | 1508.4845 | 1544.0453 | 1580.4445 | 1611.0783 | 1642.3059 | 1674.1388 | 1706.5887 | 1739.6676 | 1767.1662 | 1795.0995 | 1823.4744 | 1852.2977 | 1881.5767 | 1918.2809 | 1955.7011 | 1993.8513 | 2032.7457 | 2072.3988 | 2106.9785 | 2142.1351 | 2177.8784 | 2214.2181 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 | 2251.1642 |  | 3620 | 3555.8129 | 3492.7639 | 3430.8329 | 3370 | 3471.8175 | 3576.7112 | 3684.774 | 3796.1017 | 3910.7929 | 4018.8373 | 4129.8667 | 4243.9636 | 4361.2126 | 4481.7008 | 4578.2415 | 4676.8617 | 4777.6064 | 4880.5211 | 4985.6528 | 5075.3612 | 5166.6837 | 5259.6494 | 5354.2879 | 5450.6292 | 5568.7106 | 5689.3501 | 5812.6032 | 5938.5263 | 6067.1774 | 6167.6483 | 6269.783 | 6373.6091 | 6479.1544 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | 6586.4476 | [6 empty] | 776 | 784 | 792 | 800 | 806.5 | 822 | 838 | 854 | 870 | 886 | 900.1 | 914 | 928 | 942 | 956 | 970 | 984 | 998 | 1012 | 1026 | 1040 | 1054 | 1068 | 1082 | 1096 | 1110 | 1124 | 1138 | 1152 | 1166 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | 1173.5 | [6 empty] | 2.7262 | 2.7262 | 2.7262 | 2.7262 | 2.7262 | 2.7369 | 2.7477 | 2.7585 | 2.7693 | 2.7802 | 2.7912 | 2.8023 | 2.8134 | 2.8245 | 2.8357 | 2.8417 | 2.8477 | 2.8538 | 2.8598 | 2.8659 | 2.872 | 2.8782 | 2.8844 | 2.8906 | 2.8968 | 2.903 | 2.9091 | 2.9153 | 2.9214 | 2.9276 | 2.9272 | 2.9269 | 2.9265 | 2.9262 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258 | 2.9258
299 | Albert - Eden | AHP | Mt Roskill | 2060 | 944.6779 | 924.19 | 904.1464 | 884.5375 | 865.3538 | 883.5697 | 902.169 | 921.1598 | 940.5503 | 960.3491 | 978.9817 | 997.9758 | 1017.3385 | 1037.0768 | 1057.1981 | 1074.4222 | 1091.9269 | 1109.7169 | 1127.7966 | 1146.171 | 1161.6356 | 1177.3089 | 1193.1937 | 1209.2928 | 1225.6092 | 1246.1961 | 1267.1289 | 1288.4133 | 1310.0552 | 1332.0607 | 1351.4001 | 1371.0203 | 1390.9254 | 1411.1194 | 1431.6066 | 1236.1392 | 1067.3603 | 921.626 | 795.7899 | 687.135 | 593.3156 | 512.306 | 442.3572 | 442.3572 | 442.3572 | 442.3572 | 442.3572 | 442.3572 | 442.3572 | 442.3572 | 442.3572 | 442.3572 | 442.3572 | 442.3572 | 442.3572 | 442.3572 | 442.3572 | 442.3572 | 442.3572 | 442.3572 | 442.3572 | 442.3572 | 442.3572 |  | 2620 | 2563.1781 | 2507.5885 | 2453.2045 | 2400 | 2450.4963 | 2502.0549 | 2554.6984 | 2608.4496 | 2663.3316 | 2715.4021 | 2768.4907 | 2822.6172 | 2877.8019 | 2934.0655 | 2979.3057 | 3025.2434 | 3071.8895 | 3119.2547 | 3167.3503 | 3207.8898 | 3248.9481 | 3290.5319 | 3332.6479 | 3375.303 | 3429.2057 | 3483.9692 | 3539.6073 | 3596.1339 | 3653.5632 | 3704.1162 | 3755.3686 | 3807.3302 | 3860.0108 | 3913.4203 | 3379.8909 | 2919.0993 | 2521.1289 | 2177.4151 | 1880.5609 | 1624.1779 | 1402.7484 | 1211.5071 | 1211.5071 | 1211.5071 | 1211.5071 | 1211.5071 | 1211.5071 | 1211.5071 | 1211.5071 | 1211.5071 | 1211.5071 | 1211.5071 | 1211.5071 | 1211.5071 | 1211.5071 | 1211.5071 | 1211.5071 | 1211.5071 | 1211.5071 | 1211.5071 | 1211.5071 | 1211.5071 | [6 empty] | 4356 | 4405 | 4454 | 4503 | 4553.3 | 4626 | 4698 | 4770 | 4842 | 4914 | 4987.2 | 5047 | 5107 | 5167 | 5227 | 5287 | 5347 | 5407 | 5467 | 5527 | 5587 | 5647 | 5707 | 5767 | 5827 | 5887 | 5947 | 6007 | 6067 | 6127 | 6193 | 5440.4359 | 4779.3223 | 4198.5462 | 3688.3452 | 3240.143 | 2846.4057 | 2500.5147 | 2196.6559 | 2196.6559 | 2196.6559 | 2196.6559 | 2196.6559 | 2196.6559 | 2196.6559 | 2196.6559 | 2196.6559 | 2196.6559 | 2196.6559 | 2196.6559 | 2196.6559 | 2196.6559 | 2196.6559 | 2196.6559 | 2196.6559 | 2196.6559 | 2196.6559 | 2196.6559 | 2196.6559 | [6 empty] | 2.7734 | 2.7734 | 2.7734 | 2.7734 | 2.7734 | 2.7734 | 2.7734 | 2.7734 | 2.7733 | 2.7733 | 2.7737 | 2.7741 | 2.7745 | 2.7749 | 2.7753 | 2.7729 | 2.7706 | 2.7682 | 2.7658 | 2.7634 | 2.7615 | 2.7596 | 2.7578 | 2.7559 | 2.754 | 2.7517 | 2.7495 | 2.7473 | 2.745 | 2.7428 | 2.7409 | 2.7391 | 2.7373 | 2.7354 | 2.7336 | 2.7342 | 2.7349 | 2.7355 | 2.7362 | 2.7368 | 2.7375 | 2.7381 | 2.7388 | 2.7388 | 2.7388 | 2.7388 | 2.7388 | 2.7388 | 2.7388 | 2.7388 | 2.7388 | 2.7388 | 2.7388 | 2.7388 | 2.7388 | 2.7388 | 2.7388 | 2.7388 | 2.7388 | 2.7388 | 2.7388 | 2.7388 | 2.7388
300 | Albert - Eden |  |  | 2052 | 1180.8154 | 1158.7025 | 1137.0037 | 1115.7113 | 1094.8176 | 1114.9046 | 1135.36 | 1156.1908 | 1177.4038 | 1199.0059 | 1219.5351 | 1240.4157 | 1261.6539 | 1283.2557 | 1305.2274 | 1324.1602 | 1343.3677 | 1362.8538 | 1382.6226 | 1402.6781 | 1419.649 | 1436.8253 | 1454.2094 | 1471.8038 | 1489.6111 | 1512.2738 | 1535.2812 | 1558.6386 | 1582.3514 | 1606.425 | 1627.7308 | 1649.3192 | 1671.1939 | 1693.3588 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 | 1715.8176 |  | 3570 | 3503.1454 | 3437.5427 | 3373.1686 | 3310 | 3378.1135 | 3447.6287 | 3518.5744 | 3590.98 | 3664.8755 | 3736.7323 | 3809.998 | 3884.7002 | 3960.8671 | 4038.5274 | 4101.2517 | 4164.9503 | 4229.6382 | 4295.3307 | 4362.0436 | 4420.1276 | 4478.9851 | 4538.6263 | 4599.0616 | 4660.3017 | 4736.5179 | 4813.9805 | 4892.7099 | 4972.7269 | 5054.0525 | 5118.5001 | 5183.7694 | 5249.8711 | 5316.8156 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | 5384.6138 | [6 empty] | 837 | 844 | 851 | 858 | 865.7 | 879 | 892 | 905 | 918 | 931 | 944.7 | 956 | 967 | 978 | 989 | 1000 | 1011 | 1022 | 1033 | 1044 | 1055 | 1066 | 1077 | 1088 | 1099 | 1110 | 1121 | 1132 | 1143 | 1154 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | 1168.7 | [6 empty] | 3.0233 | 3.0233 | 3.0233 | 3.0233 | 3.0233 | 3.03 | 3.0366 | 3.0432 | 3.0499 | 3.0566 | 3.0641 | 3.0715 | 3.0791 | 3.0866 | 3.0941 | 3.0972 | 3.1004 | 3.1035 | 3.1067 | 3.1098 | 3.1135 | 3.1173 | 3.121 | 3.1248 | 3.1285 | 3.1321 | 3.1356 | 3.1391 | 3.1426 | 3.1461 | 3.1446 | 3.143 | 3.1414 | 3.1398 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382 | 3.1382
301 | Albert - Eden | AHP | Mt Roskill | 2060 | 1568.4043 | 1535.4558 | 1503.1994 | 1471.6207 | 1440.7054 | 1457.8473 | 1475.1931 | 1492.7453 | 1510.5064 | 1528.4788 | 1545.971 | 1563.6635 | 1581.5584 | 1599.6581 | 1617.965 | 1634.0667 | 1650.3287 | 1666.7526 | 1683.3398 | 1700.0922 | 1714.5019 | 1729.0337 | 1743.6887 | 1758.4679 | 1773.3724 | 1792.5831 | 1812.0019 | 1831.631 | 1851.4728 | 1871.5296 | 1889.5336 | 1907.7109 | 1926.063 | 1944.5916 | 1963.2985 | 2054.7308 | 2150.4212 | 2250.568 | 2355.3787 | 2465.0705 | 2579.8708 | 2700.0173 | 2825.7592 | 2825.7592 | 2825.7592 | 2825.7592 | 2825.7592 | 2825.7592 | 2825.7592 | 2825.7592 | 2825.7592 | 2825.7592 | 2825.7592 | 2825.7592 | 2825.7592 | 2825.7592 | 2825.7592 | 2825.7592 | 2825.7592 | 2825.7592 | 2825.7592 | 2825.7592 | 2825.7592 |  | 4790 | 4689.3733 | 4590.8605 | 4494.4172 | 4400 | 4455.8634 | 4512.4361 | 4569.7271 | 4627.7455 | 4686.5004 | 4743.9119 | 4802.0267 | 4860.8534 | 4920.4008 | 4980.6776 | 5028.2256 | 5076.2274 | 5124.6876 | 5173.6103 | 5223.0001 | 5265.2721 | 5307.8863 | 5350.8454 | 5394.1521 | 5437.8094 | 5494.4787 | 5551.7385 | 5609.595 | 5668.0545 | 5727.1233 | 5781.5196 | 5836.4326 | 5891.8672 | 5947.8283 | 6004.3209 | 6280.8631 | 6570.1421 | 6872.7444 | 7189.2838 | 7520.4021 | 7866.7707 | 8229.0921 | 8608.1011 | 8608.1011 | 8608.1011 | 8608.1011 | 8608.1011 | 8608.1011 | 8608.1011 | 8608.1011 | 8608.1011 | 8608.1011 | 8608.1011 | 8608.1011 | 8608.1011 | 8608.1011 | 8608.1011 | 8608.1011 | 8608.1011 | 8608.1011 | 8608.1011 | 8608.1011 | 8608.1011 | [6 empty] | 1105 | 1122 | 1139 | 1156 | 1171 | 1194 | 1217 | 1240 | 1263 | 1286 | 1307.2 | 1328 | 1349 | 1370 | 1391 | 1412 | 1433 | 1454 | 1475 | 1496 | 1517 | 1538 | 1559 | 1580 | 1601 | 1622 | 1643 | 1664 | 1685 | 1706 | 1723.7 | 1775.2331 | 1828.3068 | 1882.9673 | 1939.2619 | 1997.2396 | 2056.9506 | 2118.4468 | 2181.7815 | 2181.7815 | 2181.7815 | 2181.7815 | 2181.7815 | 2181.7815 | 2181.7815 | 2181.7815 | 2181.7815 | 2181.7815 | 2181.7815 | 2181.7815 | 2181.7815 | 2181.7815 | 2181.7815 | 2181.7815 | 2181.7815 | 2181.7815 | 2181.7815 | 2181.7815 | 2181.7815 | [6 empty] | 3.0541 | 3.0541 | 3.0541 | 3.0541 | 3.0541 | 3.0565 | 3.0589 | 3.0613 | 3.0637 | 3.0661 | 3.0686 | 3.071 | 3.0735 | 3.0759 | 3.0784 | 3.0771 | 3.0759 | 3.0747 | 3.0734 | 3.0722 | 3.071 | 3.0699 | 3.0687 | 3.0675 | 3.0664 | 3.0651 | 3.0639 | 3.0626 | 3.0614 | 3.0601 | 3.0598 | 3.0594 | 3.059 | 3.0587 | 3.0583 | 3.0568 | 3.0553 | 3.0538 | 3.0523 | 3.0508 | 3.0493 | 3.0478 | 3.0463 | 3.0463 | 3.0463 | 3.0463 | 3.0463 | 3.0463 | 3.0463 | 3.0463 | 3.0463 | 3.0463 | 3.0463 | 3.0463 | 3.0463 | 3.0463 | 3.0463 | 3.0463 | 3.0463 | 3.0463 | 3.0463 | 3.0463 | 3.0463
302 | Whau |  |  | 2052 | 1664.1691 | 1673.3432 | 1682.5679 | 1691.8434 | 1701.1701 | 1715.9434 | 1730.8451 | 1745.8762 | 1761.0378 | 1776.331 | 1791.3987 | 1806.5943 | 1821.9187 | 1837.3732 | 1852.9587 | 1866.7644 | 1880.673 | 1894.6852 | 1908.8018 | 1923.0236 | 1935.339 | 1947.7331 | 1960.2067 | 1972.7601 | 1985.3939 | 2001.9181 | 2018.5799 | 2035.3803 | 2052.3205 | 2069.4017 | 2084.9209 | 2100.5564 | 2116.3092 | 2132.1801 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 | 2148.1701 |  | 4630 | 4654.8 | 4679.7329 | 4704.7993 | 4730 | 4779.9001 | 4830.3265 | 4881.285 | 4932.7811 | 4984.8204 | 5036.391 | 5088.4952 | 5141.1383 | 5194.3262 | 5248.0642 | 5289.512 | 5331.2871 | 5373.3921 | 5415.8297 | 5458.6024 | 5496.1627 | 5533.9815 | 5572.0605 | 5610.4014 | 5649.0063 | 5698.497 | 5748.4213 | 5798.783 | 5849.5859 | 5900.8339 | 5944.108 | 5987.6994 | 6031.6104 | 6075.8436 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | 6120.401 | [6 empty] | 585 | 593 | 601 | 609 | 616.7 | 626 | 635 | 644 | 653 | 662 | 673.2 | 682 | 691 | 700 | 709 | 718 | 727 | 736 | 745 | 754 | 763 | 772 | 781 | 790 | 799 | 808 | 817 | 826 | 835 | 844 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | 845.9 | [6 empty] | 2.7822 | 2.7817 | 2.7813 | 2.7809 | 2.7804 | 2.7856 | 2.7907 | 2.7959 | 2.8011 | 2.8062 | 2.8114 | 2.8166 | 2.8218 | 2.827 | 2.8323 | 2.8335 | 2.8348 | 2.836 | 2.8373 | 2.8386 | 2.8399 | 2.8412 | 2.8426 | 2.8439 | 2.8453 | 2.8465 | 2.8478 | 2.849 | 2.8502 | 2.8515 | 2.851 | 2.8505 | 2.8501 | 2.8496 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491 | 2.8491
303 | Whau |  |  | 2052 | 1391.1781 | 1379.5936 | 1368.1056 | 1356.7132 | 1345.4157 | 1348.0923 | 1350.7743 | 1353.4616 | 1356.1542 | 1358.8523 | 1361.581 | 1364.3153 | 1367.055 | 1369.8003 | 1372.5511 | 1375.0499 | 1377.5533 | 1380.0613 | 1382.5738 | 1385.0909 | 1387.3179 | 1389.5485 | 1391.7826 | 1394.0204 | 1396.2617 | 1399.2581 | 1402.2608 | 1405.2701 | 1408.2857 | 1411.3079 | 1414.1182 | 1416.9342 | 1419.7557 | 1422.5829 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 | 1425.4157 |  | 4560 | 4522.0283 | 4484.3729 | 4447.031 | 4410 | 4422.3353 | 4434.7052 | 4447.1096 | 4459.5488 | 4472.0227 | 4484.6008 | 4497.2142 | 4509.8632 | 4522.5477 | 4535.2678 | 4541.7275 | 4548.1964 | 4554.6745 | 4561.1618 | 4567.6584 | 4573.2051 | 4578.7587 | 4584.3189 | 4589.8859 | 4595.4597 | 4603.4721 | 4611.4985 | 4619.5389 | 4627.5933 | 4635.6617 | 4644.7532 | 4653.8626 | 4662.9899 | 4672.135 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | 4681.2981 | [6 empty] | 807 | 813 | 819 | 825 | 832.8 | 843 | 853 | 863 | 873 | 883 | 894.9 | 903 | 911 | 919 | 927 | 935 | 943 | 951 | 959 | 967 | 975 | 983 | 991 | 999 | 1007 | 1015 | 1023 | 1031 | 1039 | 1047 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | 1056.7 | [6 empty] | 3.2778 | 3.2778 | 3.2778 | 3.2778 | 3.2778 | 3.2804 | 3.2831 | 3.2857 | 3.2884 | 3.291 | 3.2937 | 3.2963 | 3.299 | 3.3016 | 3.3043 | 3.303 | 3.3016 | 3.3003 | 3.299 | 3.2977 | 3.2964 | 3.2951 | 3.2938 | 3.2926 | 3.2913 | 3.2899 | 3.2886 | 3.2873 | 3.286 | 3.2847 | 3.2846 | 3.2845 | 3.2844 | 3.2843 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842 | 3.2842
304 | Whau |  |  | 2052 | 1219.0681 | 1217.4818 | 1215.8976 | 1214.3154 | 1212.7353 | 1213.5739 | 1214.4131 | 1215.2529 | 1216.0933 | 1216.9342 | 1217.7892 | 1218.6448 | 1219.5009 | 1220.3577 | 1221.2151 | 1222.0297 | 1222.8449 | 1223.6606 | 1224.4769 | 1225.2937 | 1226.0375 | 1226.7818 | 1227.5265 | 1228.2717 | 1229.0173 | 1229.9366 | 1230.8565 | 1231.7772 | 1232.6985 | 1233.6205 | 1234.4424 | 1235.2648 | 1236.0877 | 1236.9112 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 | 1237.7353 |  | 3850 | 3844.9902 | 3839.987 | 3834.9902 | 3830 | 3834.3378 | 3838.6805 | 3843.0281 | 3847.3807 | 3851.7382 | 3856.1393 | 3860.5454 | 3864.9566 | 3869.3729 | 3873.7941 | 3873.7014 | 3873.6087 | 3873.516 | 3873.4232 | 3873.3305 | 3872.9971 | 3872.6636 | 3872.3302 | 3871.9969 | 3871.6635 | 3871.8642 | 3872.0649 | 3872.2656 | 3872.4663 | 3872.667 | 3875.2379 | 3877.8105 | 3880.3848 | 3882.9609 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | 3885.5386 | [6 empty] | 1518 | 1526 | 1534 | 1542 | 1549.1 | 1568 | 1587 | 1606 | 1625 | 1644 | 1660.8 | 1672 | 1684 | 1696 | 1708 | 1720 | 1732 | 1744 | 1756 | 1768 | 1780 | 1792 | 1804 | 1816 | 1828 | 1840 | 1852 | 1864 | 1876 | 1888 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | 1892.7 | [6 empty] | 3.1582 | 3.1582 | 3.1582 | 3.1582 | 3.1582 | 3.1595 | 3.1609 | 3.1623 | 3.1637 | 3.1651 | 3.1665 | 3.1679 | 3.1693 | 3.1707 | 3.1721 | 3.1699 | 3.1677 | 3.1655 | 3.1633 | 3.1611 | 3.159 | 3.1568 | 3.1546 | 3.1524 | 3.1502 | 3.148 | 3.1458 | 3.1436 | 3.1415 | 3.1393 | 3.1393 | 3.1393 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392 | 3.1392
305 | Whau |  |  | 2052 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 4.2529 | 5.9659 | 8.3689 | 11.7398 | 16.4684 | 18.5878 | 20.9799 | 23.6799 | 26.7274 | 30.1672 | 32.3391 | 34.6673 | 37.1632 | 39.8388 | 42.707 | 44.7385 | 46.8666 | 49.096 | 51.4313 | 53.8778 | 56.5981 | 59.4558 | 62.4577 | 65.6113 | 68.924 | 71.5394 | 74.254 | 77.0717 | 79.9962 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 | 83.0318 |  | 30 | 30 | 30 | 30 | 30 | 33.308 | 36.9808 | 41.0585 | 45.5859 | 50.6125 | 54.2942 | 58.2436 | 62.4803 | 67.0252 | 71.9007 | 75.4084 | 79.0871 | 82.9454 | 86.9918 | 91.2357 | 94.4464 | 97.7701 | 101.2108 | 104.7726 | 108.4597 | 112.747 | 117.2037 | 121.8366 | 126.6527 | 131.6591 | 135.7476 | 139.9632 | 144.3096 | 148.791 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | 153.4116 | [6 empty] | 8012 | 8050 | 8088 | 8126 | 8165.5 | 8267 | 8369 | 8471 | 8573 | 8675 | 8775.3 | 8833 | 8891 | 8949 | 9007 | 9065 | 9123 | 9181 | 9239 | 9297 | 9355 | 9413 | 9471 | 9529 | 9587 | 9645 | 9703 | 9761 | 9819 | 9877 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | 9938.8 | [6 empty] | 9.8952 | 9.8952 | 9.8952 | 9.8952 | 9.8952 | 7.8318 | 6.1987 | 4.9061 | 3.883 | 3.0733 | 2.921 | 2.7762 | 2.6385 | 2.5077 | 2.3834 | 2.3318 | 2.2813 | 2.2319 | 2.1836 | 2.1363 | 2.1111 | 2.0861 | 2.0615 | 2.0371 | 2.0131 | 1.9921 | 1.9713 | 1.9507 | 1.9303 | 1.9102 | 1.8975 | 1.8849 | 1.8724 | 1.86 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476 | 1.8476
306 | Whau |  |  | 2052 | 1862.3076 | 1885.7164 | 1909.4195 | 1933.4204 | 1957.7231 | 1992.884 | 2028.6764 | 2065.1116 | 2102.2012 | 2139.9569 | 2175.8879 | 2212.4221 | 2249.5698 | 2287.3412 | 2325.7469 | 2358.7776 | 2392.2775 | 2426.2532 | 2460.7114 | 2495.659 | 2525.2053 | 2555.1014 | 2585.3515 | 2615.9597 | 2646.9303 | 2686.4806 | 2726.6219 | 2767.3629 | 2808.7128 | 2850.6804 | 2887.9041 | 2925.6138 | 2963.8159 | 3002.5168 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 | 3041.7231 |  | 5530 | 5596.2982 | 5663.3912 | 5731.2886 | 5800 | 5915.6631 | 6033.6327 | 6153.9548 | 6276.6764 | 6401.8454 | 6522.5791 | 6645.5897 | 6770.9202 | 6898.6144 | 7028.7168 | 7133.0869 | 7239.0069 | 7346.4996 | 7455.5886 | 7566.2974 | 7661.5782 | 7758.0589 | 7855.7545 | 7954.6803 | 8054.8519 | 8180.7023 | 8308.5189 | 8438.3326 | 8570.1745 | 8704.0763 | 8814.4191 | 8926.1608 | 9039.319 | 9153.9117 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | 9269.9572 | [6 empty] | 1412 | 1432 | 1452 | 1472 | 1491.8 | 1516 | 1541 | 1566 | 1591 | 1616 | 1639.9 | 1663 | 1686 | 1709 | 1732 | 1755 | 1778 | 1801 | 1824 | 1847 | 1870 | 1893 | 1916 | 1939 | 1962 | 1985 | 2008 | 2031 | 2054 | 2077 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | 2109.5 | [6 empty] | 2.9694 | 2.9677 | 2.966 | 2.9643 | 2.9626 | 2.9684 | 2.9742 | 2.98 | 2.9858 | 2.9916 | 2.9977 | 3.0038 | 3.0099 | 3.016 | 3.0221 | 3.0241 | 3.026 | 3.0279 | 3.0299 | 3.0318 | 3.034 | 3.0363 | 3.0386 | 3.0408 | 3.0431 | 3.0451 | 3.0472 | 3.0492 | 3.0513 | 3.0533 | 3.0522 | 3.051 | 3.0499 | 3.0487 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476 | 3.0476
307 | Whau |  |  | 2052 | 1370.9214 | 1356.7782 | 1342.7809 | 1328.928 | 1315.218 | 1320.4666 | 1325.7362 | 1331.0268 | 1336.3385 | 1341.6713 | 1347.0224 | 1352.3948 | 1357.7886 | 1363.2039 | 1368.6408 | 1373.5905 | 1378.558 | 1383.5435 | 1388.547 | 1393.5686 | 1398.0085 | 1402.4626 | 1406.9309 | 1411.4134 | 1415.9102 | 1421.716 | 1427.5456 | 1433.3991 | 1439.2766 | 1445.1782 | 1450.5461 | 1455.934 | 1461.3419 | 1466.7699 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 | 1472.218 |  | 4430 | 4384.2976 | 4339.0667 | 4294.3025 | 4250 | 4272.2299 | 4294.5761 | 4317.0391 | 4339.6197 | 4362.3184 | 4385.0983 | 4407.9971 | 4431.0156 | 4454.1542 | 4477.4137 | 4493.3478 | 4509.3387 | 4525.3865 | 4541.4914 | 4557.6536 | 4571.9467 | 4586.2847 | 4600.6677 | 4615.0957 | 4629.569 | 4648.2596 | 4667.0257 | 4685.8676 | 4704.7855 | 4723.7798 | 4741.0606 | 4758.4047 | 4775.8122 | 4793.2834 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | 4810.8185 | [6 empty] | 1228 | 1239 | 1250 | 1261 | 1272.1 | 1291 | 1310 | 1329 | 1348 | 1367 | 1387.2 | 1401 | 1415 | 1429 | 1443 | 1457 | 1471 | 1485 | 1499 | 1513 | 1527 | 1541 | 1555 | 1569 | 1583 | 1597 | 1611 | 1625 | 1639 | 1653 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | 1660.9 | [6 empty] | 3.2314 | 3.2314 | 3.2314 | 3.2314 | 3.2314 | 3.2354 | 3.2394 | 3.2434 | 3.2474 | 3.2514 | 3.2554 | 3.2594 | 3.2634 | 3.2674 | 3.2714 | 3.2712 | 3.2711 | 3.2709 | 3.2707 | 3.2705 | 3.2703 | 3.2702 | 3.27 | 3.2698 | 3.2697 | 3.2695 | 3.2693 | 3.2691 | 3.2689 | 3.2686 | 3.2685 | 3.2683 | 3.2681 | 3.2679 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677 | 3.2677
308 | Albert - Eden | AHP | Mt Roskill | 2060 | 1098.0016 | 1102.2353 | 1106.4854 | 1110.7518 | 1115.0347 | 1144.8122 | 1175.385 | 1206.7743 | 1239.0018 | 1272.09 | 1302.6136 | 1333.8697 | 1365.8757 | 1398.6497 | 1432.2102 | 1447.9125 | 1463.7871 | 1479.8357 | 1496.0603 | 1512.4627 | 1519.2112 | 1525.9899 | 1532.7988 | 1539.6381 | 1546.508 | 1549.6368 | 1552.772 | 1555.9135 | 1559.0614 | 1562.2156 | 1562.2156 | 1562.2156 | 1562.2156 | 1562.2156 | 1562.2156 | 1601.3998 | 1641.5668 | 1682.7413 | 1724.9485 | 1768.2144 | 1812.5656 | 1858.0291 | 1904.633 | 1904.633 | 1904.633 | 1904.633 | 1904.633 | 1904.633 | 1904.633 | 1904.633 | 1904.633 | 1904.633 | 1904.633 | 1904.633 | 1904.633 | 1904.633 | 1904.633 | 1904.633 | 1904.633 | 1904.633 | 1904.633 | 1904.633 | 1904.633 |  | 3330 | 3342.4302 | 3354.9069 | 3367.4301 | 3380 | 3478.7889 | 3580.4651 | 3685.1131 | 3792.8197 | 3903.6743 | 4007.9033 | 4114.9152 | 4224.7844 | 4337.5871 | 4453.4017 | 4508.2103 | 4563.6935 | 4619.8594 | 4676.7167 | 4734.2737 | 4762.4745 | 4790.8434 | 4819.3812 | 4848.0891 | 4876.9679 | 4894.341 | 4911.776 | 4929.2731 | 4946.8325 | 4964.4544 | 4964.4544 | 4964.4544 | 4964.4544 | 4964.4544 | 4964.4544 | 5086.4764 | 5211.4976 | 5339.5917 | 5470.8343 | 5605.3027 | 5743.0761 | 5884.236 | 6028.8654 | 6028.8654 | 6028.8654 | 6028.8654 | 6028.8654 | 6028.8654 | 6028.8654 | 6028.8654 | 6028.8654 | 6028.8654 | 6028.8654 | 6028.8654 | 6028.8654 | 6028.8654 | 6028.8654 | 6028.8654 | 6028.8654 | 6028.8654 | 6028.8654 | 6028.8654 | 6028.8654 | [6 empty] | 731 | 741 | 751 | 761 | 770.8 | 786 | 801 | 816 | 831 | 846 | 861.6 | 876 | 891 | 906 | 921 | 936 | 951 | 966 | 981 | 996 | 1011 | 1026 | 1041 | 1056 | 1071 | 1086 | 1101 | 1116 | 1131 | 1146 | 1153.5 | 1161.2462 | 1169.0445 | 1176.8951 | 1184.7984 | 1192.7548 | 1200.7647 | 1208.8283 | 1216.9461 | 1216.9461 | 1216.9461 | 1216.9461 | 1216.9461 | 1216.9461 | 1216.9461 | 1216.9461 | 1216.9461 | 1216.9461 | 1216.9461 | 1216.9461 | 1216.9461 | 1216.9461 | 1216.9461 | 1216.9461 | 1216.9461 | 1216.9461 | 1216.9461 | 1216.9461 | 1216.9461 | [6 empty] | 3.0328 | 3.0324 | 3.032 | 3.0317 | 3.0313 | 3.0387 | 3.0462 | 3.0537 | 3.0612 | 3.0687 | 3.0768 | 3.0849 | 3.0931 | 3.1013 | 3.1095 | 3.1136 | 3.1177 | 3.1219 | 3.126 | 3.1302 | 3.1348 | 3.1395 | 3.1442 | 3.1488 | 3.1535 | 3.1584 | 3.1632 | 3.1681 | 3.173 | 3.1778 | 3.1778 | 3.1778 | 3.1778 | 3.1778 | 3.1778 | 3.1763 | 3.1747 | 3.1732 | 3.1716 | 3.17 | 3.1685 | 3.1669 | 3.1654 | 3.1654 | 3.1654 | 3.1654 | 3.1654 | 3.1654 | 3.1654 | 3.1654 | 3.1654 | 3.1654 | 3.1654 | 3.1654 | 3.1654 | 3.1654 | 3.1654 | 3.1654 | 3.1654 | 3.1654 | 3.1654 | 3.1654 | 3.1654
309 | Albert - Eden | AHP | Mt Roskill | 2060 | 720.587 | 719.7955 | 719.005 | 718.2153 | 717.4265 | 717.4265 | 717.4265 | 717.4265 | 717.4265 | 717.4265 | 717.4265 | 717.4265 | 717.4265 | 717.4265 | 717.4265 | 730.718 | 744.2558 | 758.0444 | 772.0885 | 786.3927 | 805.5149 | 825.1021 | 845.1656 | 865.717 | 886.7681 | 912.295 | 938.5568 | 965.5745 | 993.37 | 1021.9657 | 1046.147 | 1070.9006 | 1096.2398 | 1122.1786 | 1148.7312 | 1070.4746 | 997.5492 | 929.5918 | 866.264 | 807.2503 | 752.2569 | 701.0099 | 653.254 | 653.254 | 653.254 | 653.254 | 653.254 | 653.254 | 653.254 | 653.254 | 653.254 | 653.254 | 653.254 | 653.254 | 653.254 | 653.254 | 653.254 | 653.254 | 653.254 | 653.254 | 653.254 | 653.254 | 653.254 |  | 2280 | 2277.4959 | 2274.9945 | 2272.4959 | 2270 | 2272.96 | 2275.9239 | 2278.8917 | 2281.8633 | 2284.8388 | 2287.7989 | 2290.7629 | 2293.7306 | 2296.7022 | 2299.6777 | 2341.5591 | 2384.2033 | 2427.6241 | 2471.8356 | 2516.8524 | 2577.1511 | 2638.8945 | 2702.1171 | 2766.8544 | 2833.1427 | 2913.6859 | 2996.519 | 3081.7069 | 3169.3166 | 3259.417 | 3335.731 | 3413.8318 | 3493.7612 | 3575.562 | 3659.278 | 3408.0547 | 3174.0787 | 2956.1661 | 2753.214 | 2564.1954 | 2388.1536 | 2224.1978 | 2071.4981 | 2071.4981 | 2071.4981 | 2071.4981 | 2071.4981 | 2071.4981 | 2071.4981 | 2071.4981 | 2071.4981 | 2071.4981 | 2071.4981 | 2071.4981 | 2071.4981 | 2071.4981 | 2071.4981 | 2071.4981 | 2071.4981 | 2071.4981 | 2071.4981 | 2071.4981 | 2071.4981 | [6 empty] | 1437 | 1459 | 1481 | 1503 | 1524.3 | 1551 | 1578 | 1605 | 1632 | 1659 | 1684.2 | 1709 | 1734 | 1759 | 1784 | 1809 | 1834 | 1859 | 1884 | 1909 | 1934 | 1959 | 1984 | 2009 | 2034 | 2059 | 2084 | 2109 | 2134 | 2159 | 2181.4 | 2053.9617 | 1933.9684 | 1820.9852 | 1714.6025 | 1614.4347 | 1520.1188 | 1431.3128 | 1347.6949 | 1347.6949 | 1347.6949 | 1347.6949 | 1347.6949 | 1347.6949 | 1347.6949 | 1347.6949 | 1347.6949 | 1347.6949 | 1347.6949 | 1347.6949 | 1347.6949 | 1347.6949 | 1347.6949 | 1347.6949 | 1347.6949 | 1347.6949 | 1347.6949 | 1347.6949 | 1347.6949 | [6 empty] | 3.1641 | 3.1641 | 3.1641 | 3.1641 | 3.1641 | 3.1682 | 3.1723 | 3.1765 | 3.1806 | 3.1848 | 3.1889 | 3.193 | 3.1972 | 3.2013 | 3.2055 | 3.2045 | 3.2035 | 3.2025 | 3.2015 | 3.2005 | 3.1994 | 3.1983 | 3.1971 | 3.196 | 3.1949 | 3.1938 | 3.1927 | 3.1916 | 3.1905 | 3.1894 | 3.1886 | 3.1878 | 3.187 | 3.1863 | 3.1855 | 3.1837 | 3.1819 | 3.1801 | 3.1783 | 3.1765 | 3.1747 | 3.1728 | 3.171 | 3.171 | 3.171 | 3.171 | 3.171 | 3.171 | 3.171 | 3.171 | 3.171 | 3.171 | 3.171 | 3.171 | 3.171 | 3.171 | 3.171 | 3.171 | 3.171 | 3.171 | 3.171 | 3.171 | 3.171
310 | Albert - Eden | AHP | Mt Roskill | 2060 | 808.533 | 800.4547 | 792.4572 | 784.5395 | 776.701 | 802.6803 | 829.5286 | 857.275 | 885.9494 | 915.5829 | 942.2964 | 969.7892 | 998.0843 | 1027.2048 | 1057.175 | 1067.0452 | 1077.0075 | 1087.0629 | 1097.2121 | 1107.4561 | 1107.4561 | 1107.4561 | 1107.4561 | 1107.4561 | 1107.4561 | 1107.4561 | 1107.4561 | 1107.4561 | 1107.4561 | 1107.4561 | 1107.4561 | 1107.4561 | 1107.4561 | 1107.4561 | 1107.4561 | 1172.0967 | 1240.5103 | 1312.9171 | 1389.5502 | 1470.6562 | 1556.4963 | 1647.3467 | 1743.5 | 1743.5 | 1743.5 | 1743.5 | 1743.5 | 1743.5 | 1743.5 | 1743.5 | 1743.5 | 1743.5 | 1743.5 | 1743.5 | 1743.5 | 1743.5 | 1743.5 | 1743.5 | 1743.5 | 1743.5 | 1743.5 | 1743.5 | 1743.5 |  | 2540 | 2514.6222 | 2489.4979 | 2464.6247 | 2440 | 2520.1393 | 2602.9107 | 2688.4007 | 2776.6985 | 2867.8963 | 2951.5735 | 3037.6921 | 3126.3235 | 3217.5408 | 3311.4197 | 3341.1512 | 3371.1498 | 3401.4177 | 3431.9573 | 3462.7712 | 3462.7712 | 3462.7712 | 3462.7712 | 3462.7712 | 3462.7712 | 3462.7712 | 3462.7712 | 3462.7712 | 3462.7712 | 3462.7712 | 3462.7712 | 3462.7712 | 3462.7712 | 3462.7712 | 3462.7712 | 3663.0128 | 3874.8339 | 4098.9039 | 4335.9313 | 4586.6652 | 4851.8983 | 5132.469 | 5429.2643 | 5429.2643 | 5429.2643 | 5429.2643 | 5429.2643 | 5429.2643 | 5429.2643 | 5429.2643 | 5429.2643 | 5429.2643 | 5429.2643 | 5429.2643 | 5429.2643 | 5429.2643 | 5429.2643 | 5429.2643 | 5429.2643 | 5429.2643 | 5429.2643 | 5429.2643 | 5429.2643 | [6 empty] | 312 | 314 | 316 | 318 | 320.4 | 326 | 331 | 336 | 341 | 346 | 352.8 | 358 | 363 | 368 | 373 | 378 | 383 | 388 | 393 | 398 | 403 | 408 | 413 | 418 | 423 | 428 | 433 | 438 | 443 | 448 | 449.8 | 472.2454 | 495.8108 | 520.5522 | 546.5282 | 573.8005 | 602.4336 | 632.4955 | 664.0576 | 664.0576 | 664.0576 | 664.0576 | 664.0576 | 664.0576 | 664.0576 | 664.0576 | 664.0576 | 664.0576 | 664.0576 | 664.0576 | 664.0576 | 664.0576 | 664.0576 | 664.0576 | 664.0576 | 664.0576 | 664.0576 | 664.0576 | 664.0576 | [6 empty] | 3.1415 | 3.1415 | 3.1415 | 3.1415 | 3.1415 | 3.1397 | 3.1378 | 3.136 | 3.1342 | 3.1323 | 3.1323 | 3.1323 | 3.1323 | 3.1323 | 3.1323 | 3.1312 | 3.1301 | 3.129 | 3.1279 | 3.1268 | 3.1268 | 3.1268 | 3.1268 | 3.1268 | 3.1268 | 3.1268 | 3.1268 | 3.1268 | 3.1268 | 3.1268 | 3.1268 | 3.1268 | 3.1268 | 3.1268 | 3.1268 | 3.1252 | 3.1236 | 3.122 | 3.1204 | 3.1188 | 3.1172 | 3.1156 | 3.114 | 3.114 | 3.114 | 3.114 | 3.114 | 3.114 | 3.114 | 3.114 | 3.114 | 3.114 | 3.114 | 3.114 | 3.114 | 3.114 | 3.114 | 3.114 | 3.114 | 3.114 | 3.114 | 3.114 | 3.114
311 | Whau | AHP | Mt Roskill | 2060 | 1252.4475 | 1245.7635 | 1239.1153 | 1232.5025 | 1225.925 | 1231.6488 | 1237.3993 | 1243.1767 | 1248.981 | 1254.8125 | 1260.6482 | 1266.511 | 1272.4011 | 1278.3186 | 1284.2636 | 1289.1944 | 1294.1442 | 1299.1129 | 1304.1007 | 1309.1077 | 1313.2686 | 1317.4427 | 1321.6301 | 1325.8308 | 1330.0449 | 1335.6378 | 1341.2542 | 1346.8943 | 1352.558 | 1358.2456 | 1363.4933 | 1368.7612 | 1374.0495 | 1379.3583 | 1384.6875 | 1498.5321 | 1621.7367 | 1755.0708 | 1899.3672 | 2055.5271 | 2224.5261 | 2407.4196 | 2605.35 | 2605.35 | 2605.35 | 2605.35 | 2605.35 | 2605.35 | 2605.35 | 2605.35 | 2605.35 | 2605.35 | 2605.35 | 2605.35 | 2605.35 | 2605.35 | 2605.35 | 2605.35 | 2605.35 | 2605.35 | 2605.35 | 2605.35 | 2605.35 |  | 4250 | 4227.3191 | 4204.7592 | 4182.3197 | 4160 | 4178.5598 | 4197.2024 | 4215.9282 | 4234.7376 | 4253.6308 | 4272.5315 | 4291.5163 | 4310.5853 | 4329.7391 | 4348.978 | 4360.4157 | 4371.8835 | 4383.3815 | 4394.9097 | 4406.4682 | 4415.134 | 4423.8169 | 4432.5168 | 4441.2338 | 4449.968 | 4463.2233 | 4476.5181 | 4489.8525 | 4503.2266 | 4516.6406 | 4533.9886 | 4551.4032 | 4568.8847 | 4586.4333 | 4604.0493 | 4980.1451 | 5386.9633 | 5827.0138 | 6303.0111 | 6817.8916 | 7374.8318 | 7977.2673 | 8628.9146 | 8628.9146 | 8628.9146 | 8628.9146 | 8628.9146 | 8628.9146 | 8628.9146 | 8628.9146 | 8628.9146 | 8628.9146 | 8628.9146 | 8628.9146 | 8628.9146 | 8628.9146 | 8628.9146 | 8628.9146 | 8628.9146 | 8628.9146 | 8628.9146 | 8628.9146 | 8628.9146 | [6 empty] | 1005 | 1012 | 1019 | 1026 | 1034.2 | 1049 | 1063 | 1077 | 1091 | 1105 | 1121 | 1132 | 1143 | 1154 | 1165 | 1176 | 1187 | 1198 | 1209 | 1220 | 1231 | 1242 | 1253 | 1264 | 1275 | 1286 | 1297 | 1308 | 1319 | 1330 | 1342.2 | 1423.254 | 1509.2027 | 1600.3418 | 1696.9847 | 1799.4637 | 1908.1313 | 2023.3613 | 2145.5498 | 2145.5498 | 2145.5498 | 2145.5498 | 2145.5498 | 2145.5498 | 2145.5498 | 2145.5498 | 2145.5498 | 2145.5498 | 2145.5498 | 2145.5498 | 2145.5498 | 2145.5498 | 2145.5498 | 2145.5498 | 2145.5498 | 2145.5498 | 2145.5498 | 2145.5498 | 2145.5498 | [6 empty] | 3.3934 | 3.3934 | 3.3934 | 3.3934 | 3.3934 | 3.3927 | 3.392 | 3.3913 | 3.3906 | 3.3899 | 3.3892 | 3.3885 | 3.3878 | 3.3871 | 3.3864 | 3.3823 | 3.3782 | 3.3741 | 3.3701 | 3.366 | 3.3619 | 3.3579 | 3.3538 | 3.3498 | 3.3457 | 3.3416 | 3.3376 | 3.3335 | 3.3294 | 3.3253 | 3.3253 | 3.3252 | 3.3251 | 3.325 | 3.325 | 3.3233 | 3.3217 | 3.3201 | 3.3185 | 3.3169 | 3.3152 | 3.3136 | 3.312 | 3.312 | 3.312 | 3.312 | 3.312 | 3.312 | 3.312 | 3.312 | 3.312 | 3.312 | 3.312 | 3.312 | 3.312 | 3.312 | 3.312 | 3.312 | 3.312 | 3.312 | 3.312 | 3.312 | 3.312
312 | Whau | AHP | Mt Roskill | 2060 | 1255.2474 | 1251.2561 | 1247.2775 | 1243.3115 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1239.3582 | 1314.9674 | 1395.1893 | 1480.3053 | 1570.6139 | 1666.432 | 1768.0956 | 1875.9614 | 1990.4077 | 1990.4077 | 1990.4077 | 1990.4077 | 1990.4077 | 1990.4077 | 1990.4077 | 1990.4077 | 1990.4077 | 1990.4077 | 1990.4077 | 1990.4077 | 1990.4077 | 1990.4077 | 1990.4077 | 1990.4077 | 1990.4077 | 1990.4077 | 1990.4077 | 1990.4077 | 1990.4077 |  | 3950 | 3937.4402 | 3924.9204 | 3912.4403 | 3900 | 3902.4734 | 3904.9485 | 3907.425 | 3909.9032 | 3912.3829 | 3914.8564 | 3917.3314 | 3919.808 | 3922.2861 | 3924.7658 | 3922.5603 | 3920.3559 | 3918.1528 | 3915.9509 | 3913.7503 | 3911.5447 | 3909.3403 | 3907.1372 | 3904.9354 | 3902.7347 | 3900.5291 | 3898.3248 | 3896.1217 | 3893.9198 | 3891.7192 | 3891.7192 | 3891.7192 | 3891.7192 | 3891.7192 | 3891.7192 | 4127.113 | 4376.7447 | 4641.4757 | 4922.2191 | 5219.9435 | 5535.6759 | 5870.5058 | 6225.5881 | 6225.5881 | 6225.5881 | 6225.5881 | 6225.5881 | 6225.5881 | 6225.5881 | 6225.5881 | 6225.5881 | 6225.5881 | 6225.5881 | 6225.5881 | 6225.5881 | 6225.5881 | 6225.5881 | 6225.5881 | 6225.5881 | 6225.5881 | 6225.5881 | 6225.5881 | 6225.5881 | [6 empty] | 546 | 550 | 554 | 558 | 562.1 | 570 | 577 | 584 | 591 | 598 | 606.7 | 613 | 620 | 627 | 634 | 641 | 648 | 655 | 662 | 669 | 676 | 683 | 690 | 697 | 704 | 711 | 718 | 725 | 732 | 739 | 740.5 | 757.6897 | 775.2784 | 793.2754 | 811.6903 | 830.5325 | 849.8122 | 869.5394 | 889.7246 | 889.7246 | 889.7246 | 889.7246 | 889.7246 | 889.7246 | 889.7246 | 889.7246 | 889.7246 | 889.7246 | 889.7246 | 889.7246 | 889.7246 | 889.7246 | 889.7246 | 889.7246 | 889.7246 | 889.7246 | 889.7246 | 889.7246 | 889.7246 | [6 empty] | 3.1468 | 3.1468 | 3.1468 | 3.1468 | 3.1468 | 3.1488 | 3.1508 | 3.1528 | 3.1548 | 3.1568 | 3.1588 | 3.1608 | 3.1628 | 3.1648 | 3.1668 | 3.165 | 3.1632 | 3.1614 | 3.1597 | 3.1579 | 3.1561 | 3.1543 | 3.1525 | 3.1508 | 3.149 | 3.1472 | 3.1454 | 3.1437 | 3.1419 | 3.1401 | 3.1401 | 3.1401 | 3.1401 | 3.1401 | 3.1401 | 3.1386 | 3.137 | 3.1355 | 3.1339 | 3.1324 | 3.1309 | 3.1293 | 3.1278 | 3.1278 | 3.1278 | 3.1278 | 3.1278 | 3.1278 | 3.1278 | 3.1278 | 3.1278 | 3.1278 | 3.1278 | 3.1278 | 3.1278 | 3.1278 | 3.1278 | 3.1278 | 3.1278 | 3.1278 | 3.1278 | 3.1278 | 3.1278
313 | Whau |  |  | 2052 | 1452.6318 | 1451.7904 | 1450.9495 | 1450.1091 | 1449.2692 | 1450.108 | 1450.9473 | 1451.7871 | 1452.6274 | 1453.4681 | 1454.3233 | 1455.179 | 1456.0351 | 1456.8918 | 1457.749 | 1458.5638 | 1459.3791 | 1460.1948 | 1461.011 | 1461.8276 | 1462.5716 | 1463.3159 | 1464.0606 | 1464.8057 | 1465.5512 | 1466.4707 | 1467.3908 | 1468.3114 | 1469.2326 | 1470.1544 | 1470.9765 | 1471.799 | 1472.6219 | 1473.4453 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 | 1474.2692 |  | 4320 | 4317.4978 | 4314.9971 | 4312.4978 | 4310 | 4325.0754 | 4340.2035 | 4355.3845 | 4370.6187 | 4385.9061 | 4401.1041 | 4416.3549 | 4431.6585 | 4447.0151 | 4462.4249 | 4470.4889 | 4478.5675 | 4486.6607 | 4494.7685 | 4502.8909 | 4510.7735 | 4518.6699 | 4526.5801 | 4534.5042 | 4542.4421 | 4550.8847 | 4559.3431 | 4567.8171 | 4576.3069 | 4584.8125 | 4587.3125 | 4589.8139 | 4592.3166 | 4594.8207 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | 4597.3261 | [6 empty] | 1165 | 1176 | 1187 | 1198 | 1208.2 | 1225 | 1242 | 1259 | 1276 | 1293 | 1311.6 | 1326 | 1341 | 1356 | 1371 | 1386 | 1401 | 1416 | 1431 | 1446 | 1461 | 1476 | 1491 | 1506 | 1521 | 1536 | 1551 | 1566 | 1581 | 1596 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | 1603 | [6 empty] | 2.9739 | 2.9739 | 2.9739 | 2.9739 | 2.9739 | 2.9826 | 2.9913 | 3 | 3.0088 | 3.0175 | 3.0262 | 3.0349 | 3.0436 | 3.0524 | 3.0612 | 3.065 | 3.0688 | 3.0726 | 3.0765 | 3.0803 | 3.0841 | 3.088 | 3.0918 | 3.0956 | 3.0995 | 3.1033 | 3.1071 | 3.1109 | 3.1148 | 3.1186 | 3.1185 | 3.1185 | 3.1185 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184 | 3.1184
314 | Whau |  |  | 2052 | 1900.8131 | 1900.0017 | 1899.1906 | 1898.3798 | 1897.5694 | 1900.2491 | 1902.9327 | 1905.62 | 1908.3111 | 1911.006 | 1913.7379 | 1916.4738 | 1919.2135 | 1921.9572 | 1924.7048 | 1927.2062 | 1929.711 | 1932.2189 | 1934.7302 | 1937.2447 | 1939.4737 | 1941.7053 | 1943.9394 | 1946.1762 | 1948.4155 | 1951.4154 | 1954.42 | 1957.4293 | 1960.4431 | 1963.4616 | 1966.2751 | 1969.0926 | 1971.9142 | 1974.7398 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 | 1977.5694 |  | 5860 | 5857.4984 | 5854.9979 | 5852.4984 | 5850 | 5848.5015 | 5847.0035 | 5845.5058 | 5844.0084 | 5842.5115 | 5841.0342 | 5839.5574 | 5838.0808 | 5836.6047 | 5835.1289 | 5828.6949 | 5822.268 | 5815.8481 | 5809.4354 | 5803.0297 | 5795.6043 | 5788.1884 | 5780.782 | 5773.3851 | 5765.9977 | 5760.6726 | 5755.3524 | 5750.0371 | 5744.7267 | 5739.4213 | 5747.5973 | 5755.785 | 5763.9843 | 5772.1954 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | 5780.4181 | [6 empty] | 902 | 910 | 918 | 926 | 932.2 | 944 | 956 | 968 | 980 | 992 | 1001.5 | 1011 | 1021 | 1031 | 1041 | 1051 | 1061 | 1071 | 1081 | 1091 | 1101 | 1111 | 1121 | 1131 | 1141 | 1151 | 1161 | 1171 | 1181 | 1191 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | 1200.5 | [6 empty] | 3.0829 | 3.0829 | 3.0829 | 3.0829 | 3.0829 | 3.0778 | 3.0726 | 3.0675 | 3.0624 | 3.0573 | 3.0522 | 3.047 | 3.0419 | 3.0368 | 3.0317 | 3.0244 | 3.0172 | 3.0099 | 3.0027 | 2.9955 | 2.9882 | 2.981 | 2.9737 | 2.9665 | 2.9593 | 2.952 | 2.9448 | 2.9375 | 2.9303 | 2.9231 | 2.9231 | 2.9231 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923 | 2.923
315 | Whau |  |  | 2052 | 1084.9354 | 1083.3124 | 1081.6919 | 1080.0738 | 1078.4582 | 1080.4662 | 1082.4779 | 1084.4934 | 1086.5126 | 1088.5356 | 1090.5827 | 1092.6337 | 1094.6885 | 1096.7471 | 1098.8097 | 1100.7478 | 1102.6893 | 1104.6342 | 1106.5826 | 1108.5344 | 1110.2975 | 1112.0634 | 1113.8321 | 1115.6036 | 1117.378 | 1119.6684 | 1121.9636 | 1124.2634 | 1126.568 | 1128.8773 | 1130.9856 | 1133.0978 | 1135.214 | 1137.3341 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 | 1139.4582 |  | 3350 | 3344.9888 | 3339.985 | 3334.9888 | 3330 | 3327.891 | 3325.7833 | 3323.6769 | 3321.5719 | 3319.4682 | 3317.3233 | 3315.1798 | 3313.0377 | 3310.8969 | 3308.7575 | 3304.3277 | 3299.9037 | 3295.4857 | 3291.0736 | 3286.6674 | 3281.5356 | 3276.4118 | 3271.296 | 3266.1882 | 3261.0884 | 3257.333 | 3253.582 | 3249.8352 | 3246.0928 | 3242.3547 | 3248.4411 | 3254.5389 | 3260.6482 | 3266.7689 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | 3272.9011 | [6 empty] | 846 | 855 | 864 | 873 | 880.7 | 892 | 904 | 916 | 928 | 940 | 949.7 | 959 | 969 | 979 | 989 | 999 | 1009 | 1019 | 1029 | 1039 | 1049 | 1059 | 1069 | 1079 | 1089 | 1099 | 1109 | 1119 | 1129 | 1139 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | 1140.2 | [6 empty] | 3.0877 | 3.0877 | 3.0877 | 3.0877 | 3.0877 | 3.0801 | 3.0724 | 3.0647 | 3.0571 | 3.0495 | 3.0418 | 3.0341 | 3.0265 | 3.0188 | 3.0112 | 3.0019 | 2.9926 | 2.9833 | 2.9741 | 2.9649 | 2.9555 | 2.9462 | 2.937 | 2.9277 | 2.9185 | 2.9092 | 2.8999 | 2.8906 | 2.8814 | 2.8722 | 2.8722 | 2.8722 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723 | 2.8723
316 | Puketapapa |  |  | 2052 | 1741.2653 | 1762.6266 | 1784.2499 | 1806.1386 | 1828.2957 | 1842.8426 | 1857.5053 | 1872.2846 | 1887.1815 | 1902.197 | 1917.0324 | 1931.9836 | 1947.0514 | 1962.2366 | 1977.5404 | 1991.1457 | 2004.8447 | 2018.6379 | 2032.526 | 2046.5097 | 2058.6526 | 2070.8676 | 2083.155 | 2095.5154 | 2107.9491 | 2124.2459 | 2140.6687 | 2157.2185 | 2173.8963 | 2190.703 | 2206.0062 | 2221.4164 | 2236.9342 | 2252.5604 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 | 2268.2957 |  | 5410 | 5476.2723 | 5543.3564 | 5611.2623 | 5680 | 5697.1982 | 5714.4484 | 5731.7508 | 5749.1057 | 5766.5131 | 5782.3614 | 5798.2533 | 5814.1889 | 5830.1682 | 5846.1915 | 5855.9534 | 5865.7315 | 5875.526 | 5885.3368 | 5895.164 | 5898.6513 | 5902.1406 | 5905.6319 | 5909.1254 | 5912.6209 | 5925.8151 | 5939.0387 | 5952.2918 | 5965.5745 | 5978.8869 | 6020.5978 | 6062.5997 | 6104.8946 | 6147.4845 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | 6190.3716 | [6 empty] | 1031 | 1041 | 1051 | 1061 | 1069.1 | 1083 | 1097 | 1111 | 1125 | 1139 | 1151.5 | 1163 | 1175 | 1187 | 1199 | 1211 | 1223 | 1235 | 1247 | 1259 | 1271 | 1283 | 1295 | 1307 | 1319 | 1331 | 1343 | 1355 | 1367 | 1379 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | 1385.7 | [6 empty] | 3.1069 | 3.1069 | 3.1068 | 3.1068 | 3.1067 | 3.0915 | 3.0764 | 3.0614 | 3.0464 | 3.0315 | 3.0163 | 3.0012 | 2.9862 | 2.9712 | 2.9563 | 2.941 | 2.9258 | 2.9106 | 2.8956 | 2.8806 | 2.8653 | 2.8501 | 2.8349 | 2.8199 | 2.8049 | 2.7896 | 2.7744 | 2.7592 | 2.7442 | 2.7292 | 2.7292 | 2.7292 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291 | 2.7291
317 | Puketapapa | AHP | Mt Roskill | 2060 | 1370.0887 | 1374.559 | 1379.0438 | 1383.5433 | 1388.0575 | 1388.9452 | 1389.8335 | 1390.7223 | 1391.6117 | 1392.5017 | 1393.4067 | 1394.3123 | 1395.2185 | 1396.1253 | 1397.0326 | 1397.8612 | 1398.6902 | 1399.5197 | 1400.3498 | 1401.1803 | 1401.9185 | 1402.657 | 1403.396 | 1404.1353 | 1404.8751 | 1405.869 | 1406.8636 | 1407.8589 | 1408.8549 | 1409.8517 | 1410.7837 | 1411.7163 | 1412.6495 | 1413.5834 | 1414.5179 | 1506.1639 | 1603.7477 | 1707.6538 | 1818.292 | 1936.0984 | 2061.5374 | 2195.1035 | 2337.3234 | 2337.3234 | 2337.3234 | 2337.3234 | 2337.3234 | 2337.3234 | 2337.3234 | 2337.3234 | 2337.3234 | 2337.3234 | 2337.3234 | 2337.3234 | 2337.3234 | 2337.3234 | 2337.3234 | 2337.3234 | 2337.3234 | 2337.3234 | 2337.3234 | 2337.3234 | 2337.3234 |  | 4620 | 4634.9275 | 4649.9032 | 4664.9273 | 4680 | 4676.2402 | 4672.4834 | 4668.7296 | 4664.9788 | 4661.231 | 4657.4854 | 4653.7429 | 4650.0033 | 4646.2667 | 4642.5332 | 4635.0665 | 4627.6118 | 4620.1691 | 4612.7383 | 4605.3195 | 4597.4978 | 4589.6894 | 4581.8942 | 4574.1123 | 4566.3436 | 4559.2906 | 4552.2485 | 4545.2174 | 4538.197 | 4531.1875 | 4534.1603 | 4537.135 | 4540.1116 | 4543.0902 | 4546.0707 | 4837.4252 | 5147.4523 | 5477.3489 | 5828.3883 | 6201.9256 | 6599.4026 | 7022.3536 | 7472.4112 | 7472.4112 | 7472.4112 | 7472.4112 | 7472.4112 | 7472.4112 | 7472.4112 | 7472.4112 | 7472.4112 | 7472.4112 | 7472.4112 | 7472.4112 | 7472.4112 | 7472.4112 | 7472.4112 | 7472.4112 | 7472.4112 | 7472.4112 | 7472.4112 | 7472.4112 | 7472.4112 | [6 empty] | 887 | 896 | 905 | 914 | 921.5 | 933 | 944 | 955 | 966 | 977 | 988.6 | 999 | 1009 | 1019 | 1029 | 1039 | 1049 | 1059 | 1069 | 1079 | 1089 | 1099 | 1109 | 1119 | 1129 | 1139 | 1149 | 1159 | 1169 | 1179 | 1190.9 | 1227.7757 | 1265.7933 | 1304.988 | 1345.3964 | 1387.0561 | 1430.0057 | 1474.2852 | 1519.9359 | 1519.9359 | 1519.9359 | 1519.9359 | 1519.9359 | 1519.9359 | 1519.9359 | 1519.9359 | 1519.9359 | 1519.9359 | 1519.9359 | 1519.9359 | 1519.9359 | 1519.9359 | 1519.9359 | 1519.9359 | 1519.9359 | 1519.9359 | 1519.9359 | 1519.9359 | 1519.9359 | [6 empty] | 3.372 | 3.3719 | 3.3718 | 3.3717 | 3.3716 | 3.3668 | 3.3619 | 3.3571 | 3.3522 | 3.3474 | 3.3425 | 3.3377 | 3.3328 | 3.328 | 3.3231 | 3.3158 | 3.3085 | 3.3013 | 3.294 | 3.2867 | 3.2794 | 3.2721 | 3.2649 | 3.2576 | 3.2504 | 3.243 | 3.2357 | 3.2285 | 3.2212 | 3.2139 | 3.2139 | 3.2139 | 3.2139 | 3.2139 | 3.2139 | 3.2118 | 3.2096 | 3.2075 | 3.2054 | 3.2033 | 3.2012 | 3.1991 | 3.197 | 3.197 | 3.197 | 3.197 | 3.197 | 3.197 | 3.197 | 3.197 | 3.197 | 3.197 | 3.197 | 3.197 | 3.197 | 3.197 | 3.197 | 3.197 | 3.197 | 3.197 | 3.197 | 3.197 | 3.197
318 | Puketapapa |  |  | 2052 | 938.1965 | 937.3782 | 936.5606 | 935.7437 | 934.9275 | 941.1427 | 947.3992 | 953.6974 | 960.0374 | 966.4195 | 972.7571 | 979.1364 | 985.5574 | 992.0205 | 998.5261 | 1004.383 | 1010.2743 | 1016.2001 | 1022.1607 | 1028.1562 | 1033.4084 | 1038.6875 | 1043.9935 | 1049.3266 | 1054.6869 | 1061.6586 | 1068.6764 | 1075.7406 | 1082.8515 | 1090.0094 | 1096.5149 | 1103.0592 | 1109.6426 | 1116.2653 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 | 1122.9275 |  | 2870 | 2867.4967 | 2864.9956 | 2862.4967 | 2860 | 2874.8892 | 2889.8558 | 2904.9004 | 2920.0234 | 2935.225 | 2950.1958 | 2965.243 | 2980.367 | 2995.568 | 3010.8466 | 3021.7381 | 3032.6689 | 3043.6393 | 3054.6494 | 3065.6993 | 3074.3484 | 3083.0219 | 3091.7198 | 3100.4424 | 3109.1895 | 3122.6067 | 3136.0817 | 3149.615 | 3163.2066 | 3176.8569 | 3196.1181 | 3215.496 | 3234.9915 | 3254.6051 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | 3274.3377 | [6 empty] | 400 | 403 | 406 | 409 | 412.5 | 417 | 422 | 427 | 432 | 437 | 441.2 | 445 | 449 | 453 | 457 | 461 | 465 | 469 | 473 | 477 | 481 | 485 | 489 | 493 | 497 | 501 | 505 | 509 | 513 | 517 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | 524.8 | [6 empty] | 3.0591 | 3.0591 | 3.0591 | 3.0591 | 3.0591 | 3.0547 | 3.0503 | 3.0459 | 3.0416 | 3.0372 | 3.0328 | 3.0284 | 3.024 | 3.0197 | 3.0153 | 3.0086 | 3.0018 | 2.9951 | 2.9884 | 2.9817 | 2.975 | 2.9682 | 2.9614 | 2.9547 | 2.948 | 2.9413 | 2.9345 | 2.9279 | 2.9212 | 2.9145 | 2.9148 | 2.9151 | 2.9153 | 2.9156 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159 | 2.9159
319 | Puketapapa | AHP | Mt Roskill | 2060 | 275.435 | 273.2343 | 271.0511 | 268.8854 | 266.7371 | 266.7371 | 266.7371 | 266.7371 | 266.7371 | 266.7371 | 266.7371 | 266.7371 | 266.7371 | 266.7371 | 266.7371 | 282.659 | 299.5314 | 317.4109 | 336.3577 | 356.4354 | 379.3917 | 403.8264 | 429.8349 | 457.5185 | 486.985 | 498.4762 | 510.2386 | 522.2785 | 534.6026 | 547.2174 | 547.2174 | 547.2174 | 547.2174 | 547.2174 | 547.2174 | 534.9584 | 522.974 | 511.2581 | 499.8047 | 488.6079 | 477.6619 | 466.9611 | 456.5 | 456.5 | 456.5 | 456.5 | 456.5 | 456.5 | 456.5 | 456.5 | 456.5 | 456.5 | 456.5 | 456.5 | 456.5 | 456.5 | 456.5 | 456.5 | 456.5 | 456.5 | 456.5 | 456.5 | 456.5 |  | 950 | 942.4095 | 934.8797 | 927.41 | 920 | 919.9901 | 919.9802 | 919.9703 | 919.9603 | 919.9504 | 919.9405 | 919.9306 | 919.9207 | 919.9108 | 919.9008 | 972.8072 | 1028.7563 | 1087.9233 | 1150.4932 | 1216.6616 | 1292.4699 | 1373.0017 | 1458.5514 | 1549.4315 | 1645.9742 | 1682.5291 | 1719.8958 | 1758.0923 | 1797.1372 | 1837.0491 | 1837.0491 | 1837.0491 | 1837.0491 | 1837.0491 | 1837.0491 | 1795.1295 | 1754.1664 | 1714.138 | 1675.023 | 1636.8006 | 1599.4504 | 1562.9525 | 1527.2875 | 1527.2875 | 1527.2875 | 1527.2875 | 1527.2875 | 1527.2875 | 1527.2875 | 1527.2875 | 1527.2875 | 1527.2875 | 1527.2875 | 1527.2875 | 1527.2875 | 1527.2875 | 1527.2875 | 1527.2875 | 1527.2875 | 1527.2875 | 1527.2875 | 1527.2875 | 1527.2875 | [6 empty] | 1309 | 1322 | 1335 | 1348 | 1361.4 | 1383 | 1405 | 1427 | 1449 | 1471 | 1490.9 | 1508 | 1525 | 1542 | 1559 | 1576 | 1593 | 1610 | 1627 | 1644 | 1661 | 1678 | 1695 | 1712 | 1729 | 1746 | 1763 | 1780 | 1797 | 1814 | 1827.4 | 1879.2625 | 1932.5968 | 1987.4449 | 2043.8495 | 2101.8549 | 2161.5065 | 2222.8511 | 2285.9367 | 2285.9367 | 2285.9367 | 2285.9367 | 2285.9367 | 2285.9367 | 2285.9367 | 2285.9367 | 2285.9367 | 2285.9367 | 2285.9367 | 2285.9367 | 2285.9367 | 2285.9367 | 2285.9367 | 2285.9367 | 2285.9367 | 2285.9367 | 2285.9367 | 2285.9367 | 2285.9367 | [6 empty] | 3.4491 | 3.4491 | 3.4491 | 3.4491 | 3.4491 | 3.4491 | 3.449 | 3.449 | 3.4489 | 3.4489 | 3.4489 | 3.4488 | 3.4488 | 3.4488 | 3.4487 | 3.4416 | 3.4346 | 3.4275 | 3.4204 | 3.4134 | 3.4067 | 3.4 | 3.3933 | 3.3866 | 3.3799 | 3.3753 | 3.3708 | 3.3662 | 3.3616 | 3.3571 | 3.3571 | 3.3571 | 3.3571 | 3.3571 | 3.3571 | 3.3556 | 3.3542 | 3.3528 | 3.3514 | 3.3499 | 3.3485 | 3.3471 | 3.3456 | 3.3456 | 3.3456 | 3.3456 | 3.3456 | 3.3456 | 3.3456 | 3.3456 | 3.3456 | 3.3456 | 3.3456 | 3.3456 | 3.3456 | 3.3456 | 3.3456 | 3.3456 | 3.3456 | 3.3456 | 3.3456 | 3.3456 | 3.3456
320 | Puketapapa | AHP | Mt Roskill | 2060 | 1183.444 | 1164.2071 | 1145.2829 | 1126.6664 | 1108.3524 | 1187.868 | 1273.0883 | 1364.4224 | 1462.309 | 1567.2183 | 1651.2701 | 1739.8298 | 1833.139 | 1931.4525 | 2035.0387 | 2128.9918 | 2227.2825 | 2330.1111 | 2437.687 | 2550.2295 | 2644.5904 | 2742.4427 | 2843.9157 | 2949.1433 | 3058.2644 | 3103.7689 | 3149.9506 | 3196.8193 | 3244.3855 | 3292.6593 | 3292.6593 | 3292.6593 | 3292.6593 | 3292.6593 | 3292.6593 | 3268.7795 | 3245.0728 | 3221.5381 | 3198.174 | 3174.9794 | 3151.953 | 3129.0936 | 3106.4 | 3106.4 | 3106.4 | 3106.4 | 3106.4 | 3106.4 | 3106.4 | 3106.4 | 3106.4 | 3106.4 | 3106.4 | 3106.4 | 3106.4 | 3106.4 | 3106.4 | 3106.4 | 3106.4 | 3106.4 | 3106.4 | 3106.4 | 3106.4 |  | 3940 | 3875.9553 | 3812.9516 | 3750.9721 | 3690 | 3959.1118 | 4247.8499 | 4557.6456 | 4890.0348 | 5246.6652 | 5534.5757 | 5838.2854 | 6158.6611 | 6496.6174 | 6853.119 | 7168.8322 | 7499.0898 | 7844.5619 | 8205.9494 | 8583.9855 | 8901.0179 | 9229.7592 | 9570.6419 | 9924.1145 | 10290.6419 | 10443.5069 | 10598.6427 | 10756.083 | 10915.862 | 11078.0145 | 11078.0145 | 11078.0145 | 11078.0145 | 11078.0145 | 11078.0145 | 10992.134 | 10906.9192 | 10822.3651 | 10738.4664 | 10655.2182 | 10572.6153 | 10490.6528 | 10409.3256 | 10409.3256 | 10409.3256 | 10409.3256 | 10409.3256 | 10409.3256 | 10409.3256 | 10409.3256 | 10409.3256 | 10409.3256 | 10409.3256 | 10409.3256 | 10409.3256 | 10409.3256 | 10409.3256 | 10409.3256 | 10409.3256 | 10409.3256 | 10409.3256 | 10409.3256 | 10409.3256 | [6 empty] | 627 | 632 | 637 | 642 | 645 | 655 | 665 | 675 | 685 | 695 | 703.9 | 712 | 721 | 730 | 739 | 748 | 757 | 766 | 775 | 784 | 793 | 802 | 811 | 820 | 829 | 838 | 847 | 856 | 865 | 874 | 874.9 | 940.0489 | 1010.0491 | 1085.2618 | 1166.0752 | 1252.9063 | 1346.2033 | 1446.4475 | 1554.1564 | 1554.1564 | 1554.1564 | 1554.1564 | 1554.1564 | 1554.1564 | 1554.1564 | 1554.1564 | 1554.1564 | 1554.1564 | 1554.1564 | 1554.1564 | 1554.1564 | 1554.1564 | 1554.1564 | 1554.1564 | 1554.1564 | 1554.1564 | 1554.1564 | 1554.1564 | 1554.1564 | [6 empty] | 3.3293 | 3.3293 | 3.3293 | 3.3293 | 3.3293 | 3.333 | 3.3366 | 3.3403 | 3.3441 | 3.3478 | 3.3517 | 3.3557 | 3.3596 | 3.3636 | 3.3676 | 3.3672 | 3.3669 | 3.3666 | 3.3663 | 3.366 | 3.3657 | 3.3655 | 3.3653 | 3.3651 | 3.3649 | 3.3648 | 3.3647 | 3.3646 | 3.3645 | 3.3645 | 3.3645 | 3.3645 | 3.3645 | 3.3645 | 3.3645 | 3.3628 | 3.3611 | 3.3594 | 3.3577 | 3.356 | 3.3543 | 3.3526 | 3.3509 | 3.3509 | 3.3509 | 3.3509 | 3.3509 | 3.3509 | 3.3509 | 3.3509 | 3.3509 | 3.3509 | 3.3509 | 3.3509 | 3.3509 | 3.3509 | 3.3509 | 3.3509 | 3.3509 | 3.3509 | 3.3509 | 3.3509 | 3.3509
321 | Albert - Eden | AHP | Mt Roskill | 2060 | 1116.8477 | 1100.4634 | 1084.3195 | 1068.4124 | 1052.7386 | 1056.3798 | 1060.0336 | 1063.7001 | 1067.3792 | 1071.0711 | 1074.7833 | 1078.5083 | 1082.2463 | 1085.9973 | 1089.7612 | 1104.7995 | 1120.0454 | 1135.5016 | 1151.1712 | 1167.0569 | 1186.9358 | 1207.1533 | 1227.7152 | 1248.6272 | 1269.8955 | 1279.2462 | 1288.6658 | 1298.1548 | 1307.7136 | 1317.3427 | 1317.3427 | 1317.3427 | 1317.3427 | 1317.3427 | 1317.3427 | 1363.1263 | 1410.5011 | 1459.5224 | 1510.2474 | 1562.7353 | 1617.0474 | 1673.2471 | 1731.4 | 1731.4 | 1731.4 | 1731.4 | 1731.4 | 1731.4 | 1731.4 | 1731.4 | 1731.4 | 1731.4 | 1731.4 | 1731.4 | 1731.4 | 1731.4 | 1731.4 | 1731.4 | 1731.4 | 1731.4 | 1731.4 | 1731.4 | 1731.4 |  | 3310 | 3261.4419 | 3213.5961 | 3166.4523 | 3120 | 3132.6156 | 3145.2822 | 3158.0001 | 3170.7694 | 3183.5903 | 3196.4807 | 3209.4234 | 3222.4185 | 3235.4662 | 3248.5667 | 3291.2478 | 3334.4897 | 3378.2997 | 3422.6852 | 3467.654 | 3524.3504 | 3581.9738 | 3640.5394 | 3700.0625 | 3760.5589 | 3785.9464 | 3811.5053 | 3837.2367 | 3863.1419 | 3889.2219 | 3889.2219 | 3889.2219 | 3889.2219 | 3889.2219 | 3889.2219 | 4022.3075 | 4159.9471 | 4302.2967 | 4449.5173 | 4601.7757 | 4759.2442 | 4922.1012 | 5090.5309 | 5090.5309 | 5090.5309 | 5090.5309 | 5090.5309 | 5090.5309 | 5090.5309 | 5090.5309 | 5090.5309 | 5090.5309 | 5090.5309 | 5090.5309 | 5090.5309 | 5090.5309 | 5090.5309 | 5090.5309 | 5090.5309 | 5090.5309 | 5090.5309 | 5090.5309 | 5090.5309 | [6 empty] | 648 | 653 | 658 | 663 | 667.8 | 678 | 688 | 698 | 708 | 718 | 726 | 734 | 742 | 750 | 758 | 766 | 774 | 782 | 790 | 798 | 806 | 814 | 822 | 830 | 838 | 846 | 854 | 862 | 870 | 878 | 888.1 | 909.506 | 931.428 | 953.8784 | 976.8699 | 1000.4156 | 1024.5288 | 1049.2233 | 1074.5129 | 1074.5129 | 1074.5129 | 1074.5129 | 1074.5129 | 1074.5129 | 1074.5129 | 1074.5129 | 1074.5129 | 1074.5129 | 1074.5129 | 1074.5129 | 1074.5129 | 1074.5129 | 1074.5129 | 1074.5129 | 1074.5129 | 1074.5129 | 1074.5129 | 1074.5129 | 1074.5129 | [6 empty] | 2.9637 | 2.9637 | 2.9637 | 2.9637 | 2.9637 | 2.9654 | 2.9672 | 2.9689 | 2.9706 | 2.9723 | 2.9741 | 2.9758 | 2.9775 | 2.9793 | 2.981 | 2.979 | 2.9771 | 2.9752 | 2.9732 | 2.9713 | 2.9693 | 2.9673 | 2.9653 | 2.9633 | 2.9613 | 2.9595 | 2.9577 | 2.9559 | 2.9541 | 2.9523 | 2.9523 | 2.9523 | 2.9523 | 2.9523 | 2.9523 | 2.9508 | 2.9493 | 2.9477 | 2.9462 | 2.9447 | 2.9432 | 2.9416 | 2.9401 | 2.9401 | 2.9401 | 2.9401 | 2.9401 | 2.9401 | 2.9401 | 2.9401 | 2.9401 | 2.9401 | 2.9401 | 2.9401 | 2.9401 | 2.9401 | 2.9401 | 2.9401 | 2.9401 | 2.9401 | 2.9401 | 2.9401 | 2.9401
322 | Albert - Eden | AHP | Mt Roskill | 2060 | 1749.7408 | 1729.6859 | 1709.8609 | 1690.2631 | 1670.8899 | 1674.5404 | 1678.1988 | 1681.8653 | 1685.5398 | 1689.2223 | 1692.9439 | 1696.6737 | 1700.4117 | 1704.1579 | 1707.9124 | 1723.0991 | 1738.4208 | 1753.8787 | 1769.4741 | 1785.2082 | 1805.3177 | 1825.6538 | 1846.2189 | 1867.0157 | 1888.0468 | 1897.4422 | 1906.8845 | 1916.3737 | 1925.9101 | 1935.494 | 1935.494 | 1935.494 | 1935.494 | 1935.494 | 1935.494 | 1985.2888 | 2036.3646 | 2088.7545 | 2142.4923 | 2197.6125 | 2254.1509 | 2312.1438 | 2371.6288 | 2371.6288 | 2371.6288 | 2371.6288 | 2371.6288 | 2371.6288 | 2371.6288 | 2371.6288 | 2371.6288 | 2371.6288 | 2371.6288 | 2371.6288 | 2371.6288 | 2371.6288 | 2371.6288 | 2371.6288 | 2371.6288 | 2371.6288 | 2371.6288 | 2371.6288 | 2371.6288 |  | 4660 | 4606.5887 | 4553.7896 | 4501.5957 | 4450 | 4472.7609 | 4495.6383 | 4518.6326 | 4541.7446 | 4564.9748 | 4588.2154 | 4611.5744 | 4635.0523 | 4658.6497 | 4682.3672 | 4730.0504 | 4778.2191 | 4826.8783 | 4876.0331 | 4925.6884 | 4987.5908 | 5050.2712 | 5113.7393 | 5178.005 | 5243.0784 | 5275.6594 | 5308.4428 | 5341.43 | 5374.6222 | 5408.0206 | 5408.0206 | 5408.0206 | 5408.0206 | 5408.0206 | 5408.0206 | 5544.3068 | 5684.0275 | 5827.2693 | 5974.121 | 6124.6733 | 6279.0197 | 6437.2558 | 6599.4795 | 6599.4795 | 6599.4795 | 6599.4795 | 6599.4795 | 6599.4795 | 6599.4795 | 6599.4795 | 6599.4795 | 6599.4795 | 6599.4795 | 6599.4795 | 6599.4795 | 6599.4795 | 6599.4795 | 6599.4795 | 6599.4795 | 6599.4795 | 6599.4795 | 6599.4795 | 6599.4795 | [6 empty] | 762 | 769 | 776 | 783 | 788.8 | 801 | 813 | 825 | 837 | 849 | 859 | 870 | 881 | 892 | 903 | 914 | 925 | 936 | 947 | 958 | 969 | 980 | 991 | 1002 | 1013 | 1024 | 1035 | 1046 | 1057 | 1068 | 1079.4 | 1081.5164 | 1083.6369 | 1085.7615 | 1087.8903 | 1090.0233 | 1092.1605 | 1094.3019 | 1096.4474 | 1096.4474 | 1096.4474 | 1096.4474 | 1096.4474 | 1096.4474 | 1096.4474 | 1096.4474 | 1096.4474 | 1096.4474 | 1096.4474 | 1096.4474 | 1096.4474 | 1096.4474 | 1096.4474 | 1096.4474 | 1096.4474 | 1096.4474 | 1096.4474 | 1096.4474 | 1096.4474 | [6 empty] | 2.6633 | 2.6633 | 2.6633 | 2.6633 | 2.6633 | 2.671 | 2.6788 | 2.6867 | 2.6945 | 2.7024 | 2.7102 | 2.718 | 2.7258 | 2.7337 | 2.7416 | 2.7451 | 2.7486 | 2.7521 | 2.7556 | 2.7592 | 2.7627 | 2.7663 | 2.7698 | 2.7734 | 2.777 | 2.7804 | 2.7838 | 2.7873 | 2.7907 | 2.7941 | 2.7941 | 2.7941 | 2.7941 | 2.7941 | 2.7941 | 2.7927 | 2.7913 | 2.7898 | 2.7884 | 2.787 | 2.7855 | 2.7841 | 2.7827 | 2.7827 | 2.7827 | 2.7827 | 2.7827 | 2.7827 | 2.7827 | 2.7827 | 2.7827 | 2.7827 | 2.7827 | 2.7827 | 2.7827 | 2.7827 | 2.7827 | 2.7827 | 2.7827 | 2.7827 | 2.7827 | 2.7827 | 2.7827
323 | Albert - Eden | AHP | Mt Roskill | 2060 | 710.2187 | 696.148 | 682.3561 | 668.8374 | 655.5865 | 665.6082 | 675.7831 | 686.1135 | 696.6019 | 707.2506 | 717.4845 | 727.8666 | 738.3989 | 749.0836 | 759.9228 | 769.3504 | 778.8949 | 788.5578 | 798.3406 | 808.2448 | 816.6878 | 825.2189 | 833.8392 | 842.5495 | 851.3508 | 862.555 | 873.9066 | 885.4076 | 897.06 | 908.8658 | 919.3532 | 929.9617 | 940.6926 | 951.5473 | 962.5273 | 869.6496 | 785.7341 | 709.9159 | 641.4136 | 579.5213 | 523.6013 | 473.0772 | 427.4283 | 427.4283 | 427.4283 | 427.4283 | 427.4283 | 427.4283 | 427.4283 | 427.4283 | 427.4283 | 427.4283 | 427.4283 | 427.4283 | 427.4283 | 427.4283 | 427.4283 | 427.4283 | 427.4283 | 427.4283 | 427.4283 | 427.4283 | 427.4283 |  | 2080 | 2038.7915 | 1998.3994 | 1958.8075 | 1920 | 1951.8517 | 1984.2318 | 2017.1491 | 2050.6125 | 2084.631 | 2117.5316 | 2150.9515 | 2184.8988 | 2219.382 | 2254.4093 | 2282.367 | 2310.6714 | 2339.3268 | 2368.3375 | 2397.7081 | 2422.8133 | 2448.1815 | 2473.8152 | 2499.7174 | 2525.8907 | 2559.1249 | 2592.7964 | 2626.9109 | 2661.4743 | 2696.4924 | 2727.2516 | 2758.3618 | 2789.8268 | 2821.6507 | 2853.8377 | 2577.4279 | 2327.79 | 2102.3309 | 1898.7087 | 1714.8084 | 1548.7198 | 1398.7179 | 1263.2444 | 1263.2444 | 1263.2444 | 1263.2444 | 1263.2444 | 1263.2444 | 1263.2444 | 1263.2444 | 1263.2444 | 1263.2444 | 1263.2444 | 1263.2444 | 1263.2444 | 1263.2444 | 1263.2444 | 1263.2444 | 1263.2444 | 1263.2444 | 1263.2444 | 1263.2444 | 1263.2444 | [6 empty] | 991 | 1001 | 1011 | 1021 | 1030.5 | 1044 | 1058 | 1072 | 1086 | 1100 | 1111.9 | 1124 | 1136 | 1148 | 1160 | 1172 | 1184 | 1196 | 1208 | 1220 | 1232 | 1244 | 1256 | 1268 | 1280 | 1292 | 1304 | 1316 | 1328 | 1340 | 1359.5 | 1237.2913 | 1126.0683 | 1024.8434 | 932.7178 | 848.8736 | 772.5663 | 703.1185 | 639.9136 | 639.9136 | 639.9136 | 639.9136 | 639.9136 | 639.9136 | 639.9136 | 639.9136 | 639.9136 | 639.9136 | 639.9136 | 639.9136 | 639.9136 | 639.9136 | 639.9136 | 639.9136 | 639.9136 | 639.9136 | 639.9136 | 639.9136 | 639.9136 | [6 empty] | 2.9287 | 2.9287 | 2.9287 | 2.9287 | 2.9287 | 2.9324 | 2.9362 | 2.94 | 2.9437 | 2.9475 | 2.9513 | 2.9551 | 2.959 | 2.9628 | 2.9666 | 2.9666 | 2.9666 | 2.9666 | 2.9666 | 2.9666 | 2.9666 | 2.9667 | 2.9668 | 2.9668 | 2.9669 | 2.9669 | 2.9669 | 2.9669 | 2.9669 | 2.9669 | 2.9665 | 2.9661 | 2.9657 | 2.9653 | 2.9649 | 2.9638 | 2.9626 | 2.9614 | 2.9602 | 2.959 | 2.9578 | 2.9566 | 2.9555 | 2.9555 | 2.9555 | 2.9555 | 2.9555 | 2.9555 | 2.9555 | 2.9555 | 2.9555 | 2.9555 | 2.9555 | 2.9555 | 2.9555 | 2.9555 | 2.9555 | 2.9555 | 2.9555 | 2.9555 | 2.9555 | 2.9555 | 2.9555
324 | Albert - Eden | AHP | Mt Roskill | 2060 | 1150.4363 | 1132.0234 | 1113.9052 | 1096.077 | 1078.5341 | 1093.9737 | 1109.6344 | 1125.5193 | 1141.6316 | 1157.9745 | 1173.7376 | 1189.7153 | 1205.9105 | 1222.3261 | 1238.9652 | 1253.4301 | 1268.0639 | 1282.8685 | 1297.846 | 1312.9983 | 1325.9196 | 1338.968 | 1352.1449 | 1365.4514 | 1378.8889 | 1396.1987 | 1413.7257 | 1431.4728 | 1449.4427 | 1467.6382 | 1483.9159 | 1500.3742 | 1517.015 | 1533.8404 | 1550.8524 | 1474.4226 | 1401.7595 | 1332.6774 | 1266.9998 | 1204.559 | 1145.1954 | 1088.7574 | 1035.1008 | 1035.1008 | 1035.1008 | 1035.1008 | 1035.1008 | 1035.1008 | 1035.1008 | 1035.1008 | 1035.1008 | 1035.1008 | 1035.1008 | 1035.1008 | 1035.1008 | 1035.1008 | 1035.1008 | 1035.1008 | 1035.1008 | 1035.1008 | 1035.1008 | 1035.1008 | 1035.1008 |  | 3520 | 3463.6618 | 3408.2253 | 3353.6761 | 3300 | 3355.6906 | 3412.3211 | 3469.9073 | 3528.4653 | 3588.0115 | 3645.9837 | 3704.8926 | 3764.7533 | 3825.5812 | 3887.3919 | 3936.5417 | 3986.3128 | 4036.7133 | 4087.751 | 4139.4339 | 4184.2721 | 4229.5959 | 4275.4106 | 4321.7216 | 4368.5343 | 4427.5623 | 4487.388 | 4548.022 | 4609.4753 | 4671.759 | 4722.9404 | 4774.6825 | 4826.9914 | 4879.8735 | 4933.3349 | 4687.6412 | 4454.1837 | 4232.3531 | 4021.5703 | 3821.285 | 3630.9744 | 3450.1419 | 3278.3153 | 3278.3153 | 3278.3153 | 3278.3153 | 3278.3153 | 3278.3153 | 3278.3153 | 3278.3153 | 3278.3153 | 3278.3153 | 3278.3153 | 3278.3153 | 3278.3153 | 3278.3153 | 3278.3153 | 3278.3153 | 3278.3153 | 3278.3153 | 3278.3153 | 3278.3153 | 3278.3153 | [6 empty] | 794 | 803 | 812 | 821 | 829.8 | 843 | 856 | 869 | 882 | 895 | 910.7 | 923 | 935 | 947 | 959 | 971 | 983 | 995 | 1007 | 1019 | 1031 | 1043 | 1055 | 1067 | 1079 | 1091 | 1103 | 1115 | 1127 | 1139 | 1155 | 1095.6065 | 1039.2673 | 985.8251 | 935.1311 | 887.044 | 841.4296 | 798.1608 | 757.1171 | 757.1171 | 757.1171 | 757.1171 | 757.1171 | 757.1171 | 757.1171 | 757.1171 | 757.1171 | 757.1171 | 757.1171 | 757.1171 | 757.1171 | 757.1171 | 757.1171 | 757.1171 | 757.1171 | 757.1171 | 757.1171 | 757.1171 | 757.1171 | [6 empty] | 3.0597 | 3.0597 | 3.0597 | 3.0597 | 3.0597 | 3.0674 | 3.0752 | 3.0829 | 3.0907 | 3.0985 | 3.1063 | 3.1141 | 3.1219 | 3.1298 | 3.1376 | 3.1406 | 3.1436 | 3.1466 | 3.1496 | 3.1527 | 3.1558 | 3.1588 | 3.1619 | 3.165 | 3.1682 | 3.1712 | 3.1742 | 3.1772 | 3.1802 | 3.1832 | 3.1828 | 3.1823 | 3.1819 | 3.1815 | 3.181 | 3.1793 | 3.1776 | 3.1758 | 3.1741 | 3.1724 | 3.1706 | 3.1689 | 3.1671 | 3.1671 | 3.1671 | 3.1671 | 3.1671 | 3.1671 | 3.1671 | 3.1671 | 3.1671 | 3.1671 | 3.1671 | 3.1671 | 3.1671 | 3.1671 | 3.1671 | 3.1671 | 3.1671 | 3.1671 | 3.1671 | 3.1671 | 3.1671
325 | Puketapapa | AHP | Mt Roskill | 2060 | 1262.847 | 1246.9367 | 1231.2269 | 1215.715 | 1200.3985 | 1223.1825 | 1246.399 | 1270.0561 | 1294.1622 | 1318.7259 | 1342.0159 | 1365.7172 | 1389.8371 | 1414.383 | 1439.3624 | 1460.8203 | 1482.5981 | 1504.7005 | 1527.1324 | 1549.8988 | 1569.1216 | 1588.5828 | 1608.2854 | 1628.2324 | 1648.4268 | 1674.153 | 1700.2807 | 1726.8162 | 1753.7658 | 1781.136 | 1805.3549 | 1829.903 | 1854.785 | 1880.0053 | 1905.5685 | 1839.6281 | 1775.9695 | 1714.5138 | 1655.1846 | 1597.9085 | 1542.6144 | 1489.2337 | 1437.7002 | 1437.7002 | 1437.7002 | 1437.7002 | 1437.7002 | 1437.7002 | 1437.7002 | 1437.7002 | 1437.7002 | 1437.7002 | 1437.7002 | 1437.7002 | 1437.7002 | 1437.7002 | 1437.7002 | 1437.7002 | 1437.7002 | 1437.7002 | 1437.7002 | 1437.7002 | 1437.7002 |  | 3640 | 3594.1406 | 3548.859 | 3504.1478 | 3460 | 3533.6519 | 3608.8716 | 3685.6926 | 3764.1487 | 3844.275 | 3921.0906 | 3999.4411 | 4079.3572 | 4160.8701 | 4244.0119 | 4310.6734 | 4378.382 | 4447.1542 | 4517.0065 | 4587.956 | 4648.7486 | 4710.3466 | 4772.7609 | 4836.0022 | 4900.0814 | 4980.4916 | 5062.2213 | 5145.2922 | 5229.7263 | 5315.5459 | 5386.686 | 5458.7783 | 5531.8353 | 5605.8701 | 5680.8958 | 5481.4775 | 5289.0595 | 5103.396 | 4924.2498 | 4751.3924 | 4584.6027 | 4423.668 | 4268.3826 | 4268.3826 | 4268.3826 | 4268.3826 | 4268.3826 | 4268.3826 | 4268.3826 | 4268.3826 | 4268.3826 | 4268.3826 | 4268.3826 | 4268.3826 | 4268.3826 | 4268.3826 | 4268.3826 | 4268.3826 | 4268.3826 | 4268.3826 | 4268.3826 | 4268.3826 | 4268.3826 | [6 empty] | 969 | 979 | 989 | 999 | 1007.3 | 1023 | 1039 | 1055 | 1071 | 1087 | 1104.2 | 1117 | 1130 | 1143 | 1156 | 1169 | 1182 | 1195 | 1208 | 1221 | 1234 | 1247 | 1260 | 1273 | 1286 | 1299 | 1312 | 1325 | 1338 | 1351 | 1369 | 1338.1123 | 1307.9216 | 1278.412 | 1249.5682 | 1221.3752 | 1193.8183 | 1166.8831 | 1140.5556 | 1140.5556 | 1140.5556 | 1140.5556 | 1140.5556 | 1140.5556 | 1140.5556 | 1140.5556 | 1140.5556 | 1140.5556 | 1140.5556 | 1140.5556 | 1140.5556 | 1140.5556 | 1140.5556 | 1140.5556 | 1140.5556 | 1140.5556 | 1140.5556 | 1140.5556 | 1140.5556 | [6 empty] | 2.8824 | 2.8824 | 2.8824 | 2.8824 | 2.8824 | 2.8889 | 2.8954 | 2.902 | 2.9086 | 2.9151 | 2.9218 | 2.9285 | 2.9351 | 2.9418 | 2.9485 | 2.9509 | 2.9532 | 2.9555 | 2.9578 | 2.9602 | 2.9626 | 2.9651 | 2.9676 | 2.9701 | 2.9726 | 2.9749 | 2.9773 | 2.9796 | 2.982 | 2.9844 | 2.9837 | 2.9831 | 2.9825 | 2.9818 | 2.9812 | 2.9797 | 2.9781 | 2.9766 | 2.975 | 2.9735 | 2.972 | 2.9704 | 2.9689 | 2.9689 | 2.9689 | 2.9689 | 2.9689 | 2.9689 | 2.9689 | 2.9689 | 2.9689 | 2.9689 | 2.9689 | 2.9689 | 2.9689 | 2.9689 | 2.9689 | 2.9689 | 2.9689 | 2.9689 | 2.9689 | 2.9689 | 2.9689
326 | Puketapapa | AHP | Mt Roskill | 2060 | 1168.9967 | 1163.711 | 1158.4492 | 1153.2111 | 1147.9968 | 1165.2474 | 1182.7572 | 1200.5301 | 1218.5701 | 1236.8812 | 1254.4961 | 1272.3618 | 1290.482 | 1308.8602 | 1327.5002 | 1343.6909 | 1360.0791 | 1376.6672 | 1393.4576 | 1410.4527 | 1424.9316 | 1439.5591 | 1454.3368 | 1469.2661 | 1484.3487 | 1503.6382 | 1523.1782 | 1542.9723 | 1563.0235 | 1583.3354 | 1601.4265 | 1619.7244 | 1638.2313 | 1656.9497 | 1675.882 | 1641.7042 | 1608.2234 | 1575.4254 | 1543.2963 | 1511.8224 | 1480.9905 | 1450.7873 | 1421.2 | 1421.2 | 1421.2 | 1421.2 | 1421.2 | 1421.2 | 1421.2 | 1421.2 | 1421.2 | 1421.2 | 1421.2 | 1421.2 | 1421.2 | 1421.2 | 1421.2 | 1421.2 | 1421.2 | 1421.2 | 1421.2 | 1421.2 | 1421.2 |  | 3340 | 3324.8979 | 3309.864 | 3294.8982 | 3280 | 3334.9916 | 3390.9051 | 3447.7561 | 3505.5603 | 3564.3335 | 3621.2994 | 3679.1756 | 3737.9769 | 3797.718 | 3858.4138 | 3906.7645 | 3955.7211 | 4005.2911 | 4055.4824 | 4106.3026 | 4149.9402 | 4194.0416 | 4238.6116 | 4283.6553 | 4329.1776 | 4386.8847 | 4445.361 | 4504.6168 | 4564.6624 | 4625.5085 | 4677.7687 | 4730.6194 | 4784.0672 | 4838.1189 | 4892.7813 | 4790.4583 | 4690.2752 | 4592.1873 | 4496.1507 | 4402.1225 | 4310.0607 | 4219.9242 | 4131.6727 | 4131.6727 | 4131.6727 | 4131.6727 | 4131.6727 | 4131.6727 | 4131.6727 | 4131.6727 | 4131.6727 | 4131.6727 | 4131.6727 | 4131.6727 | 4131.6727 | 4131.6727 | 4131.6727 | 4131.6727 | 4131.6727 | 4131.6727 | 4131.6727 | 4131.6727 | 4131.6727 | [6 empty] | 233 | 235 | 237 | 239 | 239.4 | 244 | 249 | 254 | 259 | 264 | 268.9 | 273 | 277 | 281 | 285 | 289 | 293 | 297 | 301 | 305 | 309 | 313 | 317 | 321 | 325 | 329 | 333 | 337 | 341 | 345 | 352.3 | 343.0403 | 334.024 | 325.2446 | 316.696 | 308.3721 | 300.267 | 292.3749 | 284.6903 | 284.6903 | 284.6903 | 284.6903 | 284.6903 | 284.6903 | 284.6903 | 284.6903 | 284.6903 | 284.6903 | 284.6903 | 284.6903 | 284.6903 | 284.6903 | 284.6903 | 284.6903 | 284.6903 | 284.6903 | 284.6903 | 284.6903 | 284.6903 | [6 empty] | 2.8572 | 2.8572 | 2.8572 | 2.8572 | 2.8572 | 2.862 | 2.8669 | 2.8719 | 2.8768 | 2.8817 | 2.8867 | 2.8916 | 2.8966 | 2.9015 | 2.9065 | 2.9075 | 2.9084 | 2.9094 | 2.9104 | 2.9113 | 2.9124 | 2.9134 | 2.9145 | 2.9155 | 2.9166 | 2.9175 | 2.9185 | 2.9194 | 2.9204 | 2.9214 | 2.921 | 2.9206 | 2.9203 | 2.9199 | 2.9195 | 2.918 | 2.9164 | 2.9149 | 2.9133 | 2.9118 | 2.9103 | 2.9087 | 2.9072 | 2.9072 | 2.9072 | 2.9072 | 2.9072 | 2.9072 | 2.9072 | 2.9072 | 2.9072 | 2.9072 | 2.9072 | 2.9072 | 2.9072 | 2.9072 | 2.9072 | 2.9072 | 2.9072 | 2.9072 | 2.9072 | 2.9072 | 2.9072
327 | Puketapapa | AHP | Mt Roskill | 2060 | 1660.6515 | 1640.8642 | 1621.3126 | 1601.994 | 1582.9056 | 1623.4403 | 1665.013 | 1707.6503 | 1751.3794 | 1796.2283 | 1837.7599 | 1880.2518 | 1923.7262 | 1968.2058 | 2013.7138 | 2060.7585 | 2108.9023 | 2158.1708 | 2208.5903 | 2260.1878 | 2307.4347 | 2355.6693 | 2404.9123 | 2455.1845 | 2506.5077 | 2528.8356 | 2551.3623 | 2574.0898 | 2597.0196 | 2620.1538 | 2620.1538 | 2620.1538 | 2620.1538 | 2620.1538 | 2620.1538 | 2699.7194 | 2781.7012 | 2866.1725 | 2953.209 | 3042.8884 | 3135.2911 | 3230.4999 | 3328.5997 | 3328.5997 | 3328.5997 | 3328.5997 | 3328.5997 | 3328.5997 | 3328.5997 | 3328.5997 | 3328.5997 | 3328.5997 | 3328.5997 | 3328.5997 | 3328.5997 | 3328.5997 | 3328.5997 | 3328.5997 | 3328.5997 | 3328.5997 | 3328.5997 | 3328.5997 | 3328.5997 |  | 5340 | 5276.3718 | 5213.5017 | 5151.3808 | 5090 | 5226.9753 | 5367.6367 | 5512.0834 | 5660.4173 | 5812.7429 | 5954.6954 | 6100.1146 | 6249.085 | 6401.6934 | 6558.0287 | 6710.9741 | 6867.4865 | 7027.6491 | 7191.5469 | 7359.2672 | 7512.8578 | 7669.654 | 7829.7225 | 7993.1318 | 8159.9515 | 8232.5292 | 8305.7525 | 8379.627 | 8454.1586 | 8529.3532 | 8529.3532 | 8529.3532 | 8529.3532 | 8529.3532 | 8529.3532 | 8783.9668 | 9046.181 | 9316.2226 | 9594.3254 | 9880.73 | 10175.6842 | 10479.4432 | 10792.2698 | 10792.2698 | 10792.2698 | 10792.2698 | 10792.2698 | 10792.2698 | 10792.2698 | 10792.2698 | 10792.2698 | 10792.2698 | 10792.2698 | 10792.2698 | 10792.2698 | 10792.2698 | 10792.2698 | 10792.2698 | 10792.2698 | 10792.2698 | 10792.2698 | 10792.2698 | 10792.2698 | [6 empty] | 886 | 897 | 908 | 919 | 929.2 | 945 | 960 | 975 | 990 | 1005 | 1021.8 | 1037 | 1052 | 1067 | 1082 | 1097 | 1112 | 1127 | 1142 | 1157 | 1172 | 1187 | 1202 | 1217 | 1232 | 1247 | 1262 | 1277 | 1292 | 1307 | 1322.6 | 1375.9803 | 1431.515 | 1489.2911 | 1549.399 | 1611.933 | 1676.9908 | 1744.6743 | 1815.0895 | 1815.0895 | 1815.0895 | 1815.0895 | 1815.0895 | 1815.0895 | 1815.0895 | 1815.0895 | 1815.0895 | 1815.0895 | 1815.0895 | 1815.0895 | 1815.0895 | 1815.0895 | 1815.0895 | 1815.0895 | 1815.0895 | 1815.0895 | 1815.0895 | 1815.0895 | 1815.0895 | [6 empty] | 3.2156 | 3.2156 | 3.2156 | 3.2156 | 3.2156 | 3.2197 | 3.2238 | 3.2279 | 3.232 | 3.2361 | 3.2402 | 3.2443 | 3.2484 | 3.2526 | 3.2567 | 3.2566 | 3.2564 | 3.2563 | 3.2562 | 3.256 | 3.2559 | 3.2558 | 3.2557 | 3.2556 | 3.2555 | 3.2555 | 3.2554 | 3.2554 | 3.2553 | 3.2553 | 3.2553 | 3.2553 | 3.2553 | 3.2553 | 3.2553 | 3.2537 | 3.252 | 3.2504 | 3.2488 | 3.2472 | 3.2455 | 3.2439 | 3.2423 | 3.2423 | 3.2423 | 3.2423 | 3.2423 | 3.2423 | 3.2423 | 3.2423 | 3.2423 | 3.2423 | 3.2423 | 3.2423 | 3.2423 | 3.2423 | 3.2423 | 3.2423 | 3.2423 | 3.2423 | 3.2423 | 3.2423 | 3.2423
328 | Puketapapa | AHP | Mt Roskill | 2060 | 916.1652 | 910.9319 | 905.7285 | 900.5548 | 895.4107 | 946.199 | 999.8681 | 1056.5814 | 1116.5115 | 1179.8409 | 1232.854 | 1288.2493 | 1346.1335 | 1406.6186 | 1469.8215 | 1495.1159 | 1520.8457 | 1547.0182 | 1573.6411 | 1600.7222 | 1608.7694 | 1616.8571 | 1624.9854 | 1633.1547 | 1641.3649 | 1645.0982 | 1648.84 | 1652.5903 | 1656.3492 | 1660.1165 | 1660.1165 | 1660.1165 | 1660.1165 | 1660.1165 | 1660.1165 | 1615.061 | 1571.2283 | 1528.5852 | 1487.0994 | 1446.7395 | 1407.475 | 1369.2762 | 1332.1141 | 1332.1141 | 1332.1141 | 1332.1141 | 1332.1141 | 1332.1141 | 1332.1141 | 1332.1141 | 1332.1141 | 1332.1141 | 1332.1141 | 1332.1141 | 1332.1141 | 1332.1141 | 1332.1141 | 1332.1141 | 1332.1141 | 1332.1141 | 1332.1141 | 1332.1141 | 1332.1141 |  | 3090 | 3072.3493 | 3054.7995 | 3037.3499 | 3020 | 3191.889 | 3373.5613 | 3565.5739 | 3768.5153 | 3983.0074 | 4164.1818 | 4353.5973 | 4551.6287 | 4758.668 | 4975.1247 | 5059.401 | 5145.1049 | 5232.2606 | 5320.8926 | 5411.0261 | 5437.8205 | 5464.7476 | 5491.808 | 5519.0024 | 5546.3315 | 5558.76 | 5571.2163 | 5583.7005 | 5596.2127 | 5608.753 | 5608.753 | 5608.753 | 5608.753 | 5608.753 | 5608.753 | 5453.7283 | 5302.9885 | 5156.4151 | 5013.8929 | 4875.31 | 4740.5576 | 4609.5296 | 4482.1232 | 4482.1232 | 4482.1232 | 4482.1232 | 4482.1232 | 4482.1232 | 4482.1232 | 4482.1232 | 4482.1232 | 4482.1232 | 4482.1232 | 4482.1232 | 4482.1232 | 4482.1232 | 4482.1232 | 4482.1232 | 4482.1232 | 4482.1232 | 4482.1232 | 4482.1232 | 4482.1232 | [6 empty] | 320 | 323 | 326 | 329 | 331.8 | 337 | 342 | 347 | 352 | 357 | 361.8 | 366 | 371 | 376 | 381 | 386 | 391 | 396 | 401 | 406 | 411 | 416 | 421 | 426 | 431 | 436 | 441 | 446 | 451 | 456 | 455 | 452.3526 | 449.7207 | 447.104 | 444.5026 | 441.9163 | 439.3451 | 436.7888 | 434.2474 | 434.2474 | 434.2474 | 434.2474 | 434.2474 | 434.2474 | 434.2474 | 434.2474 | 434.2474 | 434.2474 | 434.2474 | 434.2474 | 434.2474 | 434.2474 | 434.2474 | 434.2474 | 434.2474 | 434.2474 | 434.2474 | 434.2474 | 434.2474 | [6 empty] | 3.3728 | 3.3728 | 3.3728 | 3.3728 | 3.3728 | 3.3734 | 3.374 | 3.3746 | 3.3753 | 3.3759 | 3.3777 | 3.3795 | 3.3813 | 3.3831 | 3.3848 | 3.384 | 3.3831 | 3.3822 | 3.3813 | 3.3804 | 3.3801 | 3.3799 | 3.3796 | 3.3794 | 3.3791 | 3.379 | 3.3789 | 3.3788 | 3.3786 | 3.3785 | 3.3785 | 3.3785 | 3.3785 | 3.3785 | 3.3785 | 3.3768 | 3.3751 | 3.3733 | 3.3716 | 3.3699 | 3.3681 | 3.3664 | 3.3647 | 3.3647 | 3.3647 | 3.3647 | 3.3647 | 3.3647 | 3.3647 | 3.3647 | 3.3647 | 3.3647 | 3.3647 | 3.3647 | 3.3647 | 3.3647 | 3.3647 | 3.3647 | 3.3647 | 3.3647 | 3.3647 | 3.3647 | 3.3647
329 | Puketapapa | AHP | Mt Roskill | 2060 | 1675.1474 | 1656.599 | 1638.2559 | 1620.116 | 1602.1769 | 1652.1768 | 1703.7371 | 1756.9064 | 1811.735 | 1868.2747 | 1919.6307 | 1972.3985 | 2026.6167 | 2082.3253 | 2139.5652 | 2158.495 | 2177.5923 | 2196.8585 | 2216.2951 | 2235.9038 | 2235.9038 | 2235.9038 | 2235.9038 | 2235.9038 | 2235.9038 | 2235.9038 | 2235.9038 | 2235.9038 | 2235.9038 | 2235.9038 | 2235.9038 | 2235.9038 | 2235.9038 | 2235.9038 | 2235.9038 | 2335.2798 | 2439.0726 | 2547.4785 | 2660.7026 | 2778.959 | 2902.4713 | 3031.4733 | 3166.2088 | 3166.2088 | 3166.2088 | 3166.2088 | 3166.2088 | 3166.2088 | 3166.2088 | 3166.2088 | 3166.2088 | 3166.2088 | 3166.2088 | 3166.2088 | 3166.2088 | 3166.2088 | 3166.2088 | 3166.2088 | 3166.2088 | 3166.2088 | 3166.2088 | 3166.2088 | 3166.2088 |  | 5280 | 5221.5361 | 5163.7196 | 5106.5432 | 5050 | 5196.4741 | 5347.1966 | 5502.2908 | 5661.8834 | 5826.105 | 5973.4597 | 6124.5413 | 6279.4441 | 6438.2647 | 6601.1022 | 6641.3572 | 6681.8577 | 6722.6051 | 6763.601 | 6804.847 | 6786.2483 | 6767.7005 | 6749.2034 | 6730.7568 | 6712.3607 | 6693.7606 | 6675.2121 | 6656.715 | 6638.2691 | 6619.8744 | 6619.8744 | 6619.8744 | 6619.8744 | 6619.8744 | 6619.8744 | 6910.8661 | 7214.649 | 7531.7853 | 7862.8621 | 8208.4922 | 8569.3152 | 8945.999 | 9339.2409 | 9339.2409 | 9339.2409 | 9339.2409 | 9339.2409 | 9339.2409 | 9339.2409 | 9339.2409 | 9339.2409 | 9339.2409 | 9339.2409 | 9339.2409 | 9339.2409 | 9339.2409 | 9339.2409 | 9339.2409 | 9339.2409 | 9339.2409 | 9339.2409 | 9339.2409 | 9339.2409 | [6 empty] | 653 | 657 | 661 | 665 | 669.8 | 679 | 688 | 697 | 706 | 715 | 726 | 733 | 740 | 747 | 754 | 761 | 768 | 775 | 782 | 789 | 796 | 803 | 810 | 817 | 824 | 831 | 838 | 845 | 852 | 859 | 865 | 903.7881 | 944.3155 | 986.6602 | 1030.9037 | 1077.1312 | 1125.4316 | 1175.8979 | 1228.6272 | 1228.6272 | 1228.6272 | 1228.6272 | 1228.6272 | 1228.6272 | 1228.6272 | 1228.6272 | 1228.6272 | 1228.6272 | 1228.6272 | 1228.6272 | 1228.6272 | 1228.6272 | 1228.6272 | 1228.6272 | 1228.6272 | 1228.6272 | 1228.6272 | 1228.6272 | 1228.6272 | [6 empty] | 3.152 | 3.152 | 3.152 | 3.152 | 3.152 | 3.1452 | 3.1385 | 3.1318 | 3.1251 | 3.1184 | 3.1118 | 3.1051 | 3.0985 | 3.0919 | 3.0853 | 3.0768 | 3.0685 | 3.0601 | 3.0518 | 3.0434 | 3.0351 | 3.0268 | 3.0186 | 3.0103 | 3.0021 | 2.9938 | 2.9855 | 2.9772 | 2.9689 | 2.9607 | 2.9607 | 2.9607 | 2.9607 | 2.9607 | 2.9607 | 2.9593 | 2.9579 | 2.9566 | 2.9552 | 2.9538 | 2.9524 | 2.951 | 2.9497 | 2.9497 | 2.9497 | 2.9497 | 2.9497 | 2.9497 | 2.9497 | 2.9497 | 2.9497 | 2.9497 | 2.9497 | 2.9497 | 2.9497 | 2.9497 | 2.9497 | 2.9497 | 2.9497 | 2.9497 | 2.9497 | 2.9497 | 2.9497
330 | Puketapapa | AHP | Mt Roskill | 2060 | 1099.3371 | 1092.6267 | 1085.9573 | 1079.3285 | 1072.7403 | 1094.0942 | 1115.8731 | 1138.0856 | 1160.7402 | 1183.8458 | 1205.6802 | 1227.9172 | 1250.5644 | 1273.6292 | 1297.1195 | 1305.0665 | 1313.0622 | 1321.1069 | 1329.2008 | 1337.3444 | 1337.3444 | 1337.3444 | 1337.3444 | 1337.3444 | 1337.3444 | 1337.3444 | 1337.3444 | 1337.3444 | 1337.3444 | 1337.3444 | 1337.3444 | 1337.3444 | 1337.3444 | 1337.3444 | 1337.3444 | 1368.226 | 1399.8207 | 1432.145 | 1465.2157 | 1499.05 | 1533.6657 | 1569.0807 | 1605.3135 | 1605.3135 | 1605.3135 | 1605.3135 | 1605.3135 | 1605.3135 | 1605.3135 | 1605.3135 | 1605.3135 | 1605.3135 | 1605.3135 | 1605.3135 | 1605.3135 | 1605.3135 | 1605.3135 | 1605.3135 | 1605.3135 | 1605.3135 | 1605.3135 | 1605.3135 | 1605.3135 |  | 3720 | 3697.2929 | 3674.7245 | 3652.2938 | 3630 | 3699.4743 | 3770.2783 | 3842.4374 | 3915.9776 | 3990.9252 | 4061.5105 | 4133.3442 | 4206.4483 | 4280.8454 | 4356.5583 | 4376.2703 | 4396.0715 | 4415.9622 | 4435.943 | 4456.0142 | 4448.9851 | 4441.9671 | 4434.9602 | 4427.9643 | 4420.9794 | 4413.9502 | 4406.9321 | 4399.9252 | 4392.9294 | 4385.9447 | 4385.9447 | 4385.9447 | 4385.9447 | 4385.9447 | 4385.9447 | 4484.9107 | 4586.1098 | 4689.5924 | 4795.4101 | 4903.6154 | 5014.2623 | 5127.4059 | 5243.1025 | 5243.1025 | 5243.1025 | 5243.1025 | 5243.1025 | 5243.1025 | 5243.1025 | 5243.1025 | 5243.1025 | 5243.1025 | 5243.1025 | 5243.1025 | 5243.1025 | 5243.1025 | 5243.1025 | 5243.1025 | 5243.1025 | 5243.1025 | 5243.1025 | 5243.1025 | 5243.1025 | [6 empty] | 378 | 381 | 384 | 387 | 388.2 | 394 | 399 | 404 | 409 | 414 | 420.3 | 425 | 430 | 435 | 440 | 445 | 450 | 455 | 460 | 465 | 470 | 475 | 480 | 485 | 490 | 495 | 500 | 505 | 510 | 515 | 512.9 | 517.6694 | 522.4832 | 527.3417 | 532.2454 | 537.1947 | 542.19 | 547.2318 | 552.3205 | 552.3205 | 552.3205 | 552.3205 | 552.3205 | 552.3205 | 552.3205 | 552.3205 | 552.3205 | 552.3205 | 552.3205 | 552.3205 | 552.3205 | 552.3205 | 552.3205 | 552.3205 | 552.3205 | 552.3205 | 552.3205 | 552.3205 | 552.3205 | [6 empty] | 3.3839 | 3.3839 | 3.3839 | 3.3839 | 3.3839 | 3.3813 | 3.3788 | 3.3762 | 3.3737 | 3.3712 | 3.3686 | 3.3661 | 3.3636 | 3.3611 | 3.3586 | 3.3533 | 3.348 | 3.3426 | 3.3373 | 3.332 | 3.3267 | 3.3215 | 3.3162 | 3.311 | 3.3058 | 3.3005 | 3.2953 | 3.29 | 3.2848 | 3.2796 | 3.2796 | 3.2796 | 3.2796 | 3.2796 | 3.2796 | 3.2779 | 3.2762 | 3.2745 | 3.2728 | 3.2711 | 3.2695 | 3.2678 | 3.2661 | 3.2661 | 3.2661 | 3.2661 | 3.2661 | 3.2661 | 3.2661 | 3.2661 | 3.2661 | 3.2661 | 3.2661 | 3.2661 | 3.2661 | 3.2661 | 3.2661 | 3.2661 | 3.2661 | 3.2661 | 3.2661 | 3.2661 | 3.2661
331 | Puketapapa | AHP | Mt Roskill | 2060 | 1768.0239 | 1763.3196 | 1758.6278 | 1753.9485 | 1749.2816 | 1749.2816 | 1749.2816 | 1749.2816 | 1749.2816 | 1749.2816 | 1749.2816 | 1749.2816 | 1749.2816 | 1749.2816 | 1749.2816 | 1764.5819 | 1780.016 | 1795.5851 | 1811.2904 | 1827.133 | 1849.2524 | 1871.6395 | 1894.2977 | 1917.2301 | 1940.4402 | 1970.046 | 2000.1036 | 2030.6197 | 2061.6014 | 2093.0559 | 2120.9233 | 2149.1618 | 2177.7762 | 2206.7717 | 2236.1532 | 2227.1239 | 2218.1311 | 2209.1747 | 2200.2543 | 2191.3701 | 2182.5216 | 2173.7089 | 2164.9318 | 2164.9318 | 2164.9318 | 2164.9318 | 2164.9318 | 2164.9318 | 2164.9318 | 2164.9318 | 2164.9318 | 2164.9318 | 2164.9318 | 2164.9318 | 2164.9318 | 2164.9318 | 2164.9318 | 2164.9318 | 2164.9318 | 2164.9318 | 2164.9318 | 2164.9318 | 2164.9318 |  | 5660 | 5644.94 | 5629.9201 | 5614.9401 | 5600 | 5593.8597 | 5587.7262 | 5581.5994 | 5575.4793 | 5569.3659 | 5563.2255 | 5557.0919 | 5550.9651 | 5544.8451 | 5538.7318 | 5576.3167 | 5614.1567 | 5652.2535 | 5690.6088 | 5729.2243 | 5787.185 | 5845.7321 | 5904.8715 | 5964.6091 | 6024.9511 | 6104.7189 | 6185.5429 | 6267.4368 | 6350.4151 | 6434.4919 | 6520.0907 | 6606.8282 | 6694.7195 | 6783.7801 | 6874.0255 | 6843.0559 | 6812.2258 | 6781.5346 | 6750.9817 | 6720.5664 | 6690.2882 | 6660.1463 | 6630.1403 | 6630.1403 | 6630.1403 | 6630.1403 | 6630.1403 | 6630.1403 | 6630.1403 | 6630.1403 | 6630.1403 | 6630.1403 | 6630.1403 | 6630.1403 | 6630.1403 | 6630.1403 | 6630.1403 | 6630.1403 | 6630.1403 | 6630.1403 | 6630.1403 | 6630.1403 | 6630.1403 | [6 empty] | 1190 | 1200 | 1210 | 1220 | 1230.5 | 1246 | 1262 | 1278 | 1294 | 1310 | 1324.3 | 1337 | 1350 | 1363 | 1376 | 1389 | 1402 | 1415 | 1428 | 1441 | 1454 | 1467 | 1480 | 1493 | 1506 | 1519 | 1532 | 1545 | 1558 | 1571 | 1587 | 1575.5619 | 1564.2062 | 1552.9324 | 1541.7398 | 1530.6279 | 1519.5961 | 1508.6438 | 1497.7705 | 1497.7705 | 1497.7705 | 1497.7705 | 1497.7705 | 1497.7705 | 1497.7705 | 1497.7705 | 1497.7705 | 1497.7705 | 1497.7705 | 1497.7705 | 1497.7705 | 1497.7705 | 1497.7705 | 1497.7705 | 1497.7705 | 1497.7705 | 1497.7705 | 1497.7705 | 1497.7705 | [6 empty] | 3.2013 | 3.2013 | 3.2013 | 3.2013 | 3.2013 | 3.1978 | 3.1943 | 3.1908 | 3.1873 | 3.1838 | 3.1803 | 3.1768 | 3.1733 | 3.1698 | 3.1663 | 3.1601 | 3.154 | 3.1479 | 3.1417 | 3.1356 | 3.1295 | 3.1233 | 3.1172 | 3.1111 | 3.1049 | 3.0988 | 3.0926 | 3.0865 | 3.0803 | 3.0742 | 3.0742 | 3.0741 | 3.0741 | 3.0741 | 3.074 | 3.0726 | 3.0712 | 3.0697 | 3.0683 | 3.0668 | 3.0654 | 3.064 | 3.0625 | 3.0625 | 3.0625 | 3.0625 | 3.0625 | 3.0625 | 3.0625 | 3.0625 | 3.0625 | 3.0625 | 3.0625 | 3.0625 | 3.0625 | 3.0625 | 3.0625 | 3.0625 | 3.0625 | 3.0625 | 3.0625 | 3.0625 | 3.0625
332 | Puketapapa |  |  | 2052 | 1115.9943 | 1105.6929 | 1095.4866 | 1085.3746 | 1075.3558 | 1096.2833 | 1117.618 | 1139.3679 | 1161.5411 | 1184.1458 | 1205.5412 | 1227.3231 | 1249.4986 | 1272.0747 | 1295.0588 | 1314.7346 | 1334.7093 | 1354.9874 | 1375.5737 | 1396.4727 | 1414.0785 | 1431.9062 | 1449.9586 | 1468.2387 | 1486.7492 | 1510.3096 | 1534.2433 | 1558.5563 | 1583.2547 | 1608.3443 | 1630.5263 | 1653.0142 | 1675.8122 | 1698.9246 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 | 1722.3558 |  | 3570 | 3537.0465 | 3504.3972 | 3472.0493 | 3440 | 3503.329 | 3567.8238 | 3633.506 | 3700.3974 | 3768.5202 | 3832.7126 | 3897.9985 | 3964.3964 | 4031.9254 | 4100.6046 | 4155.103 | 4210.3258 | 4266.2824 | 4322.9827 | 4380.4366 | 4427.3951 | 4474.857 | 4522.8277 | 4571.3126 | 4620.3173 | 4684.5906 | 4749.7581 | 4815.832 | 4882.8251 | 4950.7502 | 5018.438 | 5087.0512 | 5156.6026 | 5227.1049 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | 5298.5711 | [6 empty] | 543 | 548 | 553 | 558 | 563.4 | 571 | 578 | 585 | 592 | 599 | 607.9 | 614 | 620 | 626 | 632 | 638 | 644 | 650 | 656 | 662 | 668 | 674 | 680 | 686 | 692 | 698 | 704 | 710 | 716 | 722 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | 731.9 | [6 empty] | 3.1989 | 3.1989 | 3.1989 | 3.1989 | 3.1989 | 3.1956 | 3.1923 | 3.1891 | 3.1858 | 3.1825 | 3.1792 | 3.176 | 3.1728 | 3.1696 | 3.1663 | 3.1604 | 3.1545 | 3.1486 | 3.1427 | 3.1368 | 3.1309 | 3.1251 | 3.1193 | 3.1135 | 3.1077 | 3.1017 | 3.0958 | 3.0899 | 3.084 | 3.0782 | 3.0778 | 3.0774 | 3.0771 | 3.0767 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764 | 3.0764
333 | Puketapapa | AHP | Mt Roskill | 2060 | 1231.3231 | 1225.5826 | 1219.8687 | 1214.1815 | 1208.5209 | 1208.5209 | 1208.5209 | 1208.5209 | 1208.5209 | 1208.5209 | 1208.5209 | 1208.5209 | 1208.5209 | 1208.5209 | 1208.5209 | 1238.0168 | 1268.2327 | 1299.186 | 1330.8948 | 1363.3775 | 1405.7386 | 1449.4159 | 1494.4503 | 1540.8839 | 1588.7603 | 1609.0335 | 1629.5654 | 1650.3592 | 1671.4185 | 1692.7464 | 1692.7464 | 1692.7464 | 1692.7464 | 1692.7464 | 1692.7464 | 1805.4051 | 1925.5617 | 2053.7151 | 2190.3977 | 2336.177 | 2491.6584 | 2657.4878 | 2834.3537 | 2834.3537 | 2834.3537 | 2834.3537 | 2834.3537 | 2834.3537 | 2834.3537 | 2834.3537 | 2834.3537 | 2834.3537 | 2834.3537 | 2834.3537 | 2834.3537 | 2834.3537 | 2834.3537 | 2834.3537 | 2834.3537 | 2834.3537 | 2834.3537 | 2834.3537 | 2834.3537 |  | 3780 | 3762.3771 | 3744.8364 | 3727.3775 | 3710 | 3714.7733 | 3719.5527 | 3724.3383 | 3729.13 | 3733.9279 | 3738.7013 | 3743.4808 | 3748.2663 | 3753.058 | 3757.8559 | 3849.2062 | 3942.7772 | 4038.6228 | 4136.7983 | 4237.3604 | 4368.4375 | 4503.5694 | 4642.8813 | 4786.5027 | 4934.5669 | 4997.238 | 5060.7052 | 5124.9784 | 5190.0678 | 5255.984 | 5255.984 | 5255.984 | 5255.984 | 5255.984 | 5255.984 | 5603.0091 | 5972.9464 | 6367.3087 | 6787.7087 | 7235.8655 | 7713.6118 | 8222.9011 | 8765.8162 | 8765.8162 | 8765.8162 | 8765.8162 | 8765.8162 | 8765.8162 | 8765.8162 | 8765.8162 | 8765.8162 | 8765.8162 | 8765.8162 | 8765.8162 | 8765.8162 | 8765.8162 | 8765.8162 | 8765.8162 | 8765.8162 | 8765.8162 | 8765.8162 | 8765.8162 | 8765.8162 | [6 empty] | 1799 | 1814 | 1829 | 1844 | 1860.8 | 1887 | 1914 | 1941 | 1968 | 1995 | 2020.1 | 2041 | 2061 | 2081 | 2101 | 2121 | 2141 | 2161 | 2181 | 2201 | 2221 | 2241 | 2261 | 2281 | 2301 | 2321 | 2341 | 2361 | 2381 | 2401 | 2428.4 | 2607.3823 | 2799.5562 | 3005.8941 | 3227.4399 | 3465.3144 | 3720.7212 | 3994.9525 | 4289.3956 | 4289.3956 | 4289.3956 | 4289.3956 | 4289.3956 | 4289.3956 | 4289.3956 | 4289.3956 | 4289.3956 | 4289.3956 | 4289.3956 | 4289.3956 | 4289.3956 | 4289.3956 | 4289.3956 | 4289.3956 | 4289.3956 | 4289.3956 | 4289.3956 | 4289.3956 | 4289.3956 | [6 empty] | 3.0699 | 3.0699 | 3.0699 | 3.0699 | 3.0699 | 3.0738 | 3.0778 | 3.0817 | 3.0857 | 3.0897 | 3.0936 | 3.0976 | 3.1015 | 3.1055 | 3.1095 | 3.1092 | 3.1089 | 3.1086 | 3.1083 | 3.108 | 3.1076 | 3.1072 | 3.1067 | 3.1063 | 3.1059 | 3.1057 | 3.1056 | 3.1054 | 3.1052 | 3.105 | 3.105 | 3.105 | 3.105 | 3.105 | 3.105 | 3.1035 | 3.1019 | 3.1004 | 3.0988 | 3.0973 | 3.0958 | 3.0942 | 3.0927 | 3.0927 | 3.0927 | 3.0927 | 3.0927 | 3.0927 | 3.0927 | 3.0927 | 3.0927 | 3.0927 | 3.0927 | 3.0927 | 3.0927 | 3.0927 | 3.0927 | 3.0927 | 3.0927 | 3.0927 | 3.0927 | 3.0927 | 3.0927
334 | Puketapapa | AHP | Mt Roskill | 2060 | 810.293 | 801.9907 | 793.7734 | 785.6404 | 777.5906 | 835.6888 | 898.1278 | 965.232 | 1037.3499 | 1114.8561 | 1176.4363 | 1241.418 | 1309.9891 | 1382.3477 | 1458.7031 | 1513.311 | 1569.9633 | 1628.7363 | 1689.7096 | 1752.9655 | 1800.4366 | 1849.1933 | 1899.2703 | 1950.7034 | 2003.5294 | 2026.1343 | 2048.9943 | 2072.1122 | 2095.491 | 2119.1335 | 2119.1335 | 2119.1335 | 2119.1335 | 2119.1335 | 2119.1335 | 1934.0001 | 1765.0404 | 1610.8416 | 1470.1139 | 1341.6807 | 1224.4677 | 1117.4948 | 1019.8673 | 1019.8673 | 1019.8673 | 1019.8673 | 1019.8673 | 1019.8673 | 1019.8673 | 1019.8673 | 1019.8673 | 1019.8673 | 1019.8673 | 1019.8673 | 1019.8673 | 1019.8673 | 1019.8673 | 1019.8673 | 1019.8673 | 1019.8673 | 1019.8673 | 1019.8673 | 1019.8673 |  | 2230 | 2207.1512 | 2184.5366 | 2162.1536 | 2140 | 2314.0008 | 2502.1493 | 2705.596 | 2925.5847 | 3163.4605 | 3358.374 | 3565.297 | 3784.9693 | 4018.1765 | 4265.7526 | 4442.615 | 4626.8104 | 4818.6427 | 5018.4285 | 5226.4977 | 5388.9396 | 5556.4303 | 5729.1267 | 5907.1905 | 6090.7887 | 6183.9582 | 6278.5529 | 6374.5946 | 6472.1055 | 6571.1079 | 6571.1079 | 6571.1079 | 6571.1079 | 6571.1079 | 6571.1079 | 5994.0989 | 5467.7571 | 4987.6334 | 4549.6693 | 4150.1629 | 3785.7371 | 3453.3115 | 3150.0762 | 3150.0762 | 3150.0762 | 3150.0762 | 3150.0762 | 3150.0762 | 3150.0762 | 3150.0762 | 3150.0762 | 3150.0762 | 3150.0762 | 3150.0762 | 3150.0762 | 3150.0762 | 3150.0762 | 3150.0762 | 3150.0762 | 3150.0762 | 3150.0762 | 3150.0762 | 3150.0762 | [6 empty] | 785 | 800 | 815 | 830 | 846.2 | 867 | 888 | 909 | 930 | 951 | 970.3 | 990 | 1010 | 1030 | 1050 | 1070 | 1090 | 1110 | 1130 | 1150 | 1170 | 1190 | 1210 | 1230 | 1250 | 1270 | 1290 | 1310 | 1330 | 1350 | 1360.8 | 1296.7785 | 1235.7691 | 1177.6299 | 1122.226 | 1069.4288 | 1019.1154 | 971.1692 | 925.4786 | 925.4786 | 925.4786 | 925.4786 | 925.4786 | 925.4786 | 925.4786 | 925.4786 | 925.4786 | 925.4786 | 925.4786 | 925.4786 | 925.4786 | 925.4786 | 925.4786 | 925.4786 | 925.4786 | 925.4786 | 925.4786 | 925.4786 | 925.4786 | [6 empty] | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.769 | 2.786 | 2.8031 | 2.8202 | 2.8376 | 2.8547 | 2.872 | 2.8893 | 2.9068 | 2.9243 | 2.9357 | 2.9471 | 2.9585 | 2.97 | 2.9815 | 2.9931 | 3.0048 | 3.0165 | 3.0282 | 3.04 | 3.0521 | 3.0642 | 3.0764 | 3.0886 | 3.1008 | 3.1008 | 3.1008 | 3.1008 | 3.1008 | 3.1008 | 3.0993 | 3.0978 | 3.0963 | 3.0948 | 3.0933 | 3.0917 | 3.0902 | 3.0887 | 3.0887 | 3.0887 | 3.0887 | 3.0887 | 3.0887 | 3.0887 | 3.0887 | 3.0887 | 3.0887 | 3.0887 | 3.0887 | 3.0887 | 3.0887 | 3.0887 | 3.0887 | 3.0887 | 3.0887 | 3.0887 | 3.0887 | 3.0887
335 | Albert - Eden | AHP | Mt Roskill | 2060 | 1147.4805 | 1127.3415 | 1107.5559 | 1088.1175 | 1069.0203 | 1085.2015 | 1101.6276 | 1118.3024 | 1135.2295 | 1152.4129 | 1168.9362 | 1185.6964 | 1202.6969 | 1219.9412 | 1237.4327 | 1252.6495 | 1268.0535 | 1283.6468 | 1299.4319 | 1315.4111 | 1329.036 | 1342.802 | 1356.7106 | 1370.7632 | 1384.9614 | 1403.2099 | 1421.6987 | 1440.4313 | 1459.4106 | 1478.64 | 1495.8041 | 1513.1674 | 1530.7323 | 1548.501 | 1566.4761 | 1526.6233 | 1487.7844 | 1449.9336 | 1413.0457 | 1377.0964 | 1342.0616 | 1307.9181 | 1274.6433 | 1274.6433 | 1274.6433 | 1274.6433 | 1274.6433 | 1274.6433 | 1274.6433 | 1274.6433 | 1274.6433 | 1274.6433 | 1274.6433 | 1274.6433 | 1274.6433 | 1274.6433 | 1274.6433 | 1274.6433 | 1274.6433 | 1274.6433 | 1274.6433 | 1274.6433 | 1274.6433 |  | 3510 | 3448.3971 | 3387.8754 | 3328.4159 | 3270 | 3323.0112 | 3376.8819 | 3431.6258 | 3487.2573 | 3543.7905 | 3598.4478 | 3653.948 | 3710.3043 | 3767.5297 | 3825.6378 | 3871.9596 | 3918.8423 | 3966.2927 | 4014.3176 | 4062.9239 | 4104.3195 | 4146.1368 | 4188.3802 | 4231.054 | 4274.1626 | 4329.6924 | 4385.9437 | 4442.9258 | 4500.6482 | 4559.1205 | 4611.7099 | 4664.9059 | 4718.7156 | 4773.1459 | 4828.2041 | 4703.0703 | 4581.1796 | 4462.448 | 4346.7937 | 4234.1367 | 4124.3995 | 4017.5064 | 3913.3837 | 3913.3837 | 3913.3837 | 3913.3837 | 3913.3837 | 3913.3837 | 3913.3837 | 3913.3837 | 3913.3837 | 3913.3837 | 3913.3837 | 3913.3837 | 3913.3837 | 3913.3837 | 3913.3837 | 3913.3837 | 3913.3837 | 3913.3837 | 3913.3837 | 3913.3837 | 3913.3837 | [6 empty] | 628 | 633 | 638 | 643 | 646.7 | 656 | 665 | 674 | 683 | 692 | 701.5 | 709 | 717 | 725 | 733 | 741 | 749 | 757 | 765 | 773 | 781 | 789 | 797 | 805 | 813 | 821 | 829 | 837 | 845 | 853 | 852.9 | 837.6424 | 822.6578 | 807.9412 | 793.4879 | 779.2932 | 765.3524 | 751.6609 | 738.2144 | 738.2144 | 738.2144 | 738.2144 | 738.2144 | 738.2144 | 738.2144 | 738.2144 | 738.2144 | 738.2144 | 738.2144 | 738.2144 | 738.2144 | 738.2144 | 738.2144 | 738.2144 | 738.2144 | 738.2144 | 738.2144 | 738.2144 | 738.2144 | [6 empty] | 3.0589 | 3.0589 | 3.0589 | 3.0589 | 3.0589 | 3.0621 | 3.0654 | 3.0686 | 3.0719 | 3.0751 | 3.0784 | 3.0817 | 3.085 | 3.0883 | 3.0916 | 3.091 | 3.0904 | 3.0899 | 3.0893 | 3.0887 | 3.0882 | 3.0877 | 3.0872 | 3.0866 | 3.0861 | 3.0856 | 3.085 | 3.0844 | 3.0839 | 3.0833 | 3.0831 | 3.0829 | 3.0827 | 3.0824 | 3.0822 | 3.0807 | 3.0792 | 3.0777 | 3.0762 | 3.0747 | 3.0732 | 3.0717 | 3.0702 | 3.0702 | 3.0702 | 3.0702 | 3.0702 | 3.0702 | 3.0702 | 3.0702 | 3.0702 | 3.0702 | 3.0702 | 3.0702 | 3.0702 | 3.0702 | 3.0702 | 3.0702 | 3.0702 | 3.0702 | 3.0702 | 3.0702 | 3.0702
336 | Albert - Eden |  |  | 2052 | 812.7285 | 799.7694 | 787.017 | 774.468 | 762.119 | 763.1241 | 764.1305 | 765.1383 | 766.1473 | 767.1577 | 768.1824 | 769.2084 | 770.2358 | 771.2646 | 772.2948 | 773.2966 | 774.2998 | 775.3042 | 776.31 | 777.317 | 778.2457 | 779.1755 | 780.1064 | 781.0384 | 781.9715 | 783.1394 | 784.3091 | 785.4805 | 786.6537 | 787.8286 | 788.8838 | 789.9405 | 790.9986 | 792.0581 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 | 793.119 |  | 2730 | 2686.4699 | 2643.6339 | 2601.4809 | 2560 | 2561.5024 | 2563.0057 | 2564.5099 | 2566.015 | 2567.5209 | 2569.0637 | 2570.6073 | 2572.1519 | 2573.6975 | 2575.2439 | 2574.4153 | 2573.5869 | 2572.7587 | 2571.9309 | 2571.1033 | 2569.9851 | 2568.8674 | 2567.7502 | 2566.6335 | 2565.5172 | 2565.1162 | 2564.7153 | 2564.3144 | 2563.9136 | 2563.5129 | 2566.8717 | 2570.2349 | 2573.6025 | 2576.9746 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | 2580.351 | [6 empty] | 559 | 565 | 571 | 577 | 583.9 | 593 | 602 | 611 | 620 | 629 | 639.7 | 648 | 656 | 664 | 672 | 680 | 688 | 696 | 704 | 712 | 720 | 728 | 736 | 744 | 752 | 760 | 768 | 776 | 784 | 792 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | 797.4 | [6 empty] | 3.3591 | 3.3591 | 3.3591 | 3.3591 | 3.3591 | 3.3566 | 3.3541 | 3.3517 | 3.3492 | 3.3468 | 3.3443 | 3.3419 | 3.3394 | 3.337 | 3.3345 | 3.3291 | 3.3238 | 3.3184 | 3.313 | 3.3077 | 3.3023 | 3.2969 | 3.2915 | 3.2862 | 3.2808 | 3.2754 | 3.27 | 3.2646 | 3.2593 | 3.2539 | 3.2538 | 3.2537 | 3.2536 | 3.2535 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534 | 3.2534
337 | Albert - Eden |  |  | 2052 | 1105.7264 | 1085.8731 | 1066.3762 | 1047.2294 | 1028.4264 | 1031.1829 | 1033.9467 | 1036.718 | 1039.4967 | 1042.2829 | 1045.0931 | 1047.9108 | 1050.7362 | 1053.5691 | 1056.4098 | 1058.9994 | 1061.5953 | 1064.1977 | 1066.8064 | 1069.4215 | 1071.7386 | 1074.0608 | 1076.3881 | 1078.7204 | 1081.0577 | 1084.1743 | 1087.2999 | 1090.4345 | 1093.5781 | 1096.7308 | 1099.6543 | 1102.5856 | 1105.5247 | 1108.4716 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 | 1111.4264 |  | 3290 | 3230.928 | 3172.9166 | 3115.9469 | 3060 | 3070.6844 | 3081.4061 | 3092.1652 | 3102.9619 | 3113.7963 | 3124.708 | 3135.6579 | 3146.6462 | 3157.673 | 3168.7385 | 3175.2272 | 3181.7293 | 3188.2446 | 3194.7733 | 3201.3154 | 3206.9599 | 3212.6143 | 3218.2787 | 3223.9531 | 3229.6375 | 3237.6363 | 3245.6549 | 3253.6934 | 3261.7518 | 3269.8302 | 3278.5272 | 3287.2474 | 3295.9907 | 3304.7573 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | 3313.5473 | [6 empty] | 620 | 624 | 628 | 632 | 637.3 | 647 | 656 | 665 | 674 | 683 | 693.2 | 701 | 708 | 715 | 722 | 729 | 736 | 743 | 750 | 757 | 764 | 771 | 778 | 785 | 792 | 799 | 806 | 813 | 820 | 827 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | 840.4 | [6 empty] | 2.9754 | 2.9754 | 2.9754 | 2.9754 | 2.9754 | 2.9778 | 2.9802 | 2.9826 | 2.9851 | 2.9875 | 2.9899 | 2.9923 | 2.9947 | 2.9971 | 2.9995 | 2.9983 | 2.9971 | 2.9959 | 2.9947 | 2.9935 | 2.9923 | 2.9911 | 2.9899 | 2.9887 | 2.9875 | 2.9863 | 2.9851 | 2.9839 | 2.9826 | 2.9814 | 2.9814 | 2.9814 | 2.9814 | 2.9814 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813 | 2.9813
338 | Puketapapa |  |  | 2052 | 1181.8111 | 1189.7404 | 1197.7228 | 1205.7589 | 1213.8488 | 1234.3885 | 1255.2757 | 1276.5163 | 1298.1164 | 1320.0819 | 1341.0654 | 1362.3823 | 1384.0382 | 1406.0383 | 1428.388 | 1447.6426 | 1467.1567 | 1486.9339 | 1506.9776 | 1527.2916 | 1544.4937 | 1561.8896 | 1579.4814 | 1597.2713 | 1615.2616 | 1638.2931 | 1661.653 | 1685.3459 | 1709.3767 | 1733.7502 | 1755.4213 | 1777.3634 | 1799.5797 | 1822.0737 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 | 1844.8488 |  | 3540 | 3562.2886 | 3584.7176 | 3607.2877 | 3630 | 3700.066 | 3771.4845 | 3844.2814 | 3918.4835 | 3994.1178 | 4067.5144 | 4142.2597 | 4218.3785 | 4295.8961 | 4374.8382 | 4438.2422 | 4502.5652 | 4567.8203 | 4634.0212 | 4701.1815 | 4759.5148 | 4818.5719 | 4878.3617 | 4938.8935 | 5000.1763 | 5076.7047 | 5154.4045 | 5233.2934 | 5313.3897 | 5394.7119 | 5459.4572 | 5524.9795 | 5591.2881 | 5658.3926 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | 5726.3025 | [6 empty] | 2468 | 2495 | 2522 | 2549 | 2576.5 | 2612 | 2648 | 2684 | 2720 | 2756 | 2791.5 | 2823 | 2854 | 2885 | 2916 | 2947 | 2978 | 3009 | 3040 | 3071 | 3102 | 3133 | 3164 | 3195 | 3226 | 3257 | 3288 | 3319 | 3350 | 3381 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | 3418.6 | [6 empty] | 2.9954 | 2.9942 | 2.9929 | 2.9917 | 2.9905 | 2.9975 | 3.0045 | 3.0115 | 3.0186 | 3.0257 | 3.033 | 3.0405 | 3.0479 | 3.0553 | 3.0628 | 3.0658 | 3.0689 | 3.072 | 3.075 | 3.0781 | 3.0816 | 3.0851 | 3.0886 | 3.0921 | 3.0956 | 3.0988 | 3.102 | 3.1052 | 3.1084 | 3.1116 | 3.1101 | 3.1085 | 3.107 | 3.1055 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039 | 3.1039
339 | Maungakiekie - Tamaki |  |  | 2052 | 1024.5247 | 1016.9351 | 1009.4017 | 1001.9241 | 994.5019 | 997.1749 | 999.855 | 1002.5423 | 1005.2368 | 1007.9385 | 1010.6635 | 1013.3959 | 1016.1356 | 1018.8828 | 1021.6373 | 1024.1331 | 1026.6349 | 1029.1429 | 1031.657 | 1034.1772 | 1036.4018 | 1038.6311 | 1040.8653 | 1043.1042 | 1045.348 | 1048.3401 | 1051.3407 | 1054.3499 | 1057.3677 | 1060.3942 | 1063.2008 | 1066.0149 | 1068.8365 | 1071.6655 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 | 1074.5019 |  | 2730 | 2709.7764 | 2689.7026 | 2669.7775 | 2650 | 2668.9155 | 2687.966 | 2707.1525 | 2726.4759 | 2745.9373 | 2765.3184 | 2784.8364 | 2804.4921 | 2824.2865 | 2844.2207 | 2858.0944 | 2872.0359 | 2886.0453 | 2900.1231 | 2914.2696 | 2927.5867 | 2940.9648 | 2954.4039 | 2967.9045 | 2981.4668 | 2997.0464 | 3012.7074 | 3028.4502 | 3044.2753 | 3060.1832 | 3067.9536 | 3075.7438 | 3083.5538 | 3091.3836 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | 3099.2332 | [6 empty] | 487 | 491 | 495 | 499 | 503.4 | 509 | 515 | 521 | 527 | 533 | 537.1 | 542 | 547 | 552 | 557 | 562 | 567 | 572 | 577 | 582 | 587 | 592 | 597 | 602 | 607 | 612 | 617 | 622 | 627 | 632 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | 637.7 | [6 empty] | 2.6647 | 2.6647 | 2.6647 | 2.6647 | 2.6647 | 2.6765 | 2.6884 | 2.7003 | 2.7123 | 2.7243 | 2.7361 | 2.748 | 2.76 | 2.7719 | 2.784 | 2.7907 | 2.7975 | 2.8043 | 2.8111 | 2.818 | 2.8248 | 2.8316 | 2.8384 | 2.8453 | 2.8521 | 2.8588 | 2.8656 | 2.8723 | 2.8791 | 2.8859 | 2.8856 | 2.8853 | 2.885 | 2.8847 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843 | 2.8843
340 | Maungakiekie - Tamaki |  |  | 2052 | 1835.5536 | 1836.5635 | 1837.5741 | 1838.5851 | 1839.5968 | 1842.2763 | 1844.9597 | 1847.647 | 1850.3382 | 1853.0334 | 1855.765 | 1858.5008 | 1861.2405 | 1863.9843 | 1866.7322 | 1869.2334 | 1871.738 | 1874.246 | 1876.7573 | 1879.272 | 1881.5009 | 1883.7324 | 1885.9666 | 1888.2034 | 1890.4428 | 1893.4425 | 1896.447 | 1899.4562 | 1902.4702 | 1905.489 | 1908.3022 | 1911.1196 | 1913.9412 | 1916.7669 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 | 1919.5968 |  | 4590 | 4592.498 | 4594.9973 | 4597.498 | 4600 | 4624.3732 | 4648.8755 | 4673.5077 | 4698.2703 | 4723.1642 | 4747.9316 | 4772.8288 | 4797.8566 | 4823.0157 | 4848.3066 | 4864.1551 | 4880.0554 | 4896.0076 | 4912.012 | 4928.0687 | 4943.3355 | 4958.6495 | 4974.011 | 4989.4201 | 5004.8769 | 5022.2811 | 5039.7458 | 5057.2712 | 5074.8576 | 5092.5052 | 5099.9499 | 5107.4055 | 5114.8719 | 5122.3493 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | 5129.8376 | [6 empty] | 773 | 781 | 789 | 797 | 805.7 | 817 | 829 | 841 | 853 | 865 | 874.8 | 886 | 897 | 908 | 919 | 930 | 941 | 952 | 963 | 974 | 985 | 996 | 1007 | 1018 | 1029 | 1040 | 1051 | 1062 | 1073 | 1084 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | 1089.4 | [6 empty] | 2.5006 | 2.5006 | 2.5006 | 2.5006 | 2.5005 | 2.5101 | 2.5198 | 2.5294 | 2.5391 | 2.5489 | 2.5585 | 2.5681 | 2.5778 | 2.5875 | 2.5972 | 2.6022 | 2.6072 | 2.6123 | 2.6173 | 2.6223 | 2.6273 | 2.6324 | 2.6374 | 2.6424 | 2.6475 | 2.6525 | 2.6575 | 2.6625 | 2.6675 | 2.6725 | 2.6725 | 2.6725 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724 | 2.6724
341 | Maungakiekie - Tamaki |  |  | 2052 | 568.252 | 565.1036 | 561.9727 | 558.8592 | 555.7629 | 569.1288 | 582.8162 | 596.8327 | 611.1863 | 625.8851 | 639.5715 | 653.5571 | 667.8485 | 682.4524 | 697.3757 | 709.984 | 722.8202 | 735.8886 | 749.1931 | 762.7383 | 774.0349 | 785.4988 | 797.1326 | 808.9386 | 820.9195 | 835.9496 | 851.2549 | 866.8404 | 882.7113 | 898.8728 | 912.9997 | 927.3487 | 941.9232 | 956.7267 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 | 971.7629 |  | 1820 | 1809.9165 | 1799.8889 | 1789.9168 | 1780 | 1822.2808 | 1865.5659 | 1909.8792 | 1955.245 | 2001.6885 | 2045.8742 | 2091.0352 | 2137.1932 | 2184.3701 | 2232.5883 | 2271.4509 | 2310.9899 | 2351.2171 | 2392.1446 | 2433.7845 | 2469.1611 | 2505.0519 | 2541.4643 | 2578.4061 | 2615.8848 | 2662.6122 | 2710.1742 | 2758.5859 | 2807.8623 | 2858.019 | 2899.7555 | 2942.1016 | 2985.066 | 3028.6579 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | 3072.8863 | [6 empty] | 3755 | 3805 | 3855 | 3905 | 3954.9 | 4006 | 4057 | 4108 | 4159 | 4210 | 4261 | 4309 | 4357 | 4405 | 4453 | 4501 | 4549 | 4597 | 4645 | 4693 | 4741 | 4789 | 4837 | 4885 | 4933 | 4981 | 5029 | 5077 | 5125 | 5173 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | 5214.6 | [6 empty] | 3.2028 | 3.2028 | 3.2028 | 3.2028 | 3.2028 | 3.2019 | 3.201 | 3.2 | 3.1991 | 3.1982 | 3.1988 | 3.1995 | 3.2001 | 3.2008 | 3.2014 | 3.1993 | 3.1972 | 3.1951 | 3.193 | 3.1909 | 3.19 | 3.1891 | 3.1883 | 3.1874 | 3.1865 | 3.1851 | 3.1837 | 3.1823 | 3.181 | 3.1796 | 3.1761 | 3.1726 | 3.1691 | 3.1656 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622 | 3.1622
342 | Albert - Eden |  |  | 2052 | 1096.1749 | 1079.4747 | 1063.029 | 1046.8339 | 1030.8855 | 1038.987 | 1047.1523 | 1055.3817 | 1063.6758 | 1072.035 | 1080.2972 | 1088.623 | 1097.0131 | 1105.4677 | 1113.9876 | 1121.5838 | 1129.2318 | 1136.932 | 1144.6846 | 1152.4901 | 1159.2806 | 1166.1111 | 1172.9819 | 1179.8931 | 1186.8451 | 1195.9091 | 1205.0423 | 1214.2453 | 1223.5186 | 1232.8627 | 1241.3496 | 1249.8949 | 1258.4991 | 1267.1624 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 | 1275.8855 |  | 3190 | 3141.4006 | 3093.5417 | 3046.4118 | 3000 | 3027.9279 | 3056.1158 | 3084.5662 | 3113.2813 | 3142.2638 | 3171.0269 | 3200.0533 | 3229.3453 | 3258.9055 | 3288.7363 | 3311.4895 | 3334.4001 | 3357.4693 | 3380.698 | 3404.0874 | 3424.5157 | 3445.0665 | 3465.7407 | 3486.5389 | 3507.4619 | 3534.6012 | 3561.9503 | 3589.5112 | 3617.2852 | 3645.2742 | 3670.215 | 3695.3264 | 3720.6096 | 3746.0658 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | 3771.6962 | [6 empty] | 1824 | 1847 | 1870 | 1893 | 1915.3 | 1941 | 1967 | 1993 | 2019 | 2045 | 2071.1 | 2097 | 2123 | 2149 | 2175 | 2201 | 2227 | 2253 | 2279 | 2305 | 2331 | 2357 | 2383 | 2409 | 2435 | 2461 | 2487 | 2513 | 2539 | 2565 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | 2581.4 | [6 empty] | 2.9101 | 2.9101 | 2.9101 | 2.9101 | 2.9101 | 2.9143 | 2.9185 | 2.9227 | 2.9269 | 2.9311 | 2.9353 | 2.9395 | 2.9438 | 2.948 | 2.9522 | 2.9525 | 2.9528 | 2.9531 | 2.9534 | 2.9537 | 2.954 | 2.9543 | 2.9546 | 2.955 | 2.9553 | 2.9556 | 2.9559 | 2.9562 | 2.9565 | 2.9568 | 2.9566 | 2.9565 | 2.9564 | 2.9563 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561 | 2.9561
343 | Maungakiekie - Tamaki |  |  | 2052 | 1400.721 | 1412.0279 | 1423.4261 | 1434.9163 | 1446.4993 | 1448.0078 | 1449.5178 | 1451.0294 | 1452.5426 | 1454.0574 | 1455.5952 | 1457.1347 | 1458.6758 | 1460.2186 | 1461.763 | 1463.2028 | 1464.6441 | 1466.0868 | 1467.531 | 1468.9765 | 1470.2775 | 1471.5796 | 1472.8829 | 1474.1873 | 1475.4928 | 1477.162 | 1478.8331 | 1480.506 | 1482.1809 | 1483.8576 | 1485.3828 | 1486.9096 | 1488.4379 | 1489.9678 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 | 1491.4993 |  | 4000 | 4032.1113 | 4064.4803 | 4097.1092 | 4130 | 4139.7269 | 4149.4767 | 4159.2495 | 4169.0453 | 4178.8641 | 4188.7321 | 4198.6234 | 4208.538 | 4218.476 | 4228.4375 | 4232.5808 | 4236.728 | 4240.8794 | 4245.0348 | 4249.1943 | 4252.9378 | 4256.6846 | 4260.4347 | 4264.1881 | 4267.9448 | 4272.7478 | 4277.5562 | 4282.3701 | 4287.1893 | 4292.014 | 4296.4028 | 4300.796 | 4305.1938 | 4309.596 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | 4314.0028 | [6 empty] | 1106 | 1118 | 1130 | 1142 | 1152.9 | 1167 | 1181 | 1195 | 1209 | 1223 | 1237.9 | 1251 | 1264 | 1277 | 1290 | 1303 | 1316 | 1329 | 1342 | 1355 | 1368 | 1381 | 1394 | 1407 | 1420 | 1433 | 1446 | 1459 | 1472 | 1485 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | 1492.9 | [6 empty] | 2.8557 | 2.8555 | 2.8554 | 2.8553 | 2.8552 | 2.8589 | 2.8627 | 2.8664 | 2.8702 | 2.8739 | 2.8777 | 2.8814 | 2.8852 | 2.8889 | 2.8927 | 2.8927 | 2.8927 | 2.8927 | 2.8926 | 2.8926 | 2.8926 | 2.8926 | 2.8926 | 2.8926 | 2.8926 | 2.8925 | 2.8925 | 2.8925 | 2.8925 | 2.8925 | 2.8925 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924 | 2.8924
344 | Maungakiekie - Tamaki |  |  | 2052 | 1580.1187 | 1573.1422 | 1566.1966 | 1559.2817 | 1552.3973 | 1553.0685 | 1553.7401 | 1554.4119 | 1555.084 | 1555.7564 | 1556.4408 | 1557.1254 | 1557.8103 | 1558.4956 | 1559.1811 | 1559.8076 | 1560.4344 | 1561.0614 | 1561.6886 | 1562.3161 | 1562.8742 | 1563.4326 | 1563.9911 | 1564.5499 | 1565.1088 | 1565.8604 | 1566.6123 | 1567.3646 | 1568.1173 | 1568.8703 | 1569.5751 | 1570.2802 | 1570.9856 | 1571.6913 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 | 1572.3973 |  | 3990 | 3972.3837 | 3954.8451 | 3937.384 | 3920 | 3986.6769 | 4054.488 | 4123.4525 | 4193.59 | 4264.9206 | 4332.0848 | 4400.3067 | 4469.603 | 4539.9906 | 4611.4866 | 4661.179 | 4711.4068 | 4762.1758 | 4813.4919 | 4865.361 | 4915.0833 | 4965.3137 | 5016.0575 | 5067.3199 | 5119.1061 | 5169.6803 | 5220.7541 | 5272.3325 | 5324.4205 | 5377.0231 | 5379.4215 | 5381.8211 | 5384.2216 | 5386.6233 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | 5389.026 | [6 empty] | 402 | 405 | 408 | 411 | 413.5 | 419 | 424 | 429 | 434 | 439 | 444.2 | 448 | 452 | 456 | 460 | 464 | 468 | 472 | 476 | 480 | 484 | 488 | 492 | 496 | 500 | 504 | 508 | 512 | 516 | 520 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | 520.8 | [6 empty] | 2.5251 | 2.5251 | 2.5251 | 2.5251 | 2.5251 | 2.567 | 2.6095 | 2.6527 | 2.6967 | 2.7414 | 2.7833 | 2.8259 | 2.8692 | 2.9131 | 2.9576 | 2.9883 | 3.0193 | 3.0506 | 3.0822 | 3.1142 | 3.1449 | 3.1759 | 3.2072 | 3.2388 | 3.2708 | 3.3015 | 3.3325 | 3.3638 | 3.3954 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273 | 3.4273
345 | Maungakiekie - Tamaki |  |  | 2052 | 1491.0649 | 1470.5615 | 1450.34 | 1430.3965 | 1410.7274 | 1430.3299 | 1450.2047 | 1470.3558 | 1490.7868 | 1511.5018 | 1531.5131 | 1551.7893 | 1572.3339 | 1593.1505 | 1614.2428 | 1632.629 | 1651.2246 | 1670.032 | 1689.0536 | 1708.2918 | 1724.7287 | 1741.3237 | 1758.0783 | 1774.9942 | 1792.0728 | 1814.0942 | 1836.3861 | 1858.952 | 1881.7952 | 1904.9191 | 1925.6257 | 1946.5573 | 1967.7165 | 1989.1057 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 | 2010.7274 |  | 4640 | 4576.196 | 4513.2693 | 4451.208 | 4390 | 4458.9693 | 4529.0222 | 4600.1756 | 4672.4468 | 4745.8535 | 4817.2083 | 4889.6358 | 4963.1524 | 5037.7742 | 5113.5181 | 5173.6221 | 5234.4326 | 5295.9579 | 5358.2063 | 5421.1864 | 5475.2994 | 5529.9524 | 5585.151 | 5640.9006 | 5697.2066 | 5769.2807 | 5842.2666 | 5916.1759 | 5991.0201 | 6066.8112 | 6132.8258 | 6199.5588 | 6267.018 | 6335.2112 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | 6404.1464 | [6 empty] | 428 | 431 | 434 | 437 | 439.1 | 446 | 453 | 460 | 467 | 474 | 478.8 | 484 | 489 | 494 | 499 | 504 | 509 | 514 | 519 | 524 | 529 | 534 | 539 | 544 | 549 | 554 | 559 | 564 | 569 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | 574 | [6 empty] | 3.1119 | 3.1119 | 3.1119 | 3.1119 | 3.1119 | 3.1174 | 3.123 | 3.1286 | 3.1342 | 3.1398 | 3.1454 | 3.151 | 3.1566 | 3.1621 | 3.1678 | 3.1689 | 3.17 | 3.1712 | 3.1723 | 3.1735 | 3.1746 | 3.1757 | 3.1768 | 3.178 | 3.1791 | 3.1803 | 3.1814 | 3.1825 | 3.1837 | 3.1848 | 3.1848 | 3.1849 | 3.1849 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185 | 3.185
346 | Maungakiekie - Tamaki |  |  | 2052 | 1688.1709 | 1690.252 | 1692.3357 | 1694.422 | 1696.5109 | 1725.4846 | 1754.9531 | 1784.9249 | 1815.4086 | 1846.4128 | 1876.0139 | 1906.0894 | 1936.6471 | 1967.6947 | 1999.2401 | 2026.483 | 2054.0972 | 2082.0876 | 2110.4595 | 2139.218 | 2163.6038 | 2188.2675 | 2213.2125 | 2238.4417 | 2263.9586 | 2296.6064 | 2329.725 | 2363.3213 | 2397.402 | 2431.9741 | 2462.6955 | 2493.8049 | 2525.3072 | 2557.2076 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 | 2589.5109 |  | 4150 | 4154.991 | 4159.988 | 4164.991 | 4170 | 4265.5379 | 4363.2646 | 4463.2303 | 4565.4863 | 4670.085 | 4771.6459 | 4875.4153 | 4981.4415 | 5089.7734 | 5200.4613 | 5289.2164 | 5379.4863 | 5471.2968 | 5564.6742 | 5659.6452 | 5743.5673 | 5828.7337 | 5915.163 | 6002.874 | 6091.8854 | 6200.1161 | 6310.2696 | 6422.3802 | 6536.4826 | 6652.6121 | 6735.3969 | 6819.2119 | 6904.0698 | 6989.9838 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | 7076.9668 | [6 empty] | 1520 | 1537 | 1554 | 1571 | 1589.4 | 1610 | 1631 | 1652 | 1673 | 1694 | 1712.7 | 1733 | 1753 | 1773 | 1793 | 1813 | 1833 | 1853 | 1873 | 1893 | 1913 | 1933 | 1953 | 1973 | 1993 | 2013 | 2033 | 2053 | 2073 | 2093 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | 2110.2 | [6 empty] | 2.4583 | 2.4582 | 2.4581 | 2.4581 | 2.458 | 2.4721 | 2.4863 | 2.5005 | 2.5149 | 2.5293 | 2.5435 | 2.5578 | 2.5722 | 2.5867 | 2.6012 | 2.61 | 2.6189 | 2.6278 | 2.6367 | 2.6457 | 2.6546 | 2.6636 | 2.6727 | 2.6817 | 2.6908 | 2.6997 | 2.7086 | 2.7175 | 2.7265 | 2.7355 | 2.735 | 2.7345 | 2.734 | 2.7334 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329 | 2.7329
347 | Maungakiekie - Tamaki |  |  | 2052 | 606.1409 | 639.499 | 674.6929 | 711.8236 | 750.9978 | 808.63 | 870.685 | 937.5021 | 1009.4468 | 1086.9126 | 1148.115 | 1212.7636 | 1281.0525 | 1353.1867 | 1429.3826 | 1487.2099 | 1547.3766 | 1609.9775 | 1675.1109 | 1742.8794 | 1795.4633 | 1849.6336 | 1905.4383 | 1962.9266 | 2022.1494 | 2092.336 | 2164.9587 | 2240.102 | 2317.8535 | 2398.3036 | 2465.0253 | 2533.6032 | 2604.0889 | 2676.5356 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 | 2750.9978 |  | 1420 | 1496.1522 | 1576.3883 | 1660.9273 | 1750 | 1886.2695 | 2033.1501 | 2191.468 | 2362.1139 | 2546.0477 | 2693.9214 | 2850.3836 | 3015.9331 | 3191.0977 | 3376.4358 | 3514.7871 | 3658.8074 | 3808.729 | 3964.7937 | 4127.2533 | 4254.5461 | 4385.7648 | 4521.0306 | 4660.4683 | 4804.2065 | 4974.2115 | 5150.2325 | 5332.4823 | 5521.1813 | 5716.5577 | 5874.5625 | 6036.9344 | 6203.7943 | 6375.2661 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | 6551.4774 | [6 empty] | 4299 | 4339 | 4379 | 4419 | 4460.7 | 4523 | 4586 | 4649 | 4712 | 4775 | 4836.5 | 4883 | 4930 | 4977 | 5024 | 5071 | 5118 | 5165 | 5212 | 5259 | 5306 | 5353 | 5400 | 5447 | 5494 | 5541 | 5588 | 5635 | 5682 | 5729 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | 5770.8 | [6 empty] | 2.3427 | 2.3396 | 2.3365 | 2.3333 | 2.3302 | 2.3327 | 2.3351 | 2.3376 | 2.34 | 2.3425 | 2.3464 | 2.3503 | 2.3543 | 2.3582 | 2.3622 | 2.3633 | 2.3645 | 2.3657 | 2.3669 | 2.3681 | 2.3696 | 2.3712 | 2.3727 | 2.3742 | 2.3758 | 2.3773 | 2.3789 | 2.3805 | 2.382 | 2.3836 | 2.3832 | 2.3827 | 2.3823 | 2.3819 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815 | 2.3815
348 | Maungakiekie - Tamaki |  |  | 2052 | 1352.2984 | 1352.2984 | 1352.2984 | 1352.2984 | 1352.2984 | 1382.8795 | 1414.1522 | 1446.1321 | 1478.8352 | 1512.2778 | 1543.5755 | 1575.521 | 1608.1276 | 1641.409 | 1675.3791 | 1704.2438 | 1733.6058 | 1763.4737 | 1793.8561 | 1824.762 | 1850.6412 | 1876.8874 | 1903.5059 | 1930.5018 | 1957.8807 | 1992.495 | 2027.7212 | 2063.5702 | 2100.053 | 2137.1808 | 2169.7937 | 2202.9043 | 2236.5201 | 2270.6488 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 | 2305.2984 |  | 3380 | 3380 | 3380 | 3380 | 3380 | 3471.0548 | 3564.5625 | 3660.5892 | 3759.2028 | 3860.473 | 3956.4601 | 4054.8338 | 4155.6534 | 4258.9799 | 4364.8754 | 4449.5752 | 4535.9186 | 4623.9374 | 4713.6642 | 4805.1322 | 4883.363 | 4962.8675 | 5043.6663 | 5125.7806 | 5209.2317 | 5312.3049 | 5417.4176 | 5524.6101 | 5633.9235 | 5745.3999 | 5833.8784 | 5923.7194 | 6014.944 | 6107.5734 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | 6201.6293 | [6 empty] | 2252 | 2270 | 2288 | 2306 | 2323.1 | 2357 | 2391 | 2425 | 2459 | 2493 | 2525.5 | 2548 | 2571 | 2594 | 2617 | 2640 | 2663 | 2686 | 2709 | 2732 | 2755 | 2778 | 2801 | 2824 | 2847 | 2870 | 2893 | 2916 | 2939 | 2962 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | 2977.7 | [6 empty] | 2.4994 | 2.4994 | 2.4994 | 2.4994 | 2.4994 | 2.51 | 2.5206 | 2.5313 | 2.542 | 2.5528 | 2.5632 | 2.5736 | 2.5842 | 2.5947 | 2.6053 | 2.6109 | 2.6165 | 2.6221 | 2.6277 | 2.6333 | 2.6387 | 2.6442 | 2.6497 | 2.6552 | 2.6606 | 2.6662 | 2.6717 | 2.6772 | 2.6828 | 2.6883 | 2.6887 | 2.689 | 2.6894 | 2.6898 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902 | 2.6902
349 | Maungakiekie - Tamaki |  |  | 2052 | 112.4553 | 110.985 | 109.5339 | 108.1018 | 106.6884 | 107.6776 | 108.676 | 109.6836 | 110.7006 | 111.7271 | 112.7361 | 113.7542 | 114.7816 | 115.8182 | 116.8641 | 117.8517 | 118.8477 | 119.8521 | 120.865 | 121.8864 | 122.8034 | 123.7273 | 124.6581 | 125.596 | 126.5409 | 127.6912 | 128.852 | 130.0233 | 131.2052 | 132.3979 | 133.4395 | 134.4893 | 135.5473 | 136.6136 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 | 137.6884 |  | 390 | 384.9009 | 379.8684 | 374.9017 | 370 | 373.6746 | 377.3858 | 381.1337 | 384.919 | 388.7418 | 392.5224 | 396.3397 | 400.1942 | 404.0862 | 408.0161 | 411.2625 | 414.5347 | 417.8329 | 421.1575 | 424.5084 | 427.5193 | 430.5516 | 433.6054 | 436.6809 | 439.7782 | 443.559 | 447.3724 | 451.2185 | 455.0977 | 459.0103 | 462.4513 | 465.9181 | 469.4109 | 472.9299 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | 476.4753 | [6 empty] | 4487 | 4511 | 4535 | 4559 | 4583.9 | 4649 | 4714 | 4779 | 4844 | 4909 | 4972.3 | 5008 | 5044 | 5080 | 5116 | 5152 | 5188 | 5224 | 5260 | 5296 | 5332 | 5368 | 5404 | 5440 | 5476 | 5512 | 5548 | 5584 | 5620 | 5656 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | 5690 | [6 empty] | 3.468 | 3.468 | 3.468 | 3.468 | 3.468 | 3.4703 | 3.4726 | 3.4748 | 3.4771 | 3.4794 | 3.4818 | 3.4842 | 3.4866 | 3.489 | 3.4914 | 3.4897 | 3.4879 | 3.4862 | 3.4845 | 3.4828 | 3.4813 | 3.4798 | 3.4784 | 3.4769 | 3.4754 | 3.4737 | 3.472 | 3.4703 | 3.4686 | 3.4669 | 3.4656 | 3.4644 | 3.4631 | 3.4618 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605 | 3.4605
350 | Maungakiekie - Tamaki |  |  | 2052 | 401.0936 | 397.2549 | 393.453 | 389.6874 | 385.9579 | 407.4462 | 430.1308 | 454.0783 | 479.3591 | 506.0475 | 528.4591 | 551.8633 | 576.3039 | 601.827 | 628.4805 | 649.4208 | 671.0589 | 693.4179 | 716.5219 | 740.3957 | 759.3241 | 778.7364 | 798.645 | 819.0625 | 840.002 | 865.268 | 891.294 | 918.1028 | 945.7179 | 974.1637 | 998.1154 | 1022.6561 | 1047.8001 | 1073.5623 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 | 1099.9579 |  | 1060 | 1049.8553 | 1039.8077 | 1029.8562 | 1020 | 1084.2676 | 1152.5845 | 1225.2058 | 1302.4029 | 1384.4639 | 1454.6881 | 1528.4742 | 1606.003 | 1687.4643 | 1773.0576 | 1839.0167 | 1907.4296 | 1978.3875 | 2051.9851 | 2128.3206 | 2190.3761 | 2254.2411 | 2319.9681 | 2387.6116 | 2457.2273 | 2539.871 | 2625.2943 | 2713.5906 | 2804.8565 | 2899.192 | 2971.2608 | 3045.1211 | 3120.8175 | 3198.3956 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | 3277.9021 | [6 empty] | 10982 | 11106 | 11230 | 11354 | 11476 | 11623 | 11770 | 11917 | 12064 | 12211 | 12357.1 | 12491 | 12625 | 12759 | 12893 | 13027 | 13161 | 13295 | 13429 | 13563 | 13697 | 13831 | 13965 | 14099 | 14233 | 14367 | 14501 | 14635 | 14769 | 14903 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | 15027.7 | [6 empty] | 2.6428 | 2.6428 | 2.6428 | 2.6428 | 2.6428 | 2.6611 | 2.6796 | 2.6982 | 2.717 | 2.7358 | 2.7527 | 2.7697 | 2.7867 | 2.8039 | 2.8212 | 2.8318 | 2.8424 | 2.8531 | 2.8638 | 2.8746 | 2.8846 | 2.8947 | 2.9049 | 2.9151 | 2.9253 | 2.9354 | 2.9455 | 2.9557 | 2.9658 | 2.9761 | 2.9769 | 2.9777 | 2.9784 | 2.9792 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98 | 2.98
351 | Maungakiekie - Tamaki |  |  | 2052 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 | 138.2638 |  | 460 | 460 | 460 | 460 | 460 | 461.2614 | 462.5263 | 463.7947 | 465.0665 | 466.3419 | 467.6034 | 468.8684 | 470.1367 | 471.4085 | 472.6838 | 473.2898 | 473.8966 | 474.5043 | 475.1127 | 475.7218 | 476.3279 | 476.9347 | 477.5424 | 478.1507 | 478.7599 | 479.366 | 479.9728 | 480.5804 | 481.1888 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | 481.798 | [6 empty] | 5223 | 5266 | 5309 | 5352 | 5394.1 | 5461 | 5528 | 5595 | 5662 | 5729 | 5797.6 | 5849 | 5900 | 5951 | 6002 | 6053 | 6104 | 6155 | 6206 | 6257 | 6308 | 6359 | 6410 | 6461 | 6512 | 6563 | 6614 | 6665 | 6716 | 6767 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | 6817.3 | [6 empty] | 3.327 | 3.327 | 3.327 | 3.327 | 3.327 | 3.3361 | 3.3452 | 3.3544 | 3.3636 | 3.3728 | 3.382 | 3.3911 | 3.4003 | 3.4095 | 3.4187 | 3.4231 | 3.4275 | 3.4319 | 3.4363 | 3.4407 | 3.4451 | 3.4495 | 3.4538 | 3.4583 | 3.4627 | 3.467 | 3.4714 | 3.4758 | 3.4802 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846 | 3.4846
352 | Maungakiekie - Tamaki |  |  | 2052 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.1837 | 3.3433 | 3.5108 | 3.6868 | 3.8715 | 4.0294 | 4.1936 | 4.3646 | 4.5425 | 4.7277 | 4.903 | 5.0847 | 5.2732 | 5.4687 | 5.6714 | 5.8464 | 6.0268 | 6.2128 | 6.4046 | 6.6023 | 6.8359 | 7.0778 | 7.3283 | 7.5876 | 7.8561 | 8.0783 | 8.3068 | 8.5417 | 8.7833 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 | 9.0318 |  | 20 | 20 | 20 | 20 | 20 | 20.2567 | 20.5167 | 20.7801 | 21.0468 | 21.317 | 21.5821 | 21.8506 | 22.1224 | 22.3976 | 22.6762 | 22.96 | 23.2474 | 23.5383 | 23.8329 | 24.1312 | 24.4117 | 24.6954 | 24.9824 | 25.2728 | 25.5665 | 25.942 | 26.323 | 26.7095 | 27.1018 | 27.4998 | 27.8531 | 28.211 | 28.5735 | 28.9406 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | 29.3125 | [6 empty] | 4818 | 4855 | 4892 | 4929 | 4965.4 | 5029 | 5093 | 5157 | 5221 | 5285 | 5348.5 | 5394 | 5439 | 5484 | 5529 | 5574 | 5619 | 5664 | 5709 | 5754 | 5799 | 5844 | 5889 | 5934 | 5979 | 6024 | 6069 | 6114 | 6159 | 6204 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | 6251 | [6 empty] | 6.5968 | 6.5968 | 6.5968 | 6.5968 | 6.5968 | 6.3626 | 6.1367 | 5.9189 | 5.7087 | 5.5061 | 5.3562 | 5.2104 | 5.0686 | 4.9306 | 4.7964 | 4.6829 | 4.572 | 4.4638 | 4.3581 | 4.2549 | 4.1755 | 4.0976 | 4.0211 | 3.946 | 3.8724 | 3.795 | 3.7191 | 3.6447 | 3.5718 | 3.5004 | 3.4479 | 3.3961 | 3.3452 | 3.2949 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455 | 3.2455
353 | Maungakiekie - Tamaki |  |  | 2052 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.4216 | 3.8616 | 4.3582 | 4.9186 | 5.5511 | 5.9898 | 6.4631 | 6.9739 | 7.525 | 8.1196 | 8.4636 | 8.822 | 9.1957 | 9.5852 | 9.9912 | 10.256 | 10.5279 | 10.807 | 11.0934 | 11.3875 | 11.741 | 12.1055 | 12.4813 | 12.8688 | 13.2683 | 13.6036 | 13.9474 | 14.2999 | 14.6612 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 | 15.0318 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3.8897 | 4.4826 | 5.1658 | 5.9531 | 6.8605 | 7.9061 | 8.4138 | 8.954 | 9.5289 | 10.1407 | 10.7918 | 11.1916 | 11.6063 | 12.0363 | 12.4823 | 12.9448 | 13.4789 | 14.035 | 14.614 | 15.2169 | 15.8447 | 16.3546 | 16.881 | 17.4242 | 17.985 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | 18.5638 | [6 empty] | 5852 | 5897 | 5942 | 5987 | 6033 | 6110 | 6187 | 6264 | 6341 | 6418 | 6495.2 | 6550 | 6605 | 6660 | 6715 | 6770 | 6825 | 6880 | 6935 | 6990 | 7045 | 7100 | 7155 | 7210 | 7265 | 7320 | 7375 | 7430 | 7485 | 7540 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | 7591.7 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0.25896 | 0.45891 | 0.60993 | 0.70071 | 0.74837 | 0.79927 | 0.85363 | 0.91169 | 0.9737 | 0.99412 | 1.015 | 1.0362 | 1.058 | 1.0801 | 1.0912 | 1.1024 | 1.1138 | 1.1252 | 1.1368 | 1.148 | 1.1594 | 1.1709 | 1.1825 | 1.1942 | 1.2022 | 1.2103 | 1.2185 | 1.2267 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235 | 1.235
354 | Maungakiekie - Tamaki |  |  | 2052 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.1837 | 3.3433 | 3.5108 | 3.6868 | 3.8715 | 4.0294 | 4.1936 | 4.3646 | 4.5425 | 4.7277 | 4.903 | 5.0847 | 5.2732 | 5.4687 | 5.6714 | 5.8464 | 6.0268 | 6.2128 | 6.4046 | 6.6023 | 6.7626 | 6.9269 | 7.0951 | 7.2674 | 7.4439 | 7.558 | 7.6737 | 7.7913 | 7.9106 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 | 8.0318 |  | 10 | 10 | 10 | 10 | 10 | 10.2505 | 10.5073 | 10.7706 | 11.0404 | 11.317 | 11.5766 | 11.8422 | 12.1139 | 12.3919 | 12.6762 | 12.9547 | 13.2393 | 13.5302 | 13.8274 | 14.1312 | 14.4072 | 14.6887 | 14.9757 | 15.2682 | 15.5665 | 15.8178 | 16.0732 | 16.3327 | 16.5963 | 16.8643 | 17.0418 | 17.2211 | 17.4024 | 17.5855 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | 17.7706 | [6 empty] | 5988 | 6034 | 6080 | 6126 | 6172.3 | 6251 | 6330 | 6409 | 6488 | 6567 | 6646.5 | 6703 | 6759 | 6815 | 6871 | 6927 | 6983 | 7039 | 7095 | 7151 | 7207 | 7263 | 7319 | 7375 | 7431 | 7487 | 7543 | 7599 | 7655 | 7711 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | 7768 | [6 empty] | 3.2984 | 3.2984 | 3.2984 | 3.2984 | 3.2984 | 3.2197 | 3.1428 | 3.0678 | 2.9946 | 2.9231 | 2.8731 | 2.8239 | 2.7755 | 2.728 | 2.6812 | 2.6422 | 2.6037 | 2.5658 | 2.5285 | 2.4917 | 2.4643 | 2.4372 | 2.4104 | 2.3839 | 2.3578 | 2.339 | 2.3204 | 2.302 | 2.2837 | 2.2655 | 2.2548 | 2.2442 | 2.2336 | 2.223 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125 | 2.2125
355 | Maungakiekie - Tamaki |  |  | 2052 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.1837 | 3.3433 | 3.5108 | 3.6868 | 3.8715 | 4.0294 | 4.1936 | 4.3646 | 4.5425 | 4.7277 | 4.8464 | 4.968 | 5.0927 | 5.2205 | 5.3516 | 5.4416 | 5.5331 | 5.6262 | 5.7208 | 5.817 | 5.9373 | 6.0601 | 6.1854 | 6.3134 | 6.4439 | 6.5574 | 6.6729 | 6.7905 | 6.9101 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 | 7.0318 |  | 10 | 10 | 10 | 10 | 10 | 10.2505 | 10.5073 | 10.7706 | 11.0404 | 11.317 | 11.5766 | 11.8422 | 12.1139 | 12.3919 | 12.6762 | 12.863 | 13.0525 | 13.2449 | 13.44 | 13.6381 | 13.7787 | 13.9207 | 14.0643 | 14.2093 | 14.3558 | 14.5441 | 14.7349 | 14.9282 | 15.124 | 15.3224 | 15.4995 | 15.6787 | 15.8599 | 16.0433 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | 16.2287 | [6 empty] | 4725 | 4761 | 4797 | 4833 | 4869.8 | 4932 | 4995 | 5058 | 5121 | 5184 | 5245 | 5289 | 5333 | 5377 | 5421 | 5465 | 5509 | 5553 | 5597 | 5641 | 5685 | 5729 | 5773 | 5817 | 5861 | 5905 | 5949 | 5993 | 6037 | 6081 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | 6130 | [6 empty] | 3.2984 | 3.2984 | 3.2984 | 3.2984 | 3.2984 | 3.2197 | 3.1428 | 3.0678 | 2.9946 | 2.9231 | 2.8731 | 2.8239 | 2.7755 | 2.728 | 2.6812 | 2.6541 | 2.6273 | 2.6007 | 2.5745 | 2.5484 | 2.5321 | 2.5159 | 2.4998 | 2.4838 | 2.4679 | 2.4496 | 2.4315 | 2.4134 | 2.3956 | 2.3778 | 2.3637 | 2.3496 | 2.3356 | 2.3217 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079 | 2.3079
356 | Maungakiekie - Tamaki |  |  | 2052 | 69.7306 | 70.6204 | 71.5214 | 72.434 | 73.3582 | 75.8679 | 78.4634 | 81.1476 | 83.9237 | 86.7948 | 89.3764 | 92.0347 | 94.7721 | 97.591 | 100.4936 | 102.885 | 105.3334 | 107.84 | 110.4062 | 113.0335 | 115.1842 | 117.3759 | 119.6093 | 121.8851 | 124.2043 | 127.0775 | 130.0172 | 133.0248 | 136.1021 | 139.2505 | 141.9642 | 144.7308 | 147.5513 | 150.4267 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 | 153.3582 |  | 240 | 242.4619 | 244.949 | 247.4616 | 250 | 257.288 | 264.7884 | 272.5076 | 280.4517 | 288.6274 | 296.1908 | 303.9523 | 311.9173 | 320.091 | 328.4788 | 335.2031 | 342.0651 | 349.0675 | 356.2133 | 363.5054 | 369.542 | 375.6789 | 381.9177 | 388.2601 | 394.7078 | 402.7765 | 411.0102 | 419.4122 | 427.986 | 436.735 | 444.3462 | 452.0901 | 459.969 | 467.9851 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | 476.141 | [6 empty] | 5337 | 5357 | 5377 | 5397 | 5418.8 | 5487 | 5555 | 5623 | 5691 | 5759 | 5825.8 | 5860 | 5895 | 5930 | 5965 | 6000 | 6035 | 6070 | 6105 | 6140 | 6175 | 6210 | 6245 | 6280 | 6315 | 6350 | 6385 | 6420 | 6455 | 6490 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | 6517.4 | [6 empty] | 3.4418 | 3.4333 | 3.4248 | 3.4164 | 3.4079 | 3.3913 | 3.3747 | 3.3582 | 3.3417 | 3.3254 | 3.314 | 3.3026 | 3.2912 | 3.2799 | 3.2687 | 3.258 | 3.2475 | 3.2369 | 3.2264 | 3.2159 | 3.2083 | 3.2006 | 3.193 | 3.1855 | 3.1779 | 3.1695 | 3.1612 | 3.1529 | 3.1446 | 3.1363 | 3.13 | 3.1237 | 3.1174 | 3.1111 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048 | 3.1048
357 | Maungakiekie - Tamaki |  |  | 2052 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 5.4394 | 9.7589 | 17.5086 | 31.4127 | 56.3582 | 64.5083 | 73.8369 | 84.5145 | 96.7362 | 110.7253 | 119.2465 | 128.4234 | 138.3065 | 148.9502 | 160.413 | 168.417 | 176.8203 | 185.6429 | 194.9058 | 204.6308 | 215.3573 | 226.646 | 238.5266 | 251.0298 | 264.1885 | 274.5173 | 285.25 | 296.4022 | 307.9904 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 | 320.0318 |  | 10 | 10 | 10 | 10 | 10 | 17.7128 | 31.3744 | 55.573 | 98.4354 | 174.3569 | 198.9617 | 227.0386 | 259.0776 | 295.6379 | 337.3575 | 362.9595 | 390.5045 | 420.1399 | 452.0243 | 486.3285 | 510.3496 | 535.5573 | 562.01 | 589.7694 | 618.8998 | 651.086 | 684.946 | 720.567 | 758.0404 | 797.4627 | 828.4452 | 860.6313 | 894.068 | 928.8037 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | 964.889 | [6 empty] | 1573 | 1579 | 1585 | 1591 | 1596.3 | 1617 | 1637 | 1657 | 1677 | 1697 | 1717.5 | 1728 | 1738 | 1748 | 1758 | 1768 | 1778 | 1788 | 1798 | 1808 | 1818 | 1828 | 1838 | 1848 | 1858 | 1868 | 1878 | 1888 | 1898 | 1908 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | 1922.9 | [6 empty] | 3.2984 | 3.2984 | 3.2984 | 3.2984 | 3.2984 | 3.2564 | 3.215 | 3.174 | 3.1336 | 3.0937 | 3.0843 | 3.0749 | 3.0655 | 3.0561 | 3.0468 | 3.0438 | 3.0408 | 3.0377 | 3.0347 | 3.0317 | 3.0303 | 3.0288 | 3.0274 | 3.0259 | 3.0245 | 3.0233 | 3.0221 | 3.0209 | 3.0197 | 3.0185 | 3.0178 | 3.0171 | 3.0164 | 3.0157 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015 | 3.015
358 | Maungakiekie - Tamaki |  |  | 2052 | 717.7815 | 735.6217 | 753.9054 | 772.6436 | 791.8474 | 800.4751 | 809.1968 | 818.0135 | 826.9263 | 835.9362 | 844.7387 | 853.6339 | 862.6227 | 871.7063 | 880.8854 | 888.9805 | 897.15 | 905.3946 | 913.715 | 922.1118 | 929.3514 | 936.6477 | 944.0014 | 951.4128 | 958.8824 | 968.5892 | 978.3944 | 988.2988 | 998.3034 | 1008.4093 | 1017.5305 | 1026.7341 | 1036.0209 | 1045.3918 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 | 1054.8474 |  | 2350 | 2405.5026 | 2462.316 | 2520.4712 | 2580 | 2610.116 | 2640.5835 | 2671.4067 | 2702.5897 | 2734.1367 | 2765.157 | 2796.5292 | 2828.2573 | 2860.3454 | 2892.7976 | 2918.2886 | 2944.0043 | 2969.9465 | 2996.1173 | 3022.5188 | 3045.3125 | 3068.2781 | 3091.4169 | 3114.7302 | 3138.2193 | 3168.7859 | 3199.6502 | 3230.8152 | 3262.2836 | 3294.0586 | 3322.7775 | 3351.7467 | 3380.9685 | 3410.445 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | 3440.1785 | [6 empty] | 579 | 587 | 595 | 603 | 612.4 | 620 | 628 | 636 | 644 | 652 | 657.5 | 665 | 673 | 681 | 689 | 697 | 705 | 713 | 721 | 729 | 737 | 745 | 753 | 761 | 769 | 777 | 785 | 793 | 801 | 809 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | 811.2 | [6 empty] | 3.274 | 3.27 | 3.2661 | 3.2621 | 3.2582 | 3.2607 | 3.2632 | 3.2657 | 3.2682 | 3.2707 | 3.2734 | 3.276 | 3.2787 | 3.2813 | 3.284 | 3.2827 | 3.2815 | 3.2803 | 3.2791 | 3.2778 | 3.2768 | 3.2758 | 3.2748 | 3.2738 | 3.2728 | 3.2715 | 3.2703 | 3.2691 | 3.2678 | 3.2666 | 3.2655 | 3.2645 | 3.2634 | 3.2624 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613 | 3.2613
359 | Orakei |  |  | 2052 | 1431.6598 | 1425.6232 | 1419.612 | 1413.6261 | 1407.6655 | 1419.8805 | 1432.2015 | 1444.6294 | 1457.1652 | 1469.8097 | 1482.2681 | 1494.8321 | 1507.5026 | 1520.2805 | 1533.1667 | 1544.5944 | 1556.1074 | 1567.7061 | 1579.3913 | 1591.1636 | 1601.3649 | 1611.6317 | 1621.9643 | 1632.3631 | 1642.8286 | 1656.5163 | 1670.318 | 1684.2348 | 1698.2675 | 1712.4171 | 1725.2723 | 1738.224 | 1751.273 | 1764.4199 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 | 1777.6655 |  | 3580 | 3564.9048 | 3549.8732 | 3534.9051 | 3520 | 3556.7498 | 3593.8833 | 3631.4045 | 3669.3175 | 3707.6262 | 3745.551 | 3783.8636 | 3822.5682 | 3861.6687 | 3901.1691 | 3931.5928 | 3962.2538 | 3993.1539 | 4024.295 | 4055.679 | 4083.1089 | 4110.7243 | 4138.5265 | 4166.5167 | 4194.6962 | 4231.0902 | 4267.7999 | 4304.828 | 4342.1775 | 4379.851 | 4412.5728 | 4445.5391 | 4478.7517 | 4512.2125 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | 4545.9232 | [6 empty] | 1174 | 1183 | 1192 | 1201 | 1211.5 | 1226 | 1241 | 1256 | 1271 | 1286 | 1299.1 | 1312 | 1325 | 1338 | 1351 | 1364 | 1377 | 1390 | 1403 | 1416 | 1429 | 1442 | 1455 | 1468 | 1481 | 1494 | 1507 | 1520 | 1533 | 1546 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | 1551.3 | [6 empty] | 2.5006 | 2.5006 | 2.5006 | 2.5006 | 2.5006 | 2.505 | 2.5093 | 2.5137 | 2.5181 | 2.5225 | 2.5269 | 2.5313 | 2.5357 | 2.5401 | 2.5445 | 2.5454 | 2.5463 | 2.5471 | 2.548 | 2.5489 | 2.5498 | 2.5507 | 2.5516 | 2.5524 | 2.5533 | 2.5542 | 2.5551 | 2.556 | 2.5568 | 2.5577 | 2.5576 | 2.5575 | 2.5574 | 2.5573 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572 | 2.5572
360 | Orakei |  |  | 2052 | 1509.3627 | 1489.6527 | 1470.2002 | 1451.0017 | 1432.0538 | 1445.6515 | 1459.3782 | 1473.2352 | 1487.2239 | 1501.3453 | 1515.2154 | 1529.2136 | 1543.3412 | 1557.5992 | 1571.989 | 1584.7285 | 1597.5713 | 1610.5182 | 1623.57 | 1636.7275 | 1648.1102 | 1659.5721 | 1671.1137 | 1682.7356 | 1694.4383 | 1709.707 | 1725.1133 | 1740.6584 | 1756.3435 | 1772.1701 | 1786.5128 | 1800.9716 | 1815.5474 | 1830.2411 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 | 1845.0538 |  | 4100 | 4046.4604 | 3993.6199 | 3941.4695 | 3890 | 3914.5283 | 3939.2113 | 3964.0499 | 3989.0451 | 4014.198 | 4038.3068 | 4062.5605 | 4086.9598 | 4111.5057 | 4136.199 | 4154.3728 | 4172.6265 | 4190.9604 | 4209.3748 | 4227.8702 | 4241.3668 | 4254.9065 | 4268.4894 | 4282.1156 | 4295.7854 | 4317.9297 | 4340.1881 | 4362.5613 | 4385.0498 | 4407.6542 | 4443.0391 | 4478.708 | 4514.6633 | 4550.9073 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | 4587.4422 | [6 empty] | 614 | 621 | 628 | 635 | 642.6 | 653 | 664 | 675 | 686 | 697 | 705.7 | 716 | 726 | 736 | 746 | 756 | 766 | 776 | 786 | 796 | 806 | 816 | 826 | 836 | 846 | 856 | 866 | 876 | 886 | 896 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | 909.8 | [6 empty] | 2.7164 | 2.7164 | 2.7164 | 2.7164 | 2.7164 | 2.7078 | 2.6992 | 2.6907 | 2.6822 | 2.6737 | 2.6652 | 2.6566 | 2.6481 | 2.6396 | 2.6312 | 2.6215 | 2.6119 | 2.6022 | 2.5927 | 2.5831 | 2.5735 | 2.5639 | 2.5543 | 2.5447 | 2.5352 | 2.5255 | 2.5159 | 2.5063 | 2.4967 | 2.4872 | 2.487 | 2.4868 | 2.4867 | 2.4865 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863 | 2.4863
361 | Orakei |  |  | 2052 | 1811.8064 | 1797.9218 | 1784.1436 | 1770.471 | 1756.9032 | 1773.5485 | 1790.3515 | 1807.3137 | 1824.4365 | 1841.7217 | 1858.7004 | 1875.8357 | 1893.129 | 1910.5817 | 1928.1953 | 1943.8041 | 1959.5393 | 1975.4018 | 1991.3928 | 2007.5132 | 2021.4675 | 2035.5188 | 2049.6679 | 2063.9152 | 2078.2616 | 2096.9798 | 2115.8667 | 2134.9236 | 2154.1522 | 2173.554 | 2191.137 | 2208.8623 | 2226.731 | 2244.7442 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 | 2262.9032 |  | 3960 | 3929.6529 | 3899.5384 | 3869.6547 | 3840 | 3883.4681 | 3927.4283 | 3971.8861 | 4016.8471 | 4062.3171 | 4107.1889 | 4152.5562 | 4198.4247 | 4244.7998 | 4291.6872 | 4328.1288 | 4364.8798 | 4401.9428 | 4439.3206 | 4477.0158 | 4509.8908 | 4543.0073 | 4576.3669 | 4609.9715 | 4643.8228 | 4687.4848 | 4731.5573 | 4776.0441 | 4820.9493 | 4866.2766 | 4905.7154 | 4945.4739 | 4985.5546 | 5025.9601 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | 5066.6931 | [6 empty] | 1049 | 1060 | 1071 | 1082 | 1091.7 | 1108 | 1124 | 1140 | 1156 | 1172 | 1189.4 | 1203 | 1217 | 1231 | 1245 | 1259 | 1273 | 1287 | 1301 | 1315 | 1329 | 1343 | 1357 | 1371 | 1385 | 1399 | 1413 | 1427 | 1441 | 1455 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | 1466.4 | [6 empty] | 2.1857 | 2.1857 | 2.1857 | 2.1857 | 2.1857 | 2.1897 | 2.1937 | 2.1977 | 2.2017 | 2.2057 | 2.2097 | 2.2137 | 2.2177 | 2.2217 | 2.2258 | 2.2266 | 2.2275 | 2.2284 | 2.2293 | 2.2301 | 2.231 | 2.2319 | 2.2327 | 2.2336 | 2.2345 | 2.2354 | 2.2362 | 2.2371 | 2.238 | 2.2389 | 2.2389 | 2.2389 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239 | 2.239
362 | Orakei |  |  | 2052 | 979.6125 | 975.9088 | 972.2191 | 968.5433 | 964.8815 | 967.554 | 970.2338 | 972.9211 | 975.6159 | 978.3181 | 981.0426 | 983.7748 | 986.5145 | 989.2619 | 992.0169 | 994.5123 | 997.0139 | 999.5219 | 1002.0362 | 1004.5568 | 1006.781 | 1009.0103 | 1011.2444 | 1013.4835 | 1015.7276 | 1018.7191 | 1021.7195 | 1024.7287 | 1027.7468 | 1030.7737 | 1033.58 | 1036.3938 | 1039.2154 | 1042.0446 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 | 1044.8815 |  | 2660 | 2649.9431 | 2639.9242 | 2629.9433 | 2620 | 2624.5454 | 2629.0987 | 2633.6599 | 2638.229 | 2642.806 | 2647.4159 | 2652.0338 | 2656.6598 | 2661.2938 | 2665.9359 | 2667.5785 | 2669.222 | 2670.8666 | 2672.5122 | 2674.1588 | 2674.9398 | 2675.721 | 2676.5024 | 2677.2841 | 2678.066 | 2680.7818 | 2683.5003 | 2686.2216 | 2688.9457 | 2691.6725 | 2699.1142 | 2706.5764 | 2714.0593 | 2721.5628 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | 2729.0871 | [6 empty] | 442 | 446 | 450 | 454 | 457.8 | 464 | 470 | 476 | 482 | 488 | 493.2 | 498 | 503 | 508 | 513 | 518 | 523 | 528 | 533 | 538 | 543 | 548 | 553 | 558 | 563 | 568 | 573 | 578 | 583 | 588 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | 594.7 | [6 empty] | 2.7154 | 2.7154 | 2.7154 | 2.7154 | 2.7154 | 2.7126 | 2.7098 | 2.707 | 2.7042 | 2.7014 | 2.6986 | 2.6958 | 2.693 | 2.6902 | 2.6874 | 2.6823 | 2.6772 | 2.6721 | 2.6671 | 2.662 | 2.6569 | 2.6518 | 2.6467 | 2.6417 | 2.6366 | 2.6315 | 2.6265 | 2.6214 | 2.6164 | 2.6113 | 2.6114 | 2.6115 | 2.6116 | 2.6118 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119 | 2.6119
363 | Orakei | AHP | Tamaki | 2060 | 1057.9527 | 1051.7266 | 1045.5371 | 1039.384 | 1033.2671 | 1035.9406 | 1038.6209 | 1041.3082 | 1044.0025 | 1046.7037 | 1049.4292 | 1052.1619 | 1054.9016 | 1057.6485 | 1060.4025 | 1062.8987 | 1065.4008 | 1067.9087 | 1070.4226 | 1072.9424 | 1075.1673 | 1077.3968 | 1079.631 | 1081.8698 | 1084.1132 | 1087.1059 | 1090.1068 | 1093.116 | 1096.1335 | 1099.1594 | 1101.9665 | 1104.7809 | 1107.6024 | 1110.4312 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 | 1113.2671 |  | 3000 | 2982.3448 | 2964.7934 | 2947.3454 | 2930 | 2926.5325 | 2923.069 | 2919.6097 | 2916.1545 | 2912.7033 | 2909.0944 | 2905.49 | 2901.8901 | 2898.2946 | 2894.7035 | 2889.4431 | 2884.1922 | 2878.9508 | 2873.719 | 2868.4967 | 2862.2411 | 2855.9992 | 2849.7709 | 2843.5562 | 2837.355 | 2832.8193 | 2828.2908 | 2823.7696 | 2819.2557 | 2814.7489 | 2821.8369 | 2828.9427 | 2836.0665 | 2843.2081 | 2850.3678 | 2850.0124 | 2849.8348 | 2849.6572 | 2849.4796 | 2849.302 | 2849.1244 | 2848.9468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 484 | 488 | 492 | 496 | 498.4 | 506 | 513 | 520 | 527 | 534 | 542.7 | 549 | 555 | 561 | 567 | 573 | 579 | 585 | 591 | 597 | 603 | 609 | 615 | 621 | 627 | 633 | 639 | 645 | 651 | 657 | 659.9 | 660.0222 | 660.063 | 660.1037 | 660.1445 | 660.1852 | 660.226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2.8357 | 2.8357 | 2.8357 | 2.8357 | 2.8357 | 2.825 | 2.8144 | 2.8038 | 2.7932 | 2.7827 | 2.7721 | 2.7614 | 2.7509 | 2.7403 | 2.7298 | 2.7185 | 2.7071 | 2.6959 | 2.6847 | 2.6735 | 2.6621 | 2.6508 | 2.6396 | 2.6284 | 2.6172 | 2.6058 | 2.5945 | 2.5832 | 2.572 | 2.5608 | 2.5607 | 2.5606 | 2.5605 | 2.5605 | 2.5604 | 2.56 | 2.5599 | 2.5597 | 2.5596 | 2.5594 | 2.5592 | 2.5591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
364 | Orakei |  |  | 2052 | 1101.2592 | 1082.2101 | 1063.4905 | 1045.0946 | 1027.017 | 1037.1447 | 1047.3722 | 1057.7006 | 1068.1308 | 1078.6639 | 1088.9951 | 1099.4252 | 1109.9552 | 1120.586 | 1131.3187 | 1140.783 | 1150.3266 | 1159.9499 | 1169.6538 | 1179.4389 | 1187.8814 | 1196.3844 | 1204.9482 | 1213.5734 | 1222.2603 | 1233.5839 | 1245.0124 | 1256.5468 | 1268.1881 | 1279.9372 | 1290.5749 | 1301.301 | 1312.1162 | 1323.0213 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 | 1334.017 |  | 2670 | 2623.8154 | 2578.4298 | 2533.8291 | 2490 | 2505.0291 | 2520.1489 | 2535.36 | 2550.6629 | 2566.0582 | 2580.5967 | 2595.2177 | 2609.9214 | 2624.7085 | 2639.5793 | 2650.3706 | 2661.206 | 2672.0857 | 2683.0099 | 2693.9788 | 2701.4325 | 2708.9069 | 2716.4019 | 2723.9177 | 2731.4543 | 2744.5552 | 2757.719 | 2770.9459 | 2784.2363 | 2797.5904 | 2821.2183 | 2845.0458 | 2869.0746 | 2893.3063 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | 2917.7426 | [6 empty] | 1061 | 1069 | 1077 | 1085 | 1092.2 | 1106 | 1120 | 1134 | 1148 | 1162 | 1174.2 | 1185 | 1195 | 1205 | 1215 | 1225 | 1235 | 1245 | 1255 | 1265 | 1275 | 1285 | 1295 | 1305 | 1315 | 1325 | 1335 | 1345 | 1355 | 1365 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | 1383.4 | [6 empty] | 2.4245 | 2.4245 | 2.4245 | 2.4245 | 2.4245 | 2.4153 | 2.4062 | 2.397 | 2.388 | 2.3789 | 2.3697 | 2.3605 | 2.3514 | 2.3423 | 2.3332 | 2.3233 | 2.3134 | 2.3036 | 2.2938 | 2.2841 | 2.2742 | 2.2642 | 2.2544 | 2.2445 | 2.2348 | 2.2249 | 2.215 | 2.2052 | 2.1954 | 2.1857 | 2.186 | 2.1863 | 2.1866 | 2.1869 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872 | 2.1872
365 | Orakei |  |  | 2052 | 1206.583 | 1202.1486 | 1197.7305 | 1193.3286 | 1188.9429 | 1195.7508 | 1202.5976 | 1209.4836 | 1216.4091 | 1223.3742 | 1230.3156 | 1237.2964 | 1244.3168 | 1251.3771 | 1258.4774 | 1264.8707 | 1271.2966 | 1277.7551 | 1284.2464 | 1290.7707 | 1296.4913 | 1302.2373 | 1308.0088 | 1313.8059 | 1319.6286 | 1327.2319 | 1334.879 | 1342.5702 | 1350.3056 | 1358.0857 | 1365.1826 | 1372.3165 | 1379.4878 | 1386.6965 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 | 1393.9429 |  | 3420 | 3407.4309 | 3394.908 | 3382.431 | 3370 | 3375.9501 | 3381.9108 | 3387.8819 | 3393.8636 | 3399.8559 | 3405.426 | 3411.0051 | 3416.5935 | 3422.1909 | 3427.7976 | 3430.3368 | 3432.8779 | 3435.4209 | 3437.9658 | 3440.5125 | 3440.5596 | 3440.6067 | 3440.6538 | 3440.7009 | 3440.748 | 3444.9316 | 3449.1203 | 3453.3141 | 3457.5129 | 3461.7169 | 3479.4832 | 3497.3408 | 3515.2899 | 3533.3312 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | 3551.4651 | [6 empty] | 533 | 537 | 541 | 545 | 547.2 | 554 | 560 | 566 | 572 | 578 | 585.8 | 591 | 596 | 601 | 606 | 611 | 616 | 621 | 626 | 631 | 636 | 641 | 646 | 651 | 656 | 661 | 666 | 671 | 676 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | 681 | [6 empty] | 2.8345 | 2.8345 | 2.8345 | 2.8345 | 2.8345 | 2.8233 | 2.8122 | 2.8011 | 2.7901 | 2.7791 | 2.7679 | 2.7568 | 2.7458 | 2.7347 | 2.7238 | 2.712 | 2.7003 | 2.6886 | 2.677 | 2.6655 | 2.6537 | 2.6421 | 2.6305 | 2.6189 | 2.6074 | 2.5956 | 2.5838 | 2.5722 | 2.5605 | 2.549 | 2.5487 | 2.5485 | 2.5483 | 2.548 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478 | 2.5478
366 | Orakei |  |  | 2052 | 1186.4381 | 1175.1143 | 1163.8986 | 1152.7899 | 1141.7873 | 1142.6258 | 1143.465 | 1144.3048 | 1145.1452 | 1145.9862 | 1146.8411 | 1147.6966 | 1148.5528 | 1149.4096 | 1150.2671 | 1151.0816 | 1151.8968 | 1152.7125 | 1153.5288 | 1154.3457 | 1155.0894 | 1155.8337 | 1156.5784 | 1157.3236 | 1158.0693 | 1158.9885 | 1159.9084 | 1160.829 | 1161.7504 | 1162.6725 | 1163.4943 | 1164.3166 | 1165.1396 | 1165.9631 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 | 1166.7873 |  | 3720 | 3684.4949 | 3649.3287 | 3614.4981 | 3580 | 3568.2014 | 3556.4417 | 3544.7207 | 3533.0383 | 3521.3945 | 3509.5378 | 3497.7211 | 3485.9441 | 3474.2068 | 3462.5091 | 3449.7538 | 3437.0455 | 3424.384 | 3411.7692 | 3399.2008 | 3386.1287 | 3373.1069 | 3360.1352 | 3347.2133 | 3334.3411 | 3321.6686 | 3309.0442 | 3296.4678 | 3283.9391 | 3271.4581 | 3273.7602 | 3276.0639 | 3278.3693 | 3280.6762 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | 3282.9848 | [6 empty] | 574 | 578 | 582 | 586 | 591.5 | 599 | 606 | 613 | 620 | 627 | 633.6 | 639 | 645 | 651 | 657 | 663 | 669 | 675 | 681 | 687 | 693 | 699 | 705 | 711 | 717 | 723 | 729 | 735 | 741 | 747 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | 744.5 | [6 empty] | 3.1354 | 3.1354 | 3.1354 | 3.1354 | 3.1354 | 3.1228 | 3.1102 | 3.0977 | 3.0852 | 3.0728 | 3.0602 | 3.0476 | 3.0351 | 3.0226 | 3.0102 | 2.997 | 2.9838 | 2.9707 | 2.9577 | 2.9447 | 2.9315 | 2.9183 | 2.9052 | 2.8922 | 2.8792 | 2.866 | 2.8528 | 2.8398 | 2.8267 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137 | 2.8137
367 | Orakei |  |  | 2052 | 1306.3994 | 1302.1591 | 1297.9327 | 1293.7199 | 1289.5208 | 1293.5268 | 1297.5453 | 1301.5762 | 1305.6197 | 1309.6757 | 1313.7598 | 1317.8566 | 1321.9662 | 1326.0886 | 1330.2239 | 1333.9648 | 1337.7161 | 1341.4781 | 1345.2506 | 1349.0337 | 1352.3684 | 1355.7114 | 1359.0626 | 1362.4221 | 1365.7899 | 1370.2742 | 1374.7732 | 1379.2871 | 1383.8157 | 1388.3592 | 1392.5659 | 1396.7854 | 1401.0177 | 1405.2628 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 | 1409.5208 |  | 3870 | 3857.439 | 3844.9187 | 3832.4391 | 3820 | 3833.2825 | 3846.6112 | 3859.9863 | 3873.4079 | 3886.8761 | 3900.4428 | 3914.0569 | 3927.7184 | 3941.4277 | 3955.1848 | 3963.4944 | 3971.8215 | 3980.1661 | 3988.5282 | 3996.9078 | 4004.0221 | 4011.1489 | 4018.2885 | 4025.4408 | 4032.6058 | 4042.8669 | 4053.1542 | 4063.4676 | 4073.8072 | 4084.1732 | 4095.8586 | 4107.5775 | 4119.3298 | 4131.1158 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | 4142.9355 | [6 empty] | 1279 | 1294 | 1309 | 1324 | 1337.7 | 1353 | 1368 | 1383 | 1398 | 1413 | 1426.9 | 1441 | 1455 | 1469 | 1483 | 1497 | 1511 | 1525 | 1539 | 1553 | 1567 | 1581 | 1595 | 1609 | 1623 | 1637 | 1651 | 1665 | 1679 | 1693 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | 1709.5 | [6 empty] | 2.9623 | 2.9623 | 2.9623 | 2.9623 | 2.9623 | 2.9634 | 2.9645 | 2.9656 | 2.9667 | 2.9678 | 2.9689 | 2.97 | 2.9711 | 2.9722 | 2.9733 | 2.9712 | 2.9691 | 2.967 | 2.9649 | 2.9628 | 2.9607 | 2.9587 | 2.9567 | 2.9546 | 2.9526 | 2.9504 | 2.9482 | 2.9461 | 2.9439 | 2.9417 | 2.9412 | 2.9407 | 2.9402 | 2.9397 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393
368 | Orakei | AHP | Tamaki | 2060 | 1571.7101 | 1581.245 | 1590.8378 | 1600.4887 | 1610.1982 | 1646.5022 | 1683.6247 | 1721.5841 | 1760.3994 | 1800.0899 | 1837.2436 | 1875.1643 | 1913.8676 | 1953.3697 | 1993.6871 | 2007.2511 | 2020.9073 | 2034.6564 | 2048.499 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 | 2062.4359 |  | 4560 | 4587.2547 | 4614.6723 | 4642.2537 | 4670 | 4777.4244 | 4887.3199 | 4999.7434 | 5114.753 | 5232.4081 | 5342.9541 | 5455.8356 | 5571.1019 | 5688.8036 | 5808.9919 | 5845.2626 | 5881.7598 | 5918.4848 | 5955.4392 | 5992.6243 | 5989.6755 | 5986.7282 | 5983.7822 | 5980.8378 | 5977.8947 | 5974.9459 | 5971.9986 | 5969.0526 | 5966.1082 | 5963.1652 | 5963.1652 | 5963.1652 | 5963.1652 | 5963.1652 | 5963.1652 | 5959.4923 | 5957.6567 | 5955.8216 | 5953.9871 | 5952.1532 | 5950.3199 | 5948.4871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 743 | 750 | 757 | 764 | 771.6 | 783 | 794 | 805 | 816 | 827 | 838.7 | 850 | 861 | 872 | 883 | 894 | 905 | 916 | 927 | 938 | 949 | 960 | 971 | 982 | 993 | 1004 | 1015 | 1026 | 1037 | 1048 | 1060.8 | 1060.8 | 1060.8 | 1060.8 | 1060.8 | 1060.8 | 1060.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2.9013 | 2.901 | 2.9008 | 2.9005 | 2.9003 | 2.9016 | 2.9029 | 2.9042 | 2.9055 | 2.9067 | 2.9081 | 2.9095 | 2.9109 | 2.9123 | 2.9137 | 2.9121 | 2.9105 | 2.9088 | 2.9072 | 2.9056 | 2.9042 | 2.9027 | 2.9013 | 2.8999 | 2.8985 | 2.897 | 2.8956 | 2.8942 | 2.8927 | 2.8913 | 2.8913 | 2.8913 | 2.8913 | 2.8913 | 2.8913 | 2.8895 | 2.8887 | 2.8878 | 2.8869 | 2.886 | 2.8851 | 2.8842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
369 | Orakei |  |  | 2052 | 862.9107 | 871.6128 | 880.4027 | 889.2812 | 898.2493 | 906.8989 | 915.6317 | 924.4487 | 933.3505 | 942.3381 | 951.1612 | 960.0668 | 969.0559 | 978.1291 | 987.2873 | 995.3982 | 1003.5758 | 1011.8205 | 1020.1329 | 1028.5137 | 1035.7648 | 1043.0671 | 1050.4209 | 1057.8264 | 1065.2843 | 1075.0104 | 1084.8254 | 1094.73 | 1104.725 | 1114.8112 | 1123.9478 | 1133.1593 | 1142.4463 | 1151.8094 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 | 1161.2493 |  | 2210 | 2232.1643 | 2254.551 | 2277.1621 | 2300 | 2320.7927 | 2341.7733 | 2362.9436 | 2384.3053 | 2405.8601 | 2426.9739 | 2448.273 | 2469.759 | 2491.4336 | 2513.2984 | 2530.0658 | 2546.945 | 2563.9368 | 2581.042 | 2598.2613 | 2612.5597 | 2626.9368 | 2641.393 | 2655.9288 | 2670.5446 | 2690.7332 | 2711.0744 | 2731.5694 | 2752.2193 | 2773.0253 | 2795.6525 | 2818.4643 | 2841.4623 | 2864.6479 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | 2888.0227 | [6 empty] | 1108 | 1120 | 1132 | 1144 | 1155.3 | 1170 | 1185 | 1200 | 1215 | 1230 | 1244 | 1258 | 1272 | 1286 | 1300 | 1314 | 1328 | 1342 | 1356 | 1370 | 1384 | 1398 | 1412 | 1426 | 1440 | 1454 | 1468 | 1482 | 1496 | 1510 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | 1514.2 | [6 empty] | 2.5611 | 2.561 | 2.5608 | 2.5607 | 2.5605 | 2.559 | 2.5575 | 2.5561 | 2.5546 | 2.5531 | 2.5516 | 2.5501 | 2.5486 | 2.5471 | 2.5457 | 2.5418 | 2.5379 | 2.534 | 2.5301 | 2.5262 | 2.5223 | 2.5185 | 2.5146 | 2.5107 | 2.5069 | 2.503 | 2.4991 | 2.4952 | 2.4913 | 2.4874 | 2.4874 | 2.4873 | 2.4872 | 2.4871 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487 | 2.487
370 | Orakei |  |  | 2052 | 1162.0147 | 1154.1094 | 1146.2579 | 1138.4597 | 1130.7147 | 1139.398 | 1148.1481 | 1156.9653 | 1165.8503 | 1174.8035 | 1183.6588 | 1192.5809 | 1201.5702 | 1210.6273 | 1219.7527 | 1227.8887 | 1236.079 | 1244.3239 | 1252.6238 | 1260.9791 | 1268.2489 | 1275.5606 | 1282.9145 | 1290.3107 | 1297.7496 | 1307.5072 | 1317.3381 | 1327.2429 | 1337.2222 | 1347.2766 | 1356.4387 | 1365.6632 | 1374.9504 | 1384.3007 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 | 1393.7147 |  | 2970 | 2949.7947 | 2929.7269 | 2909.7957 | 2890 | 2916.8916 | 2944.0334 | 2971.4278 | 2999.077 | 3026.9836 | 3054.6676 | 3082.6048 | 3110.7975 | 3139.248 | 3167.9588 | 3189.783 | 3211.7575 | 3233.8835 | 3256.1618 | 3278.5937 | 3298.1785 | 3317.8803 | 3337.6999 | 3357.6378 | 3377.6948 | 3403.8412 | 3430.19 | 3456.7427 | 3483.501 | 3510.4665 | 3534.5405 | 3558.7796 | 3583.185 | 3607.7577 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | 3632.4989 | [6 empty] | 355 | 357 | 359 | 361 | 361 | 367 | 373 | 379 | 385 | 391 | 398.3 | 403 | 408 | 413 | 418 | 423 | 428 | 433 | 438 | 443 | 448 | 453 | 458 | 463 | 468 | 473 | 478 | 483 | 488 | 493 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | 491 | [6 empty] | 2.5559 | 2.5559 | 2.5559 | 2.5559 | 2.5559 | 2.56 | 2.5642 | 2.5683 | 2.5724 | 2.5766 | 2.5807 | 2.5848 | 2.5889 | 2.5931 | 2.5972 | 2.5978 | 2.5983 | 2.5989 | 2.5995 | 2.6 | 2.6006 | 2.6011 | 2.6017 | 2.6022 | 2.6027 | 2.6033 | 2.6039 | 2.6045 | 2.605 | 2.6056 | 2.6058 | 2.6059 | 2.606 | 2.6062 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063 | 2.6063
371 | Orakei |  |  | 2052 | 1419.2349 | 1413.2983 | 1407.3866 | 1401.4996 | 1395.6372 | 1403.7717 | 1411.9536 | 1420.1833 | 1428.4609 | 1436.7867 | 1445.0809 | 1453.423 | 1461.8132 | 1470.2519 | 1478.7393 | 1486.3101 | 1493.9196 | 1501.5681 | 1509.2558 | 1516.9828 | 1523.7183 | 1530.4837 | 1537.2791 | 1544.1047 | 1550.9606 | 1560.0075 | 1569.1072 | 1578.26 | 1587.4662 | 1596.726 | 1605.2175 | 1613.7541 | 1622.336 | 1630.9637 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 | 1639.6372 |  | 4210 | 4192.3898 | 4174.8533 | 4157.3901 | 4140 | 4154.1031 | 4168.2543 | 4182.4537 | 4196.7015 | 4210.9978 | 4225.0084 | 4239.0656 | 4253.1697 | 4267.3206 | 4281.5186 | 4290.4767 | 4299.4535 | 4308.4492 | 4317.4636 | 4326.4969 | 4332.5036 | 4338.5187 | 4344.5422 | 4350.5739 | 4356.6141 | 4368.3706 | 4380.1588 | 4391.9788 | 4403.8308 | 4415.7147 | 4438.6313 | 4461.6669 | 4484.822 | 4508.0973 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | 4531.4934 | [6 empty] | 816 | 823 | 830 | 837 | 844.5 | 855 | 866 | 877 | 888 | 899 | 909.7 | 919 | 929 | 939 | 949 | 959 | 969 | 979 | 989 | 999 | 1009 | 1019 | 1029 | 1039 | 1049 | 1059 | 1069 | 1079 | 1089 | 1099 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | 1104.1 | [6 empty] | 2.9664 | 2.9664 | 2.9664 | 2.9664 | 2.9664 | 2.9592 | 2.9521 | 2.945 | 2.9379 | 2.9308 | 2.9237 | 2.9166 | 2.9095 | 2.9024 | 2.8954 | 2.8867 | 2.878 | 2.8693 | 2.8607 | 2.852 | 2.8434 | 2.8347 | 2.8261 | 2.8175 | 2.809 | 2.8002 | 2.7915 | 2.7828 | 2.7741 | 2.7655 | 2.7651 | 2.7648 | 2.7644 | 2.7641 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637 | 2.7637
372 | Orakei |  |  | 2052 | 2320.0903 | 2301.949 | 2283.9496 | 2266.0909 | 2248.3719 | 2258.855 | 2269.387 | 2279.9681 | 2290.5985 | 2301.2785 | 2311.9665 | 2322.7042 | 2333.4918 | 2344.3295 | 2355.2175 | 2365.0423 | 2374.9081 | 2384.8151 | 2394.7634 | 2404.7532 | 2413.5324 | 2422.3436 | 2431.1871 | 2440.0628 | 2448.9709 | 2460.7682 | 2472.6224 | 2484.5337 | 2496.5023 | 2508.5287 | 2519.5992 | 2530.7185 | 2541.887 | 2553.1047 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 | 2564.3719 |  | 6470 | 6419.4097 | 6369.215 | 6319.4128 | 6270 | 6307.0292 | 6344.2772 | 6381.7451 | 6419.4342 | 6457.346 | 6495.3141 | 6533.5055 | 6571.9214 | 6610.5632 | 6649.4322 | 6676.7108 | 6704.1013 | 6731.6042 | 6759.2199 | 6786.9489 | 6811.2529 | 6835.6439 | 6860.1223 | 6884.6883 | 6909.3423 | 6942.1519 | 6975.1172 | 7008.2391 | 7041.5183 | 7074.9555 | 7106.2122 | 7137.6069 | 7169.1404 | 7200.8131 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | 7232.6258 | [6 empty] | 3157 | 3197 | 3237 | 3277 | 3318.1 | 3363 | 3408 | 3453 | 3498 | 3543 | 3588.8 | 3632 | 3675 | 3718 | 3761 | 3804 | 3847 | 3890 | 3933 | 3976 | 4019 | 4062 | 4105 | 4148 | 4191 | 4234 | 4277 | 4320 | 4363 | 4406 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | 4446.3 | [6 empty] | 2.7887 | 2.7887 | 2.7887 | 2.7887 | 2.7887 | 2.7921 | 2.7956 | 2.7991 | 2.8025 | 2.806 | 2.8094 | 2.8129 | 2.8163 | 2.8198 | 2.8233 | 2.8231 | 2.8229 | 2.8227 | 2.8225 | 2.8223 | 2.8221 | 2.8219 | 2.8217 | 2.8215 | 2.8213 | 2.8211 | 2.8209 | 2.8207 | 2.8206 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204 | 2.8204
373 | Orakei |  |  | 2052 | 923.539 | 915.9442 | 908.4118 | 900.9413 | 893.5323 | 904.1922 | 914.9792 | 925.8949 | 936.9408 | 948.1185 | 958.9963 | 969.9989 | 981.1277 | 992.3842 | 1003.7698 | 1013.727 | 1023.7829 | 1033.9386 | 1044.195 | 1054.5532 | 1063.4321 | 1072.3858 | 1081.4149 | 1090.5201 | 1099.7018 | 1111.6037 | 1123.6344 | 1135.7953 | 1148.0879 | 1160.5134 | 1171.6995 | 1182.9933 | 1194.3961 | 1205.9087 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 | 1217.5323 |  | 2770 | 2747.2205 | 2724.6284 | 2702.2221 | 2680 | 2709.0489 | 2738.4126 | 2768.0946 | 2798.0983 | 2828.4272 | 2857.8841 | 2887.6477 | 2917.7214 | 2948.1082 | 2978.8115 | 3002.6879 | 3026.7556 | 3051.0162 | 3075.4713 | 3100.1224 | 3120.4539 | 3140.9188 | 3161.5179 | 3182.2521 | 3203.1222 | 3231.575 | 3260.2805 | 3289.241 | 3318.4587 | 3347.936 | 3379.3239 | 3411.0061 | 3442.9853 | 3475.2643 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | 3507.846 | [6 empty] | 470 | 473 | 476 | 479 | 483.9 | 491 | 498 | 505 | 512 | 519 | 524.2 | 530 | 536 | 542 | 548 | 554 | 560 | 566 | 572 | 578 | 584 | 590 | 596 | 602 | 608 | 614 | 620 | 626 | 632 | 638 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | 643.4 | [6 empty] | 2.9993 | 2.9993 | 2.9993 | 2.9993 | 2.9993 | 2.9961 | 2.9929 | 2.9896 | 2.9864 | 2.9832 | 2.9801 | 2.977 | 2.9738 | 2.9707 | 2.9676 | 2.962 | 2.9564 | 2.9509 | 2.9453 | 2.9397 | 2.9343 | 2.9289 | 2.9235 | 2.9181 | 2.9127 | 2.9071 | 2.9015 | 2.896 | 2.8904 | 2.8849 | 2.8841 | 2.8834 | 2.8826 | 2.8819 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811 | 2.8811
374 | Orakei | AHP | Tamaki | 2060 | 1119.341 | 1119.341 | 1119.341 | 1119.341 | 1119.341 | 1122.0155 | 1124.6964 | 1127.3837 | 1130.0774 | 1132.7776 | 1135.5042 | 1138.2374 | 1140.9771 | 1143.7234 | 1146.4764 | 1148.9735 | 1151.476 | 1153.9839 | 1156.4974 | 1159.0163 | 1161.2419 | 1163.4717 | 1165.7059 | 1167.9443 | 1170.1871 | 1173.1809 | 1176.1825 | 1179.1917 | 1182.2086 | 1185.2332 | 1188.0414 | 1190.8563 | 1193.6779 | 1196.5061 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 | 1199.341 |  | 2990 | 2990 | 2990 | 2990 | 2990 | 3011.6919 | 3033.5411 | 3055.5489 | 3077.7163 | 3100.0445 | 3122.2327 | 3144.5797 | 3167.0867 | 3189.7548 | 3212.5851 | 3228.2402 | 3243.9716 | 3259.7796 | 3275.6647 | 3291.6272 | 3306.7098 | 3321.8616 | 3337.0827 | 3352.3737 | 3367.7347 | 3385.1795 | 3402.7148 | 3420.3409 | 3438.0582 | 3455.8674 | 3463.9624 | 3472.0764 | 3480.2093 | 3488.3613 | 3496.5324 | 3493.77 | 3492.3895 | 3491.0097 | 3489.6303 | 3488.2516 | 3486.8733 | 3485.4956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 863 | 868 | 873 | 878 | 882.9 | 898 | 913 | 928 | 943 | 958 | 973.8 | 984 | 994 | 1004 | 1014 | 1024 | 1034 | 1044 | 1054 | 1064 | 1074 | 1084 | 1094 | 1104 | 1114 | 1124 | 1134 | 1144 | 1154 | 1164 | 1177.8 | 1177.8 | 1177.8 | 1177.8 | 1177.8 | 1177.8 | 1177.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2.6712 | 2.6712 | 2.6712 | 2.6712 | 2.6712 | 2.6842 | 2.6972 | 2.7103 | 2.7235 | 2.7367 | 2.7496 | 2.7627 | 2.7758 | 2.7889 | 2.8021 | 2.8097 | 2.8172 | 2.8248 | 2.8324 | 2.84 | 2.8476 | 2.8551 | 2.8627 | 2.8703 | 2.8779 | 2.8855 | 2.893 | 2.9006 | 2.9082 | 2.9158 | 2.9157 | 2.9156 | 2.9155 | 2.9155 | 2.9154 | 2.9131 | 2.9119 | 2.9108 | 2.9096 | 2.9085 | 2.9073 | 2.9062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
375 | Orakei | AHP | Tamaki | 2060 | 261.2257 | 261.2257 | 261.2257 | 261.2257 | 261.2257 | 295.5269 | 334.3321 | 378.2328 | 427.898 | 484.0846 | 522.8134 | 564.6406 | 609.8141 | 658.6017 | 711.2925 | 726.7434 | 742.5299 | 758.6593 | 775.1391 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 | 791.9768 |  | 940 | 940 | 940 | 940 | 940 | 1049.869 | 1172.5797 | 1309.6331 | 1462.7056 | 1633.6695 | 1750.5748 | 1875.8459 | 2010.0814 | 2153.9228 | 2308.0575 | 2347.4007 | 2387.4146 | 2428.1105 | 2469.5002 | 2511.5954 | 2503.2428 | 2494.9179 | 2486.6208 | 2478.3512 | 2470.1091 | 2461.7556 | 2453.4302 | 2445.1331 | 2436.864 | 2428.6229 | 2428.6229 | 2428.6229 | 2428.6229 | 2428.6229 | 2428.6229 | 2427.4045 | 2426.7956 | 2426.1868 | 2425.5782 | 2424.9697 | 2424.3614 | 2423.7533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1187 | 1198 | 1209 | 1220 | 1231.6 | 1250 | 1268 | 1286 | 1304 | 1322 | 1340.7 | 1355 | 1370 | 1385 | 1400 | 1415 | 1430 | 1445 | 1460 | 1475 | 1490 | 1505 | 1520 | 1535 | 1550 | 1565 | 1580 | 1595 | 1610 | 1625 | 1631 | 1631 | 1631 | 1631 | 1631 | 1631 | 1631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 3.5984 | 3.5984 | 3.5984 | 3.5984 | 3.5984 | 3.5525 | 3.5072 | 3.4625 | 3.4184 | 3.3748 | 3.3484 | 3.3222 | 3.2962 | 3.2704 | 3.2449 | 3.23 | 3.2152 | 3.2005 | 3.1859 | 3.1713 | 3.1608 | 3.1502 | 3.1398 | 3.1293 | 3.1189 | 3.1084 | 3.0979 | 3.0874 | 3.0769 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.0665 | 3.065 | 3.0642 | 3.0635 | 3.0627 | 3.0619 | 3.0612 | 3.0604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
376 | Maungakiekie - Tamaki | AHP | Tamaki | 2060 | 1063.291 | 1106.5344 | 1151.5364 | 1198.3686 | 1247.1055 | 1306.7847 | 1369.3197 | 1434.8473 | 1503.5106 | 1575.4598 | 1637.3541 | 1701.6801 | 1768.5331 | 1838.0126 | 1910.2217 | 1942.9033 | 1976.144 | 2009.9534 | 2044.3412 | 2079.3174 | 2093.7338 | 2108.2501 | 2122.867 | 2137.5853 | 2152.4056 | 2230.8822 | 2312.2201 | 2396.5235 | 2483.9006 | 2574.4635 | 2676.7681 | 2783.1381 | 2893.7351 | 3008.727 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 | 3128.2885 |  | 3440 | 3578.8632 | 3723.3318 | 3873.6323 | 4030 | 4227.5929 | 4434.8738 | 4652.3179 | 4880.4233 | 5119.7129 | 5327.0311 | 5542.7444 | 5767.1929 | 6000.7302 | 6243.7243 | 6350.1646 | 6458.4194 | 6568.5197 | 6680.497 | 6794.3831 | 6841.3271 | 6888.5954 | 6936.1902 | 6984.1139 | 7032.3687 | 7287.9168 | 7552.7512 | 7827.2094 | 8111.6411 | 8406.4087 | 8739.4643 | 9085.7153 | 9445.6845 | 9819.9154 | 10208.9731 | 10202.3745 | 10199.0768 | 10195.7801 | 10192.4846 | 10189.1901 | 10185.8966 | 10182.6043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 411 | 415 | 419 | 423 | 426.1 | 432 | 438 | 444 | 450 | 456 | 463.4 | 468 | 473 | 478 | 483 | 488 | 493 | 498 | 503 | 508 | 513 | 518 | 523 | 528 | 533 | 538 | 543 | 548 | 553 | 558 | 565.3 | 565.3 | 565.3 | 565.3 | 565.3 | 565.3 | 565.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 3.2352 | 3.2343 | 3.2334 | 3.2324 | 3.2315 | 3.2351 | 3.2387 | 3.2424 | 3.246 | 3.2497 | 3.2534 | 3.2572 | 3.261 | 3.2648 | 3.2686 | 3.2684 | 3.2682 | 3.268 | 3.2678 | 3.2676 | 3.2675 | 3.2674 | 3.2674 | 3.2673 | 3.2672 | 3.2668 | 3.2665 | 3.2661 | 3.2657 | 3.2653 | 3.2649 | 3.2646 | 3.2642 | 3.2638 | 3.2634 | 3.2613 | 3.2603 | 3.2592 | 3.2582 | 3.2571 | 3.2561 | 3.255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
377 | Maungakiekie - Tamaki | AHP | Tamaki | 2060 | 1750.6062 | 1732.7984 | 1715.1717 | 1697.7243 | 1680.4544 | 1792.9289 | 1912.9314 | 2040.9659 | 2177.5698 | 2323.3167 | 2441.7027 | 2566.1212 | 2696.8794 | 2834.3006 | 2978.7241 | 3106.6967 | 3240.1674 | 3379.3722 | 3524.5576 | 3675.9804 | 3802.2201 | 3932.7951 | 4067.8542 | 4207.5515 | 4352.0463 | 4412.7151 | 4474.2297 | 4536.6018 | 4599.8434 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 | 4663.9666 |  | 5490 | 5434.1536 | 5378.8753 | 5324.1594 | 5270 | 5626.3178 | 6006.7272 | 6412.857 | 6846.4463 | 7309.3516 | 7686.0823 | 8082.23 | 8498.7956 | 8936.8314 | 9397.4439 | 9794.9264 | 10209.2211 | 10641.0392 | 11091.1218 | 11560.2415 | 11949.1498 | 12351.1417 | 12766.6573 | 13196.1516 | 13640.095 | 13820.0459 | 14002.3709 | 14187.1013 | 14374.2688 | 14563.9056 | 14563.9056 | 14563.9056 | 14563.9056 | 14563.9056 | 14563.9056 | 14554.9401 | 14550.4595 | 14545.9802 | 14541.5023 | 14537.0258 | 14532.5507 | 14528.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 329 | 333 | 337 | 341 | 343.6 | 349 | 354 | 359 | 364 | 369 | 373.6 | 378 | 383 | 388 | 393 | 398 | 403 | 408 | 413 | 418 | 423 | 428 | 433 | 438 | 443 | 448 | 453 | 458 | 463 | 468 | 470.5 | 470.5 | 470.5 | 470.5 | 470.5 | 470.5 | 470.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 3.1361 | 3.1361 | 3.1361 | 3.1361 | 3.1361 | 3.1381 | 3.1401 | 3.1421 | 3.1441 | 3.1461 | 3.1478 | 3.1496 | 3.1513 | 3.1531 | 3.1549 | 3.1528 | 3.1508 | 3.1488 | 3.1468 | 3.1448 | 3.1427 | 3.1406 | 3.1384 | 3.1363 | 3.1342 | 3.1319 | 3.1296 | 3.1273 | 3.1249 | 3.1226 | 3.1226 | 3.1226 | 3.1226 | 3.1226 | 3.1226 | 3.1207 | 3.1198 | 3.1188 | 3.1178 | 3.1169 | 3.1159 | 3.115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
378 | Orakei | AHP | Tamaki | 2060 | 65.2504 | 64.2689 | 63.3022 | 62.35 | 61.4122 | 99.3225 | 160.6353 | 259.797 | 420.1724 | 679.549 | 774.8439 | 883.5022 | 1007.3979 | 1148.6678 | 1309.7484 | 1398.2156 | 1492.6583 | 1593.4802 | 1701.1122 | 1816.0141 | 1891.667 | 1970.4715 | 2052.559 | 2138.066 | 2227.1352 | 2263.8414 | 2301.1526 | 2339.0787 | 2377.6299 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 | 2416.8165 |  | 170 | 167.4429 | 164.9242 | 162.4435 | 160 | 264.8915 | 438.547 | 726.0463 | 1202.0219 | 1990.034 | 2278.172 | 2608.0298 | 2985.6478 | 3417.9413 | 3912.8268 | 4180.7403 | 4466.9979 | 4772.8558 | 5099.656 | 5448.8323 | 5678.2489 | 5917.3248 | 6166.4667 | 6426.0984 | 6696.6616 | 6808.054 | 6921.2993 | 7036.4283 | 7153.4724 | 7272.4634 | 7272.4634 | 7272.4634 | 7272.4634 | 7272.4634 | 7272.4634 | 7267.771 | 7265.4259 | 7263.0816 | 7260.738 | 7258.3952 | 7256.0532 | 7253.7119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2002 | 2013 | 2024 | 2035 | 2047.6 | 2074 | 2101 | 2128 | 2155 | 2182 | 2206.6 | 2223 | 2240 | 2257 | 2274 | 2291 | 2308 | 2325 | 2342 | 2359 | 2376 | 2393 | 2410 | 2427 | 2444 | 2461 | 2478 | 2495 | 2512 | 2529 | 2544.2 | 2544.2 | 2544.2 | 2544.2 | 2544.2 | 2544.2 | 2544.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2.6053 | 2.6053 | 2.6053 | 2.6053 | 2.6053 | 2.667 | 2.7301 | 2.7947 | 2.8608 | 2.9285 | 2.9402 | 2.9519 | 2.9637 | 2.9756 | 2.9875 | 2.9901 | 2.9926 | 2.9952 | 2.9978 | 3.0004 | 3.0017 | 3.003 | 3.0043 | 3.0056 | 3.0069 | 3.0073 | 3.0078 | 3.0082 | 3.0087 | 3.0091 | 3.0091 | 3.0091 | 3.0091 | 3.0091 | 3.0091 | 3.0072 | 3.0062 | 3.0052 | 3.0043 | 3.0033 | 3.0023 | 3.0013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
379 | Orakei | AHP | Tamaki | 2060 | 1431.9255 | 1454.1163 | 1476.6511 | 1499.535 | 1522.7736 | 1537.5983 | 1552.5673 | 1567.6821 | 1582.9439 | 1598.3544 | 1613.4767 | 1628.7421 | 1644.1518 | 1659.7074 | 1675.4102 | 1689.2858 | 1703.2763 | 1717.3827 | 1731.6059 | 1745.947 | 1758.337 | 1770.815 | 1783.3815 | 1796.0372 | 1808.7827 | 1825.4014 | 1842.1729 | 1859.0984 | 1876.1794 | 1893.4174 | 1909.0291 | 1924.7694 | 1940.6396 | 1956.6406 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 | 1972.7736 |  | 3840 | 3898.6429 | 3958.1814 | 4018.6291 | 4080 | 4123.6071 | 4167.6802 | 4212.2244 | 4257.2447 | 4302.7461 | 4347.5757 | 4392.8724 | 4438.641 | 4484.8865 | 4531.6138 | 4567.8511 | 4604.3781 | 4641.1972 | 4678.3108 | 4715.7211 | 4747.9249 | 4780.3485 | 4812.9936 | 4845.8616 | 4878.9541 | 4922.3711 | 4966.1744 | 5010.3675 | 5054.9538 | 5099.937 | 5141.5233 | 5183.4486 | 5225.7159 | 5268.3278 | 5311.2872 | 5303.8169 | 5300.0856 | 5296.3571 | 5292.6311 | 5288.9077 | 5285.187 | 5281.4689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 975 | 985 | 995 | 1005 | 1014.1 | 1031 | 1048 | 1065 | 1082 | 1099 | 1114.6 | 1129 | 1143 | 1157 | 1171 | 1185 | 1199 | 1213 | 1227 | 1241 | 1255 | 1269 | 1283 | 1297 | 1311 | 1325 | 1339 | 1353 | 1367 | 1381 | 1399.5 | 1399.5 | 1399.5 | 1399.5 | 1399.5 | 1399.5 | 1399.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2.6817 | 2.6811 | 2.6805 | 2.6799 | 2.6793 | 2.6818 | 2.6844 | 2.6869 | 2.6894 | 2.692 | 2.6945 | 2.6971 | 2.6997 | 2.7022 | 2.7048 | 2.704 | 2.7032 | 2.7025 | 2.7017 | 2.701 | 2.7002 | 2.6995 | 2.6988 | 2.6981 | 2.6974 | 2.6966 | 2.6958 | 2.6951 | 2.6943 | 2.6935 | 2.6933 | 2.693 | 2.6928 | 2.6925 | 2.6923 | 2.6885 | 2.6866 | 2.6847 | 2.6828 | 2.681 | 2.6791 | 2.6772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
380 | Maungakiekie - Tamaki |  |  | 2052 | 2337.9502 | 2317.6711 | 2297.568 | 2277.6393 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 | 2257.8834 |  | 5840 | 5789.3447 | 5739.1289 | 5689.3485 | 5640 | 5683.5977 | 5727.5324 | 5771.8067 | 5816.4233 | 5861.3848 | 5905.0076 | 5948.955 | 5993.2295 | 6037.8335 | 6082.7695 | 6111.8247 | 6141.0188 | 6170.3522 | 6199.8258 | 6229.4401 | 6258.5018 | 6287.6991 | 6317.0326 | 6346.5029 | 6376.1107 | 6405.1786 | 6434.379 | 6463.7125 | 6493.1797 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | 6522.7813 | [6 empty] | 2922 | 2942 | 2962 | 2982 | 3000.5 | 3044 | 3087 | 3130 | 3173 | 3216 | 3260.3 | 3291 | 3321 | 3351 | 3381 | 3411 | 3441 | 3471 | 3501 | 3531 | 3561 | 3591 | 3621 | 3651 | 3681 | 3711 | 3741 | 3771 | 3801 | 3831 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | 3868.1 | [6 empty] | 2.4979 | 2.4979 | 2.4979 | 2.4979 | 2.4979 | 2.5172 | 2.5367 | 2.5563 | 2.5761 | 2.596 | 2.6153 | 2.6347 | 2.6544 | 2.6741 | 2.694 | 2.7069 | 2.7198 | 2.7328 | 2.7459 | 2.759 | 2.7718 | 2.7848 | 2.7978 | 2.8108 | 2.8239 | 2.8368 | 2.8497 | 2.8627 | 2.8758 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889 | 2.8889
381 | Orakei |  |  | 2052 | 1965.2133 | 1959.711 | 1954.2242 | 1948.7526 | 1943.2965 | 1972.7879 | 2002.727 | 2033.1204 | 2063.975 | 2095.2979 | 2125.4132 | 2155.9614 | 2186.9486 | 2218.3812 | 2250.2656 | 2277.978 | 2306.0317 | 2334.4309 | 2363.1798 | 2392.2828 | 2417.0837 | 2442.1417 | 2467.4595 | 2493.0397 | 2518.8852 | 2552.0239 | 2585.5986 | 2619.615 | 2654.0789 | 2688.9962 | 2720.1271 | 2751.6183 | 2783.4741 | 2815.6988 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 | 2848.2965 |  | 5380 | 5364.9369 | 5349.9159 | 5334.937 | 5320 | 5412.665 | 5506.9441 | 5602.8654 | 5700.4574 | 5799.7493 | 5896.2254 | 5994.3064 | 6094.0188 | 6195.39 | 6298.4474 | 6380.8532 | 6464.3372 | 6548.9134 | 6634.5962 | 6721.4 | 6796.581 | 6872.6029 | 6949.4752 | 7027.2073 | 7105.8088 | 7204.806 | 7305.1824 | 7406.9572 | 7510.15 | 7614.7804 | 7701.3411 | 7788.8857 | 7877.4256 | 7966.9719 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | 8057.5361 | [6 empty] | 2500 | 2530 | 2560 | 2590 | 2620.6 | 2661 | 2702 | 2743 | 2784 | 2825 | 2863.7 | 2899 | 2935 | 2971 | 3007 | 3043 | 3079 | 3115 | 3151 | 3187 | 3223 | 3259 | 3295 | 3331 | 3367 | 3403 | 3439 | 3475 | 3511 | 3547 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | 3579.6 | [6 empty] | 2.7376 | 2.7376 | 2.7376 | 2.7376 | 2.7376 | 2.7437 | 2.7497 | 2.7558 | 2.7619 | 2.768 | 2.7742 | 2.7803 | 2.7865 | 2.7928 | 2.799 | 2.8011 | 2.8032 | 2.8054 | 2.8075 | 2.8096 | 2.8119 | 2.8142 | 2.8164 | 2.8187 | 2.821 | 2.8232 | 2.8253 | 2.8275 | 2.8297 | 2.8318 | 2.8312 | 2.8307 | 2.8301 | 2.8295 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289 | 2.8289
382 | Maungakiekie - Tamaki |  |  | 2052 | 1518.0976 | 1512.6854 | 1507.2925 | 1501.9188 | 1496.5643 | 1499.242 | 1501.9245 | 1504.6118 | 1507.3039 | 1510.0009 | 1512.7307 | 1515.4655 | 1518.2053 | 1520.95 | 1523.6997 | 1526.1994 | 1528.7033 | 1531.2112 | 1533.7233 | 1536.2395 | 1538.4672 | 1540.6981 | 1542.9323 | 1545.1697 | 1547.4103 | 1550.4079 | 1553.4113 | 1556.4205 | 1559.4356 | 1562.4565 | 1565.2679 | 1568.0844 | 1570.9059 | 1573.7326 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 | 1576.5643 |  | 4230 | 4214.9195 | 4199.8929 | 4184.9197 | 4170 | 4188.5292 | 4207.1407 | 4225.835 | 4244.6123 | 4263.473 | 4282.349 | 4301.3085 | 4320.352 | 4339.4798 | 4358.6922 | 4370.3852 | 4382.1095 | 4393.8652 | 4405.6525 | 4417.4714 | 4428.473 | 4439.502 | 4450.5584 | 4461.6424 | 4472.754 | 4486.01 | 4499.3053 | 4512.64 | 4526.0142 | 4539.428 | 4547.4435 | 4555.4731 | 4563.5169 | 4571.5749 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | 4579.6471 | [6 empty] | 5251 | 5299 | 5347 | 5395 | 5443.4 | 5515 | 5587 | 5659 | 5731 | 5803 | 5874 | 5928 | 5982 | 6036 | 6090 | 6144 | 6198 | 6252 | 6306 | 6360 | 6414 | 6468 | 6522 | 6576 | 6630 | 6684 | 6738 | 6792 | 6846 | 6900 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | 6950.4 | [6 empty] | 2.7864 | 2.7864 | 2.7864 | 2.7864 | 2.7864 | 2.7938 | 2.8012 | 2.8086 | 2.816 | 2.8235 | 2.8309 | 2.8383 | 2.8457 | 2.8531 | 2.8606 | 2.8636 | 2.8666 | 2.8695 | 2.8725 | 2.8755 | 2.8785 | 2.8815 | 2.8845 | 2.8875 | 2.8905 | 2.8934 | 2.8964 | 2.8994 | 2.9023 | 2.9053 | 2.9052 | 2.9051 | 2.905 | 2.9049 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048 | 2.9048
383 | Maungakiekie - Tamaki |  |  | 2052 | 1336.9598 | 1359.9565 | 1383.3488 | 1407.1434 | 1431.3473 | 1434.0246 | 1436.7069 | 1439.3942 | 1442.0865 | 1444.7839 | 1447.5133 | 1450.2479 | 1452.9877 | 1455.7326 | 1458.4827 | 1460.9821 | 1463.4858 | 1465.9937 | 1468.506 | 1471.0226 | 1473.25 | 1475.4808 | 1477.7149 | 1479.9525 | 1482.1934 | 1485.1905 | 1488.1936 | 1491.2028 | 1494.2181 | 1497.2396 | 1500.0505 | 1502.8668 | 1505.6883 | 1508.5152 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 | 1511.3473 |  | 3790 | 3853.3918 | 3917.8438 | 3983.3739 | 4050 | 4063.0435 | 4076.129 | 4089.2567 | 4102.4266 | 4115.639 | 4128.9337 | 4142.2713 | 4155.6519 | 4169.0759 | 4182.5431 | 4189.8811 | 4197.2319 | 4204.5956 | 4211.9723 | 4219.3619 | 4225.9454 | 4232.5391 | 4239.1432 | 4245.7575 | 4252.3822 | 4261.1242 | 4269.8841 | 4278.6621 | 4287.4581 | 4296.2722 | 4304.1376 | 4312.0175 | 4319.9118 | 4327.8205 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | 4335.7437 | [6 empty] | 1177 | 1194 | 1211 | 1228 | 1246.8 | 1266 | 1285 | 1304 | 1323 | 1342 | 1363.2 | 1384 | 1405 | 1426 | 1447 | 1468 | 1489 | 1510 | 1531 | 1552 | 1573 | 1594 | 1615 | 1636 | 1657 | 1678 | 1699 | 1720 | 1741 | 1762 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | 1782.2 | [6 empty] | 2.8348 | 2.8335 | 2.8321 | 2.8308 | 2.8295 | 2.8333 | 2.8371 | 2.841 | 2.8448 | 2.8486 | 2.8524 | 2.8563 | 2.8601 | 2.8639 | 2.8677 | 2.8679 | 2.868 | 2.8681 | 2.8682 | 2.8683 | 2.8685 | 2.8686 | 2.8687 | 2.8688 | 2.869 | 2.8691 | 2.8692 | 2.8693 | 2.8694 | 2.8695 | 2.8693 | 2.8692 | 2.8691 | 2.8689 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688 | 2.8688
384 | Maungakiekie - Tamaki |  |  | 2052 | 650.9552 | 644.7422 | 638.5885 | 632.4936 | 626.4569 | 630.6209 | 634.8127 | 639.0323 | 643.28 | 647.5559 | 651.802 | 656.076 | 660.378 | 664.7082 | 669.0667 | 672.9594 | 676.8747 | 680.8127 | 684.7737 | 688.7577 | 692.2307 | 695.7213 | 699.2294 | 702.7553 | 706.2989 | 710.9622 | 715.6563 | 720.3814 | 725.1377 | 729.9254 | 734.3032 | 738.7072 | 743.1377 | 747.5947 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 | 752.0784 |  | 1860 | 1842.2475 | 1824.6644 | 1807.2491 | 1790 | 1804.1584 | 1818.4288 | 1832.8121 | 1847.3091 | 1861.9209 | 1876.4681 | 1891.129 | 1905.9045 | 1920.7954 | 1935.8026 | 1946.9777 | 1958.2172 | 1969.5216 | 1980.8913 | 1992.3266 | 2002.2955 | 2012.3142 | 2022.3831 | 2032.5023 | 2042.6722 | 2056.0559 | 2069.5274 | 2083.087 | 2096.7355 | 2110.4735 | 2123.0356 | 2135.6724 | 2148.3845 | 2161.1723 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | 2174.0361 | [6 empty] | 989 | 995 | 1001 | 1007 | 1014.9 | 1029 | 1043 | 1057 | 1071 | 1085 | 1099.7 | 1111 | 1122 | 1133 | 1144 | 1155 | 1166 | 1177 | 1188 | 1199 | 1210 | 1221 | 1232 | 1243 | 1254 | 1265 | 1276 | 1287 | 1298 | 1309 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | 1320.7 | [6 empty] | 2.8573 | 2.8573 | 2.8573 | 2.8573 | 2.8573 | 2.8609 | 2.8645 | 2.8681 | 2.8717 | 2.8753 | 2.8789 | 2.8825 | 2.8861 | 2.8897 | 2.8933 | 2.8932 | 2.893 | 2.8929 | 2.8928 | 2.8926 | 2.8925 | 2.8924 | 2.8923 | 2.8922 | 2.8921 | 2.8919 | 2.8918 | 2.8916 | 2.8915 | 2.8914 | 2.8912 | 2.8911 | 2.891 | 2.8908 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907 | 2.8907
385 | Maungakiekie - Tamaki | AHP | Tamaki | 2060 | 1007.4445 | 1030.0555 | 1053.174 | 1076.8113 | 1100.9791 | 1149.2958 | 1199.7329 | 1252.3834 | 1307.3444 | 1364.7175 | 1414.6972 | 1466.5073 | 1520.2148 | 1575.8892 | 1633.6026 | 1706.2126 | 1782.0499 | 1861.2581 | 1943.9869 | 2030.3928 | 2111.3757 | 2195.5887 | 2283.1605 | 2374.2252 | 2468.922 | 2508.1226 | 2547.9456 | 2588.4009 | 2629.4985 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 | 2671.2487 |  | 3440 | 3515.0107 | 3591.657 | 3669.9746 | 3750 | 3911.2946 | 4079.5268 | 4254.9949 | 4438.0103 | 4628.8975 | 4795.1498 | 4967.3732 | 5145.7822 | 5330.599 | 5522.0537 | 5757.3396 | 6002.6506 | 6258.4139 | 6525.0748 | 6803.0978 | 7062.7313 | 7332.2734 | 7612.1023 | 7902.6106 | 8204.2058 | 8323.2375 | 8443.9961 | 8566.5068 | 8690.795 | 8816.8864 | 8816.8864 | 8816.8864 | 8816.8864 | 8816.8864 | 8816.8864 | 8811.7112 | 8809.1247 | 8806.539 | 8803.9541 | 8801.3699 | 8798.7865 | 8796.2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2806 | 2829 | 2852 | 2875 | 2896.4 | 2934 | 2971 | 3008 | 3045 | 3082 | 3119.5 | 3149 | 3178 | 3207 | 3236 | 3265 | 3294 | 3323 | 3352 | 3381 | 3410 | 3439 | 3468 | 3497 | 3526 | 3555 | 3584 | 3613 | 3642 | 3671 | 3702.6 | 3702.6 | 3702.6 | 3702.6 | 3702.6 | 3702.6 | 3702.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 3.4146 | 3.4124 | 3.4103 | 3.4082 | 3.4061 | 3.4032 | 3.4004 | 3.3975 | 3.3947 | 3.3918 | 3.3895 | 3.3872 | 3.3849 | 3.3826 | 3.3803 | 3.3743 | 3.3684 | 3.3625 | 3.3565 | 3.3506 | 3.3451 | 3.3395 | 3.334 | 3.3285 | 3.323 | 3.3185 | 3.314 | 3.3096 | 3.3051 | 3.3007 | 3.3007 | 3.3007 | 3.3007 | 3.3007 | 3.3007 | 3.2987 | 3.2978 | 3.2968 | 3.2958 | 3.2949 | 3.2939 | 3.2929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
386 | Maungakiekie - Tamaki | AHP | Tamaki | 2060 | 1472.7591 | 1476.2666 | 1479.7824 | 1483.3066 | 1486.8392 | 1523.3731 | 1560.8047 | 1599.156 | 1638.4497 | 1678.7089 | 1716.1261 | 1754.3773 | 1793.481 | 1833.4564 | 1874.3228 | 1923.5281 | 1974.0251 | 2025.8478 | 2079.031 | 2133.6104 | 2186.2071 | 2240.1005 | 2295.3224 | 2351.9057 | 2409.8837 | 2434.854 | 2460.0831 | 2485.5735 | 2511.3281 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 | 2537.3496 |  | 4180 | 4189.9643 | 4199.9524 | 4209.9643 | 4220 | 4328.7132 | 4440.227 | 4554.6135 | 4671.9469 | 4792.3028 | 4904.7679 | 5019.8723 | 5137.678 | 5258.2483 | 5381.6481 | 5522.226 | 5666.4759 | 5814.4939 | 5966.3784 | 6122.2303 | 6272.3444 | 6426.1392 | 6583.7049 | 6745.1341 | 6910.5215 | 6981.1746 | 7052.55 | 7124.6551 | 7197.4975 | 7271.0846 | 7271.0846 | 7271.0846 | 7271.0846 | 7271.0846 | 7271.0846 | 7266.6755 | 7264.472 | 7262.2692 | 7260.067 | 7257.8655 | 7255.6647 | 7253.4645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1785 | 1809 | 1833 | 1857 | 1879.4 | 1908 | 1936 | 1964 | 1992 | 2020 | 2048 | 2073 | 2098 | 2123 | 2148 | 2173 | 2198 | 2223 | 2248 | 2273 | 2298 | 2323 | 2348 | 2373 | 2398 | 2423 | 2448 | 2473 | 2498 | 2523 | 2552.5 | 2552.5 | 2552.5 | 2552.5 | 2552.5 | 2552.5 | 2552.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2.8382 | 2.8382 | 2.8382 | 2.8382 | 2.8382 | 2.8415 | 2.8448 | 2.8481 | 2.8514 | 2.8548 | 2.858 | 2.8613 | 2.8646 | 2.8679 | 2.8712 | 2.8709 | 2.8705 | 2.8702 | 2.8698 | 2.8694 | 2.8691 | 2.8687 | 2.8683 | 2.8679 | 2.8676 | 2.8672 | 2.8668 | 2.8664 | 2.866 | 2.8656 | 2.8656 | 2.8656 | 2.8656 | 2.8656 | 2.8656 | 2.8639 | 2.863 | 2.8621 | 2.8613 | 2.8604 | 2.8595 | 2.8587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
387 | Maungakiekie - Tamaki | AHP | Tamaki | 2060 | 1077.7839 | 1084.2526 | 1090.7601 | 1097.3067 | 1103.8925 | 1139.8468 | 1176.9722 | 1215.3067 | 1254.8898 | 1295.7622 | 1332.7162 | 1370.7241 | 1409.816 | 1450.0227 | 1491.3761 | 1539.963 | 1590.1328 | 1641.937 | 1695.429 | 1750.6637 | 1802.7281 | 1856.3409 | 1911.5481 | 1968.3972 | 2026.937 | 2051.8121 | 2076.9925 | 2102.4818 | 2128.284 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 | 2154.4028 |  | 2890 | 2907.3433 | 2924.7906 | 2942.3426 | 2960 | 3063.7236 | 3171.0819 | 3282.2021 | 3397.2163 | 3516.2607 | 3625.096 | 3737.2999 | 3852.9768 | 3972.2341 | 4095.1827 | 4232.1063 | 4373.608 | 4519.8408 | 4670.9629 | 4827.1379 | 4974.8047 | 5126.9887 | 5283.8282 | 5445.4656 | 5612.0476 | 5685.6021 | 5760.1207 | 5835.6159 | 5912.1007 | 5989.5879 | 5989.5879 | 5989.5879 | 5989.5879 | 5989.5879 | 5989.5879 | 5985.7256 | 5983.7954 | 5981.8659 | 5979.9369 | 5978.0086 | 5976.0809 | 5974.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 263 | 265 | 267 | 269 | 270.1 | 274 | 278 | 282 | 286 | 290 | 292.8 | 296 | 299 | 302 | 305 | 308 | 311 | 314 | 317 | 320 | 323 | 326 | 329 | 332 | 335 | 338 | 341 | 344 | 347 | 350 | 359.5 | 359.5 | 359.5 | 359.5 | 359.5 | 359.5 | 359.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2.6814 | 2.6814 | 2.6814 | 2.6814 | 2.6814 | 2.6878 | 2.6943 | 2.7007 | 2.7072 | 2.7137 | 2.7201 | 2.7265 | 2.733 | 2.7394 | 2.7459 | 2.7482 | 2.7505 | 2.7527 | 2.755 | 2.7573 | 2.7596 | 2.7619 | 2.7642 | 2.7664 | 2.7687 | 2.771 | 2.7733 | 2.7756 | 2.7779 | 2.7802 | 2.7802 | 2.7802 | 2.7802 | 2.7802 | 2.7802 | 2.7784 | 2.7775 | 2.7766 | 2.7757 | 2.7748 | 2.7739 | 2.773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
388 | Maungakiekie - Tamaki |  |  | 2052 | 510.5857 | 512.9579 | 515.3412 | 517.7355 | 520.1409 | 522.8009 | 525.4744 | 528.1617 | 530.8627 | 533.5775 | 536.2895 | 539.0154 | 541.7551 | 544.5087 | 547.2763 | 549.7616 | 552.2582 | 554.7661 | 557.2854 | 559.8162 | 562.0327 | 564.258 | 566.4921 | 568.7351 | 570.987 | 573.965 | 576.9585 | 579.9677 | 582.9925 | 586.0331 | 588.8279 | 591.636 | 594.4575 | 597.2924 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 | 600.1409 |  | 1670 | 1677.45 | 1684.9332 | 1692.4499 | 1700 | 1708.7469 | 1717.5388 | 1726.376 | 1735.2586 | 1744.1869 | 1753.1176 | 1762.094 | 1771.1163 | 1780.1849 | 1789.2998 | 1795.5608 | 1801.8437 | 1808.1486 | 1814.4756 | 1820.8246 | 1826.173 | 1831.537 | 1836.9168 | 1842.3124 | 1847.7239 | 1855.3829 | 1863.0736 | 1870.7963 | 1878.5509 | 1886.3377 | 1895.0173 | 1903.7368 | 1912.4964 | 1921.2964 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | 1930.1368 | [6 empty] | 3059 | 3088 | 3117 | 3146 | 3173 | 3218 | 3263 | 3308 | 3353 | 3398 | 3442.8 | 3476 | 3510 | 3544 | 3578 | 3612 | 3646 | 3680 | 3714 | 3748 | 3782 | 3816 | 3850 | 3884 | 3918 | 3952 | 3986 | 4020 | 4054 | 4088 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | 4114.2 | [6 empty] | 3.2708 | 3.2702 | 3.2695 | 3.2689 | 3.2683 | 3.2684 | 3.2685 | 3.2687 | 3.2688 | 3.2689 | 3.269 | 3.2691 | 3.2692 | 3.2693 | 3.2695 | 3.2661 | 3.2627 | 3.2593 | 3.2559 | 3.2525 | 3.2492 | 3.2459 | 3.2426 | 3.2393 | 3.236 | 3.2326 | 3.2291 | 3.2257 | 3.2223 | 3.2188 | 3.2183 | 3.2178 | 3.2172 | 3.2167 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161 | 3.2161
389 | Maungakiekie - Tamaki |  |  | 2052 | 27.2859 | 26.6434 | 26.0161 | 25.4035 | 24.8054 | 34.8222 | 48.8839 | 68.624 | 96.3355 | 135.2374 | 152.6533 | 172.312 | 194.5024 | 219.5506 | 247.8244 | 265.71 | 284.8864 | 305.4468 | 327.4911 | 351.1263 | 367.881 | 385.4352 | 403.8271 | 423.0965 | 443.2854 | 465.587 | 489.0105 | 513.6125 | 539.4522 | 566.5919 | 587.9608 | 610.1357 | 633.1468 | 657.0258 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 | 681.8054 |  | 110 | 107.4099 | 104.8809 | 102.4114 | 100 | 133.3735 | 177.8849 | 237.2513 | 316.4303 | 422.0341 | 473.4172 | 531.0562 | 595.7129 | 668.2416 | 749.6007 | 801.6708 | 857.3578 | 916.9131 | 980.6052 | 1048.7217 | 1097.2148 | 1147.9503 | 1201.0318 | 1256.5678 | 1314.6718 | 1379.1229 | 1446.7337 | 1517.6591 | 1592.0616 | 1670.1116 | 1732.0965 | 1796.3819 | 1863.0532 | 1932.1989 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | 2003.9109 | [6 empty] | 3184 | 3216 | 3248 | 3280 | 3310.6 | 3359 | 3408 | 3457 | 3506 | 3555 | 3603.5 | 3640 | 3676 | 3712 | 3748 | 3784 | 3820 | 3856 | 3892 | 3928 | 3964 | 4000 | 4036 | 4072 | 4108 | 4144 | 4180 | 4216 | 4252 | 4288 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | 4326.8 | [6 empty] | 4.0314 | 4.0314 | 4.0314 | 4.0314 | 4.0314 | 3.8301 | 3.6389 | 3.4573 | 3.2847 | 3.1207 | 3.1013 | 3.0819 | 3.0628 | 3.0437 | 3.0247 | 3.0171 | 3.0095 | 3.0019 | 2.9943 | 2.9867 | 2.9825 | 2.9783 | 2.9741 | 2.9699 | 2.9657 | 2.9621 | 2.9585 | 2.9549 | 2.9513 | 2.9476 | 2.9459 | 2.9442 | 2.9425 | 2.9408 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391 | 2.9391
390 | Maungakiekie - Tamaki | AHP | Tamaki | 2060 | 2576.8169 | 2575.9874 | 2575.1582 | 2574.3292 | 2573.5005 | 2595.2173 | 2617.1173 | 2639.2022 | 2661.4734 | 2683.9325 | 2706.0813 | 2728.4129 | 2750.9288 | 2773.6305 | 2796.5195 | 2816.8812 | 2837.3912 | 2858.0505 | 2878.8602 | 2899.8215 | 2918.0233 | 2936.3395 | 2954.7706 | 2973.3174 | 2991.9806 | 3016.3249 | 3040.8673 | 3065.6095 | 3090.5529 | 3115.6993 | 3138.5227 | 3161.5133 | 3184.6723 | 3208.001 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 | 3231.5005 |  | 7770 | 7767.4988 | 7764.9984 | 7762.4988 | 7760 | 7828.035 | 7896.6666 | 7965.8998 | 8035.7401 | 8106.1926 | 8175.7845 | 8245.9739 | 8316.7658 | 8388.1654 | 8460.1781 | 8515.0784 | 8570.3351 | 8625.9503 | 8681.9264 | 8738.2658 | 8786.2594 | 8834.5165 | 8883.0388 | 8931.8275 | 8980.8842 | 9046.7623 | 9113.1236 | 9179.9717 | 9247.3101 | 9315.1425 | 9382.8896 | 9451.1295 | 9519.8657 | 9589.1017 | 9658.8413 | 9643.3933 | 9635.6786 | 9627.9701 | 9620.2677 | 9612.5715 | 9604.8814 | 9597.1975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1098 | 1111 | 1124 | 1137 | 1148.9 | 1167 | 1186 | 1205 | 1224 | 1243 | 1259.9 | 1276 | 1292 | 1308 | 1324 | 1340 | 1356 | 1372 | 1388 | 1404 | 1420 | 1436 | 1452 | 1468 | 1484 | 1500 | 1516 | 1532 | 1548 | 1564 | 1578 | 1578 | 1578 | 1578 | 1578 | 1578 | 1578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 3.0153 | 3.0153 | 3.0153 | 3.0153 | 3.0153 | 3.0163 | 3.0173 | 3.0183 | 3.0193 | 3.0203 | 3.0213 | 3.0223 | 3.0233 | 3.0243 | 3.0253 | 3.0229 | 3.0205 | 3.0181 | 3.0158 | 3.0134 | 3.011 | 3.0087 | 3.0063 | 3.004 | 3.0017 | 2.9993 | 2.9969 | 2.9945 | 2.9921 | 2.9897 | 2.9896 | 2.9894 | 2.9893 | 2.9891 | 2.989 | 2.9842 | 2.9818 | 2.9794 | 2.977 | 2.9746 | 2.9723 | 2.9699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
391 | Maungakiekie - Tamaki |  |  | 2052 | 3.0318 | 4.0446 | 5.3959 | 7.1985 | 9.6034 | 11.4403 | 13.6285 | 16.2353 | 19.3407 | 23.04 | 25.2936 | 27.7677 | 30.4837 | 33.4655 | 36.7388 | 38.9612 | 41.318 | 43.8173 | 46.4678 | 49.2787 | 51.3341 | 53.4752 | 55.7057 | 58.0291 | 60.4495 | 63.1973 | 66.07 | 69.0733 | 72.2131 | 75.4957 | 78.1272 | 80.8506 | 83.6688 | 86.5853 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 | 89.6034 |  | 0 | 2 | 4 | 7 | 10 | 13.6787 | 18.7107 | 25.5939 | 35.0092 | 47.8881 | 56.2329 | 66.0319 | 77.5384 | 91.0499 | 106.9159 | 113.6312 | 120.7683 | 128.3537 | 136.4155 | 144.9837 | 151.2081 | 157.6997 | 164.4701 | 171.5311 | 178.8952 | 187.219 | 195.9301 | 205.0464 | 214.587 | 224.5714 | 232.5495 | 240.8111 | 249.3662 | 258.2251 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | 267.3989 | [6 empty] | 5613 | 5655 | 5697 | 5739 | 5782.9 | 5853 | 5923 | 5993 | 6063 | 6133 | 6205.2 | 6257 | 6309 | 6361 | 6413 | 6465 | 6517 | 6569 | 6621 | 6673 | 6725 | 6777 | 6829 | 6881 | 6933 | 6985 | 7037 | 7089 | 7141 | 7193 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | 7235.7 | [6 empty] | 0 | 0.49448 | 0.74131 | 0.97242 | 1.0413 | 1.1957 | 1.3729 | 1.5764 | 1.8101 | 2.0785 | 2.2232 | 2.378 | 2.5436 | 2.7207 | 2.9102 | 2.9165 | 2.9229 | 2.9293 | 2.9357 | 2.9421 | 2.9456 | 2.949 | 2.9525 | 2.9559 | 2.9594 | 2.9625 | 2.9655 | 2.9685 | 2.9716 | 2.9746 | 2.9765 | 2.9785 | 2.9804 | 2.9823 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842 | 2.9842
392 | Maungakiekie - Tamaki |  |  | 2052 | 101.4788 | 99.545 | 97.648 | 95.7872 | 93.9618 | 95.7407 | 97.5533 | 99.4002 | 101.282 | 103.1995 | 105.0179 | 106.8683 | 108.7513 | 110.6675 | 112.6174 | 114.3213 | 116.0509 | 117.8068 | 119.5891 | 121.3985 | 122.9413 | 124.5037 | 126.086 | 127.6884 | 129.3111 | 131.3757 | 133.4732 | 135.6042 | 137.7692 | 139.9688 | 141.9127 | 143.8835 | 145.8818 | 147.9077 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 | 149.9618 |  | 270 | 264.8548 | 259.8076 | 254.8566 | 250 | 253.7943 | 257.6462 | 261.5565 | 265.5262 | 269.5561 | 273.3037 | 277.1034 | 280.9559 | 284.862 | 288.8224 | 292.0046 | 295.2219 | 298.4746 | 301.7631 | 305.0879 | 307.7195 | 310.3739 | 313.0511 | 315.7514 | 318.475 | 322.2076 | 325.984 | 329.8046 | 333.6699 | 337.5806 | 342.1447 | 346.7704 | 351.4587 | 356.2104 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | 361.0264 | [6 empty] | 4939 | 4977 | 5015 | 5053 | 5089.4 | 5151 | 5213 | 5275 | 5337 | 5399 | 5459.5 | 5505 | 5550 | 5595 | 5640 | 5685 | 5730 | 5775 | 5820 | 5865 | 5910 | 5955 | 6000 | 6045 | 6090 | 6135 | 6180 | 6225 | 6270 | 6315 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | 6365.8 | [6 empty] | 2.6607 | 2.6607 | 2.6607 | 2.6607 | 2.6607 | 2.6508 | 2.6411 | 2.6313 | 2.6217 | 2.612 | 2.6024 | 2.5929 | 2.5835 | 2.574 | 2.5646 | 2.5542 | 2.5439 | 2.5336 | 2.5233 | 2.5131 | 2.503 | 2.4929 | 2.4828 | 2.4728 | 2.4629 | 2.4526 | 2.4423 | 2.4321 | 2.4219 | 2.4118 | 2.411 | 2.4101 | 2.4092 | 2.4083 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075 | 2.4075
393 | Maungakiekie - Tamaki |  |  | 2052 | 780.7886 | 786.5921 | 792.4386 | 798.3286 | 804.2624 | 812.893 | 821.6161 | 830.4329 | 839.3442 | 848.3512 | 857.1564 | 866.0529 | 875.0418 | 884.124 | 893.3004 | 901.3976 | 909.5681 | 917.8127 | 926.1321 | 934.5268 | 941.7679 | 949.065 | 956.4187 | 963.8293 | 971.2974 | 981.0067 | 990.8131 | 1000.7175 | 1010.7209 | 1020.8244 | 1029.9474 | 1039.1521 | 1048.4389 | 1057.8088 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 | 1067.2624 |  | 2750 | 2769.7854 | 2789.7132 | 2809.7844 | 2830 | 2863.105 | 2896.5972 | 2930.4812 | 2964.7616 | 2999.443 | 3033.5406 | 3068.0258 | 3102.903 | 3138.1766 | 3173.8513 | 3201.8271 | 3230.0495 | 3258.5206 | 3287.2427 | 3316.218 | 3341.2335 | 3366.4378 | 3391.8322 | 3417.4182 | 3443.1972 | 3476.7433 | 3510.6163 | 3544.8192 | 3579.3554 | 3614.228 | 3645.7463 | 3677.5394 | 3709.6098 | 3741.9599 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | 3774.592 | [6 empty] | 232 | 234 | 236 | 238 | 240.3 | 243 | 246 | 249 | 252 | 255 | 257.1 | 260 | 263 | 266 | 269 | 272 | 275 | 278 | 281 | 284 | 287 | 290 | 293 | 296 | 299 | 302 | 305 | 308 | 311 | 314 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | 308.8 | [6 empty] | 3.5221 | 3.5212 | 3.5204 | 3.5196 | 3.5188 | 3.5221 | 3.5255 | 3.5289 | 3.5322 | 3.5356 | 3.5391 | 3.5425 | 3.546 | 3.5495 | 3.5529 | 3.5521 | 3.5512 | 3.5503 | 3.5494 | 3.5486 | 3.5478 | 3.5471 | 3.5464 | 3.5457 | 3.5449 | 3.5441 | 3.5432 | 3.5423 | 3.5414 | 3.5405 | 3.5397 | 3.539 | 3.5382 | 3.5375 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367 | 3.5367
394 | Howick |  |  | 2052 | 2036.4744 | 2006.7632 | 1977.4854 | 1948.6348 | 1920.2051 | 1922.963 | 1925.7248 | 1928.4906 | 1931.2603 | 1934.0341 | 1936.8456 | 1939.6613 | 1942.481 | 1945.3049 | 1948.1329 | 1950.718 | 1953.3065 | 1955.8984 | 1958.4938 | 1961.0927 | 1963.4022 | 1965.7146 | 1968.0296 | 1970.3474 | 1972.6679 | 1975.7212 | 1978.7792 | 1981.8419 | 1984.9094 | 1987.9817 | 1990.8183 | 1993.6589 | 1996.5036 | 1999.3523 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 | 2002.2051 |  | 5780 | 5695.6724 | 5612.5752 | 5530.6903 | 5450 | 5434.8187 | 5419.6796 | 5404.5827 | 5389.5279 | 5374.515 | 5359.1489 | 5343.8267 | 5328.5483 | 5313.3137 | 5298.1225 | 5280.947 | 5263.8272 | 5246.7629 | 5229.7539 | 5212.8001 | 5194.5638 | 5176.3914 | 5158.2826 | 5140.2371 | 5122.2547 | 5105.6639 | 5089.1268 | 5072.6432 | 5056.2131 | 5039.8362 | 5047.0851 | 5054.3445 | 5061.6143 | 5068.8945 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | 5076.1853 | [6 empty] | 1252 | 1261 | 1270 | 1279 | 1289.1 | 1303 | 1317 | 1331 | 1345 | 1359 | 1372.2 | 1383 | 1394 | 1405 | 1416 | 1427 | 1438 | 1449 | 1460 | 1471 | 1482 | 1493 | 1504 | 1515 | 1526 | 1537 | 1548 | 1559 | 1570 | 1581 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | 1595.9 | [6 empty] | 2.8382 | 2.8382 | 2.8382 | 2.8382 | 2.8382 | 2.8263 | 2.8144 | 2.8025 | 2.7907 | 2.7789 | 2.7669 | 2.755 | 2.7432 | 2.7314 | 2.7196 | 2.7072 | 2.6948 | 2.6825 | 2.6703 | 2.6581 | 2.6457 | 2.6333 | 2.621 | 2.6088 | 2.5966 | 2.5842 | 2.5719 | 2.5596 | 2.5473 | 2.5352 | 2.5352 | 2.5352 | 2.5352 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353 | 2.5353
395 | Howick |  |  | 2052 | 1345.1437 | 1335.8924 | 1326.7047 | 1317.5802 | 1308.5185 | 1311.8605 | 1315.2111 | 1318.5702 | 1321.9379 | 1325.3142 | 1328.7214 | 1332.1373 | 1335.562 | 1338.9954 | 1342.4377 | 1345.5582 | 1348.6859 | 1351.8208 | 1354.963 | 1358.1126 | 1360.8939 | 1363.6809 | 1366.4735 | 1369.272 | 1372.0761 | 1375.8172 | 1379.5685 | 1383.33 | 1387.1017 | 1390.8838 | 1394.393 | 1397.911 | 1401.438 | 1404.9738 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 | 1408.5185 |  | 4040 | 4012.2147 | 3984.6204 | 3957.216 | 3930 | 3929.9789 | 3929.9578 | 3929.9367 | 3929.9156 | 3929.8944 | 3929.8106 | 3929.7267 | 3929.6428 | 3929.5589 | 3929.475 | 3926.2976 | 3923.1227 | 3919.9504 | 3916.7807 | 3913.6135 | 3909.2052 | 3904.802 | 3900.4037 | 3896.0103 | 3891.6219 | 3889.6076 | 3887.5943 | 3885.5821 | 3883.5709 | 3881.5607 | 3891.1071 | 3900.677 | 3910.2703 | 3919.8873 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | 3929.5279 | [6 empty] | 841 | 847 | 853 | 859 | 865.7 | 876 | 887 | 898 | 909 | 920 | 929.1 | 936 | 943 | 950 | 957 | 964 | 971 | 978 | 985 | 992 | 999 | 1006 | 1013 | 1020 | 1027 | 1034 | 1041 | 1048 | 1055 | 1062 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | 1073.6 | [6 empty] | 3.0034 | 3.0034 | 3.0034 | 3.0034 | 3.0034 | 2.9957 | 2.9881 | 2.9805 | 2.9728 | 2.9653 | 2.9576 | 2.9499 | 2.9423 | 2.9347 | 2.9271 | 2.918 | 2.9088 | 2.8998 | 2.8907 | 2.8817 | 2.8725 | 2.8634 | 2.8544 | 2.8453 | 2.8363 | 2.8271 | 2.818 | 2.8089 | 2.7998 | 2.7907 | 2.7905 | 2.7904 | 2.7902 | 2.79 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898 | 2.7898
396 | Howick |  |  | 2052 | 1707.9077 | 1698.3392 | 1688.8243 | 1679.3628 | 1669.9542 | 1674.4646 | 1678.9872 | 1683.522 | 1688.0691 | 1692.6285 | 1697.2267 | 1701.8375 | 1706.4608 | 1711.0967 | 1715.7452 | 1719.9883 | 1724.242 | 1728.5061 | 1732.7808 | 1737.0661 | 1740.8661 | 1744.6745 | 1748.4912 | 1752.3162 | 1756.1496 | 1761.2605 | 1766.3863 | 1771.527 | 1776.6827 | 1781.8534 | 1786.6477 | 1791.4549 | 1796.275 | 1801.1081 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 | 1805.9542 |  | 4500 | 4474.7889 | 4449.7191 | 4424.7897 | 4400 | 4417.661 | 4435.3928 | 4453.1959 | 4471.0704 | 4489.0166 | 4507.0676 | 4525.1912 | 4543.3876 | 4561.6573 | 4580.0004 | 4591.2882 | 4602.6039 | 4613.9475 | 4625.319 | 4636.7186 | 4646.8276 | 4656.9587 | 4667.1118 | 4677.2871 | 4687.4846 | 4701.081 | 4714.7169 | 4728.3923 | 4742.1074 | 4755.8623 | 4768.6163 | 4781.4046 | 4794.2271 | 4807.084 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | 4819.9754 | [6 empty] | 1545 | 1562 | 1579 | 1596 | 1612.7 | 1635 | 1657 | 1679 | 1701 | 1723 | 1743.6 | 1763 | 1782 | 1801 | 1820 | 1839 | 1858 | 1877 | 1896 | 1915 | 1934 | 1953 | 1972 | 1991 | 2010 | 2029 | 2048 | 2067 | 2086 | 2105 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | 2127 | [6 empty] | 2.6348 | 2.6348 | 2.6348 | 2.6348 | 2.6348 | 2.6383 | 2.6417 | 2.6452 | 2.6486 | 2.6521 | 2.6555 | 2.659 | 2.6625 | 2.6659 | 2.6694 | 2.6694 | 2.6693 | 2.6693 | 2.6693 | 2.6693 | 2.6693 | 2.6692 | 2.6692 | 2.6692 | 2.6692 | 2.6692 | 2.6691 | 2.6691 | 2.6691 | 2.6691 | 2.669 | 2.669 | 2.669 | 2.669 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689 | 2.6689
397 | Howick |  |  | 2052 | 1700.1035 | 1689.055 | 1678.0783 | 1667.1729 | 1656.3384 | 1662.8375 | 1669.3622 | 1675.9124 | 1682.4884 | 1689.0901 | 1695.7161 | 1702.368 | 1709.0461 | 1715.7504 | 1722.4809 | 1728.5827 | 1734.7061 | 1740.8512 | 1747.0181 | 1753.2068 | 1758.665 | 1764.1402 | 1769.6325 | 1775.1418 | 1780.6683 | 1788.0053 | 1795.3725 | 1802.7701 | 1810.1982 | 1817.6568 | 1824.5408 | 1831.4508 | 1838.3871 | 1845.3496 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 | 1852.3384 |  | 5050 | 5017.1815 | 4984.5762 | 4952.1828 | 4920 | 4919.1764 | 4918.3529 | 4917.5296 | 4916.7064 | 4915.8834 | 4914.6358 | 4913.3885 | 4912.1415 | 4910.8948 | 4909.6484 | 4905.0447 | 4900.4453 | 4895.8503 | 4891.2595 | 4886.673 | 4879.4938 | 4872.3252 | 4865.1671 | 4858.0195 | 4850.8824 | 4848.1171 | 4845.3534 | 4842.5912 | 4839.8307 | 4837.0717 | 4855.4638 | 4873.9258 | 4892.458 | 4911.0606 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | 4929.734 | [6 empty] | 1254 | 1263 | 1272 | 1281 | 1290.2 | 1305 | 1320 | 1335 | 1350 | 1365 | 1379.8 | 1391 | 1402 | 1413 | 1424 | 1435 | 1446 | 1457 | 1468 | 1479 | 1490 | 1501 | 1512 | 1523 | 1534 | 1545 | 1556 | 1567 | 1578 | 1589 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | 1596.5 | [6 empty] | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9704 | 2.9583 | 2.9462 | 2.9342 | 2.9223 | 2.9104 | 2.8983 | 2.8862 | 2.8742 | 2.8622 | 2.8503 | 2.8376 | 2.8249 | 2.8123 | 2.7998 | 2.7873 | 2.7745 | 2.7619 | 2.7493 | 2.7367 | 2.7242 | 2.7115 | 2.6988 | 2.6862 | 2.6736 | 2.6612 | 2.6612 | 2.6612 | 2.6613 | 2.6613 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614 | 2.6614
398 | Howick |  |  | 2052 | 1625.1444 | 1607.6072 | 1590.2592 | 1573.0984 | 1556.1228 | 1562.4535 | 1568.8099 | 1575.1922 | 1581.6004 | 1588.0347 | 1594.489 | 1600.9694 | 1607.4763 | 1614.0095 | 1620.5694 | 1626.4825 | 1632.4172 | 1638.3736 | 1644.3517 | 1650.3516 | 1655.6239 | 1660.9131 | 1666.2191 | 1671.5422 | 1676.8822 | 1683.969 | 1691.0857 | 1698.2325 | 1705.4095 | 1712.6169 | 1719.2662 | 1725.9414 | 1732.6425 | 1739.3696 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 | 1746.1228 |  | 5180 | 5124.1017 | 5068.8066 | 5014.1082 | 4960 | 4952.4849 | 4944.9812 | 4937.4888 | 4930.0078 | 4922.5381 | 4914.2728 | 4906.0213 | 4897.7837 | 4889.5599 | 4881.35 | 4870.8727 | 4860.4179 | 4849.9856 | 4839.5757 | 4829.1881 | 4815.8006 | 4802.4503 | 4789.137 | 4775.8606 | 4762.621 | 4753.4484 | 4744.2934 | 4735.1561 | 4726.0364 | 4716.9343 | 4735.3221 | 4753.7815 | 4772.313 | 4790.9166 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | 4809.5928 | [6 empty] | 1083 | 1090 | 1097 | 1104 | 1112.8 | 1126 | 1139 | 1152 | 1165 | 1178 | 1190.1 | 1200 | 1210 | 1220 | 1230 | 1240 | 1250 | 1260 | 1270 | 1280 | 1290 | 1300 | 1310 | 1320 | 1330 | 1340 | 1350 | 1360 | 1370 | 1380 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | 1388.3 | [6 empty] | 3.1874 | 3.1874 | 3.1874 | 3.1874 | 3.1874 | 3.1697 | 3.1521 | 3.1345 | 3.1171 | 3.0998 | 3.082 | 3.0644 | 3.0469 | 3.0294 | 3.0121 | 2.9947 | 2.9774 | 2.9602 | 2.9432 | 2.9262 | 2.9088 | 2.8915 | 2.8743 | 2.8572 | 2.8402 | 2.8228 | 2.8055 | 2.7883 | 2.7712 | 2.7542 | 2.7543 | 2.7543 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544 | 2.7544
399 | Howick |  |  | 2052 | 2123.7183 | 2127.3423 | 2130.9725 | 2134.6089 | 2138.2515 | 2144.4301 | 2150.6266 | 2156.841 | 2163.0733 | 2169.3236 | 2175.6227 | 2181.94 | 2188.2756 | 2194.6296 | 2201.0021 | 2206.7398 | 2212.4925 | 2218.2602 | 2224.0429 | 2229.8407 | 2234.9373 | 2240.0455 | 2245.1654 | 2250.2971 | 2255.4404 | 2262.2948 | 2269.17 | 2276.0661 | 2282.9832 | 2289.9212 | 2296.3511 | 2302.799 | 2309.265 | 2315.7492 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 | 2322.2515 |  | 5860 | 5869.9745 | 5879.966 | 5889.9745 | 5900 | 5908.1526 | 5916.3165 | 5924.4917 | 5932.6782 | 5940.8759 | 5949.1013 | 5957.3381 | 5965.5863 | 5973.8459 | 5982.1169 | 5984.1393 | 5986.1625 | 5988.1863 | 5990.2108 | 5992.2359 | 5992.191 | 5992.1461 | 5992.1011 | 5992.0562 | 5992.0112 | 5996.3005 | 6000.5928 | 6004.8882 | 6009.1866 | 6013.4882 | 6030.3319 | 6047.2227 | 6064.1609 | 6081.1465 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | 6098.1797 | [6 empty] | 1764 | 1777 | 1790 | 1803 | 1817.3 | 1840 | 1863 | 1886 | 1909 | 1932 | 1955 | 1973 | 1991 | 2009 | 2027 | 2045 | 2063 | 2081 | 2099 | 2117 | 2135 | 2153 | 2171 | 2189 | 2207 | 2225 | 2243 | 2261 | 2279 | 2297 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | 2305.2 | [6 empty] | 2.7593 | 2.7593 | 2.7593 | 2.7593 | 2.7593 | 2.7551 | 2.751 | 2.7468 | 2.7427 | 2.7386 | 2.7344 | 2.7303 | 2.7262 | 2.722 | 2.7179 | 2.7118 | 2.7056 | 2.6995 | 2.6934 | 2.6873 | 2.6811 | 2.675 | 2.6689 | 2.6628 | 2.6567 | 2.6505 | 2.6444 | 2.6383 | 2.6322 | 2.6261 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626 | 2.626
400 | Howick |  |  | 2052 | 1473.3016 | 1468.9491 | 1464.6094 | 1460.2826 | 1455.9686 | 1469.0018 | 1482.1517 | 1495.4193 | 1508.8056 | 1522.3118 | 1535.6051 | 1549.0146 | 1562.5411 | 1576.1858 | 1589.9496 | 1602.1752 | 1614.4949 | 1626.9093 | 1639.4191 | 1652.0251 | 1662.9572 | 1673.9616 | 1685.0388 | 1696.1894 | 1707.4137 | 1722.0006 | 1736.7122 | 1751.5495 | 1766.5135 | 1781.6054 | 1795.2669 | 1809.0332 | 1822.905 | 1836.8832 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 | 1850.9686 |  | 4250 | 4237.4445 | 4224.926 | 4212.4446 | 4200 | 4228.2403 | 4256.6705 | 4285.2919 | 4314.1057 | 4343.1133 | 4371.2303 | 4399.5293 | 4428.0115 | 4456.6782 | 4485.5304 | 4507.0346 | 4528.6419 | 4550.3528 | 4572.1678 | 4594.0874 | 4610.9475 | 4627.8695 | 4644.8536 | 4661.9 | 4679.009 | 4705.035 | 4731.2057 | 4757.522 | 4783.9846 | 4810.5945 | 4847.8215 | 4885.3367 | 4923.1422 | 4961.2402 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | 4999.633 | [6 empty] | 1161 | 1171 | 1181 | 1191 | 1199.3 | 1214 | 1229 | 1244 | 1259 | 1274 | 1287.7 | 1299 | 1310 | 1321 | 1332 | 1343 | 1354 | 1365 | 1376 | 1387 | 1398 | 1409 | 1420 | 1431 | 1442 | 1453 | 1464 | 1475 | 1486 | 1497 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | 1517.4 | [6 empty] | 2.8847 | 2.8847 | 2.8847 | 2.8847 | 2.8847 | 2.8783 | 2.872 | 2.8656 | 2.8593 | 2.853 | 2.8466 | 2.8402 | 2.8339 | 2.8275 | 2.8212 | 2.8131 | 2.805 | 2.7969 | 2.7889 | 2.7809 | 2.7727 | 2.7646 | 2.7565 | 2.7485 | 2.7404 | 2.7323 | 2.7242 | 2.7162 | 2.7082 | 2.7001 | 2.7003 | 2.7005 | 2.7007 | 2.7009 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011 | 2.7011
401 | Howick |  |  | 2052 | 1380.1824 | 1370.7608 | 1361.4035 | 1352.1101 | 1342.8802 | 1346.3889 | 1349.9068 | 1353.4339 | 1356.9702 | 1360.5157 | 1364.0928 | 1367.6793 | 1371.2752 | 1374.8805 | 1378.4954 | 1381.8032 | 1385.1189 | 1388.4426 | 1391.7742 | 1395.1139 | 1398.0801 | 1401.0526 | 1404.0315 | 1407.0167 | 1410.0083 | 1413.9164 | 1417.8354 | 1421.7652 | 1425.706 | 1429.6576 | 1433.2837 | 1436.919 | 1440.5635 | 1444.2172 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 | 1447.8802 |  | 4440 | 4409.6911 | 4379.589 | 4349.6925 | 4320 | 4321.7426 | 4323.4859 | 4325.2299 | 4326.9746 | 4328.72 | 4330.4312 | 4332.1432 | 4333.8558 | 4335.5691 | 4337.2831 | 4335.3163 | 4333.3503 | 4331.3852 | 4329.421 | 4327.4578 | 4324.1545 | 4320.8537 | 4317.5554 | 4314.2597 | 4310.9665 | 4310.2333 | 4309.5003 | 4308.7673 | 4308.0346 | 4307.3019 | 4318.0843 | 4328.8938 | 4339.7303 | 4350.5939 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | 4361.4847 | [6 empty] | 938 | 943 | 948 | 953 | 956.7 | 968 | 979 | 990 | 1001 | 1012 | 1022.5 | 1029 | 1035 | 1041 | 1047 | 1053 | 1059 | 1065 | 1071 | 1077 | 1083 | 1089 | 1095 | 1101 | 1107 | 1113 | 1119 | 1125 | 1131 | 1137 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | 1148.3 | [6 empty] | 3.217 | 3.217 | 3.217 | 3.217 | 3.217 | 3.2099 | 3.2028 | 3.1957 | 3.1887 | 3.1817 | 3.1746 | 3.1675 | 3.1605 | 3.1534 | 3.1464 | 3.1374 | 3.1285 | 3.1196 | 3.1107 | 3.1019 | 3.0929 | 3.084 | 3.0751 | 3.0662 | 3.0574 | 3.0484 | 3.0395 | 3.0306 | 3.0217 | 3.0128 | 3.0127 | 3.0126 | 3.0125 | 3.0124 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123 | 3.0123
402 | Howick |  |  | 2052 | 1953.512 | 1941.4104 | 1929.3837 | 1917.4316 | 1905.5534 | 1909.0676 | 1912.5882 | 1916.1153 | 1919.6489 | 1923.189 | 1926.7715 | 1930.3608 | 1933.9567 | 1937.5593 | 1941.1686 | 1944.481 | 1947.799 | 1951.1227 | 1954.4521 | 1957.7871 | 1960.757 | 1963.7313 | 1966.7102 | 1969.6936 | 1972.6815 | 1976.5958 | 1980.5179 | 1984.4478 | 1988.3854 | 1992.3309 | 1995.9622 | 1999.6 | 2003.2445 | 2006.8956 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 | 2010.5534 |  | 6110 | 6072.1497 | 6034.534 | 5997.1512 | 5960 | 5950.9634 | 5941.9405 | 5932.9312 | 5923.9356 | 5914.9537 | 5905.7564 | 5896.5735 | 5887.4048 | 5878.2503 | 5869.1101 | 5856.6171 | 5844.1507 | 5831.7109 | 5819.2975 | 5806.9105 | 5793.0213 | 5779.1653 | 5765.3425 | 5751.5527 | 5737.7959 | 5726.2923 | 5714.8119 | 5703.3545 | 5691.92 | 5680.5085 | 5690.8464 | 5701.2031 | 5711.5787 | 5721.9732 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | 5732.3866 | [6 empty] | 1318 | 1328 | 1338 | 1348 | 1356.8 | 1373 | 1389 | 1405 | 1421 | 1437 | 1453.4 | 1465 | 1477 | 1489 | 1501 | 1513 | 1525 | 1537 | 1549 | 1561 | 1573 | 1585 | 1597 | 1609 | 1621 | 1633 | 1645 | 1657 | 1669 | 1681 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | 1692.5 | [6 empty] | 3.1277 | 3.1277 | 3.1277 | 3.1277 | 3.1277 | 3.1172 | 3.1068 | 3.0963 | 3.0859 | 3.0756 | 3.0651 | 3.0546 | 3.0442 | 3.0338 | 3.0235 | 3.0119 | 3.0004 | 2.9889 | 2.9775 | 2.9661 | 2.9545 | 2.943 | 2.9315 | 2.92 | 2.9086 | 2.897 | 2.8855 | 2.874 | 2.8626 | 2.8512 | 2.8512 | 2.8512 | 2.8512 | 2.8512 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511 | 2.8511
403 | Howick |  |  | 2052 | 1470.0679 | 1450.5588 | 1431.3086 | 1412.3139 | 1393.5712 | 1400.555 | 1407.5739 | 1414.6279 | 1421.7173 | 1428.8422 | 1435.9628 | 1443.1188 | 1450.3105 | 1457.538 | 1464.8016 | 1471.3266 | 1477.8807 | 1484.464 | 1491.0767 | 1497.7188 | 1503.538 | 1509.3799 | 1515.2445 | 1521.1319 | 1527.0421 | 1534.8609 | 1542.7197 | 1550.6187 | 1558.5582 | 1566.5383 | 1573.8758 | 1581.2477 | 1588.6541 | 1596.0952 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 | 1603.5712 |  | 4420 | 4361.3426 | 4303.4637 | 4246.3529 | 4190 | 4193.9106 | 4197.8248 | 4201.7427 | 4205.6642 | 4209.5894 | 4213.0553 | 4216.524 | 4219.9956 | 4223.4701 | 4226.9474 | 4227.0165 | 4227.0855 | 4227.1546 | 4227.2237 | 4227.2928 | 4224.5865 | 4221.882 | 4219.1792 | 4216.4781 | 4213.7788 | 4215.7453 | 4217.7127 | 4219.681 | 4221.6503 | 4223.6205 | 4243.101 | 4262.6714 | 4282.3321 | 4302.0834 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | 4321.9258 | [6 empty] | 757 | 762 | 767 | 772 | 778.9 | 789 | 799 | 809 | 819 | 829 | 837.9 | 845 | 852 | 859 | 866 | 873 | 880 | 887 | 894 | 901 | 908 | 915 | 922 | 929 | 936 | 943 | 950 | 957 | 964 | 971 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | 981.9 | [6 empty] | 3.0067 | 3.0067 | 3.0067 | 3.0067 | 3.0067 | 2.9945 | 2.9823 | 2.9702 | 2.9582 | 2.9462 | 2.934 | 2.9218 | 2.9097 | 2.8977 | 2.8857 | 2.8729 | 2.8602 | 2.8476 | 2.835 | 2.8225 | 2.8098 | 2.7971 | 2.7845 | 2.7719 | 2.7594 | 2.7467 | 2.7339 | 2.7213 | 2.7087 | 2.6961 | 2.696 | 2.6958 | 2.6956 | 2.6954 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952 | 2.6952
404 | Howick |  |  | 2052 | 1557.8019 | 1552.5478 | 1547.3115 | 1542.0928 | 1536.8918 | 1543.8821 | 1550.9042 | 1557.9583 | 1565.0444 | 1572.1628 | 1579.2898 | 1586.449 | 1593.6408 | 1600.8651 | 1608.1222 | 1614.6523 | 1621.209 | 1627.7924 | 1634.4024 | 1641.0393 | 1646.8625 | 1652.7064 | 1658.571 | 1664.4564 | 1670.3627 | 1678.1882 | 1686.0505 | 1693.9495 | 1701.8856 | 1709.8589 | 1717.2021 | 1724.5769 | 1731.9833 | 1739.4216 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 | 1746.8918 |  | 4470 | 4454.9239 | 4439.8986 | 4424.9241 | 4410 | 4412.1118 | 4414.2247 | 4416.3385 | 4418.4534 | 4420.5693 | 4422.2502 | 4423.9317 | 4425.6138 | 4427.2966 | 4428.98 | 4427.2554 | 4425.5315 | 4423.8082 | 4422.0857 | 4420.3638 | 4415.955 | 4411.5507 | 4407.1507 | 4402.7551 | 4398.364 | 4398.4668 | 4398.5697 | 4398.6726 | 4398.7755 | 4398.8783 | 4417.6808 | 4436.5637 | 4455.5272 | 4474.5719 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | 4493.6979 | [6 empty] | 760 | 765 | 770 | 775 | 780.1 | 790 | 800 | 810 | 820 | 830 | 839.6 | 847 | 855 | 863 | 871 | 879 | 887 | 895 | 903 | 911 | 919 | 927 | 935 | 943 | 951 | 959 | 967 | 975 | 983 | 991 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | 993.3 | [6 empty] | 2.8694 | 2.8694 | 2.8694 | 2.8694 | 2.8694 | 2.8578 | 2.8462 | 2.8347 | 2.8232 | 2.8118 | 2.8002 | 2.7886 | 2.777 | 2.7656 | 2.7541 | 2.7419 | 2.7298 | 2.7177 | 2.7056 | 2.6936 | 2.6814 | 2.6693 | 2.6572 | 2.6452 | 2.6332 | 2.621 | 2.6088 | 2.5967 | 2.5846 | 2.5727 | 2.5726 | 2.5726 | 2.5725 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724 | 2.5724
405 | Howick |  |  | 2052 | 1174.8514 | 1161.6857 | 1148.6676 | 1135.7953 | 1123.0673 | 1130.0346 | 1137.045 | 1144.099 | 1151.1967 | 1158.3384 | 1165.4426 | 1172.5903 | 1179.7819 | 1187.0177 | 1194.2977 | 1200.8098 | 1207.3573 | 1213.9405 | 1220.5597 | 1227.2149 | 1233.0243 | 1238.8612 | 1244.7258 | 1250.6181 | 1256.5383 | 1264.34 | 1272.1902 | 1280.0891 | 1288.0371 | 1296.0344 | 1303.3578 | 1310.7225 | 1318.1289 | 1325.5771 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 | 1333.0673 |  | 3630 | 3589.3213 | 3549.0985 | 3509.3264 | 3470 | 3477.6711 | 3485.3592 | 3493.0643 | 3500.7865 | 3508.5257 | 3515.7716 | 3523.0325 | 3530.3085 | 3537.5994 | 3544.9054 | 3548.7379 | 3552.5744 | 3556.4152 | 3560.2601 | 3564.1091 | 3565.1314 | 3566.1539 | 3567.1768 | 3568.1999 | 3569.2234 | 3575.0265 | 3580.839 | 3586.661 | 3592.4924 | 3598.3333 | 3618.2408 | 3638.2583 | 3658.3867 | 3678.6264 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | 3698.978 | [6 empty] | 613 | 618 | 623 | 628 | 631.8 | 639 | 646 | 653 | 660 | 667 | 675.8 | 682 | 688 | 694 | 700 | 706 | 712 | 718 | 724 | 730 | 736 | 742 | 748 | 754 | 760 | 766 | 772 | 778 | 784 | 790 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | 791 | [6 empty] | 3.0898 | 3.0898 | 3.0898 | 3.0898 | 3.0898 | 3.0775 | 3.0653 | 3.0531 | 3.041 | 3.0289 | 3.0167 | 3.0045 | 2.9923 | 2.9802 | 2.9682 | 2.9553 | 2.9424 | 2.9296 | 2.9169 | 2.9042 | 2.8914 | 2.8786 | 2.8658 | 2.8531 | 2.8405 | 2.8276 | 2.8147 | 2.8019 | 2.7891 | 2.7764 | 2.7761 | 2.7758 | 2.7754 | 2.7751 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748
406 | Howick |  |  | 2052 | 1155.0446 | 1150.8121 | 1146.595 | 1142.3934 | 1138.2073 | 1153.1793 | 1168.3482 | 1183.7167 | 1199.2874 | 1215.0628 | 1230.3446 | 1245.8186 | 1261.4872 | 1277.3529 | 1293.4182 | 1307.4931 | 1321.7213 | 1336.1043 | 1350.6438 | 1365.3415 | 1377.9431 | 1390.6611 | 1403.4964 | 1416.4502 | 1429.5235 | 1446.3449 | 1463.3642 | 1480.5838 | 1498.0061 | 1515.6333 | 1531.4159 | 1547.3629 | 1563.476 | 1579.7569 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 | 1596.2073 |  | 3430 | 3417.4311 | 3404.9082 | 3392.4313 | 3380 | 3426.1959 | 3473.0232 | 3520.4906 | 3568.6066 | 3617.3803 | 3665.0731 | 3713.3946 | 3762.3533 | 3811.9574 | 3862.2156 | 3902.1965 | 3942.5912 | 3983.4042 | 4024.6396 | 4066.3019 | 4102.1209 | 4138.2554 | 4174.7082 | 4211.4821 | 4248.58 | 4296.4391 | 4344.8373 | 4393.7807 | 4443.2755 | 4493.3278 | 4538.2567 | 4583.6348 | 4629.4667 | 4675.7568 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | 4722.5098 | [6 empty] | 510 | 514 | 518 | 522 | 526 | 532 | 538 | 544 | 550 | 556 | 563.3 | 568 | 573 | 578 | 583 | 588 | 593 | 598 | 603 | 608 | 613 | 618 | 623 | 628 | 633 | 638 | 643 | 648 | 653 | 658 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | 662.7 | [6 empty] | 2.9696 | 2.9696 | 2.9696 | 2.9696 | 2.9696 | 2.9711 | 2.9726 | 2.9741 | 2.9756 | 2.9771 | 2.9789 | 2.9807 | 2.9825 | 2.9843 | 2.9861 | 2.9845 | 2.9829 | 2.9814 | 2.9798 | 2.9782 | 2.977 | 2.9757 | 2.9745 | 2.9733 | 2.972 | 2.9705 | 2.9691 | 2.9676 | 2.9661 | 2.9647 | 2.9634 | 2.9622 | 2.961 | 2.9598 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586
407 | Howick |  |  | 2052 | 1789.7973 | 1788.9817 | 1788.1665 | 1787.3517 | 1786.5372 | 1798.5452 | 1810.6339 | 1822.8039 | 1835.0557 | 1847.3898 | 1859.6345 | 1871.9602 | 1884.3677 | 1896.8574 | 1909.4299 | 1920.677 | 1931.9904 | 1943.3704 | 1954.8174 | 1966.3318 | 1976.379 | 1986.4774 | 1996.6275 | 2006.8295 | 2017.0836 | 2030.5736 | 2044.1539 | 2057.825 | 2071.5875 | 2085.4421 | 2098.1063 | 2110.8475 | 2123.6661 | 2136.5625 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 | 2149.5372 |  | 5490 | 5487.4983 | 5484.9977 | 5482.4983 | 5480 | 5502.6979 | 5525.4898 | 5548.3761 | 5571.3572 | 5594.4335 | 5616.8943 | 5639.4452 | 5662.0867 | 5684.819 | 5707.6427 | 5723.1039 | 5738.607 | 5754.152 | 5769.7392 | 5785.3686 | 5796.2285 | 5807.1087 | 5818.0094 | 5828.9305 | 5839.8721 | 5859.7376 | 5879.6706 | 5899.6715 | 5919.7404 | 5939.8776 | 5976.0497 | 6012.4422 | 6049.0562 | 6085.8933 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | 6122.9546 | [6 empty] | 793 | 802 | 811 | 820 | 829.6 | 841 | 852 | 863 | 874 | 885 | 897.6 | 908 | 918 | 928 | 938 | 948 | 958 | 968 | 978 | 988 | 998 | 1008 | 1018 | 1028 | 1038 | 1048 | 1058 | 1068 | 1078 | 1088 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | 1104.8 | [6 empty] | 3.0674 | 3.0674 | 3.0674 | 3.0674 | 3.0674 | 3.0595 | 3.0517 | 3.0439 | 3.0361 | 3.0283 | 3.0204 | 3.0126 | 3.0048 | 2.997 | 2.9892 | 2.9797 | 2.9703 | 2.9609 | 2.9515 | 2.9422 | 2.9328 | 2.9233 | 2.9139 | 2.9045 | 2.8952 | 2.8858 | 2.8763 | 2.8669 | 2.8576 | 2.8483 | 2.8483 | 2.8484 | 2.8484 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485 | 2.8485
408 | Howick |  |  | 2052 | 1103.6898 | 1093.1818 | 1082.7739 | 1072.465 | 1062.2543 | 1083.4757 | 1105.1211 | 1127.1988 | 1149.7176 | 1172.6863 | 1194.3857 | 1216.4866 | 1238.9964 | 1261.9228 | 1285.2733 | 1305.2998 | 1325.6384 | 1346.2938 | 1367.2711 | 1388.5753 | 1406.5364 | 1424.7298 | 1443.1586 | 1461.8258 | 1480.7344 | 1504.613 | 1528.8767 | 1553.5317 | 1578.5843 | 1604.0409 | 1626.4487 | 1649.1696 | 1672.2078 | 1695.5679 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 | 1719.2543 |  | 2930 | 2902.1041 | 2874.4739 | 2847.1067 | 2820 | 2875.4294 | 2931.9483 | 2989.5781 | 3048.3407 | 3108.2583 | 3164.8375 | 3222.4465 | 3281.1042 | 3340.8296 | 3401.6422 | 3450.1833 | 3499.4169 | 3549.3532 | 3600.002 | 3651.3736 | 3693.8675 | 3736.8559 | 3780.3447 | 3824.3395 | 3868.8464 | 3926.128 | 3984.2577 | 4043.2481 | 4103.1119 | 4163.862 | 4221.7664 | 4280.476 | 4340.002 | 4400.3559 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | 4461.5491 | [6 empty] | 2096 | 2118 | 2140 | 2162 | 2182.2 | 2207 | 2232 | 2257 | 2282 | 2307 | 2331.1 | 2354 | 2377 | 2400 | 2423 | 2446 | 2469 | 2492 | 2515 | 2538 | 2561 | 2584 | 2607 | 2630 | 2653 | 2676 | 2699 | 2722 | 2745 | 2768 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | 2796.8 | [6 empty] | 2.6547 | 2.6547 | 2.6547 | 2.6547 | 2.6547 | 2.6539 | 2.6531 | 2.6522 | 2.6514 | 2.6505 | 2.6498 | 2.649 | 2.6482 | 2.6474 | 2.6466 | 2.6432 | 2.6398 | 2.6364 | 2.633 | 2.6296 | 2.6262 | 2.6229 | 2.6195 | 2.6161 | 2.6128 | 2.6094 | 2.606 | 2.6026 | 2.5992 | 2.5959 | 2.5957 | 2.5955 | 2.5954 | 2.5952 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595 | 2.595
409 | Howick |  |  | 2052 | 1391.6111 | 1389.1944 | 1386.7819 | 1384.3736 | 1381.9695 | 1383.9791 | 1385.9917 | 1388.0072 | 1390.0256 | 1392.0469 | 1394.0957 | 1396.1475 | 1398.2023 | 1400.2602 | 1402.321 | 1404.197 | 1406.0755 | 1407.9564 | 1409.8399 | 1411.7259 | 1413.3976 | 1415.0712 | 1416.7469 | 1418.4245 | 1420.104 | 1422.3538 | 1424.6072 | 1426.8641 | 1429.1246 | 1431.3887 | 1433.4986 | 1435.6116 | 1437.7278 | 1439.8471 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 | 1441.9695 |  | 4330 | 4322.4804 | 4314.9739 | 4307.4805 | 4300 | 4303.6499 | 4307.3029 | 4310.9591 | 4314.6183 | 4318.2806 | 4322.025 | 4325.7726 | 4329.5235 | 4333.2777 | 4337.0351 | 4336.228 | 4335.4211 | 4334.6144 | 4333.8078 | 4333.0013 | 4331.5249 | 4330.049 | 4328.5736 | 4327.0987 | 4325.6242 | 4325.7513 | 4325.8784 | 4326.0055 | 4326.1325 | 4326.2596 | 4332.3302 | 4338.4093 | 4344.497 | 4350.5931 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | 4356.6979 | [6 empty] | 587 | 590 | 593 | 596 | 598 | 605 | 612 | 619 | 626 | 633 | 639.2 | 644 | 649 | 654 | 659 | 664 | 669 | 674 | 679 | 684 | 689 | 694 | 699 | 704 | 709 | 714 | 719 | 724 | 729 | 734 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | 737.8 | [6 empty] | 3.1115 | 3.1115 | 3.1115 | 3.1115 | 3.1115 | 3.1096 | 3.1077 | 3.1059 | 3.104 | 3.1021 | 3.1002 | 3.0984 | 3.0965 | 3.0946 | 3.0928 | 3.088 | 3.0833 | 3.0787 | 3.074 | 3.0693 | 3.0646 | 3.06 | 3.0553 | 3.0506 | 3.046 | 3.0413 | 3.0365 | 3.0318 | 3.0271 | 3.0224 | 3.0222 | 3.022 | 3.0218 | 3.0216 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214 | 3.0214
410 | Howick |  |  | 2052 | 1005.9037 | 996.6317 | 987.4452 | 978.3433 | 969.3254 | 976.2791 | 983.2827 | 990.3366 | 997.441 | 1004.5964 | 1011.6875 | 1018.8286 | 1026.0201 | 1033.2624 | 1040.5558 | 1047.0575 | 1053.5998 | 1060.1829 | 1066.8073 | 1073.473 | 1079.2746 | 1085.1076 | 1090.9721 | 1096.8683 | 1102.7963 | 1110.5848 | 1118.4282 | 1126.3271 | 1134.2817 | 1142.2925 | 1149.6049 | 1156.964 | 1164.3703 | 1171.824 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 | 1179.3254 |  | 3300 | 3269.582 | 3239.4444 | 3209.5846 | 3180 | 3195.1409 | 3210.3538 | 3225.6392 | 3240.9974 | 3256.4287 | 3271.4936 | 3286.6282 | 3301.8329 | 3317.1078 | 3332.4535 | 3343.2404 | 3354.0623 | 3364.9192 | 3375.8113 | 3386.7386 | 3394.7789 | 3402.8384 | 3410.9169 | 3419.0147 | 3427.1317 | 3440.6561 | 3454.2339 | 3467.8652 | 3481.5504 | 3495.2896 | 3517.163 | 3539.1734 | 3561.3215 | 3583.6082 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | 3606.0343 | [6 empty] | 1804 | 1813 | 1822 | 1831 | 1841.1 | 1866 | 1891 | 1916 | 1941 | 1966 | 1992.7 | 2008 | 2024 | 2040 | 2056 | 2072 | 2088 | 2104 | 2120 | 2136 | 2152 | 2168 | 2184 | 2200 | 2216 | 2232 | 2248 | 2264 | 2280 | 2296 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | 2305.1 | [6 empty] | 3.2806 | 3.2806 | 3.2806 | 3.2806 | 3.2806 | 3.2728 | 3.2649 | 3.2571 | 3.2493 | 3.2415 | 3.2337 | 3.2259 | 3.2181 | 3.2103 | 3.2026 | 3.193 | 3.1834 | 3.1739 | 3.1644 | 3.1549 | 3.1454 | 3.1359 | 3.1265 | 3.1171 | 3.1077 | 3.0981 | 3.0885 | 3.0789 | 3.0694 | 3.0599 | 3.0595 | 3.059 | 3.0586 | 3.0581 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577 | 3.0577
411 | Howick |  |  | 2052 | 1283.8292 | 1272.2097 | 1260.6953 | 1249.2851 | 1237.9782 | 1250.9712 | 1264.1006 | 1277.3678 | 1290.7742 | 1304.3213 | 1317.5767 | 1330.9668 | 1344.493 | 1358.1567 | 1371.9592 | 1384.1555 | 1396.4602 | 1408.8744 | 1421.3989 | 1434.0347 | 1444.9451 | 1455.9386 | 1467.0156 | 1478.177 | 1489.4232 | 1503.9745 | 1518.6679 | 1533.5048 | 1548.4867 | 1563.615 | 1577.2478 | 1590.9995 | 1604.8711 | 1618.8636 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 | 1632.9782 |  | 3640 | 3607.0554 | 3574.409 | 3542.0581 | 3510 | 3532.529 | 3555.2027 | 3578.0219 | 3600.9875 | 3624.1006 | 3645.9435 | 3667.9181 | 3690.0251 | 3712.2653 | 3734.6396 | 3751.3329 | 3768.1008 | 3784.9437 | 3801.8619 | 3818.8556 | 3830.8375 | 3842.857 | 3854.9141 | 3867.0091 | 3879.1421 | 3899.0883 | 3919.1372 | 3939.2891 | 3959.5446 | 3979.9043 | 4013.7633 | 4047.9104 | 4082.348 | 4117.0786 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | 4152.1046 | [6 empty] | 1203 | 1216 | 1229 | 1242 | 1255.9 | 1272 | 1288 | 1304 | 1320 | 1336 | 1349.9 | 1365 | 1380 | 1395 | 1410 | 1425 | 1440 | 1455 | 1470 | 1485 | 1500 | 1515 | 1530 | 1545 | 1560 | 1575 | 1590 | 1605 | 1620 | 1635 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | 1642.3 | [6 empty] | 2.8353 | 2.8353 | 2.8353 | 2.8353 | 2.8353 | 2.8238 | 2.8124 | 2.8011 | 2.7898 | 2.7785 | 2.7672 | 2.7558 | 2.7445 | 2.7333 | 2.7221 | 2.7102 | 2.6983 | 2.6865 | 2.6747 | 2.663 | 2.6512 | 2.6394 | 2.6277 | 2.6161 | 2.6045 | 2.5925 | 2.5806 | 2.5688 | 2.557 | 2.5453 | 2.5448 | 2.5443 | 2.5437 | 2.5432 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427 | 2.5427
412 | Howick |  |  | 2052 | 1790.4998 | 1774.5975 | 1758.8365 | 1743.2155 | 1727.7332 | 1728.991 | 1730.2498 | 1731.5095 | 1732.7701 | 1734.0316 | 1735.3139 | 1736.5972 | 1737.8815 | 1739.1667 | 1740.4529 | 1741.611 | 1742.7698 | 1743.9294 | 1745.0898 | 1746.251 | 1747.2738 | 1748.2972 | 1749.3212 | 1750.3458 | 1751.3709 | 1752.748 | 1754.1262 | 1755.5054 | 1756.8857 | 1758.2671 | 1759.5584 | 1760.8507 | 1762.1439 | 1763.4381 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 | 1764.7332 |  | 5420 | 5371.8625 | 5324.1525 | 5276.8663 | 5230 | 5218.2049 | 5206.4365 | 5194.6946 | 5182.9791 | 5171.2901 | 5159.4524 | 5147.6417 | 5135.8581 | 5124.1014 | 5112.3717 | 5097.9473 | 5083.5636 | 5069.2204 | 5054.9178 | 5040.6555 | 5025.7301 | 5010.8489 | 4996.0118 | 4981.2186 | 4966.4692 | 4952.4174 | 4938.4053 | 4924.4328 | 4910.4999 | 4896.6064 | 4900.1266 | 4903.6493 | 4907.1745 | 4910.7023 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | 4914.2326 | [6 empty] | 1039 | 1047 | 1055 | 1063 | 1069.6 | 1082 | 1095 | 1108 | 1121 | 1134 | 1146.9 | 1157 | 1168 | 1179 | 1190 | 1201 | 1212 | 1223 | 1234 | 1245 | 1256 | 1267 | 1278 | 1289 | 1300 | 1311 | 1322 | 1333 | 1344 | 1355 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | 1357.4 | [6 empty] | 3.0271 | 3.0271 | 3.0271 | 3.0271 | 3.0271 | 3.0181 | 3.0091 | 3.0001 | 2.9912 | 2.9822 | 2.9732 | 2.9642 | 2.9552 | 2.9463 | 2.9374 | 2.9271 | 2.9169 | 2.9068 | 2.8967 | 2.8866 | 2.8763 | 2.8661 | 2.856 | 2.8458 | 2.8358 | 2.8255 | 2.8153 | 2.8051 | 2.795 | 2.7849 | 2.7849 | 2.7848 | 2.7848 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847 | 2.7847
413 | Howick |  |  | 2052 | 751.2006 | 746.0256 | 740.8862 | 735.7822 | 730.7133 | 733.3811 | 736.0586 | 738.7459 | 741.443 | 744.1499 | 746.8697 | 749.5995 | 752.3392 | 755.0889 | 757.8487 | 760.3403 | 762.84 | 765.3479 | 767.8641 | 770.3886 | 772.6099 | 774.8376 | 777.0718 | 779.3124 | 781.5594 | 784.5457 | 787.5435 | 790.5526 | 793.5733 | 796.6056 | 799.4073 | 802.219 | 805.0405 | 807.8719 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 | 810.7133 |  | 2200 | 2184.8441 | 2169.7926 | 2154.8448 | 2140 | 2142.4556 | 2144.914 | 2147.3753 | 2149.8394 | 2152.3063 | 2154.7186 | 2157.1337 | 2159.5515 | 2161.972 | 2164.3952 | 2164.7947 | 2165.1943 | 2165.594 | 2165.9937 | 2166.3936 | 2165.8298 | 2165.2662 | 2164.7027 | 2164.1394 | 2163.5762 | 2164.8978 | 2166.2202 | 2167.5433 | 2168.8673 | 2170.1921 | 2177.7104 | 2185.2547 | 2192.8252 | 2200.4219 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | 2208.0449 | [6 empty] | 565 | 572 | 579 | 586 | 593.6 | 603 | 612 | 621 | 630 | 639 | 648.6 | 657 | 666 | 675 | 684 | 693 | 702 | 711 | 720 | 729 | 738 | 747 | 756 | 765 | 774 | 783 | 792 | 801 | 810 | 819 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | 819.2 | [6 empty] | 2.9286 | 2.9286 | 2.9286 | 2.9286 | 2.9286 | 2.9213 | 2.9141 | 2.9068 | 2.8995 | 2.8923 | 2.885 | 2.8777 | 2.8704 | 2.8632 | 2.856 | 2.8471 | 2.8383 | 2.8296 | 2.8208 | 2.8121 | 2.8033 | 2.7945 | 2.7857 | 2.777 | 2.7683 | 2.7594 | 2.7506 | 2.7418 | 2.733 | 2.7243 | 2.7242 | 2.724 | 2.7239 | 2.7237 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236 | 2.7236
414 | Howick |  |  | 2052 | 637.1122 | 633.6589 | 630.2243 | 626.8083 | 623.4109 | 624.832 | 626.2564 | 627.684 | 629.1149 | 630.5491 | 631.9979 | 633.45 | 634.9055 | 636.3644 | 637.8266 | 639.1058 | 640.3876 | 641.672 | 642.959 | 644.2485 | 645.3617 | 646.4769 | 647.594 | 648.713 | 649.8339 | 651.3316 | 652.8328 | 654.3374 | 655.8454 | 657.357 | 658.7618 | 660.1695 | 661.5803 | 662.9941 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 | 664.4109 |  | 1860 | 1849.9183 | 1839.8913 | 1829.9186 | 1820 | 1826.51 | 1833.0434 | 1839.6001 | 1846.1802 | 1852.7839 | 1859.4295 | 1866.0988 | 1872.7921 | 1879.5095 | 1886.2509 | 1890.0042 | 1893.765 | 1897.5332 | 1901.309 | 1905.0923 | 1908.3585 | 1911.6303 | 1914.9077 | 1918.1907 | 1921.4794 | 1925.8736 | 1930.2779 | 1934.6923 | 1939.1168 | 1943.5514 | 1947.673 | 1951.8033 | 1955.9424 | 1960.0902 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | 1964.2469 | [6 empty] | 1011 | 1016 | 1021 | 1026 | 1029.1 | 1043 | 1057 | 1071 | 1085 | 1099 | 1112 | 1120 | 1128 | 1136 | 1144 | 1152 | 1160 | 1168 | 1176 | 1184 | 1192 | 1200 | 1208 | 1216 | 1224 | 1232 | 1240 | 1248 | 1256 | 1264 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | 1269.3 | [6 empty] | 2.9194 | 2.9194 | 2.9194 | 2.9194 | 2.9194 | 2.9232 | 2.927 | 2.9308 | 2.9346 | 2.9384 | 2.9421 | 2.9459 | 2.9497 | 2.9535 | 2.9573 | 2.9573 | 2.9572 | 2.9572 | 2.9571 | 2.9571 | 2.957 | 2.957 | 2.957 | 2.9569 | 2.9569 | 2.9568 | 2.9568 | 2.9567 | 2.9567 | 2.9566 | 2.9566 | 2.9565 | 2.9565 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564 | 2.9564
415 | Howick |  |  | 2052 | 1601.2223 | 1581.6518 | 1562.3204 | 1543.2253 | 1524.3636 | 1527.0415 | 1529.7241 | 1532.4114 | 1535.1035 | 1537.8002 | 1540.5303 | 1543.2652 | 1546.0049 | 1548.7495 | 1551.499 | 1553.9989 | 1556.5029 | 1559.0108 | 1561.5228 | 1564.0389 | 1566.2667 | 1568.4977 | 1570.7318 | 1572.9692 | 1575.2097 | 1578.2075 | 1581.211 | 1584.2202 | 1587.2352 | 1590.2559 | 1593.0675 | 1595.884 | 1598.7056 | 1601.5321 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 | 1604.3636 |  | 5000 | 4938.8887 | 4878.5244 | 4818.8978 | 4760 | 4745.9689 | 4731.9793 | 4718.0308 | 4704.1235 | 4690.2571 | 4675.9876 | 4661.7615 | 4647.5786 | 4633.439 | 4619.3423 | 4603.7321 | 4588.1747 | 4572.6698 | 4557.2173 | 4541.8171 | 4525.0535 | 4508.3519 | 4491.7119 | 4475.1333 | 4458.6159 | 4443.6654 | 4428.765 | 4413.9146 | 4399.114 | 4384.363 | 4392.0422 | 4399.7348 | 4407.4409 | 4415.1605 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | 4422.8936 | [6 empty] | 1016 | 1025 | 1034 | 1043 | 1052.6 | 1068 | 1084 | 1100 | 1116 | 1132 | 1147.3 | 1162 | 1176 | 1190 | 1204 | 1218 | 1232 | 1246 | 1260 | 1274 | 1288 | 1302 | 1316 | 1330 | 1344 | 1358 | 1372 | 1386 | 1400 | 1414 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | 1435.6 | [6 empty] | 3.1226 | 3.1226 | 3.1226 | 3.1226 | 3.1226 | 3.108 | 3.0934 | 3.0788 | 3.0644 | 3.05 | 3.0353 | 3.0207 | 3.0062 | 2.9917 | 2.9773 | 2.9625 | 2.9477 | 2.9331 | 2.9184 | 2.9039 | 2.8891 | 2.8743 | 2.8596 | 2.845 | 2.8305 | 2.8156 | 2.8009 | 2.7862 | 2.7716 | 2.757 | 2.757 | 2.7569 | 2.7569 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568 | 2.7568
416 | Howick |  |  | 2052 | 1445.1156 | 1426.3032 | 1407.7356 | 1389.4098 | 1371.3225 | 1373.9993 | 1376.6814 | 1379.3687 | 1382.0613 | 1384.7591 | 1387.4881 | 1390.2224 | 1392.9622 | 1395.7073 | 1398.4579 | 1400.9569 | 1403.4604 | 1405.9684 | 1408.4808 | 1410.9978 | 1413.2249 | 1415.4555 | 1417.6897 | 1419.9274 | 1422.1686 | 1425.1651 | 1428.168 | 1431.1773 | 1434.1928 | 1437.2147 | 1440.0253 | 1442.8413 | 1445.6629 | 1448.4899 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 | 1451.3225 |  | 4700 | 4638.8156 | 4578.4277 | 4518.8259 | 4460 | 4468.0718 | 4476.1582 | 4484.2592 | 4492.375 | 4500.5053 | 4508.7343 | 4516.9783 | 4525.2373 | 4533.5115 | 4541.8008 | 4544.795 | 4547.7911 | 4550.7892 | 4553.7893 | 4556.7913 | 4558.8636 | 4560.9368 | 4563.011 | 4565.086 | 4567.1621 | 4571.5145 | 4575.8711 | 4580.2318 | 4584.5967 | 4588.9657 | 4597.5326 | 4606.1156 | 4614.7146 | 4623.3296 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | 4631.9608 | [6 empty] | 972 | 980 | 988 | 996 | 1002.7 | 1015 | 1027 | 1039 | 1051 | 1063 | 1076.1 | 1086 | 1096 | 1106 | 1116 | 1126 | 1136 | 1146 | 1156 | 1166 | 1176 | 1186 | 1196 | 1206 | 1216 | 1226 | 1236 | 1246 | 1256 | 1266 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | 1269.4 | [6 empty] | 3.2523 | 3.2523 | 3.2523 | 3.2523 | 3.2523 | 3.2519 | 3.2514 | 3.251 | 3.2505 | 3.25 | 3.2496 | 3.2491 | 3.2486 | 3.2482 | 3.2477 | 3.2441 | 3.2404 | 3.2368 | 3.2331 | 3.2295 | 3.2259 | 3.2222 | 3.2186 | 3.215 | 3.2114 | 3.2077 | 3.204 | 3.2003 | 3.1966 | 3.193 | 3.1927 | 3.1924 | 3.1921 | 3.1918 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915 | 3.1915
417 | Howick |  |  | 2052 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.7613 | 4.6663 | 5.7891 | 7.1821 | 8.9103 | 9.8758 | 10.9459 | 12.1319 | 13.4465 | 14.9035 | 15.8925 | 16.947 | 18.0716 | 19.2708 | 20.5496 | 21.4845 | 22.462 | 23.484 | 24.5525 | 25.6695 | 26.8522 | 28.0894 | 29.3836 | 30.7374 | 32.1535 | 33.2516 | 34.3871 | 35.5614 | 36.7759 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 | 38.0318 |  | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 8 | 11 | 14.2961 | 17.1929 | 20.6767 | 24.8664 | 29.9052 | 35.9649 | 38.618 | 41.4669 | 44.5259 | 47.8107 | 51.3377 | 53.8645 | 56.5156 | 59.2972 | 62.2158 | 65.2779 | 68.479 | 71.8371 | 75.3599 | 79.0554 | 82.9321 | 85.9112 | 88.9973 | 92.1943 | 95.5062 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | 98.937 | [6 empty] | 5138 | 5153 | 5168 | 5183 | 5198.5 | 5263 | 5328 | 5393 | 5458 | 5523 | 5588.3 | 5618 | 5648 | 5678 | 5708 | 5738 | 5768 | 5798 | 5828 | 5858 | 5888 | 5918 | 5948 | 5978 | 6008 | 6038 | 6068 | 6098 | 6128 | 6158 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | 6183.5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.53174 | 1.0715 | 1.3819 | 1.5316 | 1.6044 | 1.7409 | 1.889 | 2.0497 | 2.224 | 2.4132 | 2.43 | 2.4469 | 2.4639 | 2.481 | 2.4982 | 2.5071 | 2.516 | 2.525 | 2.534 | 2.543 | 2.5502 | 2.5574 | 2.5647 | 2.572 | 2.5793 | 2.5837 | 2.5881 | 2.5925 | 2.597 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014 | 2.6014
418 | Howick |  |  | 2052 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 |  | 10 | 10 | 10 | 10 | 10 | 8.9835 | 8.0704 | 7.2501 | 6.5131 | 5.8511 | 5.7469 | 5.6447 | 5.5442 | 5.4455 | 5.3486 | 5.309 | 5.2696 | 5.2306 | 5.1919 | 5.1534 | 5.1335 | 5.1137 | 5.094 | 5.0744 | 5.0548 | 5.0382 | 5.0216 | 5.0051 | 4.9887 | 4.9723 | 4.9622 | 4.9521 | 4.942 | 4.932 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | 4.9219 | [6 empty] | 6354 | 6373 | 6392 | 6411 | 6428.3 | 6509 | 6589 | 6669 | 6749 | 6829 | 6909.8 | 6947 | 6984 | 7021 | 7058 | 7095 | 7132 | 7169 | 7206 | 7243 | 7280 | 7317 | 7354 | 7391 | 7428 | 7465 | 7502 | 7539 | 7576 | 7613 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | 7648.2 | [6 empty] | 3.2984 | 3.2984 | 3.2984 | 3.2984 | 3.2984 | 2.9631 | 2.662 | 2.3914 | 2.1483 | 1.9299 | 1.8956 | 1.8618 | 1.8287 | 1.7962 | 1.7642 | 1.7511 | 1.7381 | 1.7253 | 1.7125 | 1.6998 | 1.6933 | 1.6867 | 1.6802 | 1.6737 | 1.6673 | 1.6618 | 1.6563 | 1.6509 | 1.6455 | 1.6401 | 1.6367 | 1.6334 | 1.6301 | 1.6268 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235 | 1.6235
419 | Howick |  |  | 2052 | 291.0497 | 283.6754 | 276.4879 | 269.4825 | 262.6546 | 299.2335 | 340.9066 | 388.3833 | 442.472 | 504.0934 | 545.8197 | 591 | 639.9201 | 692.8896 | 750.2436 | 790.6903 | 833.3174 | 878.2426 | 925.5898 | 975.4896 | 1012.6674 | 1051.2622 | 1091.3279 | 1132.9206 | 1176.0985 | 1225.7638 | 1277.5264 | 1331.4749 | 1387.7016 | 1446.3026 | 1493.7553 | 1542.765 | 1593.3826 | 1645.661 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 | 1699.6546 |  | 820 | 799.2236 | 778.9737 | 759.2368 | 740 | 838.792 | 950.773 | 1077.7037 | 1221.5801 | 1384.6643 | 1497.1343 | 1618.7398 | 1750.2227 | 1892.3854 | 2046.0953 | 2153.0501 | 2265.5957 | 2384.0244 | 2508.6437 | 2639.7771 | 2737.266 | 2838.3552 | 2943.1778 | 3051.8715 | 3164.5793 | 3294.6126 | 3429.9889 | 3570.928 | 3717.6582 | 3870.4176 | 3996.0662 | 4125.7937 | 4259.7328 | 4398.02 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | 4540.7966 | [6 empty] | 3218 | 3247 | 3276 | 3305 | 3334.9 | 3370 | 3405 | 3440 | 3475 | 3510 | 3545.2 | 3559 | 3573 | 3587 | 3601 | 3615 | 3629 | 3643 | 3657 | 3671 | 3685 | 3699 | 3713 | 3727 | 3741 | 3755 | 3769 | 3783 | 3797 | 3811 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | 3822.1 | [6 empty] | 2.8174 | 2.8174 | 2.8174 | 2.8174 | 2.8174 | 2.8031 | 2.789 | 2.7748 | 2.7608 | 2.7468 | 2.7429 | 2.739 | 2.7351 | 2.7311 | 2.7272 | 2.723 | 2.7188 | 2.7145 | 2.7103 | 2.7061 | 2.703 | 2.6999 | 2.6969 | 2.6938 | 2.6907 | 2.6878 | 2.6849 | 2.6819 | 2.679 | 2.6761 | 2.6752 | 2.6743 | 2.6734 | 2.6725 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716 | 2.6716
420 | Howick |  |  | 2052 | 37.5175 | 37.5175 | 37.5175 | 37.5175 | 37.5175 | 38.0878 | 38.6667 | 39.2544 | 39.8511 | 40.4568 | 41.0391 | 41.6298 | 42.229 | 42.8368 | 43.4534 | 43.9734 | 44.4997 | 45.0322 | 45.5712 | 46.1166 | 46.5729 | 47.0337 | 47.4991 | 47.9691 | 48.4438 | 49.0551 | 49.6741 | 50.3009 | 50.9357 | 51.5784 | 52.1533 | 52.7346 | 53.3223 | 53.9166 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 | 54.5175 |  | 60 | 60 | 60 | 60 | 60 | 61.4898 | 63.0166 | 64.5813 | 66.1848 | 67.8282 | 69.4064 | 71.0213 | 72.6738 | 74.3648 | 76.0951 | 77.5158 | 78.9631 | 80.4374 | 81.9392 | 83.469 | 84.7872 | 86.1261 | 87.4862 | 88.8678 | 90.2712 | 91.9389 | 93.6374 | 95.3673 | 97.1292 | 98.9236 | 100.1513 | 101.3943 | 102.6528 | 103.9268 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | 105.2166 | [6 empty] | 5789 | 5815 | 5841 | 5867 | 5893.7 | 5967 | 6040 | 6113 | 6186 | 6259 | 6334 | 6374 | 6414 | 6454 | 6494 | 6534 | 6574 | 6614 | 6654 | 6694 | 6734 | 6774 | 6814 | 6854 | 6894 | 6934 | 6974 | 7014 | 7054 | 7094 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | 7129.1 | [6 empty] | 1.5993 | 1.5993 | 1.5993 | 1.5993 | 1.5993 | 1.6144 | 1.6297 | 1.6452 | 1.6608 | 1.6766 | 1.6912 | 1.706 | 1.7209 | 1.736 | 1.7512 | 1.7628 | 1.7745 | 1.7862 | 1.798 | 1.81 | 1.8205 | 1.8312 | 1.8418 | 1.8526 | 1.8634 | 1.8742 | 1.885 | 1.8959 | 1.9069 | 1.9179 | 1.9203 | 1.9227 | 1.9251 | 1.9275 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93
421 | Howick |  |  | 2052 | 42.2076 | 42.2076 | 42.2076 | 42.2076 | 42.2076 | 42.9377 | 43.6805 | 44.4361 | 45.2047 | 45.9867 | 46.7326 | 47.4907 | 48.2611 | 49.0439 | 49.8395 | 50.5408 | 51.252 | 51.9732 | 52.7046 | 53.4463 | 54.0826 | 54.7264 | 55.378 | 56.0373 | 56.7044 | 57.5561 | 58.4206 | 59.2981 | 60.1888 | 61.0929 | 61.8945 | 62.7067 | 63.5295 | 64.3631 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 | 65.2076 |  | 60 | 60 | 60 | 60 | 60 | 61.587 | 63.2159 | 64.888 | 66.6042 | 68.3659 | 70.0093 | 71.6922 | 73.4155 | 75.1803 | 76.9875 | 78.4297 | 79.8988 | 81.3955 | 82.9202 | 84.4735 | 85.7847 | 87.1161 | 88.4683 | 89.8414 | 91.2359 | 92.9889 | 94.7756 | 96.5966 | 98.4526 | 100.3443 | 101.997 | 103.6769 | 105.3846 | 107.1203 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | 108.8846 | [6 empty] | 8278 | 8315 | 8352 | 8389 | 8427.2 | 8532 | 8637 | 8742 | 8847 | 8952 | 9058.3 | 9115 | 9172 | 9229 | 9286 | 9343 | 9400 | 9457 | 9514 | 9571 | 9628 | 9685 | 9742 | 9799 | 9856 | 9913 | 9970 | 10027 | 10084 | 10141 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | 10195.1 | [6 empty] | 1.4215 | 1.4215 | 1.4215 | 1.4215 | 1.4215 | 1.4343 | 1.4472 | 1.4603 | 1.4734 | 1.4866 | 1.4981 | 1.5096 | 1.5212 | 1.5329 | 1.5447 | 1.5518 | 1.5589 | 1.5661 | 1.5733 | 1.5805 | 1.5862 | 1.5918 | 1.5975 | 1.6032 | 1.609 | 1.6156 | 1.6223 | 1.629 | 1.6357 | 1.6425 | 1.6479 | 1.6534 | 1.6588 | 1.6643 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698 | 1.6698
422 | Howick |  |  | 2052 | 27.2859 | 28.3902 | 29.5392 | 30.7347 | 31.9786 | 32.0621 | 32.1459 | 32.2299 | 32.3141 | 32.3985 | 32.4836 | 32.569 | 32.6547 | 32.7405 | 32.8266 | 32.8569 | 32.8873 | 32.9177 | 32.9481 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 | 32.9786 |  | 70 | 72.3762 | 74.8331 | 77.3735 | 80 | 80.2688 | 80.5384 | 80.809 | 81.0805 | 81.3529 | 81.6276 | 81.9031 | 82.1796 | 82.4571 | 82.7354 | 82.801 | 82.8666 | 82.9322 | 82.9979 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | 83.0637 | [6 empty] | 2926 | 2939 | 2952 | 2965 | 2979.8 | 3017 | 3054 | 3091 | 3128 | 3165 | 3201.7 | 3222 | 3242 | 3262 | 3282 | 3302 | 3322 | 3342 | 3362 | 3382 | 3402 | 3422 | 3442 | 3462 | 3482 | 3502 | 3522 | 3542 | 3562 | 3582 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | 3602.6 | [6 empty] | 2.5654 | 2.5493 | 2.5334 | 2.5175 | 2.5017 | 2.5035 | 2.5054 | 2.5073 | 2.5091 | 2.511 | 2.5129 | 2.5148 | 2.5166 | 2.5185 | 2.5204 | 2.52 | 2.5197 | 2.5194 | 2.519 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187 | 2.5187
423 | Howick |  |  | 2052 | 1163.0781 | 1143.7046 | 1124.6538 | 1105.9204 | 1087.499 | 1091.1692 | 1094.8518 | 1098.5468 | 1102.2543 | 1105.9743 | 1109.7161 | 1113.4705 | 1117.2376 | 1121.0175 | 1124.8102 | 1128.2377 | 1131.6756 | 1135.1241 | 1138.583 | 1142.0525 | 1145.1081 | 1148.1718 | 1151.2438 | 1154.3239 | 1157.4123 | 1161.5208 | 1165.6438 | 1169.7814 | 1173.9337 | 1178.1008 | 1181.9551 | 1185.8221 | 1189.7017 | 1193.594 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 | 1197.499 |  | 2770 | 2723.8599 | 2678.4884 | 2633.8726 | 2590 | 2602.2782 | 2614.6146 | 2627.0094 | 2639.463 | 2651.9757 | 2664.545 | 2677.1738 | 2689.8625 | 2702.6113 | 2715.4206 | 2723.7533 | 2732.1115 | 2740.4954 | 2748.905 | 2757.3405 | 2764.7693 | 2772.2182 | 2779.6872 | 2787.1763 | 2794.6856 | 2804.6747 | 2814.6994 | 2824.76 | 2834.8566 | 2844.9893 | 2854.3611 | 2863.7639 | 2873.1976 | 2882.6624 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | 2892.1584 | [6 empty] | 352 | 353 | 354 | 355 | 357.8 | 363 | 368 | 373 | 378 | 383 | 388.2 | 392 | 396 | 400 | 404 | 408 | 412 | 416 | 420 | 424 | 428 | 432 | 436 | 440 | 444 | 448 | 452 | 456 | 460 | 464 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | 466.1 | [6 empty] | 2.3816 | 2.3816 | 2.3816 | 2.3816 | 2.3816 | 2.3849 | 2.3881 | 2.3913 | 2.3946 | 2.3979 | 2.4011 | 2.4044 | 2.4076 | 2.4109 | 2.4141 | 2.4142 | 2.4142 | 2.4143 | 2.4143 | 2.4144 | 2.4144 | 2.4145 | 2.4145 | 2.4146 | 2.4146 | 2.4147 | 2.4147 | 2.4148 | 2.4148 | 2.4149 | 2.4149 | 2.415 | 2.4151 | 2.4151 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152 | 2.4152
424 | Howick |  |  | 2052 | 1535.5146 | 1529.3724 | 1523.2548 | 1517.1616 | 1511.0929 | 1514.77 | 1518.4561 | 1522.1511 | 1525.8551 | 1529.5682 | 1533.3169 | 1537.0749 | 1540.842 | 1544.6184 | 1548.404 | 1551.8372 | 1555.278 | 1558.7265 | 1562.1826 | 1565.6463 | 1568.7063 | 1571.7723 | 1574.8443 | 1577.9222 | 1581.0062 | 1585.1224 | 1589.2493 | 1593.387 | 1597.5354 | 1601.6947 | 1605.5557 | 1609.4259 | 1613.3056 | 1617.1945 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 | 1621.0929 |  | 5030 | 5009.8796 | 4989.8397 | 4969.8799 | 4950 | 4952.3277 | 4954.6564 | 4956.9863 | 4959.3173 | 4961.6493 | 4963.9725 | 4966.2968 | 4968.6222 | 4970.9487 | 4973.2763 | 4971.0666 | 4968.8579 | 4966.6502 | 4964.4434 | 4962.2377 | 4958.5508 | 4954.8667 | 4951.1854 | 4947.5067 | 4943.8308 | 4943.1847 | 4942.5387 | 4941.8928 | 4941.2469 | 4940.6012 | 4952.544 | 4964.5158 | 4976.5165 | 4988.5462 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | 5000.6049 | [6 empty] | 1296 | 1303 | 1310 | 1317 | 1323.3 | 1339 | 1354 | 1369 | 1384 | 1399 | 1414.8 | 1425 | 1435 | 1445 | 1455 | 1465 | 1475 | 1485 | 1495 | 1505 | 1515 | 1525 | 1535 | 1545 | 1555 | 1565 | 1575 | 1585 | 1595 | 1605 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | 1612 | [6 empty] | 3.2758 | 3.2758 | 3.2758 | 3.2758 | 3.2758 | 3.2694 | 3.263 | 3.2566 | 3.2502 | 3.2438 | 3.2374 | 3.231 | 3.2246 | 3.2182 | 3.2119 | 3.2033 | 3.1948 | 3.1864 | 3.1779 | 3.1694 | 3.1609 | 3.1524 | 3.1439 | 3.1355 | 3.127 | 3.1185 | 3.11 | 3.1015 | 3.093 | 3.0846 | 3.0846 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847 | 3.0847
425 | Howick |  |  | 2052 | 1735.665 | 1731.0233 | 1726.3939 | 1721.777 | 1717.1724 | 1720.5185 | 1723.8711 | 1727.2302 | 1730.5959 | 1733.9681 | 1737.3794 | 1740.7973 | 1744.222 | 1747.6534 | 1751.0916 | 1754.2154 | 1757.3448 | 1760.4798 | 1763.6203 | 1766.7665 | 1769.5504 | 1772.3387 | 1775.1314 | 1777.9285 | 1780.73 | 1782.8378 | 1784.9481 | 1787.061 | 1789.1763 | 1791.2941 | 1792.4682 | 1793.6431 | 1794.8188 | 1795.9952 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 | 1797.1724 |  | 6570 | 6552.4296 | 6534.9063 | 6517.4298 | 6500 | 6476.7214 | 6453.5262 | 6430.414 | 6407.3846 | 6384.4377 | 6360.6897 | 6337.03 | 6313.4584 | 6289.9744 | 6266.5778 | 6241.2681 | 6216.0606 | 6190.9549 | 6165.9506 | 6141.0474 | 6113.884 | 6086.8408 | 6059.9172 | 6033.1128 | 6006.4268 | 5976.3715 | 5946.4665 | 5916.7112 | 5887.1048 | 5857.6465 | 5861.5414 | 5865.4389 | 5869.339 | 5873.2417 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | 5877.1469 | [6 empty] | 1450 | 1458 | 1466 | 1474 | 1481.3 | 1498 | 1515 | 1532 | 1549 | 1566 | 1582.3 | 1594 | 1606 | 1618 | 1630 | 1642 | 1654 | 1666 | 1678 | 1690 | 1702 | 1714 | 1726 | 1738 | 1750 | 1762 | 1774 | 1786 | 1798 | 1810 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | 1814.1 | [6 empty] | 3.7853 | 3.7853 | 3.7853 | 3.7853 | 3.7853 | 3.7644 | 3.7436 | 3.723 | 3.7024 | 3.682 | 3.6611 | 3.6403 | 3.6196 | 3.5991 | 3.5787 | 3.5579 | 3.5372 | 3.5166 | 3.4962 | 3.4759 | 3.455 | 3.4344 | 3.4138 | 3.3933 | 3.373 | 3.3522 | 3.3315 | 3.3109 | 3.2904 | 3.2701 | 3.2701 | 3.2701 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702 | 3.2702
426 | Howick |  |  | 2052 | 1325.7486 | 1315.936 | 1306.196 | 1296.528 | 1286.9317 | 1289.6078 | 1292.2896 | 1294.9769 | 1297.6698 | 1300.3682 | 1303.0965 | 1305.8305 | 1308.5703 | 1311.3158 | 1314.067 | 1316.5655 | 1319.0687 | 1321.5767 | 1324.0894 | 1326.6069 | 1328.8336 | 1331.064 | 1333.2982 | 1335.5361 | 1337.7777 | 1340.7735 | 1343.776 | 1346.7852 | 1349.8012 | 1352.8239 | 1355.6337 | 1358.4494 | 1361.271 | 1364.0984 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 | 1366.9317 |  | 4440 | 4407.1369 | 4374.5171 | 4342.1387 | 4310 | 4322.1237 | 4334.2814 | 4346.4734 | 4358.6996 | 4370.9603 | 4383.3252 | 4395.7252 | 4408.1602 | 4420.6304 | 4433.1359 | 4439.543 | 4445.9593 | 4452.385 | 4458.8199 | 4465.2641 | 4470.7318 | 4476.2062 | 4481.6873 | 4487.1751 | 4492.6696 | 4500.6546 | 4508.6538 | 4516.6673 | 4524.695 | 4532.7369 | 4542.0357 | 4551.3536 | 4560.6905 | 4570.0466 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | 4579.422 | [6 empty] | 734 | 739 | 744 | 749 | 753.8 | 763 | 772 | 781 | 790 | 799 | 809.8 | 816 | 823 | 830 | 837 | 844 | 851 | 858 | 865 | 872 | 879 | 886 | 893 | 900 | 907 | 914 | 921 | 928 | 935 | 942 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | 943 | [6 empty] | 3.3491 | 3.3491 | 3.3491 | 3.3491 | 3.3491 | 3.3515 | 3.354 | 3.3564 | 3.3589 | 3.3613 | 3.3638 | 3.3662 | 3.3687 | 3.3711 | 3.3736 | 3.3721 | 3.3705 | 3.369 | 3.3675 | 3.3659 | 3.3644 | 3.3629 | 3.3614 | 3.3598 | 3.3583 | 3.3568 | 3.3552 | 3.3537 | 3.3521 | 3.3506 | 3.3505 | 3.3504 | 3.3503 | 3.3502 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501 | 3.3501
427 | Otara - Papatoetoe |  |  | 2052 | 584.9137 | 577.6663 | 570.5087 | 563.4398 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 | 556.4585 |  | 1850 | 1827.0775 | 1804.439 | 1782.081 | 1760 | 1762.3408 | 1764.6848 | 1767.0318 | 1769.382 | 1771.7353 | 1774.0761 | 1776.4201 | 1778.7671 | 1781.1173 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | 1783.4706 | [6 empty] | 7022 | 7049 | 7076 | 7103 | 7128.9 | 7218 | 7307 | 7396 | 7485 | 7574 | 7660.6 | 7706 | 7751 | 7796 | 7841 | 7886 | 7931 | 7976 | 8021 | 8066 | 8111 | 8156 | 8201 | 8246 | 8291 | 8336 | 8381 | 8426 | 8471 | 8516 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | 8563.1 | [6 empty] | 3.1629 | 3.1629 | 3.1629 | 3.1629 | 3.1629 | 3.1671 | 3.1713 | 3.1755 | 3.1797 | 3.1839 | 3.1882 | 3.1924 | 3.1966 | 3.2008 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205 | 3.205
428 | Otara - Papatoetoe |  |  | 2052 | 1318.5057 | 1319.1374 | 1319.7693 | 1320.4016 | 1321.0341 | 1322.793 | 1324.5542 | 1326.3177 | 1328.0836 | 1329.8519 | 1331.645 | 1333.4405 | 1335.2385 | 1337.0389 | 1338.8417 | 1340.4995 | 1342.1592 | 1343.8211 | 1345.485 | 1347.151 | 1348.6371 | 1350.1249 | 1351.6143 | 1353.1054 | 1354.5982 | 1356.5984 | 1358.6016 | 1360.6077 | 1362.6169 | 1364.6289 | 1366.5048 | 1368.3833 | 1370.2643 | 1372.1479 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 | 1374.0341 |  | 5240 | 5242.4982 | 5244.9976 | 5247.4982 | 5250 | 5259.7519 | 5269.5219 | 5279.3101 | 5289.1164 | 5298.941 | 5308.8661 | 5318.8098 | 5328.7721 | 5338.7531 | 5348.7528 | 5352.0295 | 5355.3082 | 5358.5889 | 5361.8716 | 5365.1564 | 5367.7123 | 5370.2695 | 5372.8279 | 5375.3875 | 5377.9483 | 5382.4977 | 5387.0509 | 5391.608 | 5396.1689 | 5400.7337 | 5408.1232 | 5415.5229 | 5422.9327 | 5430.3526 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | 5437.7827 | [6 empty] | 160 | 164 | 168 | 172 | 175.8 | 178 | 180 | 182 | 184 | 186 | 189.4 | 191 | 193 | 195 | 197 | 199 | 201 | 203 | 205 | 207 | 209 | 211 | 213 | 215 | 217 | 219 | 221 | 223 | 225 | 227 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | 221.4 | [6 empty] | 3.9742 | 3.9742 | 3.9742 | 3.9742 | 3.9742 | 3.9762 | 3.9783 | 3.9804 | 3.9825 | 3.9846 | 3.9867 | 3.9888 | 3.9909 | 3.993 | 3.9951 | 3.9926 | 3.9901 | 3.9876 | 3.9851 | 3.9826 | 3.9801 | 3.9776 | 3.9751 | 3.9726 | 3.9701 | 3.9676 | 3.9651 | 3.9626 | 3.9602 | 3.9577 | 3.9576 | 3.9576 | 3.9576 | 3.9576 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575 | 3.9575
429 | Otara - Papatoetoe |  |  | 2052 | 449.1385 | 449.1385 | 449.1385 | 449.1385 | 449.1385 | 459.2538 | 469.5969 | 480.173 | 490.9872 | 502.0451 | 512.3971 | 522.9625 | 533.7458 | 544.7515 | 555.9841 | 565.5559 | 575.2925 | 585.1968 | 595.2715 | 605.5197 | 614.1157 | 622.8338 | 631.6756 | 640.6429 | 649.7375 | 661.2349 | 672.9357 | 684.8436 | 696.9622 | 709.2952 | 720.1279 | 731.126 | 742.2921 | 753.6287 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 | 765.1385 |  | 1860 | 1860 | 1860 | 1860 | 1860 | 1889.617 | 1919.7056 | 1950.2732 | 1981.3277 | 2012.8766 | 2041.2004 | 2069.9229 | 2099.0495 | 2128.5859 | 2158.538 | 2181.3902 | 2204.4844 | 2227.8231 | 2251.4088 | 2275.2443 | 2292.5209 | 2309.9286 | 2327.4686 | 2345.1417 | 2362.9491 | 2388.3073 | 2413.9377 | 2439.8432 | 2466.0267 | 2492.4911 | 2528.7911 | 2565.6198 | 2602.9848 | 2640.8939 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | 2679.3552 | [6 empty] | 1753 | 1777 | 1801 | 1825 | 1850.2 | 1870 | 1890 | 1910 | 1930 | 1950 | 1969.2 | 1983 | 1997 | 2011 | 2025 | 2039 | 2053 | 2067 | 2081 | 2095 | 2109 | 2123 | 2137 | 2151 | 2165 | 2179 | 2193 | 2207 | 2221 | 2235 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | 2252.2 | [6 empty] | 4.1413 | 4.1413 | 4.1413 | 4.1413 | 4.1413 | 4.1145 | 4.088 | 4.0616 | 4.0354 | 4.0094 | 3.9836 | 3.9581 | 3.9327 | 3.9074 | 3.8824 | 3.8571 | 3.8319 | 3.807 | 3.7822 | 3.7575 | 3.733 | 3.7087 | 3.6846 | 3.6606 | 3.6368 | 3.6119 | 3.5872 | 3.5626 | 3.5383 | 3.514 | 3.5116 | 3.5091 | 3.5067 | 3.5042 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018 | 3.5018
430 | Otara - Papatoetoe |  |  | 2052 | 884.9956 | 883.1305 | 881.2693 | 879.412 | 877.5587 | 881.9651 | 886.3936 | 890.8444 | 895.3175 | 899.813 | 904.3057 | 908.8207 | 913.3584 | 917.9186 | 922.5017 | 926.6343 | 930.7854 | 934.9552 | 939.1436 | 943.3508 | 947.0453 | 950.7543 | 954.4779 | 958.216 | 961.9688 | 966.8519 | 971.7598 | 976.6926 | 981.6505 | 986.6335 | 991.1765 | 995.7405 | 1000.3254 | 1004.9314 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 | 1009.5587 |  | 3570 | 3562.4762 | 3554.9684 | 3547.4763 | 3540 | 3557.3204 | 3574.7256 | 3592.2159 | 3609.7919 | 3627.4538 | 3645.0966 | 3662.8253 | 3680.6402 | 3698.5418 | 3716.5304 | 3728.8298 | 3741.17 | 3753.551 | 3765.9729 | 3778.436 | 3788.778 | 3799.1484 | 3809.5471 | 3819.9743 | 3830.43 | 3845.3413 | 3860.3105 | 3875.3381 | 3890.4241 | 3905.5688 | 3923.6225 | 3941.7596 | 3959.9806 | 3978.2857 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | 3996.6755 | [6 empty] | 538 | 542 | 546 | 550 | 554 | 560 | 566 | 572 | 578 | 584 | 590.1 | 594 | 598 | 602 | 606 | 610 | 614 | 618 | 622 | 626 | 630 | 634 | 638 | 642 | 646 | 650 | 654 | 658 | 662 | 666 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | 670.3 | [6 empty] | 4.0339 | 4.0339 | 4.0339 | 4.0339 | 4.0339 | 4.0334 | 4.0329 | 4.0324 | 4.0319 | 4.0313 | 4.0308 | 4.0303 | 4.0298 | 4.0293 | 4.0288 | 4.0241 | 4.0194 | 4.0147 | 4.01 | 4.0053 | 4.0006 | 3.9959 | 3.9912 | 3.9865 | 3.9819 | 3.9772 | 3.9725 | 3.9678 | 3.9631 | 3.9585 | 3.9586 | 3.9586 | 3.9587 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588 | 3.9588
431 | Otara - Papatoetoe |  |  | 2052 | 952.9801 | 955.6018 | 958.2307 | 960.8668 | 963.5102 | 965.2673 | 967.0277 | 968.7912 | 970.558 | 972.328 | 974.1193 | 975.914 | 977.7119 | 979.5132 | 981.3178 | 982.9741 | 984.6331 | 986.2949 | 987.9596 | 989.6271 | 991.112 | 992.5992 | 994.0887 | 995.5803 | 997.0743 | 999.0724 | 1001.0745 | 1003.0807 | 1005.0908 | 1007.105 | 1008.9791 | 1010.8566 | 1012.7376 | 1014.6222 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 | 1016.5102 |  | 3570 | 3579.9583 | 3589.9443 | 3599.9582 | 3610 | 3621.5272 | 3633.0912 | 3644.6922 | 3656.3301 | 3668.0053 | 3679.7522 | 3691.5368 | 3703.3591 | 3715.2193 | 3727.1174 | 3733.4921 | 3739.8777 | 3746.2743 | 3752.6817 | 3759.1001 | 3764.8157 | 3770.5399 | 3776.2728 | 3782.0144 | 3787.7648 | 3795.4553 | 3803.1614 | 3810.8832 | 3818.6206 | 3826.3738 | 3833.5868 | 3840.8133 | 3848.0535 | 3855.3073 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | 3862.5748 | [6 empty] | 225 | 227 | 229 | 231 | 233.9 | 236 | 238 | 240 | 242 | 244 | 246.3 | 248 | 250 | 252 | 254 | 256 | 258 | 260 | 262 | 264 | 266 | 268 | 270 | 272 | 274 | 276 | 278 | 280 | 282 | 284 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | 285.4 | [6 empty] | 3.7461 | 3.7463 | 3.7464 | 3.7466 | 3.7467 | 3.7518 | 3.757 | 3.7621 | 3.7672 | 3.7724 | 3.7775 | 3.7826 | 3.7878 | 3.7929 | 3.7981 | 3.7982 | 3.7982 | 3.7983 | 3.7984 | 3.7985 | 3.7986 | 3.7987 | 3.7987 | 3.7988 | 3.7989 | 3.799 | 3.7991 | 3.7992 | 3.7993 | 3.7994 | 3.7995 | 3.7996 | 3.7997 | 3.7997 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998 | 3.7998
432 | Otara - Papatoetoe |  |  | 2052 | 675.3005 | 676.4908 | 677.6832 | 678.8778 | 680.0744 | 682.7407 | 685.4175 | 688.1048 | 690.8026 | 693.511 | 696.2294 | 698.9584 | 701.6981 | 704.4486 | 707.2098 | 709.7002 | 712.1993 | 714.7073 | 717.224 | 719.7497 | 721.9701 | 724.1974 | 726.4315 | 728.6725 | 730.9205 | 733.8241 | 736.7393 | 739.666 | 742.6044 | 745.5545 | 748.239 | 750.9333 | 753.6373 | 756.3509 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 | 759.0744 |  | 2940 | 2944.9873 | 2949.9831 | 2954.9873 | 2960 | 2973.4171 | 2986.895 | 3000.4339 | 3014.0343 | 3027.6963 | 3041.4204 | 3055.2066 | 3069.0554 | 3082.967 | 3096.9416 | 3106.1806 | 3115.4473 | 3124.7415 | 3134.0635 | 3143.4133 | 3151.4699 | 3159.5472 | 3167.6451 | 3175.7638 | 3183.9034 | 3194.7923 | 3205.7184 | 3216.6819 | 3227.683 | 3238.7216 | 3249.9871 | 3261.2917 | 3272.6357 | 3284.0191 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | 3295.4421 | [6 empty] | 177 | 179 | 181 | 183 | 183.4 | 186 | 188 | 190 | 192 | 194 | 196.5 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | 223.7 | [6 empty] | 4.3536 | 4.3533 | 4.353 | 4.3528 | 4.3525 | 4.3551 | 4.3578 | 4.3604 | 4.3631 | 4.3658 | 4.3684 | 4.3711 | 4.3738 | 4.3764 | 4.3791 | 4.3768 | 4.3744 | 4.3721 | 4.3697 | 4.3674 | 4.3651 | 4.3628 | 4.3606 | 4.3583 | 4.356 | 4.3536 | 4.3512 | 4.3488 | 4.3464 | 4.344 | 4.3435 | 4.343 | 4.3425 | 4.3419 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414 | 4.3414
433 | Otara - Papatoetoe |  |  | 2052 | 93.0408 | 91.7917 | 90.5593 | 89.3435 | 88.144 | 89.3691 | 90.6113 | 91.8707 | 93.1477 | 94.4424 | 95.6931 | 96.9603 | 98.2444 | 99.5454 | 100.8637 | 101.9975 | 103.1441 | 104.3036 | 105.4761 | 106.6618 | 107.6667 | 108.681 | 109.7049 | 110.7385 | 111.7817 | 113.1281 | 114.4908 | 115.8698 | 117.2654 | 118.6779 | 119.9438 | 121.2232 | 122.5163 | 123.8232 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 | 125.144 |  | 190 | 187.4491 | 184.9324 | 182.4495 | 180 | 182.8881 | 185.8225 | 188.8039 | 191.8333 | 194.9112 | 197.8906 | 200.9155 | 203.9866 | 207.1047 | 210.2705 | 212.7418 | 215.2421 | 217.7718 | 220.3312 | 222.9207 | 225.1114 | 227.3235 | 229.5574 | 231.8133 | 234.0913 | 237.026 | 239.9975 | 243.0062 | 246.0526 | 249.1372 | 251.8969 | 254.6872 | 257.5083 | 260.3608 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | 263.2448 | [6 empty] | 5914 | 5969 | 6024 | 6079 | 6133.3 | 6197 | 6260 | 6323 | 6386 | 6449 | 6513.8 | 6537 | 6561 | 6585 | 6609 | 6633 | 6657 | 6681 | 6705 | 6729 | 6753 | 6777 | 6801 | 6825 | 6849 | 6873 | 6897 | 6921 | 6945 | 6969 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | 6985.5 | [6 empty] | 2.0421 | 2.0421 | 2.0421 | 2.0421 | 2.0421 | 2.0464 | 2.0508 | 2.0551 | 2.0595 | 2.0638 | 2.068 | 2.0721 | 2.0763 | 2.0805 | 2.0847 | 2.0858 | 2.0868 | 2.0879 | 2.0889 | 2.09 | 2.0908 | 2.0917 | 2.0925 | 2.0933 | 2.0942 | 2.0952 | 2.0962 | 2.0972 | 2.0983 | 2.0993 | 2.1001 | 2.101 | 2.1018 | 2.1027 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035 | 2.1035
434 | Otara - Papatoetoe |  |  | 2052 | 1010.9887 | 1006.7899 | 1002.6085 | 998.4445 | 994.2978 | 995.1362 | 995.9753 | 996.815 | 997.6555 | 998.4967 | 999.3514 | 1000.2069 | 1001.0631 | 1001.92 | 1002.7776 | 1003.592 | 1004.4071 | 1005.2228 | 1006.0392 | 1006.8562 | 1007.5998 | 1008.344 | 1009.0887 | 1009.834 | 1010.5798 | 1011.5809 | 1012.583 | 1013.5861 | 1014.5901 | 1015.5952 | 1016.534 | 1017.4736 | 1018.4142 | 1019.3555 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 | 1020.2978 |  | 4240 | 4222.3906 | 4204.8543 | 4187.3909 | 4170 | 4164.5558 | 4159.1186 | 4153.6886 | 4148.2656 | 4142.8498 | 4137.3974 | 4131.9521 | 4126.5141 | 4121.0832 | 4115.6594 | 4107.4488 | 4099.2547 | 4091.0768 | 4082.9153 | 4074.7701 | 4066.1793 | 4057.6067 | 4049.0521 | 4040.5156 | 4031.9971 | 4024.3445 | 4016.7064 | 4009.0828 | 4001.4737 | 3993.8791 | 3997.5718 | 4001.2679 | 4004.9675 | 4008.6704 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | 4012.3768 | [6 empty] | 526 | 532 | 538 | 544 | 549 | 555 | 561 | 567 | 573 | 579 | 585.5 | 590 | 594 | 598 | 602 | 606 | 610 | 614 | 618 | 622 | 626 | 630 | 634 | 638 | 642 | 646 | 650 | 654 | 658 | 662 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | 672.3 | [6 empty] | 4.1939 | 4.1939 | 4.1939 | 4.1939 | 4.1939 | 4.1849 | 4.1759 | 4.167 | 4.158 | 4.1491 | 4.1401 | 4.1311 | 4.1221 | 4.1132 | 4.1043 | 4.0927 | 4.0813 | 4.0698 | 4.0584 | 4.047 | 4.0355 | 4.024 | 4.0126 | 4.0012 | 3.9898 | 3.9783 | 3.9668 | 3.9553 | 3.9439 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326 | 3.9326
435 | Otara - Papatoetoe |  |  | 2052 | 714.019 | 715.2608 | 716.5046 | 717.7507 | 718.9989 | 720.7539 | 722.5131 | 724.2767 | 726.0445 | 727.8167 | 729.6058 | 731.3994 | 733.1973 | 734.9997 | 736.8065 | 738.4609 | 740.119 | 741.7809 | 743.4464 | 745.1157 | 746.5993 | 748.0857 | 749.5752 | 751.0676 | 752.5629 | 754.5585 | 756.5593 | 758.5655 | 760.5769 | 762.5937 | 764.4655 | 766.342 | 768.223 | 770.1086 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 | 771.9989 |  | 2900 | 2904.9871 | 2909.9828 | 2914.9871 | 2920 | 2930.8808 | 2941.8021 | 2952.7641 | 2963.7669 | 2974.8108 | 2985.9237 | 2997.0781 | 3008.2741 | 3019.512 | 3030.7919 | 3037.5248 | 3044.2726 | 3051.0354 | 3057.8133 | 3064.6062 | 3070.6437 | 3076.693 | 3082.7542 | 3088.8274 | 3094.9125 | 3103.0338 | 3111.1764 | 3119.3404 | 3127.5258 | 3135.7327 | 3143.3504 | 3150.9867 | 3158.6415 | 3166.3149 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | 3174.0069 | [6 empty] | 104 | 105 | 106 | 107 | 108.7 | 110 | 111 | 112 | 113 | 114 | 115.7 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | 133.1 | [6 empty] | 4.0615 | 4.0614 | 4.0614 | 4.0613 | 4.0612 | 4.0664 | 4.0716 | 4.0768 | 4.0821 | 4.0873 | 4.0925 | 4.0977 | 4.103 | 4.1082 | 4.1134 | 4.1133 | 4.1132 | 4.1131 | 4.113 | 4.1129 | 4.1128 | 4.1128 | 4.1127 | 4.1126 | 4.1125 | 4.1124 | 4.1123 | 4.1122 | 4.112 | 4.1119 | 4.1118 | 4.1117 | 4.1116 | 4.1115 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114 | 4.1114
436 | Otara - Papatoetoe |  |  | 2052 | 896.617 | 897.232 | 897.8474 | 898.4632 | 899.0794 | 900.5859 | 902.095 | 903.6066 | 905.1208 | 906.6375 | 908.1734 | 909.7119 | 911.253 | 912.7967 | 914.343 | 915.7177 | 917.0943 | 918.4731 | 919.8539 | 921.2368 | 922.4438 | 923.6524 | 924.8626 | 926.0743 | 927.2877 | 928.912 | 930.5391 | 932.1691 | 933.802 | 935.4377 | 936.961 | 938.4869 | 940.0152 | 941.5461 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 | 943.0794 |  | 3660 | 3662.4974 | 3664.9966 | 3667.4974 | 3670 | 3670.1479 | 3670.2959 | 3670.4438 | 3670.5918 | 3670.7397 | 3670.9056 | 3671.0715 | 3671.2374 | 3671.4033 | 3671.5693 | 3668.3594 | 3665.1523 | 3661.9481 | 3658.7466 | 3655.548 | 3651.547 | 3647.5504 | 3643.5582 | 3639.5703 | 3635.5868 | 3633.0945 | 3630.6038 | 3628.1148 | 3625.6276 | 3623.142 | 3629.0121 | 3634.8916 | 3640.7807 | 3646.6793 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | 3652.5875 | [6 empty] | 169 | 170 | 171 | 172 | 173.2 | 175 | 177 | 179 | 181 | 183 | 185.3 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | 204.6 | [6 empty] | 4.082 | 4.082 | 4.082 | 4.082 | 4.082 | 4.0753 | 4.0686 | 4.062 | 4.0554 | 4.0487 | 4.0421 | 4.0354 | 4.0288 | 4.0221 | 4.0155 | 4.006 | 3.9965 | 3.987 | 3.9775 | 3.9681 | 3.9586 | 3.9491 | 3.9396 | 3.9301 | 3.9207 | 3.9111 | 3.9016 | 3.8921 | 3.8827 | 3.8732 | 3.8732 | 3.8731 | 3.8731 | 3.8731 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 3.873
437 | Otara - Papatoetoe |  |  | 2052 | 1127.293 | 1136.1644 | 1145.1057 | 1154.1173 | 1163.1998 | 1171.3032 | 1179.4631 | 1187.6799 | 1195.9538 | 1204.2854 | 1212.5487 | 1220.8687 | 1229.2458 | 1237.6804 | 1246.1728 | 1253.7295 | 1261.3321 | 1268.9807 | 1276.6758 | 1284.4175 | 1291.1492 | 1297.9162 | 1304.7187 | 1311.5568 | 1318.4308 | 1327.4686 | 1336.5685 | 1345.7307 | 1354.9557 | 1364.2439 | 1372.7289 | 1381.2667 | 1389.8575 | 1398.5018 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 | 1407.1998 |  | 4080 | 4112.1187 | 4144.4903 | 4177.1167 | 4210 | 4226.8786 | 4243.8249 | 4260.8391 | 4277.9215 | 4295.0724 | 4311.6522 | 4328.296 | 4345.004 | 4361.7765 | 4378.6137 | 4389.8649 | 4401.1451 | 4412.4542 | 4423.7924 | 4435.1597 | 4442.6433 | 4450.1396 | 4457.6485 | 4465.1701 | 4472.7044 | 4487.1605 | 4501.6633 | 4516.213 | 4530.8098 | 4545.4537 | 4573.7353 | 4602.193 | 4630.8277 | 4659.6405 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | 4688.6327 | [6 empty] | 356 | 358 | 360 | 362 | 365.8 | 369 | 372 | 375 | 378 | 381 | 386.4 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396 | 397 | 398 | 399 | 400 | 401 | 402 | 403 | 404 | 405 | 406 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | 410.7 | [6 empty] | 3.6193 | 3.6193 | 3.6193 | 3.6193 | 3.6193 | 3.6087 | 3.5981 | 3.5875 | 3.577 | 3.5665 | 3.5559 | 3.5453 | 3.5347 | 3.5242 | 3.5136 | 3.5014 | 3.4893 | 3.4772 | 3.4651 | 3.4531 | 3.4408 | 3.4287 | 3.4166 | 3.4045 | 3.3924 | 3.3802 | 3.3681 | 3.356 | 3.3439 | 3.3318 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319
438 | Howick |  |  | 2052 | 1466.435 | 1462.3369 | 1458.2502 | 1454.175 | 1450.1111 | 1455.3636 | 1460.6351 | 1465.9256 | 1471.2354 | 1476.5644 | 1481.9193 | 1487.2936 | 1492.6875 | 1498.1009 | 1503.5339 | 1508.4236 | 1513.3291 | 1518.2507 | 1523.1882 | 1528.1418 | 1532.4922 | 1536.855 | 1541.2302 | 1545.6178 | 1550.018 | 1555.8667 | 1561.7376 | 1567.6306 | 1573.5458 | 1579.4834 | 1584.9707 | 1590.477 | 1596.0025 | 1601.5472 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 | 1607.1111 |  | 5390 | 5374.937 | 5359.916 | 5344.9371 | 5330 | 5330.1855 | 5330.3709 | 5330.5564 | 5330.7419 | 5330.9273 | 5330.787 | 5330.6466 | 5330.5062 | 5330.3659 | 5330.2255 | 5326.002 | 5321.7819 | 5317.5651 | 5313.3516 | 5309.1415 | 5302.3374 | 5295.5421 | 5288.7555 | 5281.9776 | 5275.2083 | 5272.8816 | 5270.5559 | 5268.2312 | 5265.9075 | 5263.5848 | 5281.9665 | 5300.4124 | 5318.9227 | 5337.4977 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | 5356.1375 | [6 empty] | 1870 | 1891 | 1912 | 1933 | 1953.9 | 1977 | 2000 | 2023 | 2046 | 2069 | 2092.9 | 2115 | 2137 | 2159 | 2181 | 2203 | 2225 | 2247 | 2269 | 2291 | 2313 | 2335 | 2357 | 2379 | 2401 | 2423 | 2445 | 2467 | 2489 | 2511 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | 2527.9 | [6 empty] | 3.6756 | 3.6756 | 3.6756 | 3.6756 | 3.6756 | 3.6624 | 3.6494 | 3.6363 | 3.6233 | 3.6104 | 3.5972 | 3.5841 | 3.5711 | 3.5581 | 3.5451 | 3.5308 | 3.5166 | 3.5024 | 3.4883 | 3.4742 | 3.4599 | 3.4457 | 3.4315 | 3.4174 | 3.4033 | 3.389 | 3.3748 | 3.3606 | 3.3465 | 3.3325 | 3.3325 | 3.3326 | 3.3327 | 3.3327 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328 | 3.3328
439 | Howick |  |  | 2052 | 555.512 | 563.2895 | 571.1758 | 579.1725 | 587.2812 | 601.1398 | 615.3255 | 629.8459 | 644.709 | 659.9228 | 674.1112 | 688.6047 | 703.4099 | 718.5333 | 733.9819 | 747.0211 | 760.2919 | 773.7985 | 787.545 | 801.5357 | 813.1999 | 825.0338 | 837.0399 | 849.2207 | 861.5788 | 877.2549 | 893.2163 | 909.4681 | 926.0156 | 942.8641 | 957.6749 | 972.7183 | 987.998 | 1003.5177 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 | 1019.2812 |  | 2130 | 2159.3863 | 2189.1779 | 2219.3806 | 2250 | 2294.7071 | 2340.3026 | 2386.804 | 2434.2294 | 2482.5972 | 2526.7155 | 2571.6178 | 2617.3181 | 2663.8305 | 2711.1695 | 2748.0712 | 2785.4752 | 2823.3882 | 2861.8173 | 2900.7694 | 2930.8663 | 2961.2754 | 2992 | 3023.0433 | 3054.4088 | 3096.8361 | 3139.8527 | 3183.4668 | 3227.6867 | 3272.5209 | 3323.4436 | 3375.1588 | 3427.6787 | 3481.0158 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | 3535.1829 | [6 empty] | 769 | 778 | 787 | 796 | 803.3 | 814 | 825 | 836 | 847 | 858 | 869.7 | 879 | 888 | 897 | 906 | 915 | 924 | 933 | 942 | 951 | 960 | 969 | 978 | 987 | 996 | 1005 | 1014 | 1023 | 1032 | 1041 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | 1046.5 | [6 empty] | 3.8343 | 3.8335 | 3.8328 | 3.832 | 3.8312 | 3.8173 | 3.8034 | 3.7895 | 3.7757 | 3.762 | 3.7482 | 3.7345 | 3.7209 | 3.7073 | 3.6938 | 3.6787 | 3.6637 | 3.6487 | 3.6338 | 3.619 | 3.6041 | 3.5893 | 3.5745 | 3.5598 | 3.5451 | 3.5301 | 3.5152 | 3.5004 | 3.4856 | 3.4708 | 3.4703 | 3.4698 | 3.4693 | 3.4688 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683 | 3.4683
440 | Howick |  |  | 2052 | 986.4581 | 1033.1671 | 1082.0878 | 1133.3248 | 1186.9879 | 1189.9454 | 1192.9103 | 1195.8826 | 1198.8622 | 1201.8493 | 1204.8644 | 1207.8871 | 1210.9173 | 1213.9552 | 1217.0007 | 1219.9945 | 1222.9957 | 1226.0042 | 1229.0202 | 1232.0435 | 1234.8434 | 1237.6496 | 1240.4621 | 1243.2811 | 1246.1065 | 1250.2936 | 1254.4947 | 1258.71 | 1262.9394 | 1267.183 | 1271.3169 | 1275.4644 | 1279.6253 | 1283.7998 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 | 1287.9879 |  | 4000 | 4188.7193 | 4386.3424 | 4593.2894 | 4810 | 4802.4788 | 4794.9693 | 4787.4716 | 4779.9856 | 4772.5113 | 4764.7389 | 4756.9791 | 4749.232 | 4741.4975 | 4733.7756 | 4724.4884 | 4715.2194 | 4705.9686 | 4696.7359 | 4687.5213 | 4676.9981 | 4666.4985 | 4656.0224 | 4645.5699 | 4635.1409 | 4629.2321 | 4623.3309 | 4617.4371 | 4611.5509 | 4605.6723 | 4620.5717 | 4635.5194 | 4650.5154 | 4665.56 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | 4680.6532 | [6 empty] | 1056 | 1065 | 1074 | 1083 | 1091.7 | 1106 | 1120 | 1134 | 1148 | 1162 | 1176.8 | 1186 | 1196 | 1206 | 1216 | 1226 | 1236 | 1246 | 1256 | 1266 | 1276 | 1286 | 1296 | 1306 | 1316 | 1326 | 1336 | 1346 | 1356 | 1366 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | 1369.8 | [6 empty] | 4.0549 | 4.0543 | 4.0536 | 4.0529 | 4.0523 | 4.0359 | 4.0196 | 4.0033 | 3.9871 | 3.971 | 3.9546 | 3.9383 | 3.922 | 3.9058 | 3.8897 | 3.8725 | 3.8555 | 3.8385 | 3.8215 | 3.8047 | 3.7875 | 3.7705 | 3.7535 | 3.7365 | 3.7197 | 3.7025 | 3.6854 | 3.6684 | 3.6514 | 3.6346 | 3.6345 | 3.6344 | 3.6343 | 3.6342 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341 | 3.6341
441 | Howick |  |  | 2052 | 1439.2422 | 1545.4877 | 1659.5763 | 1782.0869 | 1913.6413 | 1921.0577 | 1928.5029 | 1935.9768 | 1943.4798 | 1951.0118 | 1958.573 | 1966.1634 | 1973.7832 | 1981.4326 | 1989.1116 | 1996.0543 | 2003.0212 | 2010.0124 | 2017.028 | 2024.0681 | 2030.267 | 2036.485 | 2042.7219 | 2048.978 | 2055.2533 | 2063.5051 | 2071.79 | 2080.1082 | 2088.4598 | 2096.845 | 2104.5474 | 2112.2782 | 2120.0374 | 2127.825 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 | 2135.6413 |  | 4920 | 5274.7535 | 5655.0862 | 6062.8426 | 6500 | 6506.167 | 6512.3399 | 6518.5187 | 6524.7033 | 6530.8938 | 6536.8167 | 6542.7449 | 6548.6785 | 6554.6175 | 6560.5619 | 6560.8552 | 6561.1486 | 6561.4419 | 6561.7353 | 6562.0286 | 6559.192 | 6556.3566 | 6553.5224 | 6550.6894 | 6547.8576 | 6550.7211 | 6553.5858 | 6556.4517 | 6559.3189 | 6562.1874 | 6585.8311 | 6609.56 | 6633.3744 | 6657.2746 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | 6681.261 | [6 empty] | 1022 | 1029 | 1036 | 1043 | 1050.4 | 1062 | 1074 | 1086 | 1098 | 1110 | 1119.5 | 1129 | 1138 | 1147 | 1156 | 1165 | 1174 | 1183 | 1192 | 1201 | 1210 | 1219 | 1228 | 1237 | 1246 | 1255 | 1264 | 1273 | 1282 | 1291 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | 1308 | [6 empty] | 3.4185 | 3.413 | 3.4075 | 3.4021 | 3.3967 | 3.3868 | 3.3769 | 3.367 | 3.3572 | 3.3474 | 3.3375 | 3.3277 | 3.3178 | 3.308 | 3.2982 | 3.2869 | 3.2756 | 3.2644 | 3.2532 | 3.242 | 3.2307 | 3.2194 | 3.2082 | 3.1971 | 3.1859 | 3.1746 | 3.1632 | 3.152 | 3.1407 | 3.1296 | 3.1293 | 3.1291 | 3.1289 | 3.1287 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285 | 3.1285
442 | Howick |  |  | 2052 | 948.1662 | 999.0242 | 1052.6101 | 1109.0703 | 1168.5589 | 1179.6278 | 1190.8015 | 1202.081 | 1213.4674 | 1224.9616 | 1236.2522 | 1247.6469 | 1259.1465 | 1270.7522 | 1282.4649 | 1292.7677 | 1303.1532 | 1313.6222 | 1324.1753 | 1334.8131 | 1343.9802 | 1353.2102 | 1362.5036 | 1371.8608 | 1381.2823 | 1393.5794 | 1405.986 | 1418.503 | 1431.1315 | 1443.8724 | 1455.4234 | 1467.0668 | 1478.8034 | 1490.6338 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 | 1502.5589 |  | 3780 | 3983.0461 | 4196.9989 | 4422.4445 | 4660 | 4685.2693 | 4710.6756 | 4736.2197 | 4761.9024 | 4787.7243 | 4812.0718 | 4836.5432 | 4861.1391 | 4885.86 | 4910.7067 | 4927.7447 | 4944.8418 | 4961.9982 | 4979.2142 | 4996.4899 | 5007.4943 | 5018.5229 | 5029.5759 | 5040.6532 | 5051.7548 | 5072.5612 | 5093.4533 | 5114.4315 | 5135.496 | 5156.6473 | 5197.9317 | 5239.5466 | 5281.4947 | 5323.7786 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | 5366.4011 | [6 empty] | 717 | 720 | 723 | 726 | 728.7 | 737 | 745 | 753 | 761 | 769 | 777.2 | 782 | 787 | 792 | 797 | 802 | 807 | 812 | 817 | 822 | 827 | 832 | 837 | 842 | 847 | 852 | 857 | 862 | 867 | 872 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | 872.1 | [6 empty] | 3.9866 | 3.9869 | 3.9872 | 3.9875 | 3.9878 | 3.9718 | 3.9559 | 3.94 | 3.9242 | 3.9085 | 3.8925 | 3.8765 | 3.8607 | 3.8449 | 3.8291 | 3.8118 | 3.7945 | 3.7773 | 3.7602 | 3.7432 | 3.7259 | 3.7086 | 3.6914 | 3.6743 | 3.6573 | 3.64 | 3.6227 | 3.6055 | 3.5884 | 3.5714 | 3.5714 | 3.5714 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715 | 3.5715
443 | Manurewa |  |  | 2052 | 2193.5485 | 2225.0654 | 2257.0351 | 2289.4642 | 2322.3592 | 2338.7622 | 2355.281 | 2371.9165 | 2388.6695 | 2405.5408 | 2422.2675 | 2439.1105 | 2456.0707 | 2473.1487 | 2490.3456 | 2505.6424 | 2521.0333 | 2536.5186 | 2552.0991 | 2567.7753 | 2581.4025 | 2595.102 | 2608.8742 | 2622.7195 | 2636.6383 | 2654.9332 | 2673.3551 | 2691.9048 | 2710.5832 | 2729.3912 | 2746.5672 | 2763.8514 | 2781.2443 | 2798.7467 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 | 2816.3592 |  | 7600 | 7710.085 | 7821.7645 | 7935.0617 | 8050 | 8098.5057 | 8147.3037 | 8196.3957 | 8245.7835 | 8295.4689 | 8344.4872 | 8393.7952 | 8443.3946 | 8493.287 | 8543.4742 | 8579.6854 | 8616.0501 | 8652.5689 | 8689.2425 | 8726.0715 | 8755.5719 | 8785.1721 | 8814.8723 | 8844.673 | 8874.5743 | 8918.9449 | 8963.5374 | 9008.3528 | 9053.3922 | 9098.6568 | 9156.2494 | 9214.2065 | 9272.5304 | 9331.2235 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | 9390.2881 | [6 empty] | 1114 | 1119 | 1124 | 1129 | 1134.2 | 1147 | 1160 | 1173 | 1186 | 1199 | 1210.6 | 1219 | 1228 | 1237 | 1246 | 1255 | 1264 | 1273 | 1282 | 1291 | 1300 | 1309 | 1318 | 1327 | 1336 | 1345 | 1354 | 1363 | 1372 | 1381 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | 1385.3 | [6 empty] | 3.4647 | 3.4651 | 3.4655 | 3.4659 | 3.4663 | 3.4627 | 3.4592 | 3.4556 | 3.452 | 3.4485 | 3.4449 | 3.4413 | 3.4378 | 3.4342 | 3.4306 | 3.4241 | 3.4177 | 3.4112 | 3.4047 | 3.3983 | 3.3918 | 3.3853 | 3.3788 | 3.3723 | 3.3659 | 3.3594 | 3.3529 | 3.3465 | 3.34 | 3.3336 | 3.3337 | 3.3338 | 3.334 | 3.3341 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342 | 3.3342
444 | Howick |  |  | 2052 | 356.8081 | 463.5628 | 602.258 | 782.4498 | 1016.5539 | 1074.9513 | 1136.7033 | 1202.0028 | 1271.0535 | 1344.0709 | 1405.0605 | 1468.8178 | 1535.4681 | 1605.1428 | 1677.9791 | 1735.0889 | 1794.1425 | 1855.206 | 1918.3477 | 1983.6385 | 2035.3309 | 2088.3703 | 2142.792 | 2198.6318 | 2255.9268 | 2324.9251 | 2396.0337 | 2469.3173 | 2544.8422 | 2622.6771 | 2688.1055 | 2755.1661 | 2823.8998 | 2894.3481 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 | 2966.5539 |  | 1490 | 1939.7718 | 2525.3119 | 3287.6032 | 4280 | 4511.4796 | 4755.4786 | 5012.6741 | 5283.7797 | 5569.5478 | 5803.3163 | 6046.8966 | 6300.7006 | 6565.1575 | 6840.7143 | 7042.9817 | 7251.2298 | 7465.6354 | 7686.3806 | 7913.6529 | 8083.88 | 8257.7688 | 8435.398 | 8616.8482 | 8802.2014 | 9030.3505 | 9264.4131 | 9504.5425 | 9750.8959 | 10003.6348 | 10253.676 | 10509.9671 | 10772.6642 | 11041.9273 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | 11317.9208 | [6 empty] | 691 | 694 | 697 | 700 | 701.8 | 711 | 720 | 729 | 738 | 747 | 755.2 | 761 | 766 | 771 | 776 | 781 | 786 | 791 | 796 | 801 | 806 | 811 | 816 | 821 | 826 | 831 | 836 | 841 | 846 | 851 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | 861.9 | [6 empty] | 4.1759 | 4.1845 | 4.1931 | 4.2017 | 4.2103 | 4.1969 | 4.1836 | 4.1703 | 4.157 | 4.1438 | 4.1303 | 4.1168 | 4.1034 | 4.0901 | 4.0768 | 4.0591 | 4.0416 | 4.0242 | 4.0068 | 3.9895 | 3.9718 | 3.9542 | 3.9366 | 3.9192 | 3.9018 | 3.8841 | 3.8666 | 3.8491 | 3.8316 | 3.8143 | 3.8145 | 3.8146 | 3.8148 | 3.815 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152 | 3.8152
445 | Howick |  |  | 2052 | 513.0186 | 525.107 | 537.4803 | 550.1452 | 563.1085 | 564.7782 | 566.4527 | 568.1323 | 569.8168 | 571.5064 | 573.2086 | 574.9158 | 576.6281 | 578.3456 | 580.0681 | 581.6272 | 583.1905 | 584.758 | 586.3296 | 587.9055 | 589.2953 | 590.6884 | 592.0847 | 593.4843 | 594.8873 | 596.7563 | 598.6312 | 600.5119 | 602.3986 | 604.2912 | 606.0444 | 607.8028 | 609.5662 | 611.3348 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 | 613.1085 |  | 1740 | 1778.6903 | 1818.2409 | 1858.671 | 1900 | 1895.9727 | 1891.9539 | 1887.9436 | 1883.9418 | 1879.9485 | 1875.7432 | 1871.5474 | 1867.3609 | 1863.1837 | 1859.016 | 1856.0659 | 1853.1206 | 1850.1799 | 1847.2439 | 1844.3125 | 1840.7953 | 1837.2848 | 1833.781 | 1830.2839 | 1826.7935 | 1824.2438 | 1821.6976 | 1819.155 | 1816.6159 | 1814.0804 | 1819.0515 | 1824.0361 | 1829.0344 | 1834.0464 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | 1839.0722 | [6 empty] | 658 | 660 | 662 | 664 | 667.7 | 675 | 682 | 689 | 696 | 703 | 708.5 | 710 | 711 | 712 | 713 | 714 | 715 | 716 | 717 | 718 | 719 | 720 | 721 | 722 | 723 | 724 | 725 | 726 | 727 | 728 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | 735.6 | [6 empty] | 3.3917 | 3.3873 | 3.3829 | 3.3785 | 3.3741 | 3.357 | 3.34 | 3.3231 | 3.3062 | 3.2895 | 3.2724 | 3.2553 | 3.2384 | 3.2216 | 3.2048 | 3.1912 | 3.1776 | 3.164 | 3.1505 | 3.1371 | 3.1237 | 3.1104 | 3.0972 | 3.084 | 3.0708 | 3.0569 | 3.0431 | 3.0293 | 3.0156 | 3.002 | 3.0015 | 3.001 | 3.0006 | 3.0001 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996 | 2.9996
446 | Howick |  |  | 2052 | 1781.7933 | 1803.3751 | 1825.2183 | 1847.326 | 1869.7015 | 1886.2034 | 1902.8509 | 1919.6454 | 1936.588 | 1953.6802 | 1970.5112 | 1987.4872 | 2004.6095 | 2021.8792 | 2039.2977 | 2054.737 | 2070.2932 | 2085.9671 | 2101.7598 | 2117.6719 | 2131.4549 | 2145.3275 | 2159.2904 | 2173.3442 | 2187.4894 | 2205.9818 | 2224.6306 | 2243.4369 | 2262.4023 | 2281.528 | 2298.8962 | 2316.3967 | 2334.0304 | 2351.7983 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 | 2369.7015 |  | 6740 | 6821.0271 | 6903.0283 | 6986.0153 | 7070 | 7107.9372 | 7146.078 | 7184.4234 | 7222.9746 | 7261.7326 | 7298.7647 | 7335.9857 | 7373.3964 | 7410.998 | 7448.7913 | 7475.3797 | 7502.063 | 7528.8416 | 7555.7157 | 7582.6858 | 7601.1829 | 7619.7252 | 7638.3126 | 7656.9454 | 7675.6237 | 7708.4852 | 7741.4875 | 7774.631 | 7807.9164 | 7841.3444 | 7900.6523 | 7960.4089 | 8020.6174 | 8081.2813 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | 8142.404 | [6 empty] | 1546 | 1553 | 1560 | 1567 | 1574.3 | 1592 | 1610 | 1628 | 1646 | 1664 | 1683.3 | 1695 | 1706 | 1717 | 1728 | 1739 | 1750 | 1761 | 1772 | 1783 | 1794 | 1805 | 1816 | 1827 | 1838 | 1849 | 1860 | 1871 | 1882 | 1893 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | 1911.8 | [6 empty] | 3.7827 | 3.7824 | 3.782 | 3.7817 | 3.7814 | 3.7684 | 3.7555 | 3.7426 | 3.7297 | 3.717 | 3.704 | 3.6911 | 3.6782 | 3.6654 | 3.6526 | 3.6381 | 3.6237 | 3.6093 | 3.5949 | 3.5807 | 3.5662 | 3.5518 | 3.5374 | 3.5231 | 3.5089 | 3.4944 | 3.4799 | 3.4655 | 3.4512 | 3.4369 | 3.4367 | 3.4365 | 3.4364 | 3.4362 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436 | 3.436
447 | Franklin |  |  | 2052 | 329.2474 | 330.9163 | 332.5936 | 334.2794 | 335.9737 | 337.6368 | 339.308 | 340.9876 | 342.6754 | 344.3716 | 346.0672 | 347.7711 | 349.4834 | 351.2042 | 352.9334 | 354.4871 | 356.0477 | 357.6151 | 359.1895 | 360.7708 | 362.1565 | 363.5474 | 364.9438 | 366.3455 | 367.7525 | 369.6144 | 371.4856 | 373.3663 | 375.2566 | 377.1564 | 378.9036 | 380.6589 | 382.4223 | 384.1939 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 | 385.9737 |  | 980 | 984.9622 | 989.9495 | 994.9621 | 1000 | 1003.1191 | 1006.248 | 1009.3866 | 1012.535 | 1015.6932 | 1018.8191 | 1021.9546 | 1025.0997 | 1028.2546 | 1031.4191 | 1033.816 | 1036.2184 | 1038.6265 | 1041.0401 | 1043.4594 | 1045.3173 | 1047.1785 | 1049.0431 | 1050.9109 | 1052.7821 | 1055.8508 | 1058.9284 | 1062.015 | 1065.1105 | 1068.2151 | 1073.1548 | 1078.1174 | 1083.1029 | 1088.1114 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | 1093.1432 | [6 empty] | 208 | 209 | 210 | 211 | 210.1 | 211 | 212 | 213 | 214 | 215 | 217.8 | 217 | 216 | 215 | 214 | 213 | 212 | 211 | 210 | 209 | 208 | 207 | 206 | 205 | 204 | 203 | 202 | 201 | 200 | 199 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | [6 empty] | 2.9765 | 2.9765 | 2.9765 | 2.9764 | 2.9764 | 2.971 | 2.9656 | 2.9602 | 2.9548 | 2.9494 | 2.944 | 2.9386 | 2.9332 | 2.9278 | 2.9224 | 2.9164 | 2.9103 | 2.9043 | 2.8983 | 2.8923 | 2.8864 | 2.8804 | 2.8745 | 2.8686 | 2.8627 | 2.8566 | 2.8505 | 2.8444 | 2.8384 | 2.8323 | 2.8323 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322 | 2.8322
448 | Franklin |  |  | 2052 | 236.4779 | 238.2067 | 239.9481 | 241.7022 | 243.4692 | 243.8016 | 244.1345 | 244.4678 | 244.8016 | 245.1358 | 245.4683 | 245.8011 | 246.1345 | 246.4683 | 246.8025 | 247.1349 | 247.4678 | 247.8011 | 248.1349 | 248.4692 | 248.8016 | 249.1345 | 249.4678 | 249.8016 | 250.1358 | 250.4683 | 250.8012 | 251.1345 | 251.4683 | 251.8025 | 252.1349 | 252.4678 | 252.8012 | 253.1349 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 | 253.4692 |  | 720 | 724.9487 | 729.9315 | 734.9485 | 740 | 738.4922 | 736.9875 | 735.4858 | 733.9872 | 732.4917 | 730.9493 | 729.4102 | 727.8744 | 726.3418 | 724.8124 | 723.5739 | 722.3376 | 721.1033 | 719.8712 | 718.6412 | 717.4122 | 716.1852 | 714.9603 | 713.7376 | 712.5169 | 711.1924 | 709.8705 | 708.5509 | 707.2339 | 705.9192 | 706.8513 | 707.7845 | 708.719 | 709.6547 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | 710.5917 | [6 empty] | 212 | 212 | 212 | 212 | 212.9 | 214 | 215 | 216 | 217 | 218 | 221.8 | 221 | 220 | 219 | 218 | 217 | 216 | 215 | 214 | 213 | 212 | 211 | 210 | 209 | 208 | 207 | 206 | 205 | 204 | 203 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | 204 | [6 empty] | 3.0447 | 3.0434 | 3.042 | 3.0407 | 3.0394 | 3.0291 | 3.0188 | 3.0085 | 2.9983 | 2.9881 | 2.9778 | 2.9675 | 2.9572 | 2.947 | 2.9368 | 2.9278 | 2.9189 | 2.91 | 2.9011 | 2.8923 | 2.8835 | 2.8747 | 2.8659 | 2.8572 | 2.8485 | 2.8395 | 2.8304 | 2.8214 | 2.8124 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035 | 2.8035
449 | Franklin |  |  | 2052 | 2190.2305 | 2280.0393 | 2373.5306 | 2470.8555 | 2572.1712 | 2600.5927 | 2629.3283 | 2658.3814 | 2687.7556 | 2717.4543 | 2746.4524 | 2775.76 | 2805.3803 | 2835.3167 | 2865.5726 | 2892.2217 | 2919.1187 | 2946.2659 | 2973.6655 | 3001.3199 | 3025.1421 | 3049.1534 | 3073.3553 | 3097.7493 | 3122.3369 | 3154.1976 | 3186.3834 | 3218.8976 | 3251.7437 | 3284.9248 | 3314.8248 | 3344.997 | 3375.4437 | 3406.1676 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 | 3437.1712 |  | 6480 | 6745.7061 | 7022.3073 | 7310.2502 | 7610 | 7655.0004 | 7700.2668 | 7745.801 | 7791.6044 | 7837.6786 | 7880.0244 | 7922.599 | 7965.4037 | 8008.4396 | 8051.708 | 8091.2349 | 8130.9559 | 8170.8719 | 8210.9838 | 8251.2926 | 8280.4553 | 8309.721 | 8339.0902 | 8368.5632 | 8398.1404 | 8444.8123 | 8491.7435 | 8538.9356 | 8586.39 | 8634.1081 | 8712.6969 | 8792.0011 | 8872.0271 | 8952.7816 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | 9034.271 | [6 empty] | 1558 | 1564 | 1570 | 1576 | 1583.7 | 1595 | 1606 | 1617 | 1628 | 1639 | 1651 | 1643 | 1635 | 1627 | 1619 | 1611 | 1603 | 1595 | 1587 | 1579 | 1571 | 1563 | 1555 | 1547 | 1539 | 1531 | 1523 | 1515 | 1507 | 1499 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | 1495.9 | [6 empty] | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9586 | 2.9436 | 2.9286 | 2.9137 | 2.8989 | 2.8842 | 2.8692 | 2.8542 | 2.8393 | 2.8245 | 2.8098 | 2.7976 | 2.7854 | 2.7733 | 2.7612 | 2.7492 | 2.7372 | 2.7253 | 2.7134 | 2.7015 | 2.6897 | 2.6773 | 2.665 | 2.6528 | 2.6405 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284 | 2.6284
450 | Franklin |  |  | 2052 | 895.794 | 903.9957 | 912.2724 | 920.6249 | 929.0538 | 938.1131 | 947.2607 | 956.4975 | 965.8243 | 975.2421 | 984.4833 | 993.8119 | 1003.229 | 1012.7353 | 1022.3317 | 1028.1676 | 1034.0367 | 1039.9394 | 1045.8757 | 1051.846 | 1055.5435 | 1059.254 | 1062.9775 | 1066.7142 | 1070.464 | 1072.1764 | 1073.8917 | 1075.6096 | 1077.3304 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 | 1079.0538 |  | 2440 | 2462.1953 | 2484.5925 | 2507.1935 | 2530 | 2543.267 | 2556.6036 | 2570.0102 | 2583.487 | 2597.0346 | 2609.6862 | 2622.3994 | 2635.1746 | 2648.012 | 2660.9119 | 2665.8494 | 2670.7961 | 2675.752 | 2680.717 | 2685.6913 | 2684.8275 | 2683.9639 | 2683.1007 | 2682.2377 | 2681.375 | 2674.9157 | 2668.472 | 2662.0438 | 2655.631 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | 2649.2338 | [6 empty] | 433 | 435 | 437 | 439 | 442.4 | 445 | 448 | 451 | 454 | 457 | 458 | 456 | 454 | 452 | 450 | 448 | 446 | 444 | 442 | 440 | 438 | 436 | 434 | 432 | 430 | 428 | 426 | 424 | 422 | 420 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | [6 empty] | 2.7238 | 2.7237 | 2.7235 | 2.7234 | 2.7232 | 2.711 | 2.6989 | 2.6869 | 2.6749 | 2.663 | 2.6508 | 2.6387 | 2.6267 | 2.6147 | 2.6028 | 2.5928 | 2.5829 | 2.573 | 2.5631 | 2.5533 | 2.5435 | 2.5338 | 2.5241 | 2.5145 | 2.5049 | 2.4948 | 2.4849 | 2.4749 | 2.465 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551 | 2.4551
451 | Franklin |  |  | 2052 | 1633.9438 | 1648.2743 | 1662.7306 | 1677.3136 | 1692.0246 | 1701.9841 | 1712.0022 | 1722.0793 | 1732.2157 | 1742.4118 | 1752.5668 | 1762.7811 | 1773.0548 | 1783.3884 | 1793.7823 | 1806.8335 | 1819.9797 | 1833.2216 | 1846.5598 | 1859.995 | 1873.7534 | 1887.6137 | 1901.5764 | 1915.6424 | 1929.8125 | 1944.1198 | 1958.5333 | 1973.0536 | 1987.6815 | 2002.4179 | 2013.8089 | 2025.2647 | 2036.7857 | 2048.3722 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 | 2060.0246 |  | 4150 | 4187.0022 | 4224.3343 | 4261.9992 | 4300 | 4304.8733 | 4309.7522 | 4314.6366 | 4319.5265 | 4324.4219 | 4328.5597 | 4332.7014 | 4336.847 | 4340.9966 | 4345.1502 | 4358.9902 | 4372.8743 | 4386.8026 | 4400.7753 | 4414.7925 | 4429.3375 | 4443.9304 | 4458.5714 | 4473.2607 | 4487.9983 | 4501.8793 | 4515.8032 | 4529.7702 | 4543.7804 | 4557.8339 | 4584.1544 | 4610.627 | 4637.2524 | 4664.0315 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | 4690.9654 | [6 empty] | 1340 | 1343 | 1346 | 1349 | 1353.6 | 1369 | 1384 | 1399 | 1414 | 1429 | 1443.4 | 1448 | 1452 | 1456 | 1460 | 1464 | 1468 | 1472 | 1476 | 1480 | 1484 | 1488 | 1492 | 1496 | 1500 | 1504 | 1508 | 1512 | 1516 | 1520 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | 1525.4 | [6 empty] | 2.5399 | 2.5402 | 2.5406 | 2.541 | 2.5413 | 2.5293 | 2.5174 | 2.5055 | 2.4936 | 2.4819 | 2.4698 | 2.4579 | 2.446 | 2.4341 | 2.4223 | 2.4125 | 2.4027 | 2.3929 | 2.3832 | 2.3736 | 2.3639 | 2.3543 | 2.3447 | 2.3351 | 2.3256 | 2.3156 | 2.3057 | 2.2958 | 2.286 | 2.2762 | 2.2764 | 2.2766 | 2.2768 | 2.2769 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771 | 2.2771
452 | Mangere - Otahuhu |  |  | 2052 | 672.8762 | 686.8095 | 701.0314 | 715.5477 | 730.3646 | 747.2054 | 764.4345 | 782.0609 | 800.0937 | 818.5423 | 835.7804 | 853.3816 | 871.3535 | 889.7038 | 908.4406 | 924.3632 | 940.5648 | 957.0504 | 973.8249 | 990.8935 | 1005.1835 | 1019.6797 | 1034.3849 | 1049.3022 | 1064.4346 | 1083.5466 | 1103.0018 | 1122.8063 | 1142.9664 | 1163.4885 | 1181.4975 | 1199.7853 | 1218.3562 | 1237.2144 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 | 1256.3646 |  | 2450 | 2498.5384 | 2548.0385 | 2598.5192 | 2650 | 2704.8582 | 2760.8519 | 2818.0049 | 2876.3409 | 2935.8846 | 2991.2161 | 3047.5904 | 3105.0272 | 3163.5465 | 3223.1687 | 3270.6799 | 3318.8914 | 3367.8136 | 3417.4569 | 3467.832 | 3508.5594 | 3549.7652 | 3591.4549 | 3633.6342 | 3676.3089 | 3732.0643 | 3788.6653 | 3846.1247 | 3904.4556 | 3963.6711 | 4023.3835 | 4083.9954 | 4145.5205 | 4207.9725 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | 4271.3653 | [6 empty] | 112 | 112 | 112 | 112 | 112.5 | 114 | 115 | 116 | 117 | 118 | 120.3 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | [6 empty] | 3.6411 | 3.6379 | 3.6347 | 3.6315 | 3.6283 | 3.62 | 3.6116 | 3.6033 | 3.595 | 3.5867 | 3.5789 | 3.5712 | 3.5635 | 3.5557 | 3.548 | 3.5383 | 3.5286 | 3.519 | 3.5093 | 3.4997 | 3.4905 | 3.4813 | 3.4721 | 3.4629 | 3.4538 | 3.4443 | 3.4349 | 3.4255 | 3.4161 | 3.4067 | 3.4053 | 3.4039 | 3.4026 | 3.4012 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998 | 3.3998
453 | Mangere - Otahuhu |  |  | 2052 | 1482.9014 | 1493.6797 | 1504.5364 | 1515.4721 | 1526.4872 | 1543.7288 | 1561.1651 | 1578.7984 | 1596.6309 | 1614.6648 | 1632.2569 | 1650.0407 | 1668.0183 | 1686.1917 | 1704.5632 | 1720.7436 | 1737.0777 | 1753.5668 | 1770.2124 | 1787.016 | 1801.4879 | 1816.077 | 1830.7843 | 1845.6107 | 1860.5571 | 1879.959 | 1899.5632 | 1919.3719 | 1939.3871 | 1959.611 | 1977.8438 | 1996.2462 | 2014.8198 | 2033.5663 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 | 2052.4872 |  | 4460 | 4492.1507 | 4524.5331 | 4557.149 | 4590 | 4647.5313 | 4705.7838 | 4764.7664 | 4824.4883 | 4884.9587 | 4944.2326 | 5004.2257 | 5064.9468 | 5126.4047 | 5188.6083 | 5237.5155 | 5286.8837 | 5336.7172 | 5387.0205 | 5437.7979 | 5481.5398 | 5525.6336 | 5570.082 | 5614.888 | 5660.0544 | 5718.6989 | 5777.9509 | 5837.8169 | 5898.3031 | 5959.4161 | 6014.5256 | 6070.1447 | 6126.2781 | 6182.9307 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | 6240.1071 | [6 empty] | 770 | 775 | 780 | 785 | 788.7 | 799 | 809 | 819 | 829 | 839 | 848 | 854 | 860 | 866 | 872 | 878 | 884 | 890 | 896 | 902 | 908 | 914 | 920 | 926 | 932 | 938 | 944 | 950 | 956 | 962 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | 960.3 | [6 empty] | 3.0076 | 3.0074 | 3.0073 | 3.0071 | 3.0069 | 3.0106 | 3.0143 | 3.018 | 3.0217 | 3.0254 | 3.0291 | 3.0328 | 3.0365 | 3.0402 | 3.044 | 3.0438 | 3.0436 | 3.0433 | 3.0431 | 3.0429 | 3.0428 | 3.0426 | 3.0425 | 3.0423 | 3.0421 | 3.0419 | 3.0417 | 3.0415 | 3.0413 | 3.0411 | 3.041 | 3.0408 | 3.0406 | 3.0404 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403 | 3.0403
454 | Mangere - Otahuhu |  |  | 2052 | 973.4011 | 980.4288 | 987.5073 | 994.6369 | 1001.818 | 1006.3124 | 1010.8269 | 1015.3616 | 1019.9167 | 1024.4923 | 1029.0744 | 1033.6771 | 1038.3004 | 1042.9443 | 1047.609 | 1051.8389 | 1056.0858 | 1060.35 | 1064.6313 | 1068.9299 | 1072.7196 | 1076.5228 | 1080.3394 | 1084.1696 | 1088.0134 | 1093.1062 | 1098.223 | 1103.3636 | 1108.5283 | 1113.7172 | 1118.4962 | 1123.2957 | 1128.1157 | 1132.9565 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 | 1137.818 |  | 3140 | 3162.2621 | 3184.6821 | 3207.261 | 3230 | 3248.4566 | 3267.0186 | 3285.6867 | 3304.4615 | 3323.3436 | 3342.2701 | 3361.3044 | 3380.4471 | 3399.6988 | 3419.0602 | 3432.6364 | 3446.2665 | 3459.9507 | 3473.6893 | 3487.4824 | 3499.6456 | 3511.8513 | 3524.0995 | 3536.3904 | 3548.7242 | 3565.0705 | 3581.492 | 3597.9892 | 3614.5624 | 3631.212 | 3646.5505 | 3661.9538 | 3677.4221 | 3692.9558 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | 3708.5551 | [6 empty] | 425 | 433 | 441 | 449 | 456.4 | 463 | 469 | 475 | 481 | 487 | 493.6 | 499 | 504 | 509 | 514 | 519 | 524 | 529 | 534 | 539 | 544 | 549 | 554 | 559 | 564 | 569 | 574 | 579 | 584 | 589 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | 599.3 | [6 empty] | 3.2258 | 3.2254 | 3.225 | 3.2246 | 3.2241 | 3.2281 | 3.232 | 3.236 | 3.2399 | 3.2439 | 3.2478 | 3.2518 | 3.2558 | 3.2597 | 3.2637 | 3.2635 | 3.2632 | 3.263 | 3.2628 | 3.2626 | 3.2624 | 3.2622 | 3.262 | 3.2618 | 3.2617 | 3.2614 | 3.2612 | 3.2609 | 3.2607 | 3.2604 | 3.2602 | 3.26 | 3.2598 | 3.2596 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594 | 3.2594
455 | Mangere - Otahuhu |  |  | 2052 | 332.5725 | 356.8571 | 382.915 | 410.8756 | 440.8779 | 457.2513 | 474.2327 | 491.8448 | 510.111 | 529.0556 | 545.9246 | 563.3316 | 581.2936 | 599.8282 | 618.9539 | 634.6301 | 650.7032 | 667.1835 | 684.0811 | 701.4068 | 715.5343 | 729.9464 | 744.6488 | 759.6473 | 774.9479 | 793.8171 | 813.1458 | 832.9451 | 853.2265 | 874.0018 | 891.8343 | 910.0307 | 928.5984 | 947.5449 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 | 966.8779 |  | 1260 | 1341.7038 | 1428.7057 | 1521.3492 | 1620 | 1673.701 | 1729.1822 | 1786.5025 | 1845.7228 | 1906.9063 | 1961.7625 | 2018.1968 | 2076.2545 | 2135.9824 | 2197.4285 | 2245.72 | 2295.0728 | 2345.5101 | 2397.0559 | 2449.7345 | 2491.9977 | 2534.9899 | 2578.7239 | 2623.2124 | 2668.4684 | 2725.3174 | 2783.3775 | 2842.6746 | 2903.2349 | 2965.0854 | 3022.5471 | 3081.1225 | 3140.833 | 3201.7006 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | 3263.7478 | [6 empty] | 2980 | 3002 | 3024 | 3046 | 3069.5 | 3108 | 3147 | 3186 | 3225 | 3264 | 3301.9 | 3326 | 3350 | 3374 | 3398 | 3422 | 3446 | 3470 | 3494 | 3518 | 3542 | 3566 | 3590 | 3614 | 3638 | 3662 | 3686 | 3710 | 3734 | 3758 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | 3786.9 | [6 empty] | 3.7886 | 3.7598 | 3.7311 | 3.7027 | 3.6745 | 3.6604 | 3.6463 | 3.6322 | 3.6183 | 3.6044 | 3.5935 | 3.5826 | 3.5718 | 3.561 | 3.5502 | 3.5386 | 3.5271 | 3.5155 | 3.5041 | 3.4926 | 3.4827 | 3.4728 | 3.463 | 3.4532 | 3.4434 | 3.4332 | 3.423 | 3.4128 | 3.4027 | 3.3925 | 3.3891 | 3.3857 | 3.3823 | 3.3789 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756 | 3.3756
456 | Mangere - Otahuhu |  |  | 2052 | 554.4757 | 567.3715 | 580.5673 | 594.0699 | 607.8866 | 613.5737 | 619.3141 | 625.1081 | 630.9563 | 636.8593 | 642.6602 | 648.514 | 654.4211 | 660.3821 | 666.3973 | 671.7349 | 677.1153 | 682.5388 | 688.0057 | 693.5164 | 698.2908 | 703.0982 | 707.9386 | 712.8124 | 717.7198 | 724.0449 | 730.4257 | 736.8628 | 743.3566 | 749.9076 | 755.8098 | 761.7584 | 767.7538 | 773.7964 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 | 779.8866 |  | 1780 | 1818.7183 | 1858.2788 | 1898.6998 | 1940 | 1953.3096 | 1966.7106 | 1980.2034 | 1993.7889 | 2007.4675 | 2020.764 | 2034.1485 | 2047.6216 | 2061.184 | 2074.8362 | 2085.1232 | 2095.4612 | 2105.8504 | 2116.2912 | 2126.7837 | 2135.0119 | 2143.2719 | 2151.5639 | 2159.8879 | 2168.2442 | 2180.5067 | 2192.8386 | 2205.2402 | 2217.7119 | 2230.2542 | 2246.8847 | 2263.6392 | 2280.5186 | 2297.524 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | 2314.6561 | [6 empty] | 2365 | 2401 | 2437 | 2473 | 2509.5 | 2541 | 2573 | 2605 | 2637 | 2669 | 2700.4 | 2733 | 2766 | 2799 | 2832 | 2865 | 2898 | 2931 | 2964 | 2997 | 3030 | 3063 | 3096 | 3129 | 3162 | 3195 | 3228 | 3261 | 3294 | 3327 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | 3355.3 | [6 empty] | 3.2102 | 3.2055 | 3.2008 | 3.1961 | 3.1914 | 3.1835 | 3.1756 | 3.1678 | 3.1599 | 3.1521 | 3.1444 | 3.1366 | 3.1289 | 3.1212 | 3.1135 | 3.1041 | 3.0947 | 3.0853 | 3.076 | 3.0667 | 3.0575 | 3.0483 | 3.0392 | 3.0301 | 3.021 | 3.0116 | 3.0021 | 2.9927 | 2.9834 | 2.974 | 2.9728 | 2.9716 | 2.9704 | 2.9692 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679 | 2.9679
457 | Mangere - Otahuhu |  |  | 2052 | 821.2786 | 822.8509 | 824.4262 | 826.0045 | 827.5858 | 836.2215 | 844.9472 | 853.7641 | 862.6729 | 871.6746 | 880.4846 | 889.3836 | 898.3725 | 907.4523 | 916.6238 | 924.7247 | 932.8971 | 941.1417 | 949.4592 | 957.8502 | 965.094 | 972.3925 | 979.7461 | 987.1555 | 994.6208 | 1004.3346 | 1014.1432 | 1024.0477 | 1034.0489 | 1044.1478 | 1053.2744 | 1062.4809 | 1071.7678 | 1081.1359 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 | 1090.5858 |  | 2910 | 2914.9872 | 2919.9829 | 2924.9872 | 2930 | 2960.9677 | 2992.2626 | 3023.8883 | 3055.8483 | 3088.1461 | 3120.0339 | 3152.251 | 3184.8007 | 3217.6866 | 3250.912 | 3276.983 | 3303.2631 | 3329.7539 | 3356.4571 | 3383.3746 | 3406.6804 | 3430.1468 | 3453.7748 | 3477.5655 | 3501.5202 | 3532.7835 | 3564.3258 | 3596.1499 | 3628.258 | 3660.6528 | 3690.0195 | 3719.6216 | 3749.4613 | 3779.5404 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | 3809.8607 | [6 empty] | 1039 | 1048 | 1057 | 1066 | 1074.2 | 1087 | 1100 | 1113 | 1126 | 1139 | 1153.5 | 1163 | 1172 | 1181 | 1190 | 1199 | 1208 | 1217 | 1226 | 1235 | 1244 | 1253 | 1262 | 1271 | 1280 | 1289 | 1298 | 1307 | 1316 | 1325 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | 1343 | [6 empty] | 3.5433 | 3.5425 | 3.5418 | 3.5411 | 3.5404 | 3.5409 | 3.5414 | 3.5418 | 3.5423 | 3.5428 | 3.5435 | 3.5443 | 3.5451 | 3.5458 | 3.5466 | 3.5437 | 3.5409 | 3.538 | 3.5351 | 3.5323 | 3.5299 | 3.5275 | 3.5252 | 3.5228 | 3.5205 | 3.5175 | 3.5146 | 3.5117 | 3.5088 | 3.5059 | 3.5034 | 3.5009 | 3.4984 | 3.4959 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934 | 3.4934
458 | Mangere - Otahuhu |  |  | 2052 | 1659.7303 | 1674.0888 | 1688.5716 | 1703.1796 | 1717.914 | 1724.084 | 1730.2761 | 1736.4904 | 1742.7271 | 1748.9862 | 1755.2764 | 1761.5894 | 1767.925 | 1774.2834 | 1780.6646 | 1786.3953 | 1792.1445 | 1797.9121 | 1803.6984 | 1809.5032 | 1814.5944 | 1819.7 | 1824.8199 | 1829.9542 | 1835.1029 | 1841.9478 | 1848.8183 | 1855.7143 | 1862.6361 | 1869.5837 | 1876.0055 | 1882.4494 | 1888.9154 | 1895.4036 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 | 1901.914 |  | 4930 | 4971.9612 | 5014.2796 | 5056.9582 | 5100 | 5097.002 | 5094.0058 | 5091.0114 | 5088.0187 | 5085.0278 | 5081.6169 | 5078.2083 | 5074.802 | 5071.3979 | 5067.9961 | 5061.4655 | 5054.9434 | 5048.4296 | 5041.9242 | 5035.4272 | 5026.4256 | 5017.4401 | 5008.4707 | 4999.5173 | 4990.5799 | 4985.6003 | 4980.6256 | 4975.6558 | 4970.6911 | 4965.7312 | 4982.5128 | 4999.3511 | 5016.2463 | 5033.1986 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | 5050.2081 | [6 empty] | 957 | 965 | 973 | 981 | 988 | 999 | 1010 | 1021 | 1032 | 1043 | 1053.6 | 1062 | 1070 | 1078 | 1086 | 1094 | 1102 | 1110 | 1118 | 1126 | 1134 | 1142 | 1150 | 1158 | 1166 | 1174 | 1182 | 1190 | 1198 | 1206 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | 1221.9 | [6 empty] | 2.9704 | 2.97 | 2.9695 | 2.9691 | 2.9687 | 2.9564 | 2.944 | 2.9318 | 2.9196 | 2.9074 | 2.8951 | 2.8827 | 2.8705 | 2.8583 | 2.8461 | 2.8333 | 2.8206 | 2.8079 | 2.7953 | 2.7828 | 2.77 | 2.7573 | 2.7446 | 2.732 | 2.7195 | 2.7067 | 2.694 | 2.6813 | 2.6686 | 2.6561 | 2.6559 | 2.6558 | 2.6556 | 2.6555 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553 | 2.6553
459 | Mangere - Otahuhu |  |  | 2052 | 717.3578 | 722.9249 | 728.5352 | 734.189 | 739.8867 | 754.4206 | 769.2399 | 784.3504 | 799.7576 | 815.4675 | 830.3272 | 845.4576 | 860.8637 | 876.5506 | 892.5233 | 906.2047 | 920.0959 | 934.2 | 948.5203 | 963.0601 | 975.3115 | 987.7188 | 1000.284 | 1013.009 | 1025.8958 | 1042.2903 | 1058.9468 | 1075.8695 | 1093.0626 | 1110.5305 | 1125.9666 | 1141.6173 | 1157.4855 | 1173.5743 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 | 1189.8867 |  | 2000 | 2014.8341 | 2029.7783 | 2044.8333 | 2060 | 2090.8905 | 2122.2442 | 2154.0681 | 2186.3691 | 2219.1546 | 2249.3458 | 2279.9477 | 2310.9659 | 2342.4062 | 2374.2741 | 2399.2484 | 2424.4853 | 2449.9876 | 2475.7583 | 2501.8 | 2521.6602 | 2541.6781 | 2561.8549 | 2582.1919 | 2602.6903 | 2631.2889 | 2660.2018 | 2689.4324 | 2718.9841 | 2748.8606 | 2785.8577 | 2823.3528 | 2861.3525 | 2899.8636 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | 2938.8931 | [6 empty] | 313 | 318 | 323 | 328 | 331.4 | 336 | 341 | 346 | 351 | 356 | 359.6 | 363 | 367 | 371 | 375 | 379 | 383 | 387 | 391 | 395 | 399 | 403 | 407 | 411 | 415 | 419 | 423 | 427 | 431 | 435 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | 436.8 | [6 empty] | 2.788 | 2.7871 | 2.7861 | 2.7852 | 2.7842 | 2.7715 | 2.7589 | 2.7463 | 2.7338 | 2.7213 | 2.709 | 2.6967 | 2.6845 | 2.6723 | 2.6602 | 2.6476 | 2.635 | 2.6226 | 2.6101 | 2.5978 | 2.5855 | 2.5733 | 2.5611 | 2.549 | 2.537 | 2.5245 | 2.5121 | 2.4998 | 2.4875 | 2.4753 | 2.4742 | 2.4731 | 2.472 | 2.471 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699 | 2.4699
460 | Mangere - Otahuhu |  |  | 2052 | 98.5832 | 98.5832 | 98.5832 | 98.5832 | 98.5832 | 98.6671 | 98.751 | 98.835 | 98.919 | 99.0031 | 99.0886 | 99.1741 | 99.2598 | 99.3454 | 99.4312 | 99.5254 | 99.6197 | 99.714 | 99.8085 | 99.903 | 99.9959 | 100.089 | 100.182 | 100.2752 | 100.3685 | 100.4936 | 100.6188 | 100.7442 | 100.8697 | 100.9954 | 101.1127 | 101.2301 | 101.3477 | 101.4654 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 | 101.5832 |  | 320 | 320 | 320 | 320 | 320 | 319.4112 | 318.8234 | 318.2368 | 317.6512 | 317.0667 | 316.4755 | 315.8854 | 315.2965 | 314.7086 | 314.1218 | 313.4155 | 312.7107 | 312.0076 | 311.306 | 310.606 | 309.8867 | 309.169 | 308.453 | 307.7387 | 307.026 | 306.3879 | 305.7511 | 305.1157 | 304.4816 | 303.8488 | 304.1746 | 304.5007 | 304.8272 | 305.154 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | 305.4812 | [6 empty] | 1069 | 1075 | 1081 | 1087 | 1093.1 | 1107 | 1121 | 1135 | 1149 | 1163 | 1177.8 | 1185 | 1193 | 1201 | 1209 | 1217 | 1225 | 1233 | 1241 | 1249 | 1257 | 1265 | 1273 | 1281 | 1289 | 1297 | 1305 | 1313 | 1321 | 1329 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | 1331.1 | [6 empty] | 3.246 | 3.246 | 3.246 | 3.246 | 3.246 | 3.2373 | 3.2286 | 3.2199 | 3.2112 | 3.2026 | 3.1939 | 3.1852 | 3.1765 | 3.1678 | 3.1592 | 3.1491 | 3.139 | 3.129 | 3.119 | 3.1091 | 3.099 | 3.0889 | 3.0789 | 3.0689 | 3.059 | 3.0488 | 3.0387 | 3.0286 | 3.0186 | 3.0085 | 3.0083 | 3.008 | 3.0077 | 3.0075 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072 | 3.0072
461 | Mangere - Otahuhu | AHP | Mangere | 2060 | 996.9642 | 1023.7782 | 1051.3133 | 1079.589 | 1108.6253 | 1153.0626 | 1199.2811 | 1247.3522 | 1297.3501 | 1349.3522 | 1395.2121 | 1442.6306 | 1491.6607 | 1542.3572 | 1594.7767 | 1618.4407 | 1642.4558 | 1666.8272 | 1691.5603 | 1716.6604 | 1726.6529 | 1736.7036 | 1746.8128 | 1756.9808 | 1767.2081 | 1776.9688 | 1786.7835 | 1796.6524 | 1806.5758 | 1816.5541 | 1823.9171 | 1831.3099 | 1838.7328 | 1846.1857 | 1853.6688 | 1824.0634 | 1794.9307 | 1766.2634 | 1738.0539 | 1710.295 | 1682.9794 | 1656.1 | 1629.65 | 1629.65 | 1629.65 | 1629.65 | 1629.65 | 1629.65 | 1629.65 | 1629.65 | 1629.65 | 1629.65 | 1629.65 | 1629.65 | 1629.65 | 1629.65 | 1629.65 | 1629.65 | 1629.65 | 1629.65 | 1629.65 | 1629.65 | 1629.65 |  | 3430 | 3518.9775 | 3610.2631 | 3703.9168 | 3800 | 3931.0366 | 4066.5918 | 4206.8214 | 4351.8866 | 4501.9541 | 4630.3649 | 4762.4385 | 4898.2792 | 5037.9946 | 5181.6951 | 5231.8254 | 5282.4408 | 5333.5457 | 5385.1451 | 5437.2437 | 5441.4621 | 5445.6838 | 5449.9087 | 5454.1369 | 5458.3684 | 5460.3281 | 5462.2885 | 5464.2496 | 5466.2115 | 5468.174 | 5489.8598 | 5511.6317 | 5533.4898 | 5555.4347 | 5577.4666 | 5485.5373 | 5395.1232 | 5306.1993 | 5218.7411 | 5132.7244 | 5048.1254 | 4964.9209 | 4883.0877 | 4883.0877 | 4883.0877 | 4883.0877 | 4883.0877 | 4883.0877 | 4883.0877 | 4883.0877 | 4883.0877 | 4883.0877 | 4883.0877 | 4883.0877 | 4883.0877 | 4883.0877 | 4883.0877 | 4883.0877 | 4883.0877 | 4883.0877 | 4883.0877 | 4883.0877 | 4883.0877 | [6 empty] | 309 | 311 | 313 | 315 | 318.5 | 322 | 326 | 330 | 334 | 338 | 339.8 | 342 | 345 | 348 | 351 | 354 | 357 | 360 | 363 | 366 | 369 | 372 | 375 | 378 | 381 | 384 | 387 | 390 | 393 | 396 | 393.2 | 397.0674 | 400.9729 | 404.9167 | 408.8994 | 412.9212 | 416.9826 | 421.0839 | 425.2256 | 425.2256 | 425.2256 | 425.2256 | 425.2256 | 425.2256 | 425.2256 | 425.2256 | 425.2256 | 425.2256 | 425.2256 | 425.2256 | 425.2256 | 425.2256 | 425.2256 | 425.2256 | 425.2256 | 425.2256 | 425.2256 | 425.2256 | 425.2256 | [6 empty] | 3.4404 | 3.4372 | 3.4341 | 3.4309 | 3.4277 | 3.4092 | 3.3909 | 3.3726 | 3.3544 | 3.3364 | 3.3188 | 3.3012 | 3.2838 | 3.2664 | 3.2492 | 3.2326 | 3.2162 | 3.1998 | 3.1835 | 3.1673 | 3.1515 | 3.1356 | 3.1199 | 3.1043 | 3.0887 | 3.0728 | 3.0571 | 3.0414 | 3.0257 | 3.0102 | 3.0099 | 3.0097 | 3.0094 | 3.0091 | 3.0089 | 3.0073 | 3.0058 | 3.0042 | 3.0026 | 3.0011 | 2.9995 | 2.998 | 2.9964 | 2.9964 | 2.9964 | 2.9964 | 2.9964 | 2.9964 | 2.9964 | 2.9964 | 2.9964 | 2.9964 | 2.9964 | 2.9964 | 2.9964 | 2.9964 | 2.9964 | 2.9964 | 2.9964 | 2.9964 | 2.9964 | 2.9964 | 2.9964
462 | Mangere - Otahuhu |  |  | 2052 | 36.3812 | 38.4181 | 40.569 | 42.8403 | 45.2388 | 46.9517 | 48.7293 | 50.5743 | 52.4892 | 54.4765 | 56.2419 | 58.0645 | 59.9462 | 61.8888 | 63.8944 | 65.5613 | 67.2718 | 69.0268 | 70.8277 | 72.6755 | 74.1933 | 75.7428 | 77.3246 | 78.9395 | 80.5881 | 82.6151 | 84.6931 | 86.8233 | 89.0071 | 91.2458 | 93.1622 | 95.1189 | 97.1166 | 99.1563 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 | 101.2388 |  | 120 | 124.7148 | 129.6148 | 134.7074 | 140 | 144.0889 | 148.2973 | 152.6286 | 157.0864 | 161.6743 | 165.9183 | 170.2737 | 174.7434 | 179.3305 | 184.0379 | 187.8912 | 191.8252 | 195.8415 | 199.942 | 204.1282 | 207.6269 | 211.1856 | 214.8052 | 218.4869 | 222.2317 | 226.9075 | 231.6817 | 236.5563 | 241.5336 | 246.6155 | 251.0274 | 255.5183 | 260.0894 | 264.7424 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | 269.4786 | [6 empty] | 5452 | 5472 | 5492 | 5512 | 5533.6 | 5600 | 5666 | 5732 | 5798 | 5864 | 5931 | 5965 | 5999 | 6033 | 6067 | 6101 | 6135 | 6169 | 6203 | 6237 | 6271 | 6305 | 6339 | 6373 | 6407 | 6441 | 6475 | 6509 | 6543 | 6577 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | 6602.6 | [6 empty] | 3.2984 | 3.2463 | 3.1949 | 3.1444 | 3.0947 | 3.0689 | 3.0433 | 3.0179 | 2.9927 | 2.9678 | 2.9501 | 2.9325 | 2.915 | 2.8976 | 2.8803 | 2.8659 | 2.8515 | 2.8372 | 2.8229 | 2.8088 | 2.7985 | 2.7882 | 2.778 | 2.7678 | 2.7576 | 2.7466 | 2.7355 | 2.7246 | 2.7136 | 2.7028 | 2.6945 | 2.6863 | 2.6781 | 2.67 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618 | 2.6618
463 | Mangere - Otahuhu | AHP | Mangere | 2060 | 1102.1393 | 1110.5255 | 1118.9755 | 1127.4898 | 1136.0689 | 1180.586 | 1226.8476 | 1274.9219 | 1324.88 | 1376.7958 | 1422.7139 | 1470.1636 | 1519.1957 | 1569.8631 | 1622.2203 | 1645.8958 | 1669.9169 | 1694.2885 | 1719.0158 | 1744.104 | 1754.0983 | 1764.1499 | 1774.2592 | 1784.4263 | 1794.6517 | 1799.2919 | 1803.9441 | 1808.6084 | 1813.2847 | 1817.9731 | 1817.9731 | 1817.9731 | 1817.9731 | 1817.9731 | 1817.9731 | 1868.5236 | 1920.4796 | 1973.8803 | 2028.7659 | 2085.1776 | 2143.1579 | 2202.7504 | 2263.9999 | 2263.9999 | 2263.9999 | 2263.9999 | 2263.9999 | 2263.9999 | 2263.9999 | 2263.9999 | 2263.9999 | 2263.9999 | 2263.9999 | 2263.9999 | 2263.9999 | 2263.9999 | 2263.9999 | 2263.9999 | 2263.9999 | 2263.9999 | 2263.9999 | 2263.9999 | 2263.9999 |  | 4550 | 4584.6033 | 4619.4697 | 4654.6012 | 4690 | 4868.1292 | 5053.0239 | 5244.9409 | 5444.1471 | 5650.9193 | 5832.5977 | 6020.1171 | 6213.6653 | 6413.4361 | 6619.6296 | 6702.8422 | 6787.1008 | 6872.4186 | 6958.8089 | 7046.2852 | 7072.4042 | 7098.6199 | 7124.9329 | 7151.3434 | 7177.8518 | 7181.7911 | 7185.7326 | 7189.6763 | 7193.6221 | 7197.5701 | 7197.5701 | 7197.5701 | 7197.5701 | 7197.5701 | 7197.5701 | 7393.9389 | 7595.6651 | 7802.8949 | 8015.7786 | 8234.4702 | 8459.1283 | 8689.9157 | 8926.9996 | 8926.9996 | 8926.9996 | 8926.9996 | 8926.9996 | 8926.9996 | 8926.9996 | 8926.9996 | 8926.9996 | 8926.9996 | 8926.9996 | 8926.9996 | 8926.9996 | 8926.9996 | 8926.9996 | 8926.9996 | 8926.9996 | 8926.9996 | 8926.9996 | 8926.9996 | 8926.9996 | [6 empty] | 322 | 326 | 330 | 334 | 339.3 | 343 | 347 | 351 | 355 | 359 | 362.9 | 366 | 369 | 372 | 375 | 378 | 381 | 384 | 387 | 390 | 393 | 396 | 399 | 402 | 405 | 408 | 411 | 414 | 417 | 420 | 429.3 | 448.4677 | 468.4913 | 489.4089 | 511.2604 | 534.0876 | 557.934 | 582.8451 | 608.8684 | 608.8684 | 608.8684 | 608.8684 | 608.8684 | 608.8684 | 608.8684 | 608.8684 | 608.8684 | 608.8684 | 608.8684 | 608.8684 | 608.8684 | 608.8684 | 608.8684 | 608.8684 | 608.8684 | 608.8684 | 608.8684 | 608.8684 | 608.8684 | [6 empty] | 4.1283 | 4.1283 | 4.1283 | 4.1283 | 4.1283 | 4.1235 | 4.1187 | 4.1139 | 4.1092 | 4.1044 | 4.0996 | 4.0949 | 4.0901 | 4.0853 | 4.0806 | 4.0725 | 4.0643 | 4.0562 | 4.0481 | 4.0401 | 4.0319 | 4.0238 | 4.0157 | 4.0076 | 3.9996 | 3.9915 | 3.9833 | 3.9753 | 3.9672 | 3.9591 | 3.9591 | 3.9591 | 3.9591 | 3.9591 | 3.9591 | 3.9571 | 3.9551 | 3.9531 | 3.9511 | 3.949 | 3.947 | 3.945 | 3.943 | 3.943 | 3.943 | 3.943 | 3.943 | 3.943 | 3.943 | 3.943 | 3.943 | 3.943 | 3.943 | 3.943 | 3.943 | 3.943 | 3.943 | 3.943 | 3.943 | 3.943 | 3.943 | 3.943 | 3.943
464 | Mangere - Otahuhu | AHP | Mangere | 2060 | 578.1892 | 601.7229 | 626.2146 | 651.7031 | 678.229 | 720.7091 | 765.85 | 813.8181 | 864.7907 | 918.9559 | 963.5067 | 1010.2172 | 1059.1923 | 1110.5417 | 1164.3805 | 1187.7963 | 1211.683 | 1236.0501 | 1260.9072 | 1286.2642 | 1296.2184 | 1306.2497 | 1316.3587 | 1326.5458 | 1336.8118 | 1341.4439 | 1346.092 | 1350.7563 | 1355.4367 | 1360.1333 | 1360.1333 | 1360.1333 | 1360.1333 | 1360.1333 | 1360.1333 | 1343.6872 | 1327.44 | 1311.3892 | 1295.5325 | 1279.8675 | 1264.392 | 1249.1036 | 1234 | 1234 | 1234 | 1234 | 1234 | 1234 | 1234 | 1234 | 1234 | 1234 | 1234 | 1234 | 1234 | 1234 | 1234 | 1234 | 1234 | 1234 | 1234 | 1234 | 1234 |  | 2480 | 2578.9223 | 2681.7904 | 2788.7618 | 2900 | 3068.6686 | 3247.1472 | 3436.0065 | 3635.8501 | 3847.3169 | 4017.6568 | 4195.5386 | 4381.296 | 4575.2779 | 4777.8483 | 4853.9548 | 4931.2736 | 5009.8241 | 5089.6258 | 5170.6986 | 5189.5964 | 5208.5633 | 5227.5995 | 5246.7052 | 5265.8808 | 5262.5004 | 5259.1221 | 5255.746 | 5252.372 | 5249.0002 | 5249.0002 | 5249.0002 | 5249.0002 | 5249.0002 | 5249.0002 | 5183.0465 | 5117.9214 | 5053.6147 | 4990.1159 | 4927.4151 | 4865.502 | 4804.3669 | 4744 | 4744 | 4744 | 4744 | 4744 | 4744 | 4744 | 4744 | 4744 | 4744 | 4744 | 4744 | 4744 | 4744 | 4744 | 4744 | 4744 | 4744 | 4744 | 4744 | 4744 | [6 empty] | 132 | 133 | 134 | 135 | 136 | 138 | 140 | 142 | 144 | 146 | 145.5 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 165.8 | 171.3671 | 177.1211 | 183.0683 | 189.2153 | 195.5686 | 202.1352 | 208.9223 | 215.9374 | 215.9374 | 215.9374 | 215.9374 | 215.9374 | 215.9374 | 215.9374 | 215.9374 | 215.9374 | 215.9374 | 215.9374 | 215.9374 | 215.9374 | 215.9374 | 215.9374 | 215.9374 | 215.9374 | 215.9374 | 215.9374 | 215.9374 | 215.9374 | [6 empty] | 4.2893 | 4.2859 | 4.2825 | 4.2792 | 4.2758 | 4.2578 | 4.2399 | 4.2221 | 4.2043 | 4.1866 | 4.1698 | 4.1531 | 4.1364 | 4.1199 | 4.1033 | 4.0865 | 4.0698 | 4.0531 | 4.0365 | 4.0199 | 4.0036 | 3.9874 | 3.9713 | 3.9552 | 3.9391 | 3.923 | 3.907 | 3.891 | 3.875 | 3.8592 | 3.8592 | 3.8592 | 3.8592 | 3.8592 | 3.8592 | 3.8573 | 3.8555 | 3.8536 | 3.8518 | 3.8499 | 3.8481 | 3.8463 | 3.8444 | 3.8444 | 3.8444 | 3.8444 | 3.8444 | 3.8444 | 3.8444 | 3.8444 | 3.8444 | 3.8444 | 3.8444 | 3.8444 | 3.8444 | 3.8444 | 3.8444 | 3.8444 | 3.8444 | 3.8444 | 3.8444 | 3.8444 | 3.8444
465 | Mangere - Otahuhu | AHP | Mangere | 2060 | 775.9679 | 796.1488 | 816.8547 | 838.099 | 859.8959 | 875.6399 | 891.6723 | 907.9982 | 924.623 | 941.5521 | 957.6426 | 974.0081 | 990.6533 | 1007.5829 | 1024.8019 | 1041.9248 | 1059.3339 | 1077.0338 | 1095.0295 | 1113.3258 | 1129.9826 | 1146.8886 | 1164.0475 | 1181.4631 | 1199.1393 | 1206.9552 | 1214.8221 | 1222.7402 | 1230.7099 | 1238.7316 | 1238.7316 | 1238.7316 | 1238.7316 | 1238.7316 | 1238.7316 | 1290.7539 | 1344.9609 | 1401.4445 | 1460.3001 | 1521.6275 | 1585.5304 | 1652.117 | 1721.5 | 1721.5 | 1721.5 | 1721.5 | 1721.5 | 1721.5 | 1721.5 | 1721.5 | 1721.5 | 1721.5 | 1721.5 | 1721.5 | 1721.5 | 1721.5 | 1721.5 | 1721.5 | 1721.5 | 1721.5 | 1721.5 | 1721.5 | 1721.5 |  | 3280 | 3364.2018 | 3450.5652 | 3539.1456 | 3630 | 3651.9018 | 3673.9356 | 3696.1025 | 3718.4031 | 3740.8382 | 3756.0402 | 3771.304 | 3786.6298 | 3802.0179 | 3817.4686 | 3834.0412 | 3850.6857 | 3867.4025 | 3884.1918 | 3901.0541 | 3908.2405 | 3915.4403 | 3922.6532 | 3929.8795 | 3937.1191 | 3908.3875 | 3879.8655 | 3851.5518 | 3823.4446 | 3795.5425 | 3795.5425 | 3795.5425 | 3795.5425 | 3795.5425 | 3795.5425 | 3953.0493 | 4117.0923 | 4287.9427 | 4465.883 | 4651.2074 | 4844.2224 | 5045.2471 | 5254.6139 | 5254.6139 | 5254.6139 | 5254.6139 | 5254.6139 | 5254.6139 | 5254.6139 | 5254.6139 | 5254.6139 | 5254.6139 | 5254.6139 | 5254.6139 | 5254.6139 | 5254.6139 | 5254.6139 | 5254.6139 | 5254.6139 | 5254.6139 | 5254.6139 | 5254.6139 | 5254.6139 | [6 empty] | 266 | 270 | 274 | 278 | 280.9 | 284 | 287 | 290 | 293 | 296 | 300.1 | 303 | 306 | 309 | 312 | 315 | 318 | 321 | 324 | 327 | 330 | 333 | 336 | 339 | 342 | 345 | 348 | 351 | 354 | 357 | 358.8 | 376.6456 | 395.3787 | 415.0436 | 435.6865 | 457.3562 | 480.1036 | 503.9824 | 529.0489 | 529.0489 | 529.0489 | 529.0489 | 529.0489 | 529.0489 | 529.0489 | 529.0489 | 529.0489 | 529.0489 | 529.0489 | 529.0489 | 529.0489 | 529.0489 | 529.0489 | 529.0489 | 529.0489 | 529.0489 | 529.0489 | 529.0489 | 529.0489 | [6 empty] | 4.227 | 4.2256 | 4.2242 | 4.2228 | 4.2214 | 4.1706 | 4.1203 | 4.0706 | 4.0215 | 3.9731 | 3.9222 | 3.8719 | 3.8224 | 3.7734 | 3.7251 | 3.6798 | 3.635 | 3.5908 | 3.5471 | 3.504 | 3.4587 | 3.414 | 3.3698 | 3.3263 | 3.2833 | 3.2382 | 3.1938 | 3.1499 | 3.1067 | 3.0641 | 3.0641 | 3.0641 | 3.0641 | 3.0641 | 3.0641 | 3.0626 | 3.0611 | 3.0597 | 3.0582 | 3.0567 | 3.0553 | 3.0538 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523
466 | Mangere - Otahuhu | AHP | Mangere | 2060 | 1686.7779 | 1699.5035 | 1712.3252 | 1725.2435 | 1738.2593 | 1754.2921 | 1770.4727 | 1786.8026 | 1803.2831 | 1819.9156 | 1836.269 | 1852.7693 | 1869.418 | 1886.2162 | 1903.1653 | 1922.6479 | 1942.3299 | 1962.2134 | 1982.3004 | 2002.593 | 2022.5288 | 2042.663 | 2062.9976 | 2083.5346 | 2104.2761 | 2130.9814 | 2158.0257 | 2185.4131 | 2213.1481 | 2241.2351 | 2266.3493 | 2291.745 | 2317.4252 | 2343.3932 | 2369.6522 | 2346.2795 | 2323.1374 | 2300.2235 | 2277.5357 | 2255.0716 | 2232.829 | 2210.8059 | 2189 | 2189 | 2189 | 2189 | 2189 | 2189 | 2189 | 2189 | 2189 | 2189 | 2189 | 2189 | 2189 | 2189 | 2189 | 2189 | 2189 | 2189 | 2189 | 2189 | 2189 |  | 6960 | 7011.9162 | 7064.2197 | 7116.9133 | 7170 | 7209.6382 | 7249.4955 | 7289.5731 | 7329.8723 | 7370.3943 | 7408.9189 | 7447.6449 | 7486.5733 | 7525.7052 | 7565.0416 | 7610.4184 | 7656.0673 | 7701.99 | 7748.1881 | 7794.6634 | 7838.5618 | 7882.7074 | 7927.1016 | 7971.7458 | 8016.6415 | 8082.7098 | 8149.3225 | 8216.4843 | 8284.1995 | 8352.4728 | 8445.3014 | 8539.1616 | 8634.0649 | 8730.023 | 8827.0476 | 8735.9279 | 8645.7489 | 8556.5008 | 8468.174 | 8380.7589 | 8294.2462 | 8208.6266 | 8123.8908 | 8123.8908 | 8123.8908 | 8123.8908 | 8123.8908 | 8123.8908 | 8123.8908 | 8123.8908 | 8123.8908 | 8123.8908 | 8123.8908 | 8123.8908 | 8123.8908 | 8123.8908 | 8123.8908 | 8123.8908 | 8123.8908 | 8123.8908 | 8123.8908 | 8123.8908 | 8123.8908 | [6 empty] | 2729 | 2758 | 2787 | 2816 | 2845.3 | 2882 | 2918 | 2954 | 2990 | 3026 | 3062.5 | 3090 | 3118 | 3146 | 3174 | 3202 | 3230 | 3258 | 3286 | 3314 | 3342 | 3370 | 3398 | 3426 | 3454 | 3482 | 3510 | 3538 | 3566 | 3594 | 3621.2 | 3598.8965 | 3576.7304 | 3554.7007 | 3532.8068 | 3511.0477 | 3489.4227 | 3467.9308 | 3446.5713 | 3446.5713 | 3446.5713 | 3446.5713 | 3446.5713 | 3446.5713 | 3446.5713 | 3446.5713 | 3446.5713 | 3446.5713 | 3446.5713 | 3446.5713 | 3446.5713 | 3446.5713 | 3446.5713 | 3446.5713 | 3446.5713 | 3446.5713 | 3446.5713 | 3446.5713 | 3446.5713 | [6 empty] | 4.1262 | 4.1259 | 4.1255 | 4.1252 | 4.1248 | 4.1097 | 4.0947 | 4.0797 | 4.0647 | 4.0499 | 4.0348 | 4.0197 | 4.0048 | 3.9898 | 3.975 | 3.9583 | 3.9417 | 3.9252 | 3.9087 | 3.8923 | 3.8756 | 3.859 | 3.8425 | 3.8261 | 3.8097 | 3.793 | 3.7763 | 3.7597 | 3.7432 | 3.7267 | 3.7264 | 3.7261 | 3.7257 | 3.7254 | 3.725 | 3.7233 | 3.7216 | 3.7199 | 3.7181 | 3.7164 | 3.7147 | 3.713 | 3.7112 | 3.7112 | 3.7112 | 3.7112 | 3.7112 | 3.7112 | 3.7112 | 3.7112 | 3.7112 | 3.7112 | 3.7112 | 3.7112 | 3.7112 | 3.7112 | 3.7112 | 3.7112 | 3.7112 | 3.7112 | 3.7112 | 3.7112 | 3.7112
467 | Mangere - Otahuhu | AHP | Mangere | 2060 | 46.1747 | 46.1747 | 46.1747 | 46.1747 | 46.1747 | 50.7843 | 55.8542 | 61.4301 | 67.5627 | 74.3076 | 79.3204 | 84.6714 | 90.3834 | 96.4808 | 102.9894 | 104.9504 | 106.9487 | 108.985 | 111.0601 | 113.1747 | 113.1747 | 113.1747 | 113.1747 | 113.1747 | 113.1747 | 113.1747 | 113.1747 | 113.1747 | 113.1747 | 113.1747 | 113.1747 | 113.1747 | 113.1747 | 113.1747 | 113.1747 | 90.0306 | 71.6195 | 56.9734 | 45.3225 | 36.0541 | 28.6811 | 22.8158 | 18.15 | 18.15 | 18.15 | 18.15 | 18.15 | 18.15 | 18.15 | 18.15 | 18.15 | 18.15 | 18.15 | 18.15 | 18.15 | 18.15 | 18.15 | 18.15 | 18.15 | 18.15 | 18.15 | 18.15 | 18.15 |  | 260 | 260 | 260 | 260 | 260 | 276.3731 | 293.7773 | 312.2775 | 331.9428 | 352.8464 | 369.0516 | 386.0011 | 403.729 | 422.2711 | 441.6648 | 446.0671 | 450.5133 | 455.0038 | 459.539 | 464.1195 | 461.7266 | 459.346 | 456.9777 | 454.6216 | 452.2777 | 449.8841 | 447.5032 | 445.1349 | 442.7791 | 440.4358 | 440.4358 | 440.4358 | 440.4358 | 440.4358 | 440.4358 | 349.4768 | 277.3026 | 220.034 | 174.5924 | 138.5355 | 109.9251 | 87.2233 | 69.2099 | 69.2099 | 69.2099 | 69.2099 | 69.2099 | 69.2099 | 69.2099 | 69.2099 | 69.2099 | 69.2099 | 69.2099 | 69.2099 | 69.2099 | 69.2099 | 69.2099 | 69.2099 | 69.2099 | 69.2099 | 69.2099 | 69.2099 | 69.2099 | [6 empty] | 2689 | 2705 | 2721 | 2737 | 2752.3 | 2793 | 2833 | 2873 | 2913 | 2953 | 2994.6 | 3014 | 3034 | 3054 | 3074 | 3094 | 3114 | 3134 | 3154 | 3174 | 3194 | 3214 | 3234 | 3254 | 3274 | 3294 | 3314 | 3334 | 3354 | 3374 | 3387 | 2857.6885 | 2411.0965 | 2034.2966 | 1716.3821 | 1448.1504 | 1221.8372 | 1030.8917 | 869.7867 | 869.7867 | 869.7867 | 869.7867 | 869.7867 | 869.7867 | 869.7867 | 869.7867 | 869.7867 | 869.7867 | 869.7867 | 869.7867 | 869.7867 | 869.7867 | 869.7867 | 869.7867 | 869.7867 | 869.7867 | 869.7867 | 869.7867 | 869.7867 | [6 empty] | 5.6308 | 5.6308 | 5.6308 | 5.6308 | 5.6308 | 5.4421 | 5.2597 | 5.0835 | 4.9131 | 4.7485 | 4.6527 | 4.5588 | 4.4668 | 4.3767 | 4.2884 | 4.2503 | 4.2124 | 4.1749 | 4.1378 | 4.1009 | 4.0798 | 4.0587 | 4.0378 | 4.017 | 3.9963 | 3.9751 | 3.9541 | 3.9332 | 3.9124 | 3.8916 | 3.8916 | 3.8916 | 3.8916 | 3.8916 | 3.8916 | 3.8818 | 3.8719 | 3.862 | 3.8522 | 3.8424 | 3.8327 | 3.8229 | 3.8132 | 3.8132 | 3.8132 | 3.8132 | 3.8132 | 3.8132 | 3.8132 | 3.8132 | 3.8132 | 3.8132 | 3.8132 | 3.8132 | 3.8132 | 3.8132 | 3.8132 | 3.8132 | 3.8132 | 3.8132 | 3.8132 | 3.8132 | 3.8132
468 | Mangere - Otahuhu | AHP | Mangere | 2060 | 891.7312 | 895.2512 | 898.785 | 902.3328 | 905.8946 | 912.8909 | 919.9412 | 927.0459 | 934.2055 | 941.4204 | 948.5553 | 955.7442 | 962.9876 | 970.2859 | 977.6395 | 980.1984 | 982.764 | 985.3364 | 987.9155 | 990.5013 | 990.5013 | 990.5013 | 990.5013 | 990.5013 | 990.5013 | 990.5013 | 990.5013 | 990.5013 | 990.5013 | 990.5013 | 990.5013 | 990.5013 | 990.5013 | 990.5013 | 990.5013 | 943.4383 | 898.6115 | 855.9146 | 815.2465 | 776.5106 | 739.6153 | 704.473 | 671.0005 | 671.0005 | 671.0005 | 671.0005 | 671.0005 | 671.0005 | 671.0005 | 671.0005 | 671.0005 | 671.0005 | 671.0005 | 671.0005 | 671.0005 | 671.0005 | 671.0005 | 671.0005 | 671.0005 | 671.0005 | 671.0005 | 671.0005 | 671.0005 |  | 3820 | 3834.9125 | 3849.8831 | 3864.9122 | 3880 | 3900.5524 | 3921.2136 | 3941.9843 | 3962.8649 | 3983.8562 | 4004.2788 | 4024.806 | 4045.4384 | 4066.1766 | 4087.0211 | 4085.5534 | 4084.0863 | 4082.6196 | 4081.1535 | 4079.6879 | 4067.4861 | 4055.3207 | 4043.1917 | 4031.099 | 4019.0425 | 4006.8395 | 3994.6736 | 3982.5447 | 3970.4525 | 3958.3971 | 3958.3971 | 3958.3971 | 3958.3971 | 3958.3971 | 3958.3971 | 3768.6343 | 3587.9686 | 3415.9639 | 3252.2049 | 3096.2965 | 2947.8622 | 2806.5438 | 2672 | 2672 | 2672 | 2672 | 2672 | 2672 | 2672 | 2672 | 2672 | 2672 | 2672 | 2672 | 2672 | 2672 | 2672 | 2672 | 2672 | 2672 | 2672 | 2672 | 2672 | [6 empty] | 162 | 163 | 164 | 165 | 165 | 167 | 169 | 171 | 173 | 175 | 178.3 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 199.6 | 187.2332 | 175.6326 | 164.7508 | 154.5432 | 144.968 | 135.9861 | 127.5607 | 119.6573 | 119.6573 | 119.6573 | 119.6573 | 119.6573 | 119.6573 | 119.6573 | 119.6573 | 119.6573 | 119.6573 | 119.6573 | 119.6573 | 119.6573 | 119.6573 | 119.6573 | 119.6573 | 119.6573 | 119.6573 | 119.6573 | 119.6573 | 119.6573 | [6 empty] | 4.2838 | 4.2836 | 4.2834 | 4.2832 | 4.2831 | 4.2727 | 4.2625 | 4.2522 | 4.242 | 4.2318 | 4.2215 | 4.2112 | 4.2009 | 4.1907 | 4.1805 | 4.1681 | 4.1557 | 4.1434 | 4.1311 | 4.1188 | 4.1065 | 4.0942 | 4.082 | 4.0698 | 4.0576 | 4.0453 | 4.033 | 4.0207 | 4.0085 | 3.9964 | 3.9964 | 3.9964 | 3.9964 | 3.9964 | 3.9964 | 3.9946 | 3.9928 | 3.991 | 3.9892 | 3.9874 | 3.9857 | 3.9839 | 3.9821 | 3.9821 | 3.9821 | 3.9821 | 3.9821 | 3.9821 | 3.9821 | 3.9821 | 3.9821 | 3.9821 | 3.9821 | 3.9821 | 3.9821 | 3.9821 | 3.9821 | 3.9821 | 3.9821 | 3.9821 | 3.9821 | 3.9821 | 3.9821
469 | Mangere - Otahuhu | AHP | Mangere | 2060 | 914.6927 | 915.9446 | 917.1982 | 918.4536 | 919.7107 | 953.4161 | 988.3568 | 1024.5779 | 1062.1265 | 1101.0512 | 1135.7677 | 1171.5788 | 1208.5191 | 1246.624 | 1285.9305 | 1305.8641 | 1326.1067 | 1346.6631 | 1367.5382 | 1388.7369 | 1399.3871 | 1410.119 | 1420.9332 | 1431.8304 | 1442.8111 | 1447.7667 | 1452.7392 | 1457.7289 | 1462.7357 | 1467.7597 | 1467.7597 | 1467.7597 | 1467.7597 | 1467.7597 | 1467.7597 | 1503.3654 | 1539.8349 | 1577.189 | 1615.4493 | 1654.6378 | 1694.7769 | 1735.8898 | 1778 | 1778 | 1778 | 1778 | 1778 | 1778 | 1778 | 1778 | 1778 | 1778 | 1778 | 1778 | 1778 | 1778 | 1778 | 1778 | 1778 | 1778 | 1778 | 1778 | 1778 |  | 3700 | 3704.9899 | 3709.9865 | 3714.9899 | 3720 | 3847.0037 | 3978.3434 | 4114.1671 | 4254.628 | 4399.8843 | 4527.9148 | 4659.6708 | 4795.2607 | 4934.7961 | 5078.3918 | 5142.5124 | 5207.4426 | 5273.1926 | 5339.7728 | 5407.1937 | 5433.4326 | 5459.7989 | 5486.2932 | 5512.916 | 5539.668 | 5543.1597 | 5546.6537 | 5550.1498 | 5553.6482 | 5557.1487 | 5557.1487 | 5557.1487 | 5557.1487 | 5557.1487 | 5557.1487 | 5689.3356 | 5824.6668 | 5963.2171 | 6105.0631 | 6250.2832 | 6398.9575 | 6551.1684 | 6706.9998 | 6706.9998 | 6706.9998 | 6706.9998 | 6706.9998 | 6706.9998 | 6706.9998 | 6706.9998 | 6706.9998 | 6706.9998 | 6706.9998 | 6706.9998 | 6706.9998 | 6706.9998 | 6706.9998 | 6706.9998 | 6706.9998 | 6706.9998 | 6706.9998 | 6706.9998 | 6706.9998 | [6 empty] | 658 | 666 | 674 | 682 | 688.9 | 696 | 704 | 712 | 720 | 728 | 733.9 | 741 | 748 | 755 | 762 | 769 | 776 | 783 | 790 | 797 | 804 | 811 | 818 | 825 | 832 | 839 | 846 | 853 | 860 | 867 | 870.9 | 907.7011 | 946.0574 | 986.0344 | 1027.7007 | 1071.1277 | 1116.3898 | 1163.5645 | 1212.7326 | 1212.7326 | 1212.7326 | 1212.7326 | 1212.7326 | 1212.7326 | 1212.7326 | 1212.7326 | 1212.7326 | 1212.7326 | 1212.7326 | 1212.7326 | 1212.7326 | 1212.7326 | 1212.7326 | 1212.7326 | 1212.7326 | 1212.7326 | 1212.7326 | 1212.7326 | 1212.7326 | [6 empty] | 4.0451 | 4.045 | 4.0449 | 4.0448 | 4.0448 | 4.035 | 4.0252 | 4.0155 | 4.0058 | 3.9961 | 3.9867 | 3.9773 | 3.9679 | 3.9585 | 3.9492 | 3.938 | 3.9269 | 3.9157 | 3.9047 | 3.8936 | 3.8827 | 3.8719 | 3.861 | 3.8503 | 3.8395 | 3.8288 | 3.8181 | 3.8074 | 3.7968 | 3.7861 | 3.7861 | 3.7861 | 3.7861 | 3.7861 | 3.7861 | 3.7844 | 3.7827 | 3.7809 | 3.7792 | 3.7774 | 3.7757 | 3.774 | 3.7722 | 3.7722 | 3.7722 | 3.7722 | 3.7722 | 3.7722 | 3.7722 | 3.7722 | 3.7722 | 3.7722 | 3.7722 | 3.7722 | 3.7722 | 3.7722 | 3.7722 | 3.7722 | 3.7722 | 3.7722 | 3.7722 | 3.7722 | 3.7722
470 | Mangere - Otahuhu | AHP | Mangere | 2060 | 945.8691 | 951.1227 | 956.4054 | 961.7175 | 967.0591 | 981.1697 | 995.4862 | 1010.0116 | 1024.749 | 1039.7014 | 1054.1085 | 1068.7152 | 1083.5244 | 1098.5388 | 1113.7612 | 1178.3602 | 1246.7061 | 1319.0161 | 1395.5201 | 1476.4614 | 1563.4982 | 1655.6659 | 1753.2668 | 1856.6213 | 1966.0684 | 2009.3032 | 2053.4887 | 2098.6459 | 2144.7961 | 2191.9612 | 2191.9612 | 2191.9612 | 2191.9612 | 2191.9612 | 2191.9612 | 2144.7282 | 2098.513 | 2053.2936 | 2009.0487 | 1965.7571 | 1923.3984 | 1881.9525 | 1841.3996 | 1841.3996 | 1841.3996 | 1841.3996 | 1841.3996 | 1841.3996 | 1841.3996 | 1841.3996 | 1841.3996 | 1841.3996 | 1841.3996 | 1841.3996 | 1841.3996 | 1841.3996 | 1841.3996 | 1841.3996 | 1841.3996 | 1841.3996 | 1841.3996 | 1841.3996 | 1841.3996 |  | 4010 | 4032.3131 | 4054.7503 | 4077.3124 | 4100 | 4164.4409 | 4229.8946 | 4296.377 | 4363.9044 | 4432.4932 | 4498.866 | 4566.2327 | 4634.6081 | 4704.0074 | 4774.4459 | 5050.7578 | 5343.0606 | 5652.28 | 5979.3947 | 6325.4407 | 6697.4388 | 7091.314 | 7508.353 | 7949.918 | 8417.4513 | 8601.0971 | 8788.7494 | 8980.4959 | 9176.4257 | 9376.6302 | 9376.6302 | 9376.6302 | 9376.6302 | 9376.6302 | 9376.6302 | 9170.2019 | 8968.3181 | 8770.8789 | 8577.7863 | 8388.9447 | 8204.2605 | 8023.6421 | 7847.0001 | 7847.0001 | 7847.0001 | 7847.0001 | 7847.0001 | 7847.0001 | 7847.0001 | 7847.0001 | 7847.0001 | 7847.0001 | 7847.0001 | 7847.0001 | 7847.0001 | 7847.0001 | 7847.0001 | 7847.0001 | 7847.0001 | 7847.0001 | 7847.0001 | 7847.0001 | 7847.0001 | [6 empty] | 130 | 131 | 132 | 133 | 133 | 134 | 135 | 136 | 137 | 138 | 141.4 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 164.7 | 173.0096 | 181.7385 | 190.9078 | 200.5397 | 210.6576 | 221.2859 | 232.4505 | 244.1783 | 244.1783 | 244.1783 | 244.1783 | 244.1783 | 244.1783 | 244.1783 | 244.1783 | 244.1783 | 244.1783 | 244.1783 | 244.1783 | 244.1783 | 244.1783 | 244.1783 | 244.1783 | 244.1783 | 244.1783 | 244.1783 | 244.1783 | 244.1783 | [6 empty] | 4.2395 | 4.2395 | 4.2396 | 4.2396 | 4.2397 | 4.2444 | 4.2491 | 4.2538 | 4.2585 | 4.2632 | 4.2679 | 4.2726 | 4.2773 | 4.2821 | 4.2868 | 4.2863 | 4.2857 | 4.2852 | 4.2847 | 4.2842 | 4.2836 | 4.2831 | 4.2825 | 4.2819 | 4.2814 | 4.2806 | 4.2799 | 4.2792 | 4.2785 | 4.2777 | 4.2777 | 4.2777 | 4.2777 | 4.2777 | 4.2777 | 4.2757 | 4.2737 | 4.2716 | 4.2696 | 4.2675 | 4.2655 | 4.2635 | 4.2614 | 4.2614 | 4.2614 | 4.2614 | 4.2614 | 4.2614 | 4.2614 | 4.2614 | 4.2614 | 4.2614 | 4.2614 | 4.2614 | 4.2614 | 4.2614 | 4.2614 | 4.2614 | 4.2614 | 4.2614 | 4.2614 | 4.2614 | 4.2614
471 | Mangere - Otahuhu | AHP | Mangere | 2060 | 944.2112 | 957.4992 | 970.9742 | 984.6388 | 998.4957 | 1032.3841 | 1067.4226 | 1103.6504 | 1141.1077 | 1179.8362 | 1214.691 | 1250.5754 | 1287.52 | 1325.5559 | 1364.7155 | 1384.6838 | 1404.9443 | 1425.5013 | 1446.359 | 1467.5219 | 1478.1808 | 1488.9171 | 1499.7314 | 1510.6242 | 1521.5961 | 1526.5534 | 1531.5269 | 1536.5165 | 1541.5225 | 1546.5447 | 1546.5447 | 1546.5447 | 1546.5447 | 1546.5447 | 1546.5447 | 1535.189 | 1523.9167 | 1512.7272 | 1501.6198 | 1490.594 | 1479.6492 | 1468.7847 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 | 1458 |  | 3890 | 3943.8706 | 3998.4872 | 4053.8602 | 4110 | 4233.463 | 4360.6348 | 4491.6268 | 4626.5538 | 4765.5339 | 4887.8695 | 5013.3455 | 5142.0426 | 5274.0435 | 5409.433 | 5466.5796 | 5524.3298 | 5582.6902 | 5641.6671 | 5701.2671 | 5719.6403 | 5738.0728 | 5756.5647 | 5775.1162 | 5793.7274 | 5789.0525 | 5784.3813 | 5779.7139 | 5775.0502 | 5770.3903 | 5770.3903 | 5770.3903 | 5770.3903 | 5770.3903 | 5770.3903 | 5725.2497 | 5680.4623 | 5636.0252 | 5591.9357 | 5548.1912 | 5504.7888 | 5461.726 | 5419 | 5419 | 5419 | 5419 | 5419 | 5419 | 5419 | 5419 | 5419 | 5419 | 5419 | 5419 | 5419 | 5419 | 5419 | 5419 | 5419 | 5419 | 5419 | 5419 | 5419 | [6 empty] | 265 | 268 | 271 | 274 | 277.4 | 281 | 284 | 287 | 290 | 293 | 297.5 | 300 | 303 | 306 | 309 | 312 | 315 | 318 | 321 | 324 | 327 | 330 | 333 | 336 | 339 | 342 | 345 | 348 | 351 | 354 | 352.3 | 354.4849 | 356.6833 | 358.8953 | 361.1211 | 363.3607 | 365.6141 | 367.8816 | 370.1631 | 370.1631 | 370.1631 | 370.1631 | 370.1631 | 370.1631 | 370.1631 | 370.1631 | 370.1631 | 370.1631 | 370.1631 | 370.1631 | 370.1631 | 370.1631 | 370.1631 | 370.1631 | 370.1631 | 370.1631 | 370.1631 | 370.1631 | 370.1631 | [6 empty] | 4.1198 | 4.1189 | 4.118 | 4.1171 | 4.1162 | 4.1007 | 4.0852 | 4.0698 | 4.0544 | 4.0391 | 4.024 | 4.0088 | 3.9938 | 3.9787 | 3.9638 | 3.9479 | 3.9321 | 3.9163 | 3.9006 | 3.885 | 3.8694 | 3.8539 | 3.8384 | 3.823 | 3.8077 | 3.7922 | 3.7769 | 3.7616 | 3.7463 | 3.7312 | 3.7312 | 3.7312 | 3.7312 | 3.7312 | 3.7312 | 3.7293 | 3.7275 | 3.7257 | 3.7239 | 3.7221 | 3.7203 | 3.7185 | 3.7167 | 3.7167 | 3.7167 | 3.7167 | 3.7167 | 3.7167 | 3.7167 | 3.7167 | 3.7167 | 3.7167 | 3.7167 | 3.7167 | 3.7167 | 3.7167 | 3.7167 | 3.7167 | 3.7167 | 3.7167 | 3.7167 | 3.7167 | 3.7167
472 | Mangere - Otahuhu | AHP | Mangere | 2060 | 265.5838 | 269.3477 | 273.165 | 277.0363 | 280.9626 | 290.4766 | 300.3127 | 310.482 | 320.9956 | 331.8652 | 341.6501 | 351.7235 | 362.0939 | 372.7701 | 383.7611 | 416.2071 | 451.3963 | 489.5606 | 530.9516 | 575.8422 | 619.3123 | 666.064 | 716.345 | 770.4216 | 828.5805 | 850.6901 | 873.3897 | 896.695 | 920.6222 | 945.1878 | 945.1878 | 945.1878 | 945.1878 | 945.1878 | 945.1878 | 964.8038 | 984.8269 | 1005.2655 | 1026.1283 | 1047.424 | 1069.1618 | 1091.3506 | 1114 | 1114 | 1114 | 1114 | 1114 | 1114 | 1114 | 1114 | 1114 | 1114 | 1114 | 1114 | 1114 | 1114 | 1114 | 1114 | 1114 | 1114 | 1114 | 1114 | 1114 |  | 1110 | 1124.7052 | 1139.6052 | 1154.7026 | 1170 | 1200.513 | 1231.8218 | 1263.947 | 1296.9101 | 1330.7329 | 1359.7395 | 1389.3784 | 1419.6634 | 1450.6085 | 1482.2281 | 1592.2892 | 1710.5228 | 1837.5357 | 1973.9798 | 2120.5554 | 2260.4898 | 2409.6584 | 2568.6706 | 2738.1759 | 2918.8668 | 2974.0506 | 3030.2777 | 3087.5678 | 3145.941 | 3205.4178 | 3205.4178 | 3205.4178 | 3205.4178 | 3205.4178 | 3205.4178 | 3270.4331 | 3336.767 | 3404.4464 | 3473.4986 | 3543.9513 | 3615.833 | 3689.1727 | 3764 | 3764 | 3764 | 3764 | 3764 | 3764 | 3764 | 3764 | 3764 | 3764 | 3764 | 3764 | 3764 | 3764 | 3764 | 3764 | 3764 | 3764 | 3764 | 3764 | 3764 | [6 empty] | 2085 | 2114 | 2143 | 2172 | 2202.9 | 2230 | 2257 | 2284 | 2311 | 2338 | 2366.6 | 2395 | 2423 | 2451 | 2479 | 2507 | 2535 | 2563 | 2591 | 2619 | 2647 | 2675 | 2703 | 2731 | 2759 | 2787 | 2815 | 2843 | 2871 | 2899 | 2933.5 | 3322.9191 | 3764.0332 | 4263.7048 | 4829.7073 | 5470.846 | 6197.0952 | 7019.7533 | 7951.6183 | 7951.6183 | 7951.6183 | 7951.6183 | 7951.6183 | 7951.6183 | 7951.6183 | 7951.6183 | 7951.6183 | 7951.6183 | 7951.6183 | 7951.6183 | 7951.6183 | 7951.6183 | 7951.6183 | 7951.6183 | 7951.6183 | 7951.6183 | 7951.6183 | 7951.6183 | 7951.6183 | [6 empty] | 4.1795 | 4.1757 | 4.1719 | 4.1681 | 4.1643 | 4.1329 | 4.1018 | 4.0709 | 4.0403 | 4.0099 | 3.9799 | 3.9502 | 3.9207 | 3.8914 | 3.8624 | 3.8257 | 3.7894 | 3.7534 | 3.7178 | 3.6825 | 3.65 | 3.6178 | 3.5858 | 3.5541 | 3.5227 | 3.496 | 3.4696 | 3.4433 | 3.4172 | 3.3913 | 3.3913 | 3.3913 | 3.3913 | 3.3913 | 3.3913 | 3.3897 | 3.3882 | 3.3866 | 3.3851 | 3.3835 | 3.3819 | 3.3804 | 3.3788 | 3.3788 | 3.3788 | 3.3788 | 3.3788 | 3.3788 | 3.3788 | 3.3788 | 3.3788 | 3.3788 | 3.3788 | 3.3788 | 3.3788 | 3.3788 | 3.3788 | 3.3788 | 3.3788 | 3.3788 | 3.3788 | 3.3788 | 3.3788
473 | Mangere - Otahuhu | AHP | Mangere | 2060 | 962.506 | 964.3754 | 966.2484 | 968.125 | 970.0053 | 989.4638 | 1009.3126 | 1029.5597 | 1050.2128 | 1071.2803 | 1091.1776 | 1111.4444 | 1132.0877 | 1153.1144 | 1174.5316 | 1244.3695 | 1318.3599 | 1396.7499 | 1479.8009 | 1567.7901 | 1660.0681 | 1757.7774 | 1861.2377 | 1970.7876 | 2086.7854 | 2132.6178 | 2179.4568 | 2227.3246 | 2276.2437 | 2326.2372 | 2326.2372 | 2326.2372 | 2326.2372 | 2326.2372 | 2326.2372 | 2365.774 | 2405.9827 | 2446.8749 | 2488.462 | 2530.756 | 2573.7688 | 2617.5127 | 2662 | 2662 | 2662 | 2662 | 2662 | 2662 | 2662 | 2662 | 2662 | 2662 | 2662 | 2662 | 2662 | 2662 | 2662 | 2662 | 2662 | 2662 | 2662 | 2662 | 2662 |  | 3900 | 3907.4785 | 3914.9713 | 3922.4784 | 3930 | 4013.307 | 4098.3799 | 4185.2562 | 4273.974 | 4364.5725 | 4450.6746 | 4538.4752 | 4628.008 | 4719.307 | 4812.4071 | 5096.1984 | 5396.7251 | 5714.9741 | 6051.9905 | 6408.8809 | 6783.5678 | 7180.1603 | 7599.9391 | 8044.2597 | 8514.5569 | 8700.5047 | 8890.5134 | 9084.6717 | 9283.0701 | 9485.8013 | 9485.8013 | 9485.8013 | 9485.8013 | 9485.8013 | 9485.8013 | 9642.242 | 9801.2626 | 9962.9059 | 10127.215 | 10294.2339 | 10464.0073 | 10636.5806 | 10812 | 10812 | 10812 | 10812 | 10812 | 10812 | 10812 | 10812 | 10812 | 10812 | 10812 | 10812 | 10812 | 10812 | 10812 | 10812 | 10812 | 10812 | 10812 | 10812 | 10812 | [6 empty] | 265 | 267 | 269 | 271 | 272 | 275 | 278 | 281 | 284 | 287 | 289.9 | 292 | 294 | 296 | 298 | 300 | 302 | 304 | 306 | 308 | 310 | 312 | 314 | 316 | 318 | 320 | 322 | 324 | 326 | 328 | 333.6 | 366.5939 | 402.8511 | 442.6941 | 486.4778 | 534.5917 | 587.4643 | 645.5661 | 709.4143 | 709.4143 | 709.4143 | 709.4143 | 709.4143 | 709.4143 | 709.4143 | 709.4143 | 709.4143 | 709.4143 | 709.4143 | 709.4143 | 709.4143 | 709.4143 | 709.4143 | 709.4143 | 709.4143 | 709.4143 | 709.4143 | 709.4143 | 709.4143 | [6 empty] | 4.0519 | 4.0518 | 4.0517 | 4.0516 | 4.0515 | 4.056 | 4.0606 | 4.0651 | 4.0696 | 4.0742 | 4.0788 | 4.0834 | 4.088 | 4.0927 | 4.0973 | 4.0954 | 4.0935 | 4.0916 | 4.0897 | 4.0878 | 4.0863 | 4.0848 | 4.0833 | 4.0817 | 4.0802 | 4.0797 | 4.0792 | 4.0787 | 4.0782 | 4.0777 | 4.0777 | 4.0777 | 4.0777 | 4.0777 | 4.0777 | 4.0757 | 4.0737 | 4.0717 | 4.0697 | 4.0677 | 4.0656 | 4.0636 | 4.0616 | 4.0616 | 4.0616 | 4.0616 | 4.0616 | 4.0616 | 4.0616 | 4.0616 | 4.0616 | 4.0616 | 4.0616 | 4.0616 | 4.0616 | 4.0616 | 4.0616 | 4.0616 | 4.0616 | 4.0616 | 4.0616 | 4.0616 | 4.0616
474 | Mangere - Otahuhu | AHP | Mangere | 2060 | 673.3701 | 679.5739 | 685.8348 | 692.1534 | 698.5302 | 717.7034 | 737.4028 | 757.643 | 778.4387 | 799.8052 | 819.4649 | 839.6079 | 860.246 | 881.3913 | 903.0565 | 970.7649 | 1043.5498 | 1121.7919 | 1205.9004 | 1296.315 | 1386.6237 | 1483.2238 | 1586.5536 | 1697.0819 | 1815.3103 | 1860.857 | 1907.5465 | 1955.4075 | 2004.4693 | 2054.7621 | 2054.7621 | 2054.7621 | 2054.7621 | 2054.7621 | 2054.7621 | 2122.949 | 2193.3988 | 2266.1864 | 2341.3894 | 2419.0881 | 2499.3652 | 2582.3062 | 2667.9997 | 2667.9997 | 2667.9997 | 2667.9997 | 2667.9997 | 2667.9997 | 2667.9997 | 2667.9997 | 2667.9997 | 2667.9997 | 2667.9997 | 2667.9997 | 2667.9997 | 2667.9997 | 2667.9997 | 2667.9997 | 2667.9997 | 2667.9997 | 2667.9997 | 2667.9997 | 2667.9997 |  | 2700 | 2724.6601 | 2749.5454 | 2774.658 | 2800 | 2880.1319 | 2962.557 | 3047.341 | 3134.5514 | 3224.2576 | 3307.3525 | 3392.5889 | 3480.022 | 3569.7084 | 3661.7062 | 3934.8303 | 4228.3264 | 4543.7143 | 4882.6266 | 5246.8182 | 5610.8873 | 6000.2185 | 6416.5649 | 6861.8009 | 7337.9312 | 7521.4472 | 7709.5528 | 7902.3628 | 8099.9948 | 8302.5694 | 8302.5694 | 8302.5694 | 8302.5694 | 8302.5694 | 8302.5694 | 8573.5603 | 8853.3961 | 9142.3657 | 9440.767 | 9748.908 | 10067.1065 | 10395.6909 | 10735 | 10735 | 10735 | 10735 | 10735 | 10735 | 10735 | 10735 | 10735 | 10735 | 10735 | 10735 | 10735 | 10735 | 10735 | 10735 | 10735 | 10735 | 10735 | 10735 | 10735 | [6 empty] | 263 | 265 | 267 | 269 | 272.8 | 275 | 278 | 281 | 284 | 287 | 288.9 | 291 | 293 | 295 | 297 | 299 | 301 | 303 | 305 | 307 | 309 | 311 | 313 | 315 | 317 | 319 | 321 | 323 | 325 | 327 | 331.8 | 379.2049 | 433.3827 | 495.301 | 566.0657 | 646.9407 | 739.3704 | 845.0058 | 965.7335 | 965.7335 | 965.7335 | 965.7335 | 965.7335 | 965.7335 | 965.7335 | 965.7335 | 965.7335 | 965.7335 | 965.7335 | 965.7335 | 965.7335 | 965.7335 | 965.7335 | 965.7335 | 965.7335 | 965.7335 | 965.7335 | 965.7335 | 965.7335 | [6 empty] | 4.0097 | 4.0094 | 4.009 | 4.0087 | 4.0084 | 4.013 | 4.0176 | 4.0221 | 4.0267 | 4.0313 | 4.036 | 4.0407 | 4.0454 | 4.0501 | 4.0548 | 4.0533 | 4.0519 | 4.0504 | 4.0489 | 4.0475 | 4.0464 | 4.0454 | 4.0443 | 4.0433 | 4.0422 | 4.0419 | 4.0416 | 4.0413 | 4.041 | 4.0406 | 4.0406 | 4.0406 | 4.0406 | 4.0406 | 4.0406 | 4.0385 | 4.0364 | 4.0343 | 4.0321 | 4.03 | 4.0279 | 4.0257 | 4.0236 | 4.0236 | 4.0236 | 4.0236 | 4.0236 | 4.0236 | 4.0236 | 4.0236 | 4.0236 | 4.0236 | 4.0236 | 4.0236 | 4.0236 | 4.0236 | 4.0236 | 4.0236 | 4.0236 | 4.0236 | 4.0236 | 4.0236 | 4.0236
475 | Mangere - Otahuhu |  |  | 2052 | 15.1588 | 15.1588 | 15.1588 | 15.1588 | 15.1588 | 16.8411 | 18.7101 | 20.7865 | 23.0933 | 25.6562 | 27.509 | 29.4956 | 31.6256 | 33.9095 | 36.3584 | 38.1485 | 40.0268 | 41.9976 | 44.0655 | 46.2351 | 47.8822 | 49.588 | 51.3545 | 53.184 | 55.0786 | 57.2781 | 59.5654 | 61.9441 | 64.4178 | 66.9902 | 69.0883 | 71.2521 | 73.4838 | 75.7853 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 | 78.1588 |  | 90 | 90 | 90 | 90 | 90 | 93.5285 | 97.1954 | 101.006 | 104.9661 | 109.0814 | 112.7645 | 116.5719 | 120.508 | 124.5769 | 128.7832 | 132.1795 | 135.6654 | 139.2432 | 142.9154 | 146.6844 | 149.7585 | 152.8971 | 156.1014 | 159.3729 | 162.713 | 166.8184 | 171.0274 | 175.3425 | 179.7666 | 184.3022 | 188.1838 | 192.1471 | 196.1939 | 200.3259 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | 204.545 | [6 empty] | 3532 | 3545 | 3558 | 3571 | 3584.6 | 3627 | 3670 | 3713 | 3756 | 3799 | 3841.3 | 3863 | 3885 | 3907 | 3929 | 3951 | 3973 | 3995 | 4017 | 4039 | 4061 | 4083 | 4105 | 4127 | 4149 | 4171 | 4193 | 4215 | 4237 | 4259 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | 4277.7 | [6 empty] | 5.9371 | 5.9371 | 5.9371 | 5.9371 | 5.9371 | 5.5536 | 5.1948 | 4.8592 | 4.5453 | 4.2517 | 4.0992 | 3.9522 | 3.8105 | 3.6738 | 3.5421 | 3.4649 | 3.3894 | 3.3155 | 3.2433 | 3.1726 | 3.1276 | 3.0834 | 3.0397 | 2.9966 | 2.9542 | 2.9124 | 2.8713 | 2.8307 | 2.7906 | 2.7512 | 2.7238 | 2.6967 | 2.6699 | 2.6433 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617 | 2.617
476 | Mangere - Otahuhu |  |  | 2052 | 24.0033 | 24.0033 | 24.0033 | 24.0033 | 24.0033 | 25.3541 | 26.7809 | 28.288 | 29.8799 | 31.5614 | 32.9708 | 34.4433 | 35.9814 | 37.5883 | 39.2669 | 40.614 | 42.0073 | 43.4484 | 44.9389 | 46.4805 | 47.7163 | 48.9849 | 50.2873 | 51.6243 | 52.9968 | 54.6463 | 56.3471 | 58.1008 | 59.9091 | 61.7737 | 63.3384 | 64.9426 | 66.5875 | 68.274 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 | 70.0033 |  | 60 | 60 | 60 | 60 | 60 | 63.9859 | 68.2365 | 72.7695 | 77.6036 | 82.7589 | 86.7966 | 91.0312 | 95.4725 | 100.1304 | 105.0156 | 108.6438 | 112.3974 | 116.2807 | 120.2981 | 124.4543 | 127.5596 | 130.7423 | 134.0044 | 137.3479 | 140.7748 | 144.9304 | 149.2086 | 153.6131 | 158.1476 | 162.816 | 167.388 | 172.0884 | 176.9208 | 181.8888 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | 186.9964 | [6 empty] | 4320 | 4333 | 4346 | 4359 | 4373.3 | 4425 | 4477 | 4529 | 4581 | 4633 | 4683.7 | 4708 | 4733 | 4758 | 4783 | 4808 | 4833 | 4858 | 4883 | 4908 | 4933 | 4958 | 4983 | 5008 | 5033 | 5058 | 5083 | 5108 | 5133 | 5158 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | 5177.3 | [6 empty] | 2.4997 | 2.4997 | 2.4997 | 2.4997 | 2.4997 | 2.5237 | 2.548 | 2.5725 | 2.5972 | 2.6222 | 2.6325 | 2.6429 | 2.6534 | 2.6639 | 2.6744 | 2.675 | 2.6757 | 2.6763 | 2.6769 | 2.6776 | 2.6733 | 2.669 | 2.6648 | 2.6605 | 2.6563 | 2.6522 | 2.648 | 2.6439 | 2.6398 | 2.6357 | 2.6428 | 2.6499 | 2.657 | 2.6641 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713 | 2.6713
477 | Mangere - Otahuhu |  |  | 2052 | 101.3773 | 102.1865 | 103.0022 | 103.8244 | 104.6531 | 115.2237 | 126.8619 | 139.6757 | 153.7837 | 169.3167 | 180.8268 | 193.1194 | 206.2477 | 220.2684 | 235.2422 | 239.7484 | 244.3409 | 249.0214 | 253.7916 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 | 258.6531 |  | 360 | 362.4744 | 364.9658 | 367.4743 | 370 | 403.5179 | 440.0722 | 479.9378 | 523.4149 | 570.8305 | 607.3264 | 646.1558 | 687.4677 | 731.4208 | 778.1841 | 792.1564 | 806.3796 | 820.8582 | 835.5967 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | 850.5999 | [6 empty] | 2212 | 2236 | 2260 | 2284 | 2306.1 | 2347 | 2387 | 2427 | 2467 | 2507 | 2548.7 | 2575 | 2601 | 2627 | 2653 | 2679 | 2705 | 2731 | 2757 | 2783 | 2809 | 2835 | 2861 | 2887 | 2913 | 2939 | 2965 | 2991 | 3017 | 3043 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | 3069.8 | [6 empty] | 3.5511 | 3.5472 | 3.5433 | 3.5394 | 3.5355 | 3.502 | 3.4689 | 3.4361 | 3.4036 | 3.3714 | 3.3586 | 3.3459 | 3.3332 | 3.3206 | 3.308 | 3.3041 | 3.3002 | 3.2963 | 3.2925 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886 | 3.2886
478 | Mangere - Otahuhu |  |  | 2052 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 4.6338 | 7.0822 | 10.8245 | 16.5442 | 25.2861 | 28.7414 | 32.6689 | 37.133 | 42.2072 | 47.9748 | 51.5174 | 55.3215 | 59.4066 | 63.7934 | 68.5041 | 71.8015 | 75.2576 | 78.8801 | 82.677 | 86.6566 | 91.073 | 95.7144 | 100.5923 | 105.7188 | 111.1066 | 115.3542 | 119.7642 | 124.3428 | 129.0964 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 | 134.0318 |  | 20 | 20 | 20 | 20 | 20 | 26.4711 | 35.036 | 46.3721 | 61.376 | 81.2345 | 91.0321 | 102.0115 | 114.315 | 128.1024 | 143.5528 | 153.3872 | 163.8954 | 175.1235 | 187.1209 | 199.9401 | 209.0442 | 218.5628 | 228.5149 | 238.9202 | 249.7992 | 261.9826 | 274.7602 | 288.1611 | 302.2155 | 316.9554 | 328.6531 | 340.7825 | 353.3595 | 366.4007 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | 379.9232 | [6 empty] | 9241 | 9339 | 9437 | 9535 | 9631 | 9801 | 9971 | 10141 | 10311 | 10481 | 10651.1 | 10760 | 10869 | 10978 | 11087 | 11196 | 11305 | 11414 | 11523 | 11632 | 11741 | 11850 | 11959 | 12068 | 12177 | 12286 | 12395 | 12504 | 12613 | 12722 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | 12827.6 | [6 empty] | 6.5968 | 6.5968 | 6.5968 | 6.5968 | 6.5968 | 5.7127 | 4.947 | 4.284 | 3.7098 | 3.2126 | 3.1673 | 3.1226 | 3.0785 | 3.0351 | 2.9923 | 2.9774 | 2.9626 | 2.9479 | 2.9332 | 2.9187 | 2.9114 | 2.9042 | 2.897 | 2.8898 | 2.8826 | 2.8766 | 2.8706 | 2.8646 | 2.8587 | 2.8527 | 2.8491 | 2.8454 | 2.8418 | 2.8382 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346 | 2.8346
479 | Mangere - Otahuhu | AHP | Mangere | 2060 | 1418.2915 | 1429.531 | 1440.8596 | 1452.278 | 1463.7869 | 1463.7869 | 1463.7869 | 1463.7869 | 1463.7869 | 1463.7869 | 1463.7869 | 1463.7869 | 1463.7869 | 1463.7869 | 1463.7869 | 1467.0034 | 1470.2271 | 1473.4578 | 1476.6956 | 1479.9406 | 1484.6131 | 1489.3003 | 1494.0024 | 1498.7193 | 1503.4511 | 1509.7318 | 1516.0387 | 1522.3719 | 1528.7316 | 1535.1179 | 1541.0109 | 1546.9264 | 1552.8647 | 1558.8258 | 1564.8097 | 1557.8899 | 1551.0006 | 1544.1418 | 1537.3133 | 1530.515 | 1523.7468 | 1517.0085 | 1510.3 | 1510.3 | 1510.3 | 1510.3 | 1510.3 | 1510.3 | 1510.3 | 1510.3 | 1510.3 | 1510.3 | 1510.3 | 1510.3 | 1510.3 | 1510.3 | 1510.3 | 1510.3 | 1510.3 | 1510.3 | 1510.3 | 1510.3 | 1510.3 |  | 5920 | 5966.9388 | 6014.2497 | 6061.9358 | 6110 | 6072.5255 | 6035.2809 | 5998.2647 | 5961.4756 | 5924.912 | 5887.423 | 5850.1712 | 5813.1551 | 5776.3732 | 5739.8241 | 5716.1025 | 5692.479 | 5668.9531 | 5645.5245 | 5622.1927 | 5603.1599 | 5584.1915 | 5565.2874 | 5546.4473 | 5527.6709 | 5513.3432 | 5499.0526 | 5484.799 | 5470.5824 | 5456.4026 | 5477.3581 | 5498.3941 | 5519.5109 | 5540.7087 | 5561.988 | 5534.896 | 5507.936 | 5481.1072 | 5454.4092 | 5427.8412 | 5401.4026 | 5375.0928 | 5348.9112 | 5348.9112 | 5348.9112 | 5348.9112 | 5348.9112 | 5348.9112 | 5348.9112 | 5348.9112 | 5348.9112 | 5348.9112 | 5348.9112 | 5348.9112 | 5348.9112 | 5348.9112 | 5348.9112 | 5348.9112 | 5348.9112 | 5348.9112 | 5348.9112 | 5348.9112 | 5348.9112 | [6 empty] | 765 | 770 | 775 | 780 | 783.3 | 791 | 799 | 807 | 815 | 823 | 830.3 | 836 | 842 | 848 | 854 | 860 | 866 | 872 | 878 | 884 | 890 | 896 | 902 | 908 | 914 | 920 | 926 | 932 | 938 | 944 | 953.3 | 932.619 | 912.3867 | 892.5933 | 873.2294 | 854.2854 | 835.7525 | 817.6216 | 799.8841 | 799.8841 | 799.8841 | 799.8841 | 799.8841 | 799.8841 | 799.8841 | 799.8841 | 799.8841 | 799.8841 | 799.8841 | 799.8841 | 799.8841 | 799.8841 | 799.8841 | 799.8841 | 799.8841 | 799.8841 | 799.8841 | 799.8841 | 799.8841 | [6 empty] | 4.174 | 4.1741 | 4.1741 | 4.1741 | 4.1741 | 4.1485 | 4.1231 | 4.0978 | 4.0726 | 4.0477 | 4.022 | 3.9966 | 3.9713 | 3.9462 | 3.9212 | 3.8964 | 3.8718 | 3.8474 | 3.8231 | 3.7989 | 3.7742 | 3.7495 | 3.7251 | 3.7008 | 3.6767 | 3.6519 | 3.6273 | 3.6028 | 3.5785 | 3.5544 | 3.5544 | 3.5544 | 3.5544 | 3.5544 | 3.5544 | 3.5528 | 3.5512 | 3.5496 | 3.548 | 3.5464 | 3.5448 | 3.5432 | 3.5416 | 3.5416 | 3.5416 | 3.5416 | 3.5416 | 3.5416 | 3.5416 | 3.5416 | 3.5416 | 3.5416 | 3.5416 | 3.5416 | 3.5416 | 3.5416 | 3.5416 | 3.5416 | 3.5416 | 3.5416 | 3.5416 | 3.5416 | 3.5416
480 | Mangere - Otahuhu | AHP | Mangere | 2060 | 384.1934 | 383.1451 | 382.0996 | 381.0571 | 380.0173 | 381.0719 | 382.1295 | 383.1899 | 384.2533 | 385.3197 | 386.3948 | 387.473 | 388.5542 | 389.6383 | 390.7255 | 391.7502 | 392.7776 | 393.8077 | 394.8405 | 395.8759 | 396.8119 | 397.7501 | 398.6905 | 399.6332 | 400.578 | 401.8368 | 403.0995 | 404.3661 | 405.6368 | 406.9114 | 408.0922 | 409.2764 | 410.4641 | 411.6552 | 412.8498 | 411.6247 | 410.4032 | 409.1854 | 407.9711 | 406.7605 | 405.5535 | 404.35 | 403.1501 | 403.1501 | 403.1501 | 403.1501 | 403.1501 | 403.1501 | 403.1501 | 403.1501 | 403.1501 | 403.1501 | 403.1501 | 403.1501 | 403.1501 | 403.1501 | 403.1501 | 403.1501 | 403.1501 | 403.1501 | 403.1501 | 403.1501 | 403.1501 |  | 1840 | 1834.9795 | 1829.9727 | 1824.9795 | 1820 | 1813.383 | 1806.79 | 1800.221 | 1793.6759 | 1787.1546 | 1780.306 | 1773.4836 | 1766.6874 | 1759.9173 | 1753.173 | 1746.389 | 1739.6312 | 1732.8996 | 1726.194 | 1719.5144 | 1712.0648 | 1704.6475 | 1697.2623 | 1689.9091 | 1682.5878 | 1676.1572 | 1669.7512 | 1663.3697 | 1657.0125 | 1650.6797 | 1655.2767 | 1659.8865 | 1664.5092 | 1669.1447 | 1673.7931 | 1667.9962 | 1662.2194 | 1656.4626 | 1650.7257 | 1645.0088 | 1639.3116 | 1633.6341 | 1627.9763 | 1627.9763 | 1627.9763 | 1627.9763 | 1627.9763 | 1627.9763 | 1627.9763 | 1627.9763 | 1627.9763 | 1627.9763 | 1627.9763 | 1627.9763 | 1627.9763 | 1627.9763 | 1627.9763 | 1627.9763 | 1627.9763 | 1627.9763 | 1627.9763 | 1627.9763 | 1627.9763 | [6 empty] | 1489 | 1518 | 1547 | 1576 | 1605.1 | 1632 | 1659 | 1686 | 1713 | 1740 | 1765.4 | 1807 | 1848 | 1889 | 1930 | 1971 | 2012 | 2053 | 2094 | 2135 | 2176 | 2217 | 2258 | 2299 | 2340 | 2381 | 2422 | 2463 | 2504 | 2545 | 2587.6 | 2442.7304 | 2305.9715 | 2176.8692 | 2054.9948 | 1939.9437 | 1831.3339 | 1728.8047 | 1632.0157 | 1632.0157 | 1632.0157 | 1632.0157 | 1632.0157 | 1632.0157 | 1632.0157 | 1632.0157 | 1632.0157 | 1632.0157 | 1632.0157 | 1632.0157 | 1632.0157 | 1632.0157 | 1632.0157 | 1632.0157 | 1632.0157 | 1632.0157 | 1632.0157 | 1632.0157 | 1632.0157 | [6 empty] | 4.7893 | 4.7893 | 4.7893 | 4.7893 | 4.7893 | 4.7586 | 4.7282 | 4.698 | 4.668 | 4.6381 | 4.6075 | 4.5771 | 4.5468 | 4.5168 | 4.487 | 4.4579 | 4.429 | 4.4004 | 4.3719 | 4.3436 | 4.3145 | 4.2857 | 4.2571 | 4.2287 | 4.2004 | 4.1712 | 4.1423 | 4.1135 | 4.085 | 4.0566 | 4.0561 | 4.0557 | 4.0552 | 4.0547 | 4.0542 | 4.0522 | 4.0502 | 4.0482 | 4.0462 | 4.0442 | 4.0422 | 4.0401 | 4.0381 | 4.0381 | 4.0381 | 4.0381 | 4.0381 | 4.0381 | 4.0381 | 4.0381 | 4.0381 | 4.0381 | 4.0381 | 4.0381 | 4.0381 | 4.0381 | 4.0381 | 4.0381 | 4.0381 | 4.0381 | 4.0381 | 4.0381 | 4.0381
481 | Mangere - Otahuhu | AHP | Mangere | 2060 | 774.8484 | 767.9713 | 761.1552 | 754.3997 | 747.704 | 754.2687 | 760.891 | 767.5715 | 774.3106 | 781.1089 | 787.8044 | 794.5574 | 801.3682 | 808.2375 | 815.1656 | 821.3662 | 827.614 | 833.9093 | 840.2525 | 846.644 | 852.2128 | 857.8182 | 863.4605 | 869.1399 | 874.8566 | 882.2273 | 889.6601 | 897.1555 | 904.7141 | 912.3363 | 919.2095 | 926.1345 | 933.1117 | 940.1415 | 947.2242 | 982.9747 | 1020.0746 | 1058.5746 | 1098.5278 | 1139.9889 | 1183.0148 | 1227.6647 | 1273.9997 | 1273.9997 | 1273.9997 | 1273.9997 | 1273.9997 | 1273.9997 | 1273.9997 | 1273.9997 | 1273.9997 | 1273.9997 | 1273.9997 | 1273.9997 | 1273.9997 | 1273.9997 | 1273.9997 | 1273.9997 | 1273.9997 | 1273.9997 | 1273.9997 | 1273.9997 | 1273.9997 |  | 3140 | 3112.1312 | 3084.5097 | 3057.1334 | 3030 | 3058.8706 | 3088.0163 | 3117.4397 | 3147.1435 | 3177.1303 | 3206.7412 | 3236.628 | 3266.7934 | 3297.2399 | 3327.9702 | 3351.7718 | 3375.7436 | 3399.8868 | 3424.2027 | 3448.6925 | 3469.8297 | 3491.0965 | 3512.4936 | 3534.0219 | 3555.6821 | 3584.0047 | 3612.553 | 3641.3286 | 3670.3335 | 3699.5694 | 3727.2905 | 3755.2194 | 3783.3575 | 3811.7065 | 3840.2679 | 3983.2678 | 4131.5925 | 4285.4405 | 4445.0172 | 4610.5361 | 4782.2185 | 4960.2938 | 5145 | 5145 | 5145 | 5145 | 5145 | 5145 | 5145 | 5145 | 5145 | 5145 | 5145 | 5145 | 5145 | 5145 | 5145 | 5145 | 5145 | 5145 | 5145 | 5145 | 5145 | [6 empty] | 147 | 148 | 149 | 150 | 149.7 | 152 | 154 | 156 | 158 | 160 | 161.4 | 163 | 165 | 167 | 169 | 171 | 173 | 175 | 177 | 179 | 181 | 183 | 185 | 187 | 189 | 191 | 193 | 195 | 197 | 199 | 191.6 | 198.0286 | 204.6729 | 211.5401 | 218.6377 | 225.9735 | 233.5554 | 241.3917 | 249.4909 | 249.4909 | 249.4909 | 249.4909 | 249.4909 | 249.4909 | 249.4909 | 249.4909 | 249.4909 | 249.4909 | 249.4909 | 249.4909 | 249.4909 | 249.4909 | 249.4909 | 249.4909 | 249.4909 | 249.4909 | 249.4909 | 249.4909 | 249.4909 | [6 empty] | 4.0524 | 4.0524 | 4.0524 | 4.0524 | 4.0524 | 4.0554 | 4.0584 | 4.0614 | 4.0644 | 4.0675 | 4.0705 | 4.0735 | 4.0765 | 4.0795 | 4.0826 | 4.0807 | 4.0789 | 4.077 | 4.0752 | 4.0734 | 4.0716 | 4.0697 | 4.0679 | 4.0661 | 4.0643 | 4.0625 | 4.0606 | 4.0587 | 4.0569 | 4.0551 | 4.0549 | 4.0547 | 4.0546 | 4.0544 | 4.0542 | 4.0523 | 4.0503 | 4.0483 | 4.0463 | 4.0444 | 4.0424 | 4.0404 | 4.0385 | 4.0385 | 4.0385 | 4.0385 | 4.0385 | 4.0385 | 4.0385 | 4.0385 | 4.0385 | 4.0385 | 4.0385 | 4.0385 | 4.0385 | 4.0385 | 4.0385 | 4.0385 | 4.0385 | 4.0385 | 4.0385 | 4.0385 | 4.0385
482 | Mangere - Otahuhu | AHP | Mangere | 2060 | 1145.0502 | 1165.1949 | 1185.694 | 1206.5537 | 1227.7804 | 1241.7741 | 1255.9274 | 1270.2419 | 1284.7195 | 1299.3622 | 1313.6407 | 1328.0761 | 1342.67 | 1357.4244 | 1372.3409 | 1377.4853 | 1382.649 | 1387.832 | 1393.0345 | 1398.2565 | 1398.2565 | 1398.2565 | 1398.2565 | 1398.2565 | 1398.2565 | 1398.2565 | 1398.2565 | 1398.2565 | 1398.2565 | 1398.2565 | 1398.2565 | 1398.2565 | 1398.2565 | 1398.2565 | 1398.2565 | 1456.9598 | 1518.1277 | 1581.8635 | 1648.2753 | 1717.4752 | 1789.5803 | 1864.7126 | 1942.9992 | 1942.9992 | 1942.9992 | 1942.9992 | 1942.9992 | 1942.9992 | 1942.9992 | 1942.9992 | 1942.9992 | 1942.9992 | 1942.9992 | 1942.9992 | 1942.9992 | 1942.9992 | 1942.9992 | 1942.9992 | 1942.9992 | 1942.9992 | 1942.9992 | 1942.9992 | 1942.9992 |  | 4120 | 4190.6613 | 4262.5345 | 4335.6403 | 4410 | 4454.7892 | 4500.0334 | 4545.737 | 4591.9048 | 4638.5415 | 4683.7907 | 4729.4812 | 4775.6174 | 4822.2037 | 4869.2444 | 4878.1331 | 4887.0379 | 4895.959 | 4904.8964 | 4913.8501 | 4904.6798 | 4895.5266 | 4886.3905 | 4877.2714 | 4868.1694 | 4858.9987 | 4849.8454 | 4840.7093 | 4831.5904 | 4822.4886 | 4822.4886 | 4822.4886 | 4822.4886 | 4822.4886 | 4822.4886 | 5022.4858 | 5230.7773 | 5447.7069 | 5673.633 | 5908.9287 | 6153.9825 | 6409.1991 | 6675 | 6675 | 6675 | 6675 | 6675 | 6675 | 6675 | 6675 | 6675 | 6675 | 6675 | 6675 | 6675 | 6675 | 6675 | 6675 | 6675 | 6675 | 6675 | 6675 | 6675 | [6 empty] | 803 | 813 | 823 | 833 | 841.1 | 851 | 861 | 871 | 881 | 891 | 900 | 907 | 914 | 921 | 928 | 935 | 942 | 949 | 956 | 963 | 970 | 977 | 984 | 991 | 998 | 1005 | 1012 | 1019 | 1026 | 1033 | 1048.4 | 1074.169 | 1100.5714 | 1127.6228 | 1155.339 | 1183.7365 | 1212.832 | 1242.6426 | 1273.186 | 1273.186 | 1273.186 | 1273.186 | 1273.186 | 1273.186 | 1273.186 | 1273.186 | 1273.186 | 1273.186 | 1273.186 | 1273.186 | 1273.186 | 1273.186 | 1273.186 | 1273.186 | 1273.186 | 1273.186 | 1273.186 | 1273.186 | 1273.186 | [6 empty] | 3.5981 | 3.5965 | 3.595 | 3.5934 | 3.5918 | 3.5874 | 3.583 | 3.5786 | 3.5742 | 3.5699 | 3.5655 | 3.5612 | 3.5568 | 3.5525 | 3.5481 | 3.5413 | 3.5345 | 3.5278 | 3.521 | 3.5143 | 3.5077 | 3.5012 | 3.4946 | 3.4881 | 3.4816 | 3.475 | 3.4685 | 3.462 | 3.4554 | 3.4489 | 3.4489 | 3.4489 | 3.4489 | 3.4489 | 3.4489 | 3.4472 | 3.4455 | 3.4439 | 3.4422 | 3.4405 | 3.4388 | 3.4371 | 3.4354 | 3.4354 | 3.4354 | 3.4354 | 3.4354 | 3.4354 | 3.4354 | 3.4354 | 3.4354 | 3.4354 | 3.4354 | 3.4354 | 3.4354 | 3.4354 | 3.4354 | 3.4354 | 3.4354 | 3.4354 | 3.4354 | 3.4354 | 3.4354
483 | Otara - Papatoetoe | AHP | Mangere | 2060 | 865.1965 | 881.0319 | 897.1571 | 913.5774 | 930.2983 | 930.2983 | 930.2983 | 930.2983 | 930.2983 | 930.2983 | 930.2983 | 930.2983 | 930.2983 | 930.2983 | 930.2983 | 934.8006 | 939.3246 | 943.8706 | 948.4386 | 953.0286 | 959.5551 | 966.1263 | 972.7424 | 979.4039 | 986.111 | 994.9092 | 1003.7859 | 1012.7418 | 1021.7775 | 1030.8939 | 1039.1795 | 1047.5317 | 1055.951 | 1064.4379 | 1072.9931 | 1096.2724 | 1120.0568 | 1144.3572 | 1169.1848 | 1194.5511 | 1220.4677 | 1246.9466 | 1274 | 1274 | 1274 | 1274 | 1274 | 1274 | 1274 | 1274 | 1274 | 1274 | 1274 | 1274 | 1274 | 1274 | 1274 | 1274 | 1274 | 1274 | 1274 | 1274 | 1274 |  | 3410 | 3470.8517 | 3532.7893 | 3595.8321 | 3660 | 3644.5352 | 3629.1358 | 3613.8014 | 3598.5319 | 3583.3268 | 3567.8592 | 3552.4584 | 3537.124 | 3521.8559 | 3506.6536 | 3506.8612 | 3507.0688 | 3507.2764 | 3507.4841 | 3507.6917 | 3514.2554 | 3520.8313 | 3527.4195 | 3534.0201 | 3540.633 | 3553.9239 | 3567.2647 | 3580.6555 | 3594.0966 | 3607.5882 | 3635.5226 | 3663.6733 | 3692.0419 | 3720.6303 | 3749.44 | 3828.8796 | 3910.0023 | 3992.8438 | 4077.4404 | 4163.8294 | 4252.0488 | 4342.1372 | 4434.1344 | 4434.1344 | 4434.1344 | 4434.1344 | 4434.1344 | 4434.1344 | 4434.1344 | 4434.1344 | 4434.1344 | 4434.1344 | 4434.1344 | 4434.1344 | 4434.1344 | 4434.1344 | 4434.1344 | 4434.1344 | 4434.1344 | 4434.1344 | 4434.1344 | 4434.1344 | 4434.1344 | [6 empty] | 488 | 492 | 496 | 500 | 505 | 510 | 515 | 520 | 525 | 530 | 533.1 | 535 | 537 | 539 | 541 | 543 | 545 | 547 | 549 | 551 | 553 | 555 | 557 | 559 | 561 | 563 | 565 | 567 | 569 | 571 | 573.3 | 585.5781 | 598.1192 | 610.9288 | 624.0128 | 637.3771 | 651.0275 | 664.9703 | 679.2116 | 679.2116 | 679.2116 | 679.2116 | 679.2116 | 679.2116 | 679.2116 | 679.2116 | 679.2116 | 679.2116 | 679.2116 | 679.2116 | 679.2116 | 679.2116 | 679.2116 | 679.2116 | 679.2116 | 679.2116 | 679.2116 | 679.2116 | 679.2116 | [6 empty] | 3.9413 | 3.9395 | 3.9378 | 3.936 | 3.9342 | 3.9176 | 3.901 | 3.8846 | 3.8681 | 3.8518 | 3.8352 | 3.8186 | 3.8021 | 3.7857 | 3.7694 | 3.7515 | 3.7336 | 3.7158 | 3.6982 | 3.6806 | 3.6624 | 3.6443 | 3.6263 | 3.6083 | 3.5905 | 3.5721 | 3.5538 | 3.5356 | 3.5175 | 3.4995 | 3.4985 | 3.4974 | 3.4964 | 3.4954 | 3.4944 | 3.4926 | 3.4909 | 3.4892 | 3.4874 | 3.4857 | 3.484 | 3.4822 | 3.4805 | 3.4805 | 3.4805 | 3.4805 | 3.4805 | 3.4805 | 3.4805 | 3.4805 | 3.4805 | 3.4805 | 3.4805 | 3.4805 | 3.4805 | 3.4805 | 3.4805 | 3.4805 | 3.4805 | 3.4805 | 3.4805 | 3.4805 | 3.4805
484 | Otara - Papatoetoe | AHP | Mangere | 2060 | 709.8696 | 712.5033 | 715.1469 | 717.8002 | 720.4634 | 727.0238 | 733.6439 | 740.3243 | 747.0656 | 753.8682 | 760.5597 | 767.3106 | 774.1214 | 780.9927 | 787.9249 | 794.1224 | 800.3685 | 806.6638 | 813.0086 | 819.4033 | 824.9697 | 830.5739 | 836.2162 | 841.8968 | 847.616 | 854.9827 | 862.4135 | 869.9089 | 877.4694 | 885.0957 | 891.9657 | 898.8892 | 905.8663 | 912.8976 | 919.9835 | 923.318 | 926.6645 | 930.0231 | 933.394 | 936.777 | 940.1723 | 943.5799 | 946.9999 | 946.9999 | 946.9999 | 946.9999 | 946.9999 | 946.9999 | 946.9999 | 946.9999 | 946.9999 | 946.9999 | 946.9999 | 946.9999 | 946.9999 | 946.9999 | 946.9999 | 946.9999 | 946.9999 | 946.9999 | 946.9999 | 946.9999 | 946.9999 |  | 2690 | 2699.9447 | 2709.9262 | 2719.9446 | 2730 | 2754.8702 | 2779.9669 | 2805.2922 | 2830.8483 | 2856.6371 | 2882.0088 | 2907.6057 | 2933.43 | 2959.4837 | 2985.7688 | 3006.1217 | 3026.6134 | 3047.2447 | 3068.0167 | 3088.9302 | 3106.6708 | 3124.5132 | 3142.4581 | 3160.5061 | 3178.6577 | 3202.9087 | 3227.3446 | 3251.967 | 3276.7773 | 3301.7768 | 3327.3412 | 3353.1036 | 3379.0655 | 3405.2283 | 3431.5937 | 3442.2773 | 3452.9942 | 3463.7445 | 3474.5282 | 3485.3454 | 3496.1964 | 3507.0811 | 3517.9998 | 3517.9998 | 3517.9998 | 3517.9998 | 3517.9998 | 3517.9998 | 3517.9998 | 3517.9998 | 3517.9998 | 3517.9998 | 3517.9998 | 3517.9998 | 3517.9998 | 3517.9998 | 3517.9998 | 3517.9998 | 3517.9998 | 3517.9998 | 3517.9998 | 3517.9998 | 3517.9998 | [6 empty] | 219 | 221 | 223 | 225 | 225.8 | 228 | 230 | 232 | 234 | 236 | 239.2 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 268.3 | 270.6686 | 273.0582 | 275.4688 | 277.9007 | 280.3541 | 282.8292 | 285.3261 | 287.845 | 287.845 | 287.845 | 287.845 | 287.845 | 287.845 | 287.845 | 287.845 | 287.845 | 287.845 | 287.845 | 287.845 | 287.845 | 287.845 | 287.845 | 287.845 | 287.845 | 287.845 | 287.845 | 287.845 | 287.845 | [6 empty] | 3.7894 | 3.7894 | 3.7893 | 3.7893 | 3.7892 | 3.7892 | 3.7893 | 3.7893 | 3.7893 | 3.7893 | 3.7893 | 3.7893 | 3.7894 | 3.7894 | 3.7894 | 3.7855 | 3.7815 | 3.7776 | 3.7737 | 3.7697 | 3.7658 | 3.7619 | 3.7579 | 3.754 | 3.7501 | 3.7462 | 3.7422 | 3.7383 | 3.7343 | 3.7304 | 3.7303 | 3.7303 | 3.7302 | 3.7301 | 3.7301 | 3.7282 | 3.7263 | 3.7244 | 3.7225 | 3.7206 | 3.7187 | 3.7168 | 3.7149 | 3.7149 | 3.7149 | 3.7149 | 3.7149 | 3.7149 | 3.7149 | 3.7149 | 3.7149 | 3.7149 | 3.7149 | 3.7149 | 3.7149 | 3.7149 | 3.7149 | 3.7149 | 3.7149 | 3.7149 | 3.7149 | 3.7149 | 3.7149
485 | Otara - Papatoetoe |  |  | 2052 | 1919.4715 | 1937.5511 | 1955.801 | 1974.2227 | 1992.818 | 1996.3327 | 1999.8536 | 2003.3807 | 2006.914 | 2010.4535 | 2014.0367 | 2017.6262 | 2021.2221 | 2024.8244 | 2028.4332 | 2031.7461 | 2035.0643 | 2038.388 | 2041.7171 | 2045.0517 | 2048.0219 | 2050.9965 | 2053.9754 | 2056.9586 | 2059.9461 | 2063.9429 | 2067.9474 | 2071.9597 | 2075.9798 | 2080.0076 | 2083.7562 | 2087.5115 | 2091.2735 | 2095.0424 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 | 2098.818 |  | 6820 | 6884.0909 | 6948.7841 | 7014.0852 | 7080 | 7063.0641 | 7046.1688 | 7029.3139 | 7012.4992 | 6995.7248 | 6978.5041 | 6961.3258 | 6944.1898 | 6927.0959 | 6910.0441 | 6890.0012 | 6870.0164 | 6850.0896 | 6830.2206 | 6810.4093 | 6788.7178 | 6767.0954 | 6745.5419 | 6724.057 | 6702.6405 | 6683.8021 | 6665.0167 | 6646.284 | 6627.604 | 6608.9765 | 6620.8586 | 6632.762 | 6644.6869 | 6656.6332 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | 6668.601 | [6 empty] | 747 | 752 | 757 | 762 | 768.1 | 775 | 782 | 789 | 796 | 803 | 809.6 | 811 | 813 | 815 | 817 | 819 | 821 | 823 | 825 | 827 | 829 | 831 | 833 | 835 | 837 | 839 | 841 | 843 | 845 | 847 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | 842.4 | [6 empty] | 3.5531 | 3.553 | 3.5529 | 3.5528 | 3.5528 | 3.538 | 3.5233 | 3.5087 | 3.4942 | 3.4797 | 3.4649 | 3.4503 | 3.4356 | 3.4211 | 3.4066 | 3.3912 | 3.3758 | 3.3605 | 3.3453 | 3.3302 | 3.3148 | 3.2994 | 3.2841 | 3.2689 | 3.2538 | 3.2384 | 3.223 | 3.2077 | 3.1925 | 3.1774 | 3.1774 | 3.1774 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773 | 3.1773
486 | Otara - Papatoetoe |  |  | 2052 | 2028.5778 | 2054.3349 | 2080.419 | 2106.8343 | 2133.585 | 2136.2655 | 2138.9495 | 2141.6368 | 2144.3275 | 2147.0215 | 2149.7543 | 2152.4906 | 2155.2304 | 2157.9736 | 2160.7203 | 2163.2225 | 2165.7276 | 2168.2356 | 2170.7464 | 2173.2602 | 2175.4898 | 2177.7217 | 2179.9558 | 2182.1923 | 2184.431 | 2187.432 | 2190.4371 | 2193.4463 | 2196.4597 | 2199.4772 | 2202.2915 | 2205.1095 | 2207.931 | 2210.7562 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 | 2213.585 |  | 7210 | 7300.7714 | 7392.6856 | 7485.7569 | 7580 | 7571.5644 | 7563.1382 | 7554.7214 | 7546.314 | 7537.9159 | 7529.4366 | 7520.9668 | 7512.5065 | 7504.0558 | 7495.6145 | 7481.92 | 7468.2505 | 7454.6059 | 7440.9863 | 7427.3915 | 7412.5165 | 7397.6713 | 7382.8558 | 7368.0699 | 7353.3137 | 7340.7738 | 7328.2553 | 7315.7581 | 7303.2822 | 7290.8276 | 7300.0772 | 7309.3386 | 7318.6117 | 7327.8966 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | 7337.1933 | [6 empty] | 935 | 943 | 951 | 959 | 967.6 | 977 | 986 | 995 | 1004 | 1013 | 1022.7 | 1025 | 1028 | 1031 | 1034 | 1037 | 1040 | 1043 | 1046 | 1049 | 1052 | 1055 | 1058 | 1061 | 1064 | 1067 | 1070 | 1073 | 1076 | 1079 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | 1078.6 | [6 empty] | 3.5542 | 3.5538 | 3.5535 | 3.5531 | 3.5527 | 3.5443 | 3.5359 | 3.5275 | 3.5192 | 3.5109 | 3.5025 | 3.4941 | 3.4857 | 3.4774 | 3.469 | 3.4587 | 3.4484 | 3.4381 | 3.4278 | 3.4176 | 3.4073 | 3.397 | 3.3867 | 3.3765 | 3.3662 | 3.3559 | 3.3456 | 3.3353 | 3.325 | 3.3148 | 3.3148 | 3.3147 | 3.3147 | 3.3147 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146 | 3.3146
487 | Otara - Papatoetoe |  |  | 2052 | 3.0318 | 2.7395 | 2.4754 | 2.2368 | 2.0212 | 3.8758 | 7.4323 | 14.2522 | 27.3301 | 52.4084 | 60.0817 | 68.8786 | 78.9634 | 90.5248 | 103.7789 | 111.7378 | 120.3072 | 129.5337 | 139.4678 | 150.1638 | 157.585 | 165.373 | 173.5459 | 182.1227 | 191.1234 | 198.7957 | 206.776 | 215.0766 | 223.7104 | 232.6909 | 238.8249 | 245.1206 | 251.5823 | 258.2143 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 | 265.0212 |  | 30 | 27.1081 | 24.4949 | 22.1336 | 20 | 31.2898 | 48.9527 | 76.5861 | 119.8184 | 187.455 | 212.9449 | 241.901 | 274.7945 | 312.1609 | 354.6083 | 380.6713 | 408.6498 | 438.6847 | 470.9271 | 505.5392 | 529.76 | 555.1412 | 581.7384 | 609.6099 | 638.8168 | 663.8307 | 689.8241 | 716.8354 | 744.9043 | 774.0722 | 794.0535 | 814.5505 | 835.5766 | 857.1455 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | 879.2711 | [6 empty] | 7550 | 7659 | 7768 | 7877 | 7987.6 | 8073 | 8159 | 8245 | 8331 | 8417 | 8501.1 | 8578 | 8654 | 8730 | 8806 | 8882 | 8958 | 9034 | 9110 | 9186 | 9262 | 9338 | 9414 | 9490 | 9566 | 9642 | 9718 | 9794 | 9870 | 9946 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | 10029.4 | [6 empty] | 9.8952 | 9.8952 | 9.8952 | 9.8952 | 9.8952 | 8.0731 | 6.5865 | 5.3736 | 4.3841 | 3.5768 | 3.5443 | 3.512 | 3.48 | 3.4483 | 3.417 | 3.4068 | 3.3967 | 3.3866 | 3.3766 | 3.3666 | 3.3617 | 3.3569 | 3.3521 | 3.3472 | 3.3424 | 3.3393 | 3.3361 | 3.3329 | 3.3298 | 3.3266 | 3.3248 | 3.3231 | 3.3213 | 3.3195 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177 | 3.3177
488 | Otara - Papatoetoe |  |  | 2052 | 214.6315 | 230.3777 | 247.2791 | 265.4204 | 284.8927 | 288.8937 | 292.9509 | 297.065 | 301.237 | 305.4675 | 309.552 | 313.6912 | 317.8857 | 322.1363 | 326.4438 | 330.2121 | 334.0239 | 337.8797 | 341.7801 | 345.7254 | 349.1031 | 352.5138 | 355.9578 | 359.4354 | 362.9471 | 367.4721 | 372.0535 | 376.692 | 381.3883 | 386.1432 | 390.3983 | 394.7003 | 399.0497 | 403.447 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 | 407.8927 |  | 820 | 874.3531 | 932.309 | 994.1064 | 1060 | 1073.0536 | 1086.268 | 1099.6451 | 1113.1869 | 1126.8955 | 1140.1408 | 1153.5419 | 1167.1005 | 1180.8184 | 1194.6976 | 1205.7136 | 1216.8311 | 1228.0512 | 1239.3747 | 1250.8026 | 1260.2943 | 1269.8581 | 1279.4945 | 1289.2039 | 1298.9871 | 1312.1279 | 1325.4016 | 1338.8096 | 1352.3532 | 1366.0339 | 1380.1491 | 1394.4101 | 1408.8185 | 1423.3757 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | 1438.0834 | [6 empty] | 1222 | 1230 | 1238 | 1246 | 1255.3 | 1267 | 1279 | 1291 | 1303 | 1315 | 1326.6 | 1328 | 1329 | 1330 | 1331 | 1332 | 1333 | 1334 | 1335 | 1336 | 1337 | 1338 | 1339 | 1340 | 1341 | 1342 | 1343 | 1344 | 1345 | 1346 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | 1350.2 | [6 empty] | 3.8205 | 3.7953 | 3.7703 | 3.7454 | 3.7207 | 3.7144 | 3.708 | 3.7017 | 3.6954 | 3.6891 | 3.6832 | 3.6773 | 3.6714 | 3.6656 | 3.6597 | 3.6513 | 3.6429 | 3.6346 | 3.6262 | 3.6179 | 3.6101 | 3.6023 | 3.5945 | 3.5867 | 3.579 | 3.5707 | 3.5624 | 3.5541 | 3.5459 | 3.5376 | 3.5352 | 3.5328 | 3.5304 | 3.528 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256 | 3.5256
489 | Otara - Papatoetoe |  |  | 2052 | 353.3445 | 356.8373 | 360.3646 | 363.9268 | 367.5242 | 369.1062 | 370.6949 | 372.2905 | 373.8929 | 375.5022 | 377.115 | 378.7348 | 380.3615 | 381.9952 | 383.6359 | 385.0978 | 386.5653 | 388.0384 | 389.5171 | 391.0015 | 392.2961 | 393.5951 | 394.8983 | 396.2059 | 397.5178 | 399.2579 | 401.0056 | 402.7609 | 404.524 | 406.2947 | 407.9274 | 409.5667 | 411.2126 | 412.8651 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 | 414.5242 |  | 1500 | 1514.7801 | 1529.7059 | 1544.7787 | 1560 | 1567.8353 | 1575.71 | 1583.6243 | 1591.5783 | 1599.5722 | 1607.588 | 1615.644 | 1623.7404 | 1631.8773 | 1640.055 | 1645.5196 | 1651.0024 | 1656.5034 | 1662.0227 | 1667.5605 | 1672.2848 | 1677.0225 | 1681.7736 | 1686.5382 | 1691.3163 | 1697.9036 | 1704.5166 | 1711.1554 | 1717.82 | 1724.5106 | 1731.4213 | 1738.3597 | 1745.3259 | 1752.32 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | 1759.3422 | [6 empty] | 42 | 42 | 42 | 42 | 43.8 | 44 | 44 | 44 | 44 | 44 | 45.8 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | 51.7 | [6 empty] | 4.2451 | 4.245 | 4.2449 | 4.2448 | 4.2446 | 4.2477 | 4.2507 | 4.2537 | 4.2568 | 4.2598 | 4.2629 | 4.2659 | 4.2689 | 4.272 | 4.275 | 4.273 | 4.271 | 4.2689 | 4.2669 | 4.2648 | 4.2628 | 4.2608 | 4.2588 | 4.2567 | 4.2547 | 4.2526 | 4.2506 | 4.2486 | 4.2465 | 4.2445 | 4.2444 | 4.2444 | 4.2443 | 4.2443 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442 | 4.2442
490 | Otara - Papatoetoe |  |  | 2052 | 792.5688 | 805.1908 | 818.0138 | 831.041 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 | 844.2757 |  | 2770 | 2813.9432 | 2858.5836 | 2903.9321 | 2950 | 2939.1342 | 2928.3083 | 2917.5224 | 2906.7762 | 2896.0695 | 2885.2022 | 2874.3756 | 2863.5897 | 2852.8442 | 2842.1391 | 2830.5073 | 2818.9231 | 2807.3863 | 2795.8968 | 2784.4542 | 2772.8204 | 2761.2353 | 2749.6985 | 2738.2099 | 2726.7694 | 2715.1335 | 2703.5473 | 2692.0105 | 2680.523 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | 2669.0845 | [6 empty] | 550 | 553 | 556 | 559 | 563.4 | 569 | 574 | 579 | 584 | 589 | 595.4 | 597 | 598 | 599 | 600 | 601 | 602 | 603 | 604 | 605 | 606 | 607 | 608 | 609 | 610 | 611 | 612 | 613 | 614 | 615 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | 619.1 | [6 empty] | 3.495 | 3.4948 | 3.4945 | 3.4943 | 3.4941 | 3.4812 | 3.4684 | 3.4557 | 3.4429 | 3.4302 | 3.4174 | 3.4045 | 3.3918 | 3.379 | 3.3664 | 3.3526 | 3.3389 | 3.3252 | 3.3116 | 3.298 | 3.2843 | 3.2705 | 3.2569 | 3.2433 | 3.2297 | 3.2159 | 3.2022 | 3.1885 | 3.1749 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614 | 3.1614
491 | Otara - Papatoetoe | AHP | Mangere | 2060 | 1114.3321 | 1139.549 | 1165.3364 | 1191.7075 | 1218.6753 | 1239.1828 | 1260.0354 | 1281.2389 | 1302.7993 | 1324.7224 | 1345.6725 | 1366.9539 | 1388.5719 | 1410.5318 | 1432.8389 | 1440.4366 | 1448.0746 | 1455.7531 | 1463.4723 | 1471.2324 | 1471.2324 | 1471.2324 | 1471.2324 | 1471.2324 | 1471.2324 | 1471.2324 | 1471.2324 | 1471.2324 | 1471.2324 | 1471.2324 | 1471.2324 | 1471.2324 | 1471.2324 | 1471.2324 | 1471.2324 | 1486.1622 | 1501.2435 | 1516.4778 | 1531.8668 | 1547.4118 | 1563.1147 | 1578.9769 | 1595 | 1595 | 1595 | 1595 | 1595 | 1595 | 1595 | 1595 | 1595 | 1595 | 1595 | 1595 | 1595 | 1595 | 1595 | 1595 | 1595 | 1595 | 1595 | 1595 | 1595 |  | 3770 | 3854.6089 | 3941.1166 | 4029.5658 | 4120 | 4189.635 | 4260.4469 | 4332.4557 | 4405.6815 | 4480.145 | 4551.4324 | 4623.854 | 4697.4281 | 4772.1729 | 4848.1069 | 4852.965 | 4857.8279 | 4862.6956 | 4867.5683 | 4872.4458 | 4851.3432 | 4830.332 | 4809.4118 | 4788.5822 | 4767.8428 | 4746.7361 | 4725.7229 | 4704.8027 | 4683.9751 | 4663.2397 | 4663.2397 | 4663.2397 | 4663.2397 | 4663.2397 | 4663.2397 | 4708.2616 | 4753.7181 | 4799.6135 | 4845.952 | 4892.7378 | 4939.9754 | 4987.669 | 5035.8231 | 5035.8231 | 5035.8231 | 5035.8231 | 5035.8231 | 5035.8231 | 5035.8231 | 5035.8231 | 5035.8231 | 5035.8231 | 5035.8231 | 5035.8231 | 5035.8231 | 5035.8231 | 5035.8231 | 5035.8231 | 5035.8231 | 5035.8231 | 5035.8231 | 5035.8231 | 5035.8231 | [6 empty] | 281 | 283 | 285 | 287 | 290.2 | 293 | 295 | 297 | 299 | 301 | 304.9 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 323.6 | 328.0284 | 332.5175 | 337.068 | 341.6807 | 346.3566 | 351.0965 | 355.9012 | 360.7717 | 360.7717 | 360.7717 | 360.7717 | 360.7717 | 360.7717 | 360.7717 | 360.7717 | 360.7717 | 360.7717 | 360.7717 | 360.7717 | 360.7717 | 360.7717 | 360.7717 | 360.7717 | 360.7717 | 360.7717 | 360.7717 | 360.7717 | 360.7717 | [6 empty] | 3.3832 | 3.3826 | 3.382 | 3.3813 | 3.3807 | 3.381 | 3.3812 | 3.3815 | 3.3817 | 3.382 | 3.3823 | 3.3826 | 3.3829 | 3.3832 | 3.3836 | 3.3691 | 3.3547 | 3.3403 | 3.326 | 3.3118 | 3.2975 | 3.2832 | 3.269 | 3.2548 | 3.2407 | 3.2264 | 3.2121 | 3.1979 | 3.1837 | 3.1696 | 3.1696 | 3.1696 | 3.1696 | 3.1696 | 3.1696 | 3.1681 | 3.1665 | 3.165 | 3.1634 | 3.1619 | 3.1603 | 3.1588 | 3.1573 | 3.1573 | 3.1573 | 3.1573 | 3.1573 | 3.1573 | 3.1573 | 3.1573 | 3.1573 | 3.1573 | 3.1573 | 3.1573 | 3.1573 | 3.1573 | 3.1573 | 3.1573 | 3.1573 | 3.1573 | 3.1573 | 3.1573 | 3.1573
492 | Otara - Papatoetoe |  |  | 2052 | 372.4133 | 388.517 | 405.3171 | 422.8436 | 441.128 | 452.7544 | 464.6872 | 476.9345 | 489.5045 | 502.4059 | 514.3218 | 526.5204 | 539.0083 | 551.7923 | 564.8796 | 575.9146 | 587.1653 | 598.6357 | 610.3302 | 622.2532 | 632.1745 | 642.2541 | 652.4944 | 662.898 | 673.4674 | 686.7309 | 700.2555 | 714.0466 | 728.1092 | 742.4488 | 754.9561 | 767.6741 | 780.6063 | 793.7564 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 | 807.128 |  | 1140 | 1184.7905 | 1231.3407 | 1279.72 | 1330 | 1366.5838 | 1404.1739 | 1442.798 | 1482.4845 | 1523.2626 | 1561.6205 | 1600.9443 | 1641.2583 | 1682.5876 | 1724.9575 | 1759.1628 | 1794.0464 | 1829.6218 | 1865.9025 | 1902.9028 | 1934.3013 | 1966.2179 | 1998.6611 | 2031.6396 | 2065.1623 | 2106.7264 | 2149.127 | 2192.3809 | 2236.5054 | 2281.518 | 2318.1988 | 2355.4694 | 2393.3393 | 2431.8179 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | 2470.9153 | [6 empty] | 1613 | 1635 | 1657 | 1679 | 1700.1 | 1719 | 1738 | 1757 | 1776 | 1795 | 1813.5 | 1825 | 1837 | 1849 | 1861 | 1873 | 1885 | 1897 | 1909 | 1921 | 1933 | 1945 | 1957 | 1969 | 1981 | 1993 | 2005 | 2017 | 2029 | 2041 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | 2050.1 | [6 empty] | 3.0611 | 3.0495 | 3.038 | 3.0265 | 3.015 | 3.0184 | 3.0218 | 3.0251 | 3.0285 | 3.0319 | 3.0363 | 3.0406 | 3.045 | 3.0493 | 3.0537 | 3.0546 | 3.0554 | 3.0563 | 3.0572 | 3.0581 | 3.0598 | 3.0614 | 3.0631 | 3.0648 | 3.0665 | 3.0678 | 3.0691 | 3.0704 | 3.0717 | 3.073 | 3.0706 | 3.0683 | 3.066 | 3.0637 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614 | 3.0614
493 | Otara - Papatoetoe |  |  | 2052 | 1412.9618 | 1450.2091 | 1488.4383 | 1527.6752 | 1567.9465 | 1568.5339 | 1569.1215 | 1569.7094 | 1570.2974 | 1570.8857 | 1571.4846 | 1572.0837 | 1572.683 | 1573.2825 | 1573.8823 | 1574.4785 | 1575.0748 | 1575.6714 | 1576.2682 | 1576.8653 | 1577.4234 | 1577.9818 | 1578.5403 | 1579.099 | 1579.658 | 1580.3273 | 1580.9969 | 1581.6667 | 1582.3369 | 1583.0073 | 1583.5947 | 1584.1823 | 1584.7702 | 1585.3582 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 | 1585.9465 |  | 4490 | 4607.7838 | 4728.6573 | 4852.7017 | 4980 | 4972.907 | 4965.8242 | 4958.7514 | 4951.6887 | 4944.636 | 4937.5451 | 4930.4643 | 4923.3938 | 4916.3333 | 4909.283 | 4898.8437 | 4888.4267 | 4878.0318 | 4867.659 | 4857.3083 | 4846.7056 | 4836.1261 | 4825.5697 | 4815.0364 | 4804.526 | 4794.2147 | 4783.9255 | 4773.6584 | 4763.4134 | 4753.1903 | 4754.9456 | 4756.7015 | 4758.458 | 4760.2152 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | 4761.9731 | [6 empty] | 745 | 751 | 757 | 763 | 769.8 | 777 | 784 | 791 | 798 | 805 | 813.9 | 816 | 819 | 822 | 825 | 828 | 831 | 834 | 837 | 840 | 843 | 846 | 849 | 852 | 855 | 858 | 861 | 864 | 867 | 870 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | 865.7 | [6 empty] | 3.1777 | 3.1773 | 3.1769 | 3.1765 | 3.1761 | 3.1704 | 3.1647 | 3.159 | 3.1533 | 3.1477 | 3.142 | 3.1363 | 3.1306 | 3.1249 | 3.1192 | 3.1114 | 3.1036 | 3.0958 | 3.0881 | 3.0804 | 3.0725 | 3.0648 | 3.057 | 3.0492 | 3.0415 | 3.0337 | 3.0259 | 3.0181 | 3.0104 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026 | 3.0026
494 | Otara - Papatoetoe |  |  | 2052 | 1094.1022 | 1105.7892 | 1117.6011 | 1129.5391 | 1141.6047 | 1144.2795 | 1146.9605 | 1149.6478 | 1152.3414 | 1155.0413 | 1157.7682 | 1160.5015 | 1163.2412 | 1165.9874 | 1168.7401 | 1171.2374 | 1173.74 | 1176.248 | 1178.7613 | 1181.28 | 1183.5057 | 1185.7357 | 1187.9698 | 1190.2082 | 1192.4508 | 1195.4449 | 1198.4466 | 1201.4558 | 1204.4726 | 1207.4969 | 1210.3054 | 1213.1204 | 1215.9419 | 1218.77 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 | 1221.6047 |  | 3750 | 3789.3755 | 3829.1644 | 3869.3711 | 3910 | 3917.2994 | 3924.6125 | 3931.9392 | 3939.2796 | 3946.6337 | 3954.0681 | 3961.5165 | 3968.979 | 3976.4555 | 3983.946 | 3986.7979 | 3989.6519 | 3992.5078 | 3995.3659 | 3998.2259 | 4000.057 | 4001.8889 | 4003.7217 | 4005.5552 | 4007.3897 | 4011.6527 | 4015.9203 | 4020.1924 | 4024.469 | 4028.7502 | 4037.9704 | 4047.2118 | 4056.4743 | 4065.758 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | 4075.0629 | [6 empty] | 743 | 750 | 757 | 764 | 770.9 | 778 | 785 | 792 | 799 | 806 | 814.1 | 817 | 820 | 823 | 826 | 829 | 832 | 835 | 838 | 841 | 844 | 847 | 850 | 853 | 856 | 859 | 862 | 865 | 868 | 871 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | 876.9 | [6 empty] | 3.4275 | 3.4269 | 3.4262 | 3.4256 | 3.425 | 3.4234 | 3.4218 | 3.4201 | 3.4185 | 3.4169 | 3.4153 | 3.4136 | 3.412 | 3.4104 | 3.4088 | 3.4039 | 3.3991 | 3.3943 | 3.3895 | 3.3847 | 3.3798 | 3.375 | 3.3702 | 3.3654 | 3.3606 | 3.3558 | 3.3509 | 3.3461 | 3.3413 | 3.3364 | 3.3363 | 3.3362 | 3.3361 | 3.336 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358 | 3.3358
495 | Otara - Papatoetoe |  |  | 2052 | 1296.6701 | 1299.8402 | 1303.0181 | 1306.2037 | 1309.3972 | 1311.4899 | 1313.586 | 1315.6855 | 1317.7883 | 1319.8945 | 1322.028 | 1324.165 | 1326.3054 | 1328.4493 | 1330.5967 | 1332.5662 | 1334.5386 | 1336.5139 | 1338.4922 | 1340.4734 | 1342.2375 | 1344.0038 | 1345.7726 | 1347.5436 | 1349.317 | 1351.609 | 1353.905 | 1356.2049 | 1358.5086 | 1360.8163 | 1362.9259 | 1365.0388 | 1367.155 | 1369.2744 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 | 1371.3972 |  | 4100 | 4109.9636 | 4119.9515 | 4129.9636 | 4140 | 4142.4039 | 4144.8092 | 4147.2159 | 4149.624 | 4152.0335 | 4154.498 | 4156.964 | 4159.4315 | 4161.9005 | 4164.3709 | 4162.7517 | 4161.1331 | 4159.5152 | 4157.8978 | 4156.2812 | 4153.9152 | 4151.5506 | 4149.1874 | 4146.8255 | 4144.4649 | 4143.6052 | 4142.7458 | 4141.8865 | 4141.0274 | 4140.1684 | 4146.5486 | 4152.9386 | 4159.3385 | 4165.7482 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | 4172.1678 | [6 empty] | 563 | 568 | 573 | 578 | 584.1 | 590 | 596 | 602 | 608 | 614 | 618.4 | 621 | 623 | 625 | 627 | 629 | 631 | 633 | 635 | 637 | 639 | 641 | 643 | 645 | 647 | 649 | 651 | 653 | 655 | 657 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | 667.8 | [6 empty] | 3.1619 | 3.1619 | 3.1619 | 3.1618 | 3.1618 | 3.1585 | 3.1553 | 3.1521 | 3.1489 | 3.1457 | 3.1425 | 3.1393 | 3.1361 | 3.1329 | 3.1297 | 3.1239 | 3.118 | 3.1122 | 3.1064 | 3.1006 | 3.0948 | 3.0889 | 3.0831 | 3.0773 | 3.0715 | 3.0657 | 3.0598 | 3.054 | 3.0482 | 3.0424 | 3.0424 | 3.0424 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423 | 3.0423
496 | Otara - Papatoetoe |  |  | 2052 | 961.54 | 971.4565 | 981.4753 | 991.5974 | 1001.8238 | 1003.9978 | 1006.1765 | 1008.36 | 1010.5481 | 1012.7411 | 1014.9574 | 1017.1786 | 1019.4046 | 1021.6355 | 1023.8713 | 1025.9206 | 1027.9741 | 1030.0316 | 1032.0932 | 1034.159 | 1035.9965 | 1037.8373 | 1039.6814 | 1041.5287 | 1043.3793 | 1045.8008 | 1048.228 | 1050.6607 | 1053.0991 | 1055.5432 | 1057.7898 | 1060.0411 | 1062.2972 | 1064.5581 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 | 1066.8238 |  | 3050 | 3079.5673 | 3109.4212 | 3139.5645 | 3170 | 3170.2187 | 3170.4374 | 3170.6561 | 3170.8749 | 3171.0936 | 3171.3103 | 3171.5269 | 3171.7436 | 3171.9603 | 3172.177 | 3169.8969 | 3167.6184 | 3165.3416 | 3163.0664 | 3160.7928 | 3157.7713 | 3154.7526 | 3151.7369 | 3148.724 | 3145.714 | 3144.1505 | 3142.5878 | 3141.0258 | 3139.4647 | 3137.9043 | 3143.9884 | 3150.0843 | 3156.192 | 3162.3115 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | 3168.443 | [6 empty] | 506 | 510 | 514 | 518 | 521.2 | 525 | 529 | 533 | 537 | 541 | 546.9 | 549 | 551 | 553 | 555 | 557 | 559 | 561 | 563 | 565 | 567 | 569 | 571 | 573 | 575 | 577 | 579 | 581 | 583 | 585 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | 588.9 | [6 empty] | 3.172 | 3.1701 | 3.1681 | 3.1662 | 3.1642 | 3.1576 | 3.151 | 3.1444 | 3.1378 | 3.1312 | 3.1246 | 3.118 | 3.1114 | 3.1048 | 3.0982 | 3.0898 | 3.0814 | 3.0731 | 3.0647 | 3.0564 | 3.0481 | 3.0397 | 3.0314 | 3.0232 | 3.0149 | 3.0065 | 2.998 | 2.9896 | 2.9812 | 2.9728 | 2.9722 | 2.9717 | 2.9711 | 2.9705 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97 | 2.97
497 | Otara - Papatoetoe |  |  | 2052 | 722.1841 | 724.0696 | 725.96 | 727.8553 | 729.7556 | 738.3677 | 747.0814 | 755.898 | 764.8186 | 773.8445 | 782.6324 | 791.5202 | 800.5089 | 809.5996 | 818.7936 | 826.8777 | 835.0416 | 843.2861 | 851.612 | 860.0201 | 867.2515 | 874.5438 | 881.8974 | 889.3128 | 896.7906 | 906.4842 | 916.2825 | 926.1867 | 936.198 | 946.3176 | 955.4281 | 964.6263 | 973.913 | 983.2892 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 | 992.7556 |  | 2010 | 2014.9815 | 2019.9752 | 2024.9814 | 2030 | 2058.4531 | 2087.305 | 2116.5613 | 2146.2277 | 2176.3099 | 2205.9041 | 2235.9007 | 2266.3053 | 2297.1232 | 2328.3603 | 2353.1656 | 2378.2353 | 2403.572 | 2429.1786 | 2455.0581 | 2477.7997 | 2500.7519 | 2523.9168 | 2547.2962 | 2570.8922 | 2600.6769 | 2630.8067 | 2661.2856 | 2692.1175 | 2723.3067 | 2748.5572 | 2774.0418 | 2799.7626 | 2825.722 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | 2851.9221 | [6 empty] | 653 | 662 | 671 | 680 | 690.7 | 698 | 706 | 714 | 722 | 730 | 736.1 | 740 | 744 | 748 | 752 | 756 | 760 | 764 | 768 | 772 | 776 | 780 | 784 | 788 | 792 | 796 | 800 | 804 | 808 | 812 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | 813.3 | [6 empty] | 2.7832 | 2.7829 | 2.7825 | 2.7821 | 2.7818 | 2.7878 | 2.7939 | 2.8001 | 2.8062 | 2.8123 | 2.8186 | 2.8248 | 2.8311 | 2.8374 | 2.8436 | 2.8458 | 2.848 | 2.8502 | 2.8524 | 2.8547 | 2.8571 | 2.8595 | 2.8619 | 2.8643 | 2.8668 | 2.869 | 2.8712 | 2.8734 | 2.8756 | 2.8778 | 2.8768 | 2.8758 | 2.8748 | 2.8737 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727 | 2.8727
498 | Otara - Papatoetoe |  |  | 2052 | 1561.2546 | 1582.8987 | 1604.8429 | 1627.0913 | 1649.6481 | 1650.6469 | 1651.6463 | 1652.6463 | 1653.6469 | 1654.6481 | 1655.6469 | 1656.6463 | 1657.6463 | 1658.6469 | 1659.6481 | 1660.6469 | 1661.6463 | 1662.6463 | 1663.6469 | 1664.6481 | 1665.6469 | 1666.6463 | 1667.6463 | 1668.6469 | 1669.6481 | 1670.6469 | 1671.6463 | 1672.6463 | 1673.6469 | 1674.6481 | 1675.6469 | 1676.6463 | 1677.6463 | 1678.6469 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 | 1679.6481 |  | 4980 | 5048.5707 | 5118.0856 | 5188.5576 | 5260 | 5257.7682 | 5255.5373 | 5253.3073 | 5251.0783 | 5248.8503 | 5246.5856 | 5244.322 | 5242.0593 | 5239.7975 | 5237.5368 | 5230.8797 | 5224.231 | 5217.5908 | 5210.959 | 5204.3356 | 5197.6193 | 5190.9115 | 5184.2125 | 5177.522 | 5170.8402 | 5164.0646 | 5157.2978 | 5150.5399 | 5143.7908 | 5137.0506 | 5140.1145 | 5143.1802 | 5146.2477 | 5149.3171 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | 5152.3883 | [6 empty] | 560 | 564 | 568 | 572 | 574.4 | 580 | 585 | 590 | 595 | 600 | 605.3 | 607 | 609 | 611 | 613 | 615 | 617 | 619 | 621 | 623 | 625 | 627 | 629 | 631 | 633 | 635 | 637 | 639 | 641 | 643 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | 637.1 | [6 empty] | 3.1897 | 3.1894 | 3.1892 | 3.1889 | 3.1886 | 3.1853 | 3.182 | 3.1787 | 3.1755 | 3.1722 | 3.1689 | 3.1656 | 3.1624 | 3.1591 | 3.1558 | 3.1499 | 3.144 | 3.1381 | 3.1323 | 3.1264 | 3.1205 | 3.1146 | 3.1087 | 3.1028 | 3.097 | 3.0911 | 3.0852 | 3.0793 | 3.0734 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675 | 3.0675
499 | Otara - Papatoetoe |  |  | 2052 | 498.2814 | 501.118 | 503.9708 | 506.8398 | 509.7252 | 518.66 | 527.7515 | 537.0023 | 546.4153 | 555.9933 | 565.1227 | 574.402 | 583.8337 | 593.4203 | 603.1643 | 611.579 | 620.1112 | 628.7624 | 637.5342 | 646.4285 | 653.9682 | 661.5958 | 669.3124 | 677.119 | 685.0166 | 695.1098 | 705.3517 | 715.7444 | 726.2904 | 736.9917 | 746.4903 | 756.1114 | 765.8565 | 775.7272 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 | 785.7252 |  | 1770 | 1779.9164 | 1789.8883 | 1799.916 | 1810 | 1834.9403 | 1860.2242 | 1885.8566 | 1911.8421 | 1938.1857 | 1962.8449 | 1987.8178 | 2013.1084 | 2038.7208 | 2064.6591 | 2085.1688 | 2105.8822 | 2126.8014 | 2147.9284 | 2169.2653 | 2185.856 | 2202.5736 | 2219.4191 | 2236.3933 | 2253.4975 | 2277.3953 | 2301.5465 | 2325.9539 | 2350.6201 | 2375.5478 | 2405.7625 | 2436.3614 | 2467.3496 | 2498.7318 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | 2530.5133 | [6 empty] | 456 | 463 | 470 | 477 | 483.1 | 506 | 529 | 552 | 575 | 598 | 622.6 | 626 | 630 | 634 | 638 | 642 | 646 | 650 | 654 | 658 | 662 | 666 | 670 | 674 | 678 | 682 | 686 | 690 | 694 | 698 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | 693.7 | [6 empty] | 3.5522 | 3.5519 | 3.5516 | 3.5513 | 3.5509 | 3.5378 | 3.5248 | 3.5118 | 3.4989 | 3.486 | 3.4733 | 3.4607 | 3.4481 | 3.4355 | 3.423 | 3.4095 | 3.396 | 3.3825 | 3.3691 | 3.3558 | 3.3425 | 3.3292 | 3.316 | 3.3028 | 3.2897 | 3.2763 | 3.263 | 3.2497 | 3.2365 | 3.2233 | 3.2228 | 3.2222 | 3.2217 | 3.2211 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206 | 3.2206
500 | Otara - Papatoetoe |  |  | 2052 | 383.4695 | 381.8059 | 380.1494 | 378.5001 | 376.858 | 387.2041 | 397.8343 | 408.7563 | 419.9781 | 431.508 | 442.1167 | 452.9862 | 464.1229 | 475.5334 | 487.2245 | 497.0412 | 507.0558 | 517.2721 | 527.6943 | 538.3264 | 547.1483 | 556.1147 | 565.228 | 574.4907 | 583.9051 | 595.6973 | 607.7276 | 620.0009 | 632.522 | 645.296 | 656.4183 | 667.7323 | 679.2414 | 690.9488 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 | 702.858 |  | 1160 | 1154.9673 | 1149.9565 | 1144.9674 | 1140 | 1171.6577 | 1204.1945 | 1237.6348 | 1272.0038 | 1307.3272 | 1340.5191 | 1374.5538 | 1409.4525 | 1445.2373 | 1481.9307 | 1511.4117 | 1541.4793 | 1572.145 | 1603.4207 | 1635.3186 | 1662.0651 | 1689.249 | 1716.8774 | 1744.9578 | 1773.4974 | 1809.2025 | 1845.6265 | 1882.7837 | 1920.6891 | 1959.3575 | 1992.3478 | 2025.8935 | 2060.004 | 2094.6889 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | 2129.9577 | [6 empty] | 5605 | 5660 | 5715 | 5770 | 5826.5 | 5881 | 5936 | 5991 | 6046 | 6101 | 6155.4 | 6185 | 6215 | 6245 | 6275 | 6305 | 6335 | 6365 | 6395 | 6425 | 6455 | 6485 | 6515 | 6545 | 6575 | 6605 | 6635 | 6665 | 6695 | 6725 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | 6750.8 | [6 empty] | 3.025 | 3.025 | 3.025 | 3.025 | 3.025 | 3.0259 | 3.0269 | 3.0278 | 3.0287 | 3.0297 | 3.032 | 3.0344 | 3.0368 | 3.0392 | 3.0416 | 3.0408 | 3.0401 | 3.0393 | 3.0385 | 3.0378 | 3.0377 | 3.0376 | 3.0375 | 3.0374 | 3.0373 | 3.0371 | 3.0369 | 3.0367 | 3.0366 | 3.0364 | 3.0352 | 3.034 | 3.0328 | 3.0316 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304 | 3.0304
501 | Otara - Papatoetoe |  |  | 2052 | 3.0318 | 7.1737 | 16.9742 | 40.164 | 95.0351 | 103.6037 | 112.9449 | 123.1283 | 134.2299 | 146.3324 | 155.5541 | 165.3571 | 175.7778 | 186.8552 | 198.6306 | 207.4124 | 216.5824 | 226.1579 | 236.1567 | 246.5975 | 254.6154 | 262.894 | 271.4417 | 280.2674 | 289.38 | 300.0833 | 311.1825 | 322.6922 | 334.6276 | 347.0045 | 357.1943 | 367.6834 | 378.4805 | 389.5946 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 | 401.0351 |  | 10 | 19.6799 | 38.7298 | 76.2199 | 150 | 173.5739 | 200.8525 | 232.4183 | 268.945 | 311.2121 | 346.8112 | 386.4824 | 430.6916 | 479.9578 | 534.8595 | 564.2522 | 595.26 | 627.9719 | 662.4815 | 698.8874 | 728.7683 | 759.9267 | 792.4172 | 826.297 | 861.6252 | 901.9514 | 944.1649 | 988.3541 | 1034.6115 | 1083.0339 | 1114.7283 | 1147.3503 | 1180.927 | 1215.4862 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | 1251.0568 | [6 empty] | 1842 | 1865 | 1888 | 1911 | 1933 | 1951 | 1969 | 1987 | 2005 | 2023 | 2042.3 | 2054 | 2066 | 2078 | 2090 | 2102 | 2114 | 2126 | 2138 | 2150 | 2162 | 2174 | 2186 | 2198 | 2210 | 2222 | 2234 | 2246 | 2258 | 2270 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | 2273 | [6 empty] | 3.2984 | 2.7433 | 2.2817 | 1.8977 | 1.5784 | 1.6754 | 1.7783 | 1.8876 | 2.0036 | 2.1267 | 2.2295 | 2.3373 | 2.4502 | 2.5686 | 2.6927 | 2.7204 | 2.7484 | 2.7767 | 2.8053 | 2.8341 | 2.8622 | 2.8906 | 2.9193 | 2.9482 | 2.9775 | 3.0057 | 3.0341 | 3.0628 | 3.0918 | 3.1211 | 3.1208 | 3.1205 | 3.1202 | 3.1199 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196 | 3.1196
502 | Otara - Papatoetoe |  |  | 2052 | 446.0756 | 475.1746 | 506.1719 | 539.1912 | 574.3645 | 606.0301 | 639.4415 | 674.6949 | 711.8919 | 751.1397 | 784.1524 | 818.6161 | 854.5945 | 892.1541 | 931.3645 | 962.2575 | 994.1752 | 1027.1516 | 1061.2218 | 1096.4222 | 1124.3764 | 1153.0433 | 1182.4411 | 1212.5884 | 1243.5044 | 1280.7451 | 1319.1011 | 1358.6059 | 1399.2937 | 1441.2001 | 1476.4644 | 1512.5917 | 1549.603 | 1587.5198 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 | 1626.3645 |  | 850 | 900.3474 | 953.6771 | 1010.1656 | 1070 | 1148.4073 | 1232.5602 | 1322.8796 | 1419.8175 | 1523.8587 | 1617.9253 | 1717.7986 | 1823.8369 | 1936.421 | 2055.9547 | 2151.8544 | 2252.2274 | 2357.2823 | 2467.2374 | 2582.3213 | 2681.562 | 2784.6166 | 2891.6316 | 3002.7594 | 3118.1578 | 3249.5951 | 3386.5727 | 3529.3242 | 3678.093 | 3833.1327 | 3924.9391 | 4018.9444 | 4115.2011 | 4213.7632 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | 4314.686 | [6 empty] | 4529 | 4583 | 4637 | 4691 | 4744.5 | 4793 | 4842 | 4891 | 4940 | 4989 | 5037.6 | 5070 | 5102 | 5134 | 5166 | 5198 | 5230 | 5262 | 5294 | 5326 | 5358 | 5390 | 5422 | 5454 | 5486 | 5518 | 5550 | 5582 | 5614 | 5646 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | 5677.4 | [6 empty] | 1.9055 | 1.8948 | 1.8841 | 1.8735 | 1.8629 | 1.895 | 1.9276 | 1.9607 | 1.9944 | 2.0287 | 2.0633 | 2.0984 | 2.1342 | 2.1705 | 2.2075 | 2.2363 | 2.2654 | 2.295 | 2.3249 | 2.3552 | 2.3849 | 2.415 | 2.4455 | 2.4763 | 2.5076 | 2.5373 | 2.5673 | 2.5978 | 2.6285 | 2.6597 | 2.6583 | 2.657 | 2.6556 | 2.6543 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653 | 2.653
503 | Otara - Papatoetoe |  |  | 2052 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 3.0318 | 5.7364 | 10.8537 | 20.5362 | 38.8563 | 73.5196 | 84.2607 | 96.5711 | 110.6801 | 126.8503 | 145.383 | 156.652 | 168.7945 | 181.8782 | 195.9761 | 211.1667 | 221.7678 | 232.9011 | 244.5934 | 256.8726 | 269.7683 | 283.9315 | 298.8382 | 314.5276 | 331.0408 | 348.4209 | 362.0365 | 376.1842 | 390.8848 | 406.1598 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 | 422.0318 |  | 20 | 20 | 20 | 20 | 20 | 32.4983 | 52.8069 | 85.8066 | 139.4283 | 226.559 | 258.6003 | 295.173 | 336.9181 | 384.567 | 438.9548 | 472.3609 | 508.3094 | 546.9937 | 588.622 | 633.4184 | 664.7992 | 697.7347 | 732.3019 | 768.5817 | 806.6588 | 848.5746 | 892.6685 | 939.0536 | 987.849 | 1039.1798 | 1079.4579 | 1121.2971 | 1164.758 | 1209.9034 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | 1256.7986 | [6 empty] | 8003 | 8093 | 8183 | 8273 | 8361.6 | 8451 | 8540 | 8629 | 8718 | 8807 | 8895.2 | 8949 | 9003 | 9057 | 9111 | 9165 | 9219 | 9273 | 9327 | 9381 | 9435 | 9489 | 9543 | 9597 | 9651 | 9705 | 9759 | 9813 | 9867 | 9921 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | 9973 | [6 empty] | 6.5968 | 6.5968 | 6.5968 | 6.5968 | 6.5968 | 5.6653 | 4.8653 | 4.1783 | 3.5883 | 3.0816 | 3.069 | 3.0565 | 3.0441 | 3.0317 | 3.0193 | 3.0154 | 3.0114 | 3.0075 | 3.0035 | 2.9996 | 2.9977 | 2.9958 | 2.994 | 2.9921 | 2.9902 | 2.9887 | 2.9871 | 2.9856 | 2.9841 | 2.9825 | 2.9816 | 2.9807 | 2.9798 | 2.9789 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978 | 2.978
504 | Manurewa |  |  | 2052 | 3.0318 | 2.8673 | 2.7117 | 2.5646 | 2.4254 | 4.0613 | 6.8006 | 11.3876 | 19.0683 | 31.9297 | 36.4626 | 41.6391 | 47.5504 | 54.3009 | 62.0098 | 66.7465 | 71.845 | 77.333 | 83.2401 | 89.5986 | 94.0542 | 98.7314 | 103.6412 | 108.7952 | 114.2055 | 120.1763 | 126.4594 | 133.0709 | 140.0281 | 147.349 | 153.0978 | 159.071 | 165.2772 | 171.7255 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 | 178.4254 |  | 50 | 47.2871 | 44.7214 | 42.2949 | 40 | 48.9673 | 59.9449 | 73.3834 | 89.8347 | 109.974 | 124.096 | 140.0315 | 158.0133 | 178.3042 | 201.2006 | 215.721 | 231.2892 | 247.981 | 265.8774 | 285.0653 | 298.6715 | 312.9271 | 327.8631 | 343.512 | 359.9078 | 377.4061 | 395.7552 | 414.9965 | 435.1732 | 456.3308 | 473.6852 | 491.6996 | 510.399 | 529.8096 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | 549.9583 | [6 empty] | 6048 | 6082 | 6116 | 6150 | 6184.9 | 6259 | 6334 | 6409 | 6484 | 6559 | 6631.9 | 6677 | 6723 | 6769 | 6815 | 6861 | 6907 | 6953 | 6999 | 7045 | 7091 | 7137 | 7183 | 7229 | 7275 | 7321 | 7367 | 7413 | 7459 | 7505 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | 7543.5 | [6 empty] | 16.4921 | 16.4921 | 16.4921 | 16.4921 | 16.4921 | 12.057 | 8.8146 | 6.4442 | 4.7112 | 3.4443 | 3.4034 | 3.363 | 3.3231 | 3.2836 | 3.2447 | 3.2319 | 3.2193 | 3.2067 | 3.1941 | 3.1816 | 3.1755 | 3.1695 | 3.1634 | 3.1574 | 3.1514 | 3.1404 | 3.1295 | 3.1186 | 3.1078 | 3.0969 | 3.094 | 3.0911 | 3.0881 | 3.0852 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823 | 3.0823
505 | Manurewa |  |  | 2052 | 497.5776 | 506.0208 | 514.6072 | 523.3393 | 532.2197 | 548.7907 | 565.8776 | 583.4966 | 601.6641 | 620.3973 | 637.4172 | 654.9039 | 672.8704 | 691.3298 | 710.2957 | 726.0699 | 742.1944 | 758.677 | 775.5257 | 792.7485 | 806.9395 | 821.3845 | 836.0881 | 851.0549 | 866.2896 | 885.2519 | 904.6292 | 924.4307 | 944.6657 | 965.3435 | 983.2426 | 1001.4735 | 1020.0425 | 1038.9557 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 | 1058.2197 |  | 2180 | 2214.1874 | 2248.9108 | 2284.1789 | 2320 | 2385.2865 | 2452.4101 | 2521.4227 | 2592.3773 | 2665.3287 | 2731.7519 | 2799.8305 | 2869.6056 | 2941.1197 | 3014.4159 | 3072.4891 | 3131.681 | 3192.0133 | 3253.5079 | 3316.1872 | 3366.7764 | 3418.1373 | 3470.2818 | 3523.2217 | 3576.9692 | 3645.2959 | 3714.9277 | 3785.8897 | 3858.2071 | 3931.9059 | 4001.7816 | 4072.8991 | 4145.2804 | 4218.948 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | 4293.9248 | [6 empty] | 298 | 301 | 304 | 307 | 311.3 | 315 | 319 | 323 | 327 | 331 | 334 | 338 | 342 | 346 | 350 | 354 | 358 | 362 | 366 | 370 | 374 | 378 | 382 | 386 | 390 | 394 | 398 | 402 | 406 | 410 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | 404.5 | [6 empty] | 4.3812 | 4.3757 | 4.3702 | 4.3646 | 4.3591 | 4.3464 | 4.3338 | 4.3212 | 4.3087 | 4.2962 | 4.2857 | 4.2752 | 4.2647 | 4.2543 | 4.2439 | 4.2317 | 4.2195 | 4.2073 | 4.1952 | 4.1832 | 4.1723 | 4.1614 | 4.1506 | 4.1398 | 4.1291 | 4.1178 | 4.1066 | 4.0954 | 4.0842 | 4.0731 | 4.07 | 4.0669 | 4.0638 | 4.0608 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577 | 4.0577
506 | Manurewa |  |  | 2052 | 450.8335 | 485.116 | 522.0054 | 561.7 | 604.413 | 610.9868 | 617.632 | 624.3495 | 631.1401 | 638.0045 | 644.7114 | 651.4888 | 658.3374 | 665.2581 | 672.2515 | 678.4076 | 684.6202 | 690.8896 | 697.2164 | 703.6012 | 709.1 | 714.6417 | 720.2268 | 725.8555 | 731.5282 | 738.9011 | 746.3484 | 753.8707 | 761.4689 | 769.1436 | 776.0715 | 783.0619 | 790.1152 | 797.2321 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 | 804.413 |  | 1750 | 1875.7784 | 2010.5969 | 2155.1053 | 2310 | 2336.9484 | 2364.2112 | 2391.7921 | 2419.6947 | 2447.9228 | 2475.6802 | 2503.7524 | 2532.1428 | 2560.8552 | 2589.8932 | 2612.6551 | 2635.6172 | 2658.781 | 2682.1485 | 2705.7213 | 2726.0499 | 2746.5313 | 2767.1666 | 2787.957 | 2808.9035 | 2836.1648 | 2863.6907 | 2891.4838 | 2919.5466 | 2947.8817 | 2973.4948 | 2999.3305 | 3025.3906 | 3051.6771 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | 3078.1921 | [6 empty] | 299 | 306 | 313 | 320 | 326 | 331 | 336 | 341 | 346 | 351 | 353 | 358 | 363 | 368 | 373 | 378 | 383 | 388 | 393 | 398 | 403 | 408 | 413 | 418 | 423 | 428 | 433 | 438 | 443 | 448 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | 447 | [6 empty] | 3.8817 | 3.8667 | 3.8517 | 3.8368 | 3.8219 | 3.8249 | 3.8279 | 3.8309 | 3.8338 | 3.8368 | 3.84 | 3.8431 | 3.8463 | 3.8494 | 3.8526 | 3.8512 | 3.8498 | 3.8483 | 3.8469 | 3.8455 | 3.8444 | 3.8432 | 3.8421 | 3.8409 | 3.8398 | 3.8384 | 3.8369 | 3.8355 | 3.8341 | 3.8327 | 3.8315 | 3.8303 | 3.829 | 3.8278 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266 | 3.8266
507 | Manurewa |  |  | 2052 | 155.3532 | 170.7485 | 187.6693 | 206.267 | 226.7077 | 229.3335 | 231.9897 | 234.6767 | 237.3948 | 240.1443 | 242.8236 | 245.5328 | 248.2722 | 251.0422 | 253.8431 | 256.303 | 258.7866 | 261.2944 | 263.8264 | 266.383 | 268.5806 | 270.7963 | 273.0303 | 275.2828 | 277.5538 | 280.4998 | 283.4771 | 286.486 | 289.5268 | 292.6 | 295.3686 | 298.1635 | 300.9848 | 303.8328 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 | 306.7077 |  | 520 | 562.1045 | 607.6183 | 656.8173 | 710 | 718.2129 | 726.5209 | 734.9249 | 743.4261 | 752.0257 | 760.519 | 769.1082 | 777.7945 | 786.5788 | 795.4624 | 802.5263 | 809.653 | 816.8429 | 824.0967 | 831.4149 | 837.7954 | 844.2249 | 850.7037 | 857.2322 | 863.8108 | 872.2754 | 880.8228 | 889.4541 | 898.1699 | 906.9711 | 914.5635 | 922.2195 | 929.9395 | 937.7242 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | 945.5741 | [6 empty] | 4280 | 4313 | 4346 | 4379 | 4411.3 | 4465 | 4518 | 4571 | 4624 | 4677 | 4731.6 | 4768 | 4804 | 4840 | 4876 | 4912 | 4948 | 4984 | 5020 | 5056 | 5092 | 5128 | 5164 | 5200 | 5236 | 5272 | 5308 | 5344 | 5380 | 5416 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | 5455.1 | [6 empty] | 3.3472 | 3.292 | 3.2377 | 3.1843 | 3.1318 | 3.1317 | 3.1317 | 3.1316 | 3.1316 | 3.1316 | 3.132 | 3.1324 | 3.1328 | 3.1333 | 3.1337 | 3.1312 | 3.1287 | 3.1261 | 3.1236 | 3.1211 | 3.1193 | 3.1176 | 3.1158 | 3.114 | 3.1122 | 3.1097 | 3.1072 | 3.1047 | 3.1022 | 3.0997 | 3.0963 | 3.093 | 3.0897 | 3.0863 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083 | 3.083
508 | Manurewa |  |  | 2052 | 110.77 | 116.9083 | 123.3866 | 130.224 | 137.4403 | 141.5535 | 145.7898 | 150.1529 | 154.6466 | 159.2747 | 163.497 | 167.8311 | 172.2802 | 176.8472 | 181.5353 | 185.4392 | 189.427 | 193.5006 | 197.6619 | 201.9126 | 205.4192 | 208.9866 | 212.6161 | 216.3085 | 220.0651 | 224.7513 | 229.5372 | 234.425 | 239.4169 | 244.5151 | 248.9373 | 253.4394 | 258.023 | 262.6894 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 | 267.4403 |  | 370 | 388.5567 | 408.0441 | 428.5089 | 450 | 463.3385 | 477.0724 | 491.2134 | 505.7736 | 520.7653 | 534.5405 | 548.6801 | 563.1937 | 578.0912 | 593.3828 | 605.5402 | 617.9466 | 630.6073 | 643.5273 | 656.7121 | 667.597 | 678.6623 | 689.911 | 701.3462 | 712.9709 | 727.4853 | 742.2951 | 757.4065 | 772.8255 | 788.5584 | 802.2194 | 816.1171 | 830.2555 | 844.6389 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | 859.2714 | [6 empty] | 4280 | 4311 | 4342 | 4373 | 4402.1 | 4499 | 4596 | 4693 | 4790 | 4887 | 4983.4 | 4925 | 4867 | 4809 | 4751 | 4693 | 4635 | 4577 | 4519 | 4461 | 4403 | 4345 | 4287 | 4229 | 4171 | 4113 | 4055 | 3997 | 3939 | 3881 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | 3824.4 | [6 empty] | 3.3403 | 3.3236 | 3.307 | 3.2906 | 3.2741 | 3.2732 | 3.2723 | 3.2714 | 3.2705 | 3.2696 | 3.2694 | 3.2692 | 3.2691 | 3.2689 | 3.2687 | 3.2654 | 3.2622 | 3.2589 | 3.2557 | 3.2525 | 3.2499 | 3.2474 | 3.2449 | 3.2423 | 3.2398 | 3.2368 | 3.2339 | 3.2309 | 3.2279 | 3.225 | 3.2226 | 3.2202 | 3.2178 | 3.2154 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129 | 3.2129
509 | Otara - Papatoetoe |  |  | 2052 | 25.6979 | 25.3374 | 24.9819 | 24.6315 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 | 24.2859 |  | 910 | 897.2339 | 884.6468 | 872.2364 | 860 | 859.7469 | 859.4939 | 859.2409 | 858.988 | 858.7352 | 858.4821 | 858.2291 | 857.9762 | 857.7233 | 857.4705 | 857.1973 | 856.9241 | 856.6511 | 856.3781 | 856.1053 | 855.832 | 855.5589 | 855.2859 | 855.0129 | 854.74 | 854.4668 | 854.1937 | 853.9206 | 853.6477 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | 853.3748 | [6 empty] | 4854 | 8926 | 12998 | 17070 | 21141.7 | 19023 | 16904 | 14785 | 12666 | 10547 | 8428.5 | 8988 | 9548 | 10108 | 10668 | 11228 | 11788 | 12348 | 12908 | 13468 | 14028 | 14588 | 15148 | 15708 | 16268 | 16828 | 17388 | 17948 | 18508 | 19068 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | 19623.2 | [6 empty] | 35.4114 | 35.4114 | 35.4114 | 35.4114 | 35.4114 | 35.401 | 35.3906 | 35.3802 | 35.3698 | 35.3594 | 35.3489 | 35.3385 | 35.3281 | 35.3177 | 35.3073 | 35.296 | 35.2848 | 35.2735 | 35.2623 | 35.2511 | 35.2398 | 35.2286 | 35.2173 | 35.2061 | 35.1949 | 35.1836 | 35.1724 | 35.1611 | 35.1499 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386 | 35.1386
510 | Manurewa |  |  | 2052 | 1190.0066 | 1202.0663 | 1214.2482 | 1226.5536 | 1238.9836 | 1241.4287 | 1243.8787 | 1246.3334 | 1248.793 | 1251.2575 | 1253.7502 | 1256.2479 | 1258.7505 | 1261.2581 | 1263.7708 | 1266.1463 | 1268.5262 | 1270.9106 | 1273.2995 | 1275.6929 | 1277.8624 | 1280.0355 | 1282.2124 | 1284.393 | 1286.5772 | 1289.496 | 1292.4215 | 1295.3535 | 1298.2922 | 1301.2376 | 1303.9753 | 1306.7187 | 1309.4679 | 1312.2229 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 | 1314.9836 |  | 3970 | 4009.4093 | 4049.2098 | 4089.4054 | 4130 | 4131.9167 | 4133.8342 | 4135.7527 | 4137.672 | 4139.5923 | 4141.5425 | 4143.4937 | 4145.4459 | 4147.3989 | 4149.3529 | 4147.8149 | 4146.2775 | 4144.7407 | 4143.2045 | 4141.6688 | 4139.2933 | 4136.9192 | 4134.5464 | 4132.175 | 4129.805 | 4129.6472 | 4129.4894 | 4129.3316 | 4129.1738 | 4129.0161 | 4135.5128 | 4142.0197 | 4148.5369 | 4155.0643 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | 4161.602 | [6 empty] | 771 | 775 | 779 | 783 | 785 | 794 | 803 | 812 | 821 | 830 | 837.3 | 843 | 848 | 853 | 858 | 863 | 868 | 873 | 878 | 883 | 888 | 893 | 898 | 903 | 908 | 913 | 918 | 923 | 928 | 933 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | 944.2 | [6 empty] | 3.3361 | 3.3354 | 3.3347 | 3.3341 | 3.3334 | 3.3284 | 3.3233 | 3.3183 | 3.3133 | 3.3083 | 3.3033 | 3.2983 | 3.2933 | 3.2883 | 3.2833 | 3.2759 | 3.2686 | 3.2612 | 3.2539 | 3.2466 | 3.2392 | 3.2319 | 3.2245 | 3.2172 | 3.2099 | 3.2025 | 3.1952 | 3.1878 | 3.1805 | 3.1731 | 3.1715 | 3.1698 | 3.1681 | 3.1664 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648 | 3.1648
511 | Manurewa |  |  | 2052 | 1161.0979 | 1171.0426 | 1181.0724 | 1191.1882 | 1201.3906 | 1203.8354 | 1206.2852 | 1208.7399 | 1211.1997 | 1213.6644 | 1216.1568 | 1218.6544 | 1221.157 | 1223.6648 | 1226.1777 | 1228.5529 | 1230.9327 | 1233.3172 | 1235.7062 | 1238.0998 | 1240.2691 | 1242.4422 | 1244.619 | 1246.7997 | 1248.9842 | 1251.9026 | 1254.8278 | 1257.7599 | 1260.6988 | 1263.6446 | 1266.3819 | 1269.1252 | 1271.8743 | 1274.6295 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 | 1277.3906 |  | 4010 | 4044.5509 | 4079.3995 | 4114.5483 | 4150 | 4152.6525 | 4155.3067 | 4157.9626 | 4160.6201 | 4163.2794 | 4165.9774 | 4168.6771 | 4171.3786 | 4174.0818 | 4176.7868 | 4175.7606 | 4174.7347 | 4173.7091 | 4172.6836 | 4171.6585 | 4169.7617 | 4167.8658 | 4165.9707 | 4164.0766 | 4162.1832 | 4162.6212 | 4163.0592 | 4163.4973 | 4163.9354 | 4164.3736 | 4173.4138 | 4182.4737 | 4191.5532 | 4200.6524 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | 4209.7713 | [6 empty] | 1099 | 1106 | 1113 | 1120 | 1128.7 | 1141 | 1154 | 1167 | 1180 | 1193 | 1205.2 | 1214 | 1223 | 1232 | 1241 | 1250 | 1259 | 1268 | 1277 | 1286 | 1295 | 1304 | 1313 | 1322 | 1331 | 1340 | 1349 | 1358 | 1367 | 1376 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | 1377.5 | [6 empty] | 3.4536 | 3.4538 | 3.454 | 3.4542 | 3.4543 | 3.4495 | 3.4447 | 3.4399 | 3.4351 | 3.4303 | 3.4255 | 3.4207 | 3.4159 | 3.4111 | 3.4063 | 3.3989 | 3.3915 | 3.3841 | 3.3768 | 3.3694 | 3.362 | 3.3546 | 3.3472 | 3.3398 | 3.3325 | 3.325 | 3.3176 | 3.3102 | 3.3029 | 3.2955 | 3.2955 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956 | 3.2956
512 | Manurewa |  |  | 2052 | 1932.6912 | 1946.4252 | 1960.2568 | 1974.1867 | 1988.2156 | 1991.897 | 1995.5853 | 1999.2803 | 2002.9822 | 2006.691 | 2010.4441 | 2014.2042 | 2017.9713 | 2021.7455 | 2025.5268 | 2028.9636 | 2032.4062 | 2035.8547 | 2039.309 | 2042.7691 | 2045.8319 | 2048.8993 | 2051.9712 | 2055.0478 | 2058.129 | 2062.2501 | 2066.3796 | 2070.5172 | 2074.6632 | 2078.8175 | 2082.6827 | 2086.5551 | 2090.4347 | 2094.3216 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 | 2098.2156 |  | 6550 | 6596.9919 | 6644.3209 | 6691.9894 | 6740 | 6761.5869 | 6783.2429 | 6804.9682 | 6826.7632 | 6848.6279 | 6870.6294 | 6892.7015 | 6914.8445 | 6937.0586 | 6959.3441 | 6971.2313 | 6983.1389 | 6995.0668 | 7007.015 | 7018.9837 | 7029.5776 | 7040.1875 | 7050.8135 | 7061.4554 | 7072.1135 | 7086.3686 | 7100.6525 | 7114.9652 | 7129.3067 | 7143.6772 | 7157.0476 | 7170.443 | 7183.8635 | 7197.3091 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | 7210.7799 | [6 empty] | 719 | 723 | 727 | 731 | 734.8 | 744 | 754 | 764 | 774 | 784 | 791.9 | 799 | 806 | 813 | 820 | 827 | 834 | 841 | 848 | 855 | 862 | 869 | 876 | 883 | 890 | 897 | 904 | 911 | 918 | 925 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | 930.2 | [6 empty] | 3.3891 | 3.3893 | 3.3895 | 3.3897 | 3.39 | 3.3945 | 3.3991 | 3.4037 | 3.4083 | 3.4129 | 3.4175 | 3.422 | 3.4266 | 3.4312 | 3.4358 | 3.4359 | 3.4359 | 3.4359 | 3.436 | 3.436 | 3.436 | 3.4361 | 3.4361 | 3.4362 | 3.4362 | 3.4362 | 3.4363 | 3.4363 | 3.4364 | 3.4364 | 3.4365 | 3.4365 | 3.4365 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366 | 3.4366
513 | Manurewa |  |  | 2052 | 1160.5276 | 1167.9137 | 1175.3469 | 1182.8273 | 1190.3554 | 1194.6702 | 1199.0006 | 1203.3467 | 1207.7085 | 1212.0862 | 1216.4851 | 1220.9 | 1225.3309 | 1229.7779 | 1234.241 | 1238.3728 | 1242.5185 | 1246.678 | 1250.8514 | 1255.0388 | 1258.7802 | 1262.5328 | 1266.2966 | 1270.0716 | 1273.8579 | 1278.7563 | 1283.6736 | 1288.6098 | 1293.5649 | 1298.5391 | 1303.0707 | 1307.618 | 1312.1812 | 1316.7603 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 | 1321.3554 |  | 3900 | 3924.7631 | 3949.6835 | 3974.7621 | 4000 | 4000.633 | 4001.2662 | 4001.8994 | 4002.5327 | 4003.1661 | 4003.5736 | 4003.9811 | 4004.3887 | 4004.7962 | 4005.2039 | 4002.8803 | 4000.558 | 3998.2371 | 3995.9176 | 3993.5994 | 3989.5138 | 3985.4325 | 3981.3553 | 3977.2823 | 3973.2135 | 3972.2392 | 3971.2653 | 3970.2915 | 3969.318 | 3968.3447 | 3982.1718 | 3996.0471 | 4009.9707 | 4023.9428 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | 4037.9636 | [6 empty] | 696 | 701 | 706 | 711 | 715.7 | 724 | 732 | 740 | 748 | 756 | 763.8 | 770 | 776 | 782 | 788 | 794 | 800 | 806 | 812 | 818 | 824 | 830 | 836 | 842 | 848 | 854 | 860 | 866 | 872 | 878 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | 892.9 | [6 empty] | 3.3605 | 3.3605 | 3.3604 | 3.3604 | 3.3603 | 3.3487 | 3.3372 | 3.3256 | 3.3142 | 3.3027 | 3.2911 | 3.2795 | 3.268 | 3.2565 | 3.2451 | 3.2324 | 3.2197 | 3.2071 | 3.1946 | 3.1821 | 3.1693 | 3.1567 | 3.1441 | 3.1315 | 3.119 | 3.1063 | 3.0937 | 3.0811 | 3.0685 | 3.056 | 3.056 | 3.056 | 3.056 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559 | 3.0559
514 | Manurewa |  |  | 2052 | 1418.9339 | 1452.738 | 1487.3475 | 1522.7815 | 1559.0597 | 1566.8051 | 1574.589 | 1582.4115 | 1590.2729 | 1598.1734 | 1606.0704 | 1614.0064 | 1621.9816 | 1629.9962 | 1638.0504 | 1645.3145 | 1652.6108 | 1659.9394 | 1667.3005 | 1674.6943 | 1681.1883 | 1687.7074 | 1694.2518 | 1700.8216 | 1707.4169 | 1716.0002 | 1724.6266 | 1733.2964 | 1742.0099 | 1750.7671 | 1758.7524 | 1766.7742 | 1774.8325 | 1782.9277 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 | 1791.0597 |  | 4850 | 4965.7872 | 5084.3387 | 5205.7204 | 5330 | 5354.0812 | 5378.2711 | 5402.5704 | 5426.9794 | 5451.4987 | 5475.9773 | 5500.5658 | 5525.2647 | 5550.0745 | 5574.9957 | 5591.8358 | 5608.7269 | 5625.669 | 5642.6622 | 5659.7068 | 5673.5951 | 5687.5175 | 5701.4741 | 5715.4649 | 5729.4901 | 5750.0747 | 5770.7332 | 5791.466 | 5812.2733 | 5833.1554 | 5859.7909 | 5886.548 | 5913.4273 | 5940.4294 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | 5967.5548 | [6 empty] | 410 | 415 | 420 | 425 | 431.7 | 437 | 443 | 449 | 455 | 461 | 465.3 | 470 | 475 | 480 | 485 | 490 | 495 | 500 | 505 | 510 | 515 | 520 | 525 | 530 | 535 | 540 | 545 | 550 | 555 | 560 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | [6 empty] | 3.4181 | 3.4182 | 3.4184 | 3.4186 | 3.4187 | 3.4172 | 3.4157 | 3.4141 | 3.4126 | 3.4111 | 3.4096 | 3.408 | 3.4065 | 3.405 | 3.4034 | 3.3986 | 3.3939 | 3.3891 | 3.3843 | 3.3795 | 3.3748 | 3.37 | 3.3652 | 3.3604 | 3.3556 | 3.3509 | 3.3461 | 3.3413 | 3.3365 | 3.3318 | 3.3318 | 3.3318 | 3.3318 | 3.3318 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319 | 3.3319
515 | Manurewa |  |  | 2052 | 877.9558 | 916.4921 | 956.7199 | 998.7134 | 1042.5502 | 1047.2948 | 1052.0611 | 1056.8491 | 1061.6588 | 1066.4904 | 1071.3279 | 1076.1872 | 1081.0686 | 1085.9721 | 1090.8979 | 1095.3472 | 1099.8146 | 1104.3003 | 1108.8042 | 1113.3265 | 1117.3037 | 1121.2951 | 1125.3007 | 1129.3207 | 1133.355 | 1138.6126 | 1143.8947 | 1149.2012 | 1154.5324 | 1159.8883 | 1164.7792 | 1169.6908 | 1174.6231 | 1179.5762 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 | 1184.5502 |  | 3380 | 3527.5536 | 3681.5486 | 3842.2662 | 4010 | 4025.6276 | 4041.3161 | 4057.0657 | 4072.8767 | 4088.7493 | 4104.6148 | 4120.5419 | 4136.5308 | 4152.5817 | 4168.6949 | 4179.145 | 4189.6213 | 4200.1238 | 4210.6527 | 4221.2079 | 4229.6144 | 4238.0376 | 4246.4775 | 4254.9343 | 4263.4079 | 4276.367 | 4289.3655 | 4302.4035 | 4315.4811 | 4328.5985 | 4346.7739 | 4365.0257 | 4383.3541 | 4401.7594 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | 4420.242 | [6 empty] | 244 | 249 | 254 | 259 | 264.5 | 268 | 271 | 274 | 277 | 280 | 285 | 288 | 291 | 294 | 297 | 300 | 303 | 306 | 309 | 312 | 315 | 318 | 321 | 324 | 327 | 330 | 333 | 336 | 339 | 342 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | 349.8 | [6 empty] | 3.8499 | 3.849 | 3.8481 | 3.8472 | 3.8463 | 3.8438 | 3.8413 | 3.8388 | 3.8363 | 3.8338 | 3.8313 | 3.8288 | 3.8263 | 3.8238 | 3.8213 | 3.8154 | 3.8094 | 3.8034 | 3.7975 | 3.7915 | 3.7856 | 3.7796 | 3.7736 | 3.7677 | 3.7618 | 3.7558 | 3.7498 | 3.7438 | 3.7379 | 3.7319 | 3.7318 | 3.7318 | 3.7317 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316 | 3.7316
516 | Manurewa |  |  | 2052 | 1045.1535 | 1054.4323 | 1063.7936 | 1073.2379 | 1082.766 | 1087.4285 | 1092.1111 | 1096.8138 | 1101.5368 | 1106.2801 | 1111.0336 | 1115.8076 | 1120.6021 | 1125.4172 | 1130.253 | 1134.6082 | 1138.9803 | 1143.3692 | 1147.775 | 1152.1977 | 1156.0813 | 1159.9779 | 1163.8876 | 1167.8105 | 1171.7466 | 1176.9661 | 1182.2088 | 1187.4748 | 1192.7644 | 1198.0774 | 1202.9749 | 1207.8925 | 1212.8301 | 1217.7879 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 | 1222.766 |  | 4210 | 4247.0091 | 4284.3436 | 4322.0063 | 4360 | 4382.449 | 4405.0135 | 4427.6943 | 4450.4918 | 4473.4067 | 4496.3832 | 4519.4777 | 4542.6908 | 4566.0232 | 4589.4754 | 4605.4462 | 4621.4726 | 4637.5547 | 4653.6928 | 4669.887 | 4683.893 | 4697.9409 | 4712.031 | 4726.1633 | 4740.338 | 4759.6607 | 4779.0621 | 4798.5427 | 4818.1026 | 4837.7422 | 4857.4116 | 4877.1608 | 4896.9904 | 4916.9006 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | 4936.8918 | [6 empty] | 115 | 116 | 117 | 118 | 118.2 | 120 | 122 | 124 | 126 | 128 | 128.4 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | 155.6 | [6 empty] | 4.0281 | 4.0278 | 4.0274 | 4.0271 | 4.0267 | 4.0301 | 4.0335 | 4.0369 | 4.0403 | 4.0436 | 4.047 | 4.0504 | 4.0538 | 4.0572 | 4.0606 | 4.0591 | 4.0576 | 4.056 | 4.0545 | 4.053 | 4.0515 | 4.05 | 4.0485 | 4.047 | 4.0455 | 4.044 | 4.0425 | 4.041 | 4.0394 | 4.0379 | 4.0378 | 4.0377 | 4.0377 | 4.0376 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375 | 4.0375
517 | Manurewa |  |  | 2052 | 2604.8857 | 2624.7331 | 2644.7317 | 2664.8827 | 2685.1873 | 2694.9417 | 2704.7315 | 2714.5569 | 2724.4179 | 2734.3148 | 2744.2595 | 2754.2403 | 2764.2574 | 2774.3109 | 2784.4011 | 2793.5268 | 2802.6825 | 2811.8682 | 2821.0839 | 2830.3299 | 2838.4748 | 2846.6432 | 2854.835 | 2863.0505 | 2871.2895 | 2882.2395 | 2893.2313 | 2904.265 | 2915.3408 | 2926.4588 | 2936.7321 | 2947.0415 | 2957.3871 | 2967.769 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 | 2978.1873 |  | 9410 | 9481.6769 | 9553.8997 | 9626.6727 | 9700 | 9748.1095 | 9796.4577 | 9845.0456 | 9893.8746 | 9942.9457 | 9992.2166 | 10041.7317 | 10091.4922 | 10141.4993 | 10191.7541 | 10225.1482 | 10258.6517 | 10292.265 | 10325.9884 | 10359.8223 | 10389.6272 | 10419.5177 | 10449.4943 | 10479.5571 | 10509.7064 | 10549.7761 | 10589.9985 | 10630.3743 | 10670.904 | 10711.5882 | 10749.1816 | 10786.9069 | 10824.7646 | 10862.7551 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | 10900.879 | [6 empty] | 979 | 988 | 997 | 1006 | 1015.2 | 1027 | 1039 | 1051 | 1063 | 1075 | 1088.7 | 1099 | 1110 | 1121 | 1132 | 1143 | 1154 | 1165 | 1176 | 1187 | 1198 | 1209 | 1220 | 1231 | 1242 | 1253 | 1264 | 1275 | 1286 | 1297 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | 1302.4 | [6 empty] | 3.6124 | 3.6124 | 3.6124 | 3.6124 | 3.6124 | 3.6172 | 3.622 | 3.6268 | 3.6316 | 3.6364 | 3.6411 | 3.6459 | 3.6507 | 3.6555 | 3.6603 | 3.6603 | 3.6603 | 3.6603 | 3.6603 | 3.6603 | 3.6603 | 3.6603 | 3.6603 | 3.6603 | 3.6603 | 3.6603 | 3.6603 | 3.6603 | 3.6603 | 3.6603 | 3.6603 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602 | 3.6602
518 | Manurewa |  |  | 2052 | 1694.5338 | 1715.8375 | 1737.409 | 1759.2518 | 1781.3691 | 1787.375 | 1793.401 | 1799.4474 | 1805.5142 | 1811.6015 | 1817.7244 | 1823.868 | 1830.0324 | 1836.2176 | 1842.4238 | 1848.0324 | 1853.6582 | 1859.3011 | 1864.9612 | 1870.6385 | 1875.6385 | 1880.652 | 1885.6788 | 1890.719 | 1895.7728 | 1902.4957 | 1909.2425 | 1916.0132 | 1922.8079 | 1929.6267 | 1935.9338 | 1942.2615 | 1948.61 | 1954.9791 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 | 1961.3691 |  | 6440 | 6520.9605 | 6602.9387 | 6685.9476 | 6770 | 6801.8155 | 6833.7806 | 6865.8959 | 6898.1621 | 6930.5799 | 6963.1477 | 6995.8685 | 7028.7431 | 7061.7722 | 7094.9565 | 7116.5545 | 7138.2183 | 7159.948 | 7181.7439 | 7203.6061 | 7222.8604 | 7242.1662 | 7261.5235 | 7280.9326 | 7300.3936 | 7326.2823 | 7352.2628 | 7378.3355 | 7404.5006 | 7430.7585 | 7455.0461 | 7479.413 | 7503.8596 | 7528.3861 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | 7552.9928 | [6 empty] | 535 | 541 | 547 | 553 | 558.5 | 565 | 572 | 579 | 586 | 593 | 598.6 | 605 | 611 | 617 | 623 | 629 | 635 | 641 | 647 | 653 | 659 | 665 | 671 | 677 | 683 | 689 | 695 | 701 | 707 | 713 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | 718.3 | [6 empty] | 3.8005 | 3.8005 | 3.8005 | 3.8004 | 3.8004 | 3.8055 | 3.8105 | 3.8156 | 3.8206 | 3.8257 | 3.8307 | 3.8357 | 3.8408 | 3.8458 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509 | 3.8509
519 | Manurewa |  |  | 2052 | 1068.9351 | 1096.5395 | 1124.8568 | 1153.9053 | 1183.7041 | 1191.5766 | 1199.5016 | 1207.4792 | 1215.5099 | 1223.594 | 1231.6216 | 1239.7019 | 1247.8352 | 1256.0219 | 1264.2623 | 1271.606 | 1278.9924 | 1286.4217 | 1293.8942 | 1301.4101 | 1307.9533 | 1314.5295 | 1321.1387 | 1327.7812 | 1334.457 | 1343.2429 | 1352.0866 | 1360.9885 | 1369.9491 | 1378.9686 | 1387.2164 | 1395.5136 | 1403.8604 | 1412.2571 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 | 1420.7041 |  | 3660 | 3753.8297 | 3850.0649 | 3948.7673 | 4050 | 4077.9877 | 4106.1689 | 4134.5447 | 4163.1167 | 4191.8861 | 4220.4838 | 4249.2765 | 4278.2656 | 4307.4525 | 4336.8386 | 4358.3919 | 4380.0523 | 4401.8203 | 4423.6965 | 4445.6815 | 4464.3171 | 4483.0308 | 4501.823 | 4520.6939 | 4539.644 | 4565.6771 | 4591.8595 | 4618.192 | 4644.6756 | 4671.311 | 4699.0876 | 4727.0294 | 4755.1374 | 4783.4124 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | 4811.8556 | [6 empty] | 542 | 549 | 556 | 563 | 568.2 | 575 | 582 | 589 | 596 | 603 | 609.4 | 616 | 623 | 630 | 637 | 644 | 651 | 658 | 665 | 672 | 679 | 686 | 693 | 700 | 707 | 714 | 721 | 728 | 735 | 742 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | 740.7 | [6 empty] | 3.424 | 3.4233 | 3.4227 | 3.4221 | 3.4215 | 3.4223 | 3.4232 | 3.4241 | 3.425 | 3.4259 | 3.4268 | 3.4277 | 3.4286 | 3.4294 | 3.4303 | 3.4275 | 3.4246 | 3.4218 | 3.4189 | 3.416 | 3.4132 | 3.4104 | 3.4075 | 3.4047 | 3.4019 | 3.399 | 3.3961 | 3.3933 | 3.3904 | 3.3875 | 3.3874 | 3.3873 | 3.3872 | 3.3871 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387 | 3.387
520 | Manurewa |  |  | 2052 | 1101.4675 | 1121.2972 | 1141.4838 | 1162.0339 | 1182.954 | 1212.9678 | 1243.7432 | 1275.2994 | 1307.6562 | 1340.834 | 1371.5831 | 1403.0374 | 1435.213 | 1468.1265 | 1501.7948 | 1530.1708 | 1559.0829 | 1588.5413 | 1618.5562 | 1649.1384 | 1674.5918 | 1700.4381 | 1726.6833 | 1753.3336 | 1780.3953 | 1814.4276 | 1849.1104 | 1884.4563 | 1920.4777 | 1957.1877 | 1989.2717 | 2021.8816 | 2055.0261 | 2088.7139 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 | 2122.954 |  | 3410 | 3470.8517 | 3532.7893 | 3595.8321 | 3660 | 3753.1246 | 3848.6187 | 3946.5425 | 4046.9578 | 4149.9282 | 4245.5606 | 4343.3968 | 4443.4876 | 4545.8849 | 4650.6419 | 4734.021 | 4818.8949 | 4905.2905 | 4993.235 | 5082.7562 | 5156.4406 | 5231.1931 | 5307.0294 | 5383.965 | 5462.016 | 5561.1924 | 5662.1696 | 5764.9803 | 5869.6577 | 5976.2359 | 6073.7162 | 6172.7866 | 6273.4729 | 6375.8016 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | 6479.7993 | [6 empty] | 1905 | 1933 | 1961 | 1989 | 2015.9 | 2042 | 2068 | 2094 | 2120 | 2146 | 2171.2 | 2196 | 2220 | 2244 | 2268 | 2292 | 2316 | 2340 | 2364 | 2388 | 2412 | 2436 | 2460 | 2484 | 2508 | 2532 | 2556 | 2580 | 2604 | 2628 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | 2660.3 | [6 empty] | 3.0959 | 3.0954 | 3.0949 | 3.0944 | 3.0939 | 3.0942 | 3.0944 | 3.0946 | 3.0948 | 3.095 | 3.0954 | 3.0957 | 3.096 | 3.0964 | 3.0967 | 3.0938 | 3.0909 | 3.0879 | 3.085 | 3.0821 | 3.0792 | 3.0764 | 3.0735 | 3.0707 | 3.0679 | 3.065 | 3.0621 | 3.0592 | 3.0564 | 3.0535 | 3.0532 | 3.053 | 3.0527 | 3.0525 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523 | 3.0523
521 | Manurewa |  |  | 2052 | 1353.313 | 1391.53 | 1430.8262 | 1471.2321 | 1512.7791 | 1523.9569 | 1535.2173 | 1546.5609 | 1557.9883 | 1569.5001 | 1580.8989 | 1592.3805 | 1603.9455 | 1615.5945 | 1627.328 | 1637.7579 | 1648.2546 | 1658.8185 | 1669.4502 | 1680.15 | 1689.4448 | 1698.791 | 1708.1888 | 1717.6387 | 1727.1408 | 1739.6178 | 1752.185 | 1764.8429 | 1777.5922 | 1790.4337 | 1802.1484 | 1813.9399 | 1825.8084 | 1837.7547 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 | 1849.7791 |  | 4600 | 4727.1318 | 4857.7773 | 4992.0334 | 5130 | 5146.6686 | 5163.3913 | 5180.1683 | 5196.9999 | 5213.8861 | 5229.737 | 5245.636 | 5261.5834 | 5277.5793 | 5293.6238 | 5303.759 | 5313.9136 | 5324.0876 | 5334.2811 | 5344.4942 | 5349.5863 | 5354.6832 | 5359.7851 | 5364.8917 | 5370.0033 | 5383.4642 | 5396.9588 | 5410.4873 | 5424.0497 | 5437.6461 | 5472.7103 | 5508.0006 | 5543.5185 | 5579.2654 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | 5615.2429 | [6 empty] | 729 | 738 | 747 | 756 | 764.7 | 775 | 786 | 797 | 808 | 819 | 828.1 | 835 | 842 | 849 | 856 | 863 | 870 | 877 | 884 | 891 | 898 | 905 | 912 | 919 | 926 | 933 | 940 | 947 | 954 | 961 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | 974.3 | [6 empty] | 3.3991 | 3.3971 | 3.3951 | 3.3931 | 3.3911 | 3.3772 | 3.3633 | 3.3495 | 3.3357 | 3.322 | 3.3081 | 3.2942 | 3.2804 | 3.2666 | 3.253 | 3.2384 | 3.224 | 3.2096 | 3.1952 | 3.181 | 3.1665 | 3.1521 | 3.1377 | 3.1234 | 3.1092 | 3.0946 | 3.0801 | 3.0657 | 3.0513 | 3.0371 | 3.0368 | 3.0365 | 3.0362 | 3.0359 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356 | 3.0356
522 | Manurewa |  |  | 2052 | 1802.2931 | 1832.1427 | 1862.4866 | 1893.3331 | 1924.6905 | 1936.5607 | 1948.504 | 1960.521 | 1972.6121 | 1984.7778 | 1996.8813 | 2009.0585 | 2021.31 | 2033.6363 | 2046.0377 | 2057.1086 | 2068.2394 | 2079.4304 | 2090.682 | 2101.9945 | 2111.8574 | 2121.7666 | 2131.7223 | 2141.7247 | 2151.7741 | 2165.0198 | 2178.3471 | 2191.7564 | 2205.2482 | 2218.8231 | 2231.2565 | 2243.7595 | 2256.3326 | 2268.9761 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 | 2281.6905 |  | 5850 | 5947.5336 | 6046.6933 | 6147.5063 | 6250 | 6295.6976 | 6341.7293 | 6388.0975 | 6434.8048 | 6481.8536 | 6528.7521 | 6575.9899 | 6623.5695 | 6671.4934 | 6719.7639 | 6755.1054 | 6790.6327 | 6826.3468 | 6862.2488 | 6898.3396 | 6929.6406 | 6961.0837 | 6992.6694 | 7024.3984 | 7056.2715 | 7098.6541 | 7141.2913 | 7184.1846 | 7227.3355 | 7270.7456 | 7311.6502 | 7352.785 | 7394.1511 | 7435.75 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | 7477.583 | [6 empty] | 1055 | 1069 | 1083 | 1097 | 1111.2 | 1128 | 1145 | 1162 | 1179 | 1196 | 1210.5 | 1223 | 1235 | 1247 | 1259 | 1271 | 1283 | 1295 | 1307 | 1319 | 1331 | 1343 | 1355 | 1367 | 1379 | 1391 | 1403 | 1415 | 1427 | 1439 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | 1456.6 | [6 empty] | 3.2459 | 3.2462 | 3.2466 | 3.2469 | 3.2473 | 3.251 | 3.2547 | 3.2584 | 3.2621 | 3.2658 | 3.2695 | 3.2732 | 3.2769 | 3.2806 | 3.2843 | 3.2838 | 3.2833 | 3.2828 | 3.2823 | 3.2818 | 3.2813 | 3.2808 | 3.2803 | 3.2798 | 3.2793 | 3.2788 | 3.2783 | 3.2778 | 3.2773 | 3.2768 | 3.2769 | 3.277 | 3.2771 | 3.2771 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772 | 3.2772
523 | Manurewa |  |  | 2052 | 1094.0315 | 1106.3501 | 1118.8075 | 1131.4052 | 1144.1447 | 1152.0137 | 1159.9368 | 1167.9144 | 1175.9468 | 1184.0346 | 1192.0587 | 1200.1373 | 1208.2706 | 1216.459 | 1224.7029 | 1232.0439 | 1239.4289 | 1246.8582 | 1254.332 | 1261.8507 | 1268.3919 | 1274.967 | 1281.5762 | 1288.2197 | 1294.8976 | 1303.68 | 1312.5219 | 1321.4238 | 1330.3861 | 1339.4092 | 1347.6542 | 1355.9499 | 1364.2967 | 1372.6948 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 | 1381.1447 |  | 3890 | 3934.2396 | 3978.9823 | 4024.2338 | 4070 | 4092.2178 | 4114.5568 | 4137.0179 | 4159.6015 | 4182.3084 | 4204.6635 | 4227.1381 | 4249.7328 | 4272.4483 | 4295.2853 | 4311.5414 | 4327.859 | 4344.2384 | 4360.6797 | 4377.1833 | 4390.0644 | 4402.9834 | 4415.9404 | 4428.9355 | 4441.9689 | 4462.0693 | 4482.2608 | 4502.5436 | 4522.9182 | 4543.385 | 4571.5935 | 4599.9771 | 4628.5369 | 4657.274 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | 4686.1896 | [6 empty] | 495 | 502 | 509 | 516 | 521.8 | 528 | 534 | 540 | 546 | 552 | 556.6 | 562 | 568 | 574 | 580 | 586 | 592 | 598 | 604 | 610 | 616 | 622 | 628 | 634 | 640 | 646 | 652 | 658 | 664 | 670 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | 674.5 | [6 empty] | 3.5557 | 3.5561 | 3.5564 | 3.5568 | 3.5572 | 3.5522 | 3.5472 | 3.5422 | 3.5372 | 3.5323 | 3.5272 | 3.5222 | 3.5172 | 3.5122 | 3.5072 | 3.4995 | 3.4918 | 3.4841 | 3.4765 | 3.4689 | 3.4611 | 3.4534 | 3.4457 | 3.438 | 3.4304 | 3.4227 | 3.415 | 3.4073 | 3.3997 | 3.3921 | 3.3923 | 3.3924 | 3.3926 | 3.3928 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393 | 3.393
524 | Manurewa |  |  | 2052 | 1019.3084 | 1041.936 | 1065.0659 | 1088.7093 | 1112.8775 | 1118.201 | 1123.5499 | 1128.9244 | 1134.3246 | 1139.7507 | 1145.1783 | 1150.6317 | 1156.1111 | 1161.6166 | 1167.1483 | 1172.1217 | 1177.1162 | 1182.1321 | 1187.1693 | 1192.228 | 1196.6632 | 1201.1149 | 1205.5832 | 1210.0681 | 1214.5696 | 1220.5293 | 1226.5182 | 1232.5366 | 1238.5844 | 1244.662 | 1250.2546 | 1255.8723 | 1261.5153 | 1267.1837 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 | 1272.8775 |  | 4090 | 4179.518 | 4270.9952 | 4364.4746 | 4460 | 4475.6451 | 4491.345 | 4507.1 | 4522.9103 | 4538.7761 | 4554.564 | 4570.4068 | 4586.3048 | 4602.2581 | 4618.2668 | 4628.3145 | 4638.3841 | 4648.4756 | 4658.5891 | 4668.7245 | 4676.2765 | 4683.8408 | 4691.4173 | 4699.006 | 4706.607 | 4719.6508 | 4732.7306 | 4745.8467 | 4758.9992 | 4772.1881 | 4793.482 | 4814.8709 | 4836.3552 | 4857.9354 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | 4879.6119 | [6 empty] | 230 | 232 | 234 | 236 | 236.2 | 239 | 242 | 245 | 248 | 251 | 254 | 256 | 258 | 260 | 262 | 264 | 266 | 268 | 270 | 272 | 274 | 276 | 278 | 280 | 282 | 284 | 286 | 288 | 290 | 292 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | 299.5 | [6 empty] | 4.0125 | 4.0113 | 4.0101 | 4.0089 | 4.0076 | 4.0025 | 3.9975 | 3.9924 | 3.9873 | 3.9823 | 3.9772 | 3.9721 | 3.967 | 3.9619 | 3.9569 | 3.9487 | 3.9405 | 3.9323 | 3.9241 | 3.916 | 3.9078 | 3.8996 | 3.8914 | 3.8833 | 3.8751 | 3.8669 | 3.8587 | 3.8505 | 3.8423 | 3.8341 | 3.834 | 3.8339 | 3.8338 | 3.8336 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335 | 3.8335
525 | Manurewa |  |  | 2052 | 2619.6774 | 2658.2256 | 2697.341 | 2737.032 | 2777.307 | 2788.3048 | 2799.346 | 2810.4311 | 2821.56 | 2832.733 | 2843.9453 | 2855.2021 | 2866.5035 | 2877.8495 | 2889.2405 | 2899.5126 | 2909.8212 | 2920.1665 | 2930.5485 | 2940.9675 | 2950.1262 | 2959.3134 | 2968.5292 | 2977.7737 | 2987.047 | 2999.3582 | 3011.7201 | 3024.133 | 3036.5971 | 3049.1125 | 3060.6635 | 3072.2583 | 3083.8971 | 3095.5799 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 | 3107.307 |  | 8900 | 9029.6398 | 9161.168 | 9294.6121 | 9430 | 9468.7648 | 9507.689 | 9546.7732 | 9586.018 | 9625.4242 | 9664.974 | 9704.6864 | 9744.5618 | 9784.6012 | 9824.805 | 9850.7022 | 9876.6676 | 9902.7014 | 9928.8039 | 9954.9752 | 9976.7961 | 9998.6649 | 10020.5816 | 10042.5464 | 10064.5593 | 10096.6808 | 10128.9048 | 10161.2317 | 10193.6617 | 10226.1953 | 10264.8379 | 10303.6266 | 10342.5618 | 10381.6442 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | 10420.8742 | [6 empty] | 636 | 641 | 646 | 651 | 654.5 | 662 | 670 | 678 | 686 | 694 | 700.3 | 706 | 712 | 718 | 724 | 730 | 736 | 742 | 748 | 754 | 760 | 766 | 772 | 778 | 784 | 790 | 796 | 802 | 808 | 814 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | 810.9 | [6 empty] | 3.3974 | 3.3969 | 3.3964 | 3.3959 | 3.3954 | 3.3959 | 3.3964 | 3.3969 | 3.3974 | 3.3979 | 3.3984 | 3.3989 | 3.3995 | 3.4 | 3.4005 | 3.3974 | 3.3943 | 3.3911 | 3.388 | 3.3849 | 3.3818 | 3.3787 | 3.3756 | 3.3725 | 3.3694 | 3.3663 | 3.3632 | 3.36 | 3.3569 | 3.3538 | 3.3538 | 3.3538 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537 | 3.3537
526 | Manurewa |  |  | 2052 | 2156.8877 | 2172.403 | 2188.0299 | 2203.7693 | 2219.6218 | 2241.039 | 2262.6628 | 2284.4952 | 2306.5383 | 2328.7941 | 2350.6409 | 2372.6926 | 2394.9513 | 2417.4187 | 2440.0969 | 2460.204 | 2480.4768 | 2500.9167 | 2521.525 | 2542.3031 | 2560.2924 | 2578.4089 | 2596.6537 | 2615.0275 | 2633.5313 | 2657.581 | 2681.8504 | 2706.3413 | 2731.0559 | 2755.9962 | 2778.5492 | 2801.2867 | 2824.2103 | 2847.3215 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 | 2870.6218 |  | 6240 | 6284.5213 | 6329.3602 | 6374.519 | 6420 | 6472.2009 | 6524.8262 | 6577.8794 | 6631.364 | 6685.2834 | 6737.8137 | 6790.7568 | 6844.1159 | 6897.8943 | 6952.0952 | 6993.5044 | 7035.1602 | 7077.0642 | 7119.2178 | 7161.6224 | 7195.8484 | 7230.238 | 7264.792 | 7299.511 | 7334.396 | 7384.2097 | 7434.3618 | 7484.8544 | 7535.69 | 7586.8709 | 7648.5426 | 7710.7157 | 7773.3941 | 7836.582 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | 7900.2836 | [6 empty] | 804 | 810 | 816 | 822 | 826.2 | 835 | 844 | 853 | 862 | 871 | 880.7 | 888 | 895 | 902 | 909 | 916 | 923 | 930 | 937 | 944 | 951 | 958 | 965 | 972 | 979 | 986 | 993 | 1000 | 1007 | 1014 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | 1026.4 | [6 empty] | 2.8931 | 2.8929 | 2.8927 | 2.8926 | 2.8924 | 2.888 | 2.8837 | 2.8794 | 2.875 | 2.8707 | 2.8664 | 2.862 | 2.8577 | 2.8534 | 2.8491 | 2.8427 | 2.8362 | 2.8298 | 2.8234 | 2.817 | 2.8106 | 2.8041 | 2.7978 | 2.7914 | 2.785 | 2.7785 | 2.7721 | 2.7657 | 2.7593 | 2.7529 | 2.7527 | 2.7526 | 2.7524 | 2.7523 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521 | 2.7521
527 | Papakura |  |  | 2052 | 829.35 | 865.2801 | 902.7668 | 941.8776 | 982.6828 | 985.3555 | 988.0355 | 990.7228 | 993.4174 | 996.1194 | 998.8442 | 1001.5764 | 1004.3162 | 1007.0634 | 1009.8182 | 1012.3138 | 1014.8156 | 1017.3235 | 1019.8377 | 1022.358 | 1024.5825 | 1026.8118 | 1029.046 | 1031.285 | 1033.5288 | 1036.5207 | 1039.5212 | 1042.5304 | 1045.5484 | 1048.575 | 1051.3815 | 1054.1955 | 1057.017 | 1059.8461 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 | 1062.6828 |  | 2530 | 2637.8992 | 2750.4 | 2867.6987 | 2990 | 2985.7961 | 2981.5981 | 2977.406 | 2973.2198 | 2969.0394 | 2964.6547 | 2960.2764 | 2955.9046 | 2951.5392 | 2947.1803 | 2941.238 | 2935.3076 | 2929.3893 | 2923.4828 | 2917.5883 | 2910.5613 | 2903.5513 | 2896.5582 | 2889.5819 | 2882.6224 | 2877.4481 | 2872.283 | 2867.1272 | 2861.9807 | 2856.8434 | 2864.3375 | 2871.8512 | 2879.3847 | 2886.9379 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | 2894.511 | [6 empty] | 464 | 468 | 472 | 476 | 479.1 | 486 | 493 | 500 | 507 | 514 | 519.1 | 525 | 531 | 537 | 543 | 549 | 555 | 561 | 567 | 573 | 579 | 585 | 591 | 597 | 603 | 609 | 615 | 621 | 627 | 633 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | 636.4 | [6 empty] | 3.0506 | 3.0486 | 3.0466 | 3.0447 | 3.0427 | 3.0302 | 3.0177 | 3.0053 | 2.9929 | 2.9806 | 2.9681 | 2.9556 | 2.9432 | 2.9308 | 2.9185 | 2.9055 | 2.8925 | 2.8795 | 2.8666 | 2.8538 | 2.8407 | 2.8277 | 2.8148 | 2.8019 | 2.7891 | 2.7761 | 2.7631 | 2.7502 | 2.7373 | 2.7245 | 2.7244 | 2.7242 | 2.7241 | 2.7239 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238 | 2.7238
528 | Papakura |  |  | 2052 | 405.0511 | 408.3907 | 411.758 | 415.1529 | 418.5759 | 421.2294 | 423.8997 | 426.5869 | 429.2911 | 432.0125 | 434.7182 | 437.4408 | 440.1804 | 442.9372 | 445.7113 | 448.1915 | 450.6855 | 453.1934 | 455.7153 | 458.2512 | 460.4639 | 462.6872 | 464.9213 | 467.1662 | 469.422 | 472.3934 | 475.3835 | 478.3927 | 481.4208 | 484.4681 | 487.2574 | 490.0627 | 492.8842 | 495.7219 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 | 498.5759 |  | 1630 | 1642.3587 | 1654.8112 | 1667.358 | 1680 | 1677.547 | 1675.0977 | 1672.6518 | 1670.2096 | 1667.7709 | 1664.7227 | 1661.6801 | 1658.643 | 1655.6114 | 1652.5854 | 1648.5205 | 1644.4655 | 1640.4205 | 1636.3855 | 1632.3604 | 1626.7286 | 1621.1163 | 1615.5233 | 1609.9497 | 1604.3953 | 1600.4927 | 1596.5997 | 1592.7161 | 1588.842 | 1584.9773 | 1593.3473 | 1601.7615 | 1610.2201 | 1618.7234 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | 1627.2716 | [6 empty] | 2565 | 2580 | 2595 | 2610 | 2623.3 | 2657 | 2691 | 2725 | 2759 | 2793 | 2828.2 | 2847 | 2865 | 2883 | 2901 | 2919 | 2937 | 2955 | 2973 | 2991 | 3009 | 3027 | 3045 | 3063 | 3081 | 3099 | 3117 | 3135 | 3153 | 3171 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | 3196 | [6 empty] | 4.0242 | 4.0215 | 4.0189 | 4.0163 | 4.0136 | 3.9825 | 3.9516 | 3.921 | 3.8906 | 3.8605 | 3.8294 | 3.7986 | 3.7681 | 3.7378 | 3.7077 | 3.6782 | 3.6488 | 3.6197 | 3.5908 | 3.5622 | 3.5328 | 3.5037 | 3.4748 | 3.4462 | 3.4178 | 3.3881 | 3.3586 | 3.3293 | 3.3003 | 3.2716 | 3.27 | 3.2685 | 3.2669 | 3.2654 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638 | 3.2638
529 | Papakura |  |  | 2052 | 846.8264 | 861.4201 | 876.2654 | 891.3665 | 906.7278 | 907.4824 | 908.2376 | 908.9934 | 909.7498 | 910.5069 | 911.2761 | 912.046 | 912.8166 | 913.5878 | 914.3596 | 915.0161 | 915.673 | 916.3304 | 916.9883 | 917.6466 | 918.2045 | 918.7627 | 919.3212 | 919.8801 | 920.4393 | 921.1904 | 921.9421 | 922.6944 | 923.4473 | 924.2009 | 924.9052 | 925.61 | 926.3154 | 927.0214 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 | 927.7278 |  | 2650 | 2693.8972 | 2738.5215 | 2783.885 | 2830 | 2834.1979 | 2838.402 | 2842.6123 | 2846.8289 | 2851.0517 | 2855.31 | 2859.5747 | 2863.8458 | 2868.1232 | 2872.407 | 2873.0559 | 2873.7048 | 2874.3539 | 2875.0031 | 2875.6525 | 2875.9942 | 2876.336 | 2876.6777 | 2877.0195 | 2877.3614 | 2878.2766 | 2879.192 | 2880.1078 | 2881.0238 | 2881.9402 | 2884.0563 | 2886.1739 | 2888.2932 | 2890.4139 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | 2892.5363 | [6 empty] | 721 | 726 | 731 | 736 | 741.6 | 752 | 762 | 772 | 782 | 792 | 803 | 810 | 817 | 824 | 831 | 838 | 845 | 852 | 859 | 866 | 873 | 880 | 887 | 894 | 901 | 908 | 915 | 922 | 929 | 936 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | 939.7 | [6 empty] | 3.1293 | 3.1273 | 3.1252 | 3.1232 | 3.1211 | 3.1231 | 3.1252 | 3.1272 | 3.1292 | 3.1313 | 3.1333 | 3.1353 | 3.1374 | 3.1394 | 3.1414 | 3.1399 | 3.1384 | 3.1368 | 3.1353 | 3.1337 | 3.1322 | 3.1307 | 3.1291 | 3.1276 | 3.1261 | 3.1245 | 3.123 | 3.1214 | 3.1199 | 3.1183 | 3.1182 | 3.1181 | 3.118 | 3.118 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179 | 3.1179
530 | Papakura |  |  | 2052 | 890.1968 | 900.66 | 911.2462 | 921.9569 | 932.7934 | 935.4654 | 938.145 | 940.8323 | 943.5273 | 946.23 | 948.954 | 951.6859 | 954.4256 | 957.1733 | 959.9288 | 962.4238 | 964.9252 | 967.4332 | 969.9477 | 972.4687 | 974.6926 | 976.9217 | 979.1558 | 981.3951 | 983.6395 | 986.6305 | 989.6305 | 992.6398 | 995.6581 | 998.6856 | 1001.4914 | 1004.305 | 1007.1265 | 1009.956 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 | 1012.7934 |  | 2360 | 2387.032 | 2414.3736 | 2442.0284 | 2470 | 2476.7845 | 2483.5877 | 2490.4096 | 2497.2502 | 2504.1096 | 2511.0252 | 2517.9599 | 2524.9138 | 2531.8869 | 2538.8792 | 2542.618 | 2546.3623 | 2550.1121 | 2553.8674 | 2557.6283 | 2560.6019 | 2563.5789 | 2566.5594 | 2569.5433 | 2572.5307 | 2577.3982 | 2582.2749 | 2587.1608 | 2592.0559 | 2596.9603 | 2604.0853 | 2611.2299 | 2618.3941 | 2625.5779 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | 2632.7815 | [6 empty] | 799 | 803 | 807 | 811 | 814.8 | 827 | 840 | 853 | 866 | 879 | 890 | 897 | 904 | 911 | 918 | 925 | 932 | 939 | 946 | 953 | 960 | 967 | 974 | 981 | 988 | 995 | 1002 | 1009 | 1016 | 1023 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | 1030.5 | [6 empty] | 2.6511 | 2.6503 | 2.6495 | 2.6487 | 2.648 | 2.6476 | 2.6473 | 2.647 | 2.6467 | 2.6464 | 2.6461 | 2.6458 | 2.6455 | 2.6452 | 2.6449 | 2.6419 | 2.6389 | 2.636 | 2.633 | 2.63 | 2.6271 | 2.6241 | 2.6212 | 2.6183 | 2.6153 | 2.6123 | 2.6093 | 2.6063 | 2.6034 | 2.6004 | 2.6002 | 2.6 | 2.5999 | 2.5997 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995 | 2.5995
531 | Papakura |  |  | 2052 | 1447.7186 | 1633.7864 | 1843.7686 | 2080.7388 | 2348.1655 | 2351.5151 | 2354.8694 | 2358.2286 | 2361.5925 | 2364.9612 | 2368.3761 | 2371.7958 | 2375.2205 | 2378.6502 | 2382.0847 | 2385.2115 | 2388.3423 | 2391.4773 | 2394.6164 | 2397.7596 | 2400.5458 | 2403.3353 | 2406.128 | 2408.9239 | 2411.7231 | 2415.473 | 2419.2286 | 2422.9902 | 2426.7576 | 2430.5308 | 2434.0475 | 2437.5694 | 2441.0963 | 2444.6284 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 | 2448.1655 |  | 5010 | 5654.5875 | 6382.1078 | 7203.231 | 8130 | 8114.5678 | 8099.1648 | 8083.7912 | 8068.4466 | 8053.1313 | 8037.5332 | 8021.9653 | 8006.4275 | 7990.9199 | 7975.4423 | 7955.1347 | 7934.8788 | 7914.6745 | 7894.5216 | 7874.42 | 7852.5903 | 7830.8212 | 7809.1124 | 7787.4637 | 7765.8751 | 7746.775 | 7727.7218 | 7708.7154 | 7689.7558 | 7670.8429 | 7677.025 | 7683.212 | 7689.4041 | 7695.6011 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | 7701.8031 | [6 empty] | 954 | 964 | 974 | 984 | 992.7 | 1008 | 1023 | 1038 | 1053 | 1068 | 1081.9 | 1093 | 1104 | 1115 | 1126 | 1137 | 1148 | 1159 | 1170 | 1181 | 1192 | 1203 | 1214 | 1225 | 1236 | 1247 | 1258 | 1269 | 1280 | 1291 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | 1307.7 | [6 empty] | 3.4606 | 3.461 | 3.4614 | 3.4619 | 3.4623 | 3.4508 | 3.4393 | 3.4279 | 3.4165 | 3.4052 | 3.3937 | 3.3822 | 3.3708 | 3.3594 | 3.3481 | 3.3352 | 3.3223 | 3.3095 | 3.2968 | 3.2841 | 3.2712 | 3.2583 | 3.2455 | 3.2328 | 3.2201 | 3.2071 | 3.1943 | 3.1815 | 3.1687 | 3.156 | 3.154 | 3.152 | 3.15 | 3.148 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459 | 3.1459
532 | Franklin |  |  | 2052 | 150.01 | 151.6765 | 153.3615 | 155.0652 | 156.7879 | 157.4489 | 158.1128 | 158.7794 | 159.4489 | 160.1212 | 160.7824 | 161.4463 | 162.1129 | 162.7824 | 163.4545 | 164.1158 | 164.7798 | 165.4464 | 166.1158 | 166.7879 | 167.4493 | 168.1133 | 168.7799 | 169.4492 | 170.1212 | 170.7827 | 171.4468 | 172.1134 | 172.7827 | 173.4545 | 174.1161 | 174.7803 | 175.4469 | 176.1161 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 | 176.7879 |  | 460 | 464.9205 | 469.8936 | 474.9199 | 480 | 479.8492 | 479.6985 | 479.5478 | 479.3971 | 479.2465 | 479.0043 | 478.7622 | 478.5203 | 478.2784 | 478.0367 | 478.1258 | 478.2148 | 478.3039 | 478.3929 | 478.482 | 478.53 | 478.5779 | 478.6259 | 478.6738 | 478.7218 | 478.6401 | 478.5585 | 478.4769 | 478.3953 | 478.3137 | 480.1381 | 481.9695 | 483.8078 | 485.6532 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | 487.5056 | [6 empty] | 768 | 799 | 830 | 861 | 892.2 | 921 | 950 | 979 | 1008 | 1037 | 1066.2 | 1080 | 1094 | 1108 | 1122 | 1136 | 1150 | 1164 | 1178 | 1192 | 1206 | 1220 | 1234 | 1248 | 1262 | 1276 | 1290 | 1304 | 1318 | 1332 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | 1342.9 | [6 empty] | 3.0665 | 3.0652 | 3.064 | 3.0627 | 3.0615 | 3.0476 | 3.0339 | 3.0202 | 3.0066 | 2.993 | 2.9792 | 2.9655 | 2.9518 | 2.9381 | 2.9246 | 2.9133 | 2.9021 | 2.891 | 2.8799 | 2.8688 | 2.8578 | 2.8468 | 2.8358 | 2.8249 | 2.814 | 2.8026 | 2.7913 | 2.78 | 2.7688 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576 | 2.7576
533 | Franklin |  |  | 2052 | 98.916 | 99.7528 | 100.5968 | 101.4478 | 102.3061 | 102.9642 | 103.6266 | 104.2932 | 104.9641 | 105.6394 | 106.2978 | 106.9603 | 107.6269 | 108.2977 | 108.9727 | 109.6314 | 110.294 | 110.9607 | 111.6313 | 112.3061 | 112.9649 | 113.6277 | 114.2943 | 114.9649 | 115.6394 | 116.2985 | 116.9614 | 117.628 | 118.2985 | 118.9727 | 119.632 | 120.295 | 120.9617 | 121.632 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 | 122.3061 |  | 270 | 272.466 | 274.9545 | 277.4658 | 280 | 280.224 | 280.4481 | 280.6725 | 280.897 | 281.1217 | 281.2449 | 281.3682 | 281.4916 | 281.615 | 281.7385 | 282.1044 | 282.4708 | 282.8376 | 283.205 | 283.5728 | 283.8829 | 284.1934 | 284.5042 | 284.8154 | 285.1269 | 285.3164 | 285.506 | 285.6957 | 285.8855 | 286.0755 | 287.6609 | 289.255 | 290.858 | 292.4699 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | 294.0907 | [6 empty] | 195 | 195 | 195 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 204.9 | 204 | 203 | 202 | 201 | 200 | 199 | 198 | 197 | 196 | 195 | 194 | 193 | 192 | 191 | 190 | 189 | 188 | 187 | 186 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | 191.2 | [6 empty] | 2.7296 | 2.7314 | 2.7332 | 2.7351 | 2.7369 | 2.7216 | 2.7063 | 2.6912 | 2.6761 | 2.6611 | 2.6458 | 2.6306 | 2.6154 | 2.6004 | 2.5854 | 2.5732 | 2.5611 | 2.549 | 2.537 | 2.525 | 2.513 | 2.5011 | 2.4892 | 2.4774 | 2.4657 | 2.4533 | 2.441 | 2.4288 | 2.4166 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045 | 2.4045
534 | Papakura |  |  | 2052 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 | 79.9615 |  | 250 | 250 | 250 | 250 | 250 | 248.7673 | 247.5407 | 246.3202 | 245.1056 | 243.8971 | 242.6641 | 241.4373 | 240.2168 | 239.0024 | 237.7942 | 236.8044 | 235.8188 | 234.8373 | 233.8598 | 232.8865 | 231.914 | 230.9457 | 229.9813 | 229.0211 | 228.0648 | 227.063 | 226.0656 | 225.0727 | 224.084 | 223.0998 | 222.6206 | 222.1425 | 221.6654 | 221.1893 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | 220.7143 | [6 empty] | 98 | 98 | 98 | 98 | 98.6 | 100 | 101 | 102 | 103 | 104 | 106.4 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | 119.8 | [6 empty] | 3.1265 | 3.1265 | 3.1265 | 3.1265 | 3.1265 | 3.1111 | 3.0957 | 3.0805 | 3.0653 | 3.0502 | 3.0348 | 3.0194 | 3.0042 | 2.989 | 2.9739 | 2.9615 | 2.9492 | 2.9369 | 2.9247 | 2.9125 | 2.9003 | 2.8882 | 2.8762 | 2.8641 | 2.8522 | 2.8397 | 2.8272 | 2.8148 | 2.8024 | 2.7901 | 2.7841 | 2.7781 | 2.7722 | 2.7662 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603 | 2.7603
535 | Papakura |  |  | 2052 | 228.882 | 239.5126 | 250.6369 | 262.2779 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 | 274.4595 |  | 660 | 690.3427 | 722.0803 | 755.2771 | 790 | 788.0089 | 786.0227 | 784.0416 | 782.0655 | 780.0944 | 778.1031 | 776.1169 | 774.1358 | 772.1598 | 770.1888 | 768.2642 | 766.3444 | 764.4295 | 762.5193 | 760.6139 | 758.7232 | 756.8371 | 754.9557 | 753.079 | 751.2069 | 749.2595 | 747.3172 | 745.3799 | 743.4476 | 741.5204 | 739.107 | 736.7014 | 734.3037 | 731.9138 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | 729.5317 | [6 empty] | 143 | 144 | 145 | 146 | 145.1 | 147 | 149 | 151 | 153 | 155 | 155.2 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | 175.3 | [6 empty] | 2.8836 | 2.8823 | 2.881 | 2.8797 | 2.8784 | 2.8711 | 2.8639 | 2.8567 | 2.8495 | 2.8423 | 2.835 | 2.8278 | 2.8206 | 2.8134 | 2.8062 | 2.7992 | 2.7922 | 2.7852 | 2.7783 | 2.7713 | 2.7644 | 2.7576 | 2.7507 | 2.7439 | 2.737 | 2.7299 | 2.7229 | 2.7158 | 2.7088 | 2.7017 | 2.693 | 2.6842 | 2.6755 | 2.6667 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581 | 2.6581
536 | Franklin |  |  | 2052 | 180.525 | 236.9241 | 310.9434 | 408.0876 | 535.5814 | 537.9419 | 540.3129 | 542.6943 | 545.0862 | 547.4886 | 549.8952 | 552.3125 | 554.7403 | 557.1789 | 559.6281 | 560.4877 | 561.3485 | 562.2107 | 563.0742 | 563.939 | 563.939 | 563.939 | 563.939 | 563.939 | 563.939 | 564.6497 | 565.3612 | 566.0737 | 566.787 | 567.5012 | 568.5136 | 569.5279 | 570.5439 | 571.5617 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 | 572.5814 |  | 670 | 877.3496 | 1148.869 | 1504.4175 | 1970 | 1969.4657 | 1968.9316 | 1968.3977 | 1967.8639 | 1967.3302 | 1966.5725 | 1965.8151 | 1965.058 | 1964.3012 | 1963.5447 | 1958.7904 | 1954.0477 | 1949.3164 | 1944.5967 | 1939.8883 | 1932.2479 | 1924.6375 | 1917.0571 | 1909.5066 | 1901.9858 | 1896.4693 | 1890.9688 | 1885.4843 | 1880.0157 | 1874.5629 | 1877.8632 | 1881.1693 | 1884.4812 | 1887.799 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | 1891.1226 | [6 empty] | 230 | 232 | 234 | 236 | 236.7 | 240 | 243 | 246 | 249 | 252 | 254.9 | 257 | 259 | 261 | 263 | 265 | 267 | 269 | 271 | 273 | 275 | 277 | 279 | 281 | 283 | 285 | 287 | 289 | 291 | 293 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | 290.9 | [6 empty] | 3.7114 | 3.7031 | 3.6948 | 3.6865 | 3.6782 | 3.6611 | 3.6441 | 3.6271 | 3.6102 | 3.5934 | 3.5763 | 3.5592 | 3.5423 | 3.5254 | 3.5087 | 3.4948 | 3.481 | 3.4672 | 3.4535 | 3.4399 | 3.4263 | 3.4128 | 3.3994 | 3.386 | 3.3727 | 3.3587 | 3.3447 | 3.3308 | 3.317 | 3.3032 | 3.3031 | 3.303 | 3.303 | 3.3029 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028 | 3.3028
537 | Papakura |  |  | 2052 | 500.8382 | 603.1134 | 726.2741 | 874.5851 | 1053.1824 | 1081.2109 | 1109.9852 | 1139.5253 | 1169.8516 | 1200.985 | 1229.7145 | 1259.1313 | 1289.2519 | 1320.0929 | 1351.6717 | 1378.1977 | 1405.2442 | 1432.8215 | 1460.94 | 1489.6104 | 1513.4132 | 1537.5963 | 1562.1659 | 1587.1281 | 1612.4892 | 1644.3098 | 1676.7584 | 1709.8473 | 1743.5892 | 1777.997 | 1808.004 | 1838.5174 | 1869.5458 | 1901.0979 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 | 1933.1824 |  | 1770 | 2112.2901 | 2520.7737 | 3008.2516 | 3590 | 3674.5616 | 3761.115 | 3849.7072 | 3940.3861 | 4033.201 | 4117.1956 | 4202.9394 | 4290.469 | 4379.8214 | 4471.0346 | 4541.2865 | 4612.6422 | 4685.1192 | 4758.7349 | 4833.5073 | 4891.5841 | 4950.3586 | 5009.8394 | 5070.0349 | 5130.9536 | 5211.2712 | 5292.846 | 5375.6977 | 5459.8463 | 5545.3122 | 5638.418 | 5733.087 | 5829.3455 | 5927.2202 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | 6026.7382 | [6 empty] | 601 | 607 | 613 | 619 | 626.4 | 635 | 643 | 651 | 659 | 667 | 675.7 | 684 | 692 | 700 | 708 | 716 | 724 | 732 | 740 | 748 | 756 | 764 | 772 | 780 | 788 | 796 | 804 | 812 | 820 | 828 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | 843.1 | [6 empty] | 3.5341 | 3.5023 | 3.4708 | 3.4396 | 3.4087 | 3.3986 | 3.3884 | 3.3783 | 3.3683 | 3.3582 | 3.3481 | 3.338 | 3.3279 | 3.3178 | 3.3078 | 3.2951 | 3.2824 | 3.2699 | 3.2573 | 3.2448 | 3.2322 | 3.2195 | 3.207 | 3.1945 | 3.182 | 3.1693 | 3.1566 | 3.144 | 3.1314 | 3.1189 | 3.1186 | 3.1183 | 3.1181 | 3.1178 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175 | 3.1175
538 | Papakura |  |  | 2052 | 759.4271 | 769.2235 | 779.1462 | 789.1969 | 799.3773 | 802.2952 | 805.2237 | 808.1629 | 811.1129 | 814.0736 | 817.0484 | 820.034 | 823.0306 | 826.0381 | 829.0566 | 831.8291 | 834.6108 | 837.4019 | 840.2022 | 843.012 | 845.5105 | 848.0165 | 850.5299 | 853.0508 | 855.5791 | 858.8569 | 862.1472 | 865.4501 | 868.7656 | 872.0939 | 875.1294 | 878.1754 | 881.2321 | 884.2993 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 | 887.3773 |  | 2220 | 2247.0033 | 2274.3351 | 2301.9993 | 2330 | 2340.9642 | 2351.98 | 2363.0477 | 2374.1674 | 2385.3395 | 2396.5686 | 2407.8506 | 2419.1856 | 2430.5741 | 2442.0161 | 2449.7539 | 2457.5163 | 2465.3032 | 2473.1148 | 2480.9512 | 2487.9243 | 2494.917 | 2501.9293 | 2508.9614 | 2516.0132 | 2525.1616 | 2534.3432 | 2543.5582 | 2552.8068 | 2562.0889 | 2570.5608 | 2579.0607 | 2587.5886 | 2596.1448 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | 2604.7293 | [6 empty] | 1703 | 1722 | 1741 | 1760 | 1779.9 | 1806 | 1832 | 1858 | 1884 | 1910 | 1935.8 | 1956 | 1977 | 1998 | 2019 | 2040 | 2061 | 2082 | 2103 | 2124 | 2145 | 2166 | 2187 | 2208 | 2229 | 2250 | 2271 | 2292 | 2313 | 2334 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | 2346.9 | [6 empty] | 2.9233 | 2.9211 | 2.919 | 2.9169 | 2.9148 | 2.9178 | 2.9209 | 2.924 | 2.927 | 2.9301 | 2.9332 | 2.9363 | 2.9394 | 2.9424 | 2.9455 | 2.945 | 2.9445 | 2.944 | 2.9435 | 2.943 | 2.9425 | 2.9421 | 2.9416 | 2.9412 | 2.9407 | 2.9401 | 2.9396 | 2.939 | 2.9384 | 2.9379 | 2.9373 | 2.9368 | 2.9363 | 2.9358 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353 | 2.9353
539 | Papakura |  |  | 2052 | 1480.2045 | 1518.6674 | 1558.1297 | 1598.6175 | 1640.1573 | 1657.4254 | 1674.8753 | 1692.5089 | 1710.3281 | 1728.335 | 1745.9518 | 1763.7483 | 1781.7261 | 1799.8871 | 1818.2333 | 1834.4327 | 1850.7763 | 1867.2656 | 1883.9018 | 1900.6862 | 1915.1719 | 1929.768 | 1944.4754 | 1959.2949 | 1974.2273 | 1993.652 | 2013.2679 | 2033.0768 | 2053.0806 | 2073.2812 | 2091.5323 | 2109.944 | 2128.5178 | 2147.2551 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 | 2166.1573 |  | 3490 | 3576.7143 | 3665.5832 | 3756.6601 | 3850 | 3918.2238 | 3987.6566 | 4058.3197 | 4130.2351 | 4203.4248 | 4275.5879 | 4348.9898 | 4423.6519 | 4499.5957 | 4576.8434 | 4638.1939 | 4700.3669 | 4763.3732 | 4827.2242 | 4891.931 | 4950.9516 | 5010.6843 | 5071.1376 | 5132.3204 | 5194.2412 | 5267.695 | 5342.1875 | 5417.7335 | 5494.3478 | 5572.0455 | 5619.7238 | 5667.8101 | 5716.3078 | 5765.2206 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | 5814.5518 | [6 empty] | 3648 | 3694 | 3740 | 3786 | 3832.5 | 3885 | 3937 | 3989 | 4041 | 4093 | 4147.1 | 4195 | 4242 | 4289 | 4336 | 4383 | 4430 | 4477 | 4524 | 4571 | 4618 | 4665 | 4712 | 4759 | 4806 | 4853 | 4900 | 4947 | 4994 | 5041 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | 5096.5 | [6 empty] | 2.3578 | 2.3552 | 2.3526 | 2.3499 | 2.3473 | 2.364 | 2.3809 | 2.3978 | 2.4149 | 2.4321 | 2.4489 | 2.4658 | 2.4828 | 2.4999 | 2.5172 | 2.5284 | 2.5397 | 2.551 | 2.5624 | 2.5738 | 2.5851 | 2.5965 | 2.608 | 2.6195 | 2.631 | 2.6422 | 2.6535 | 2.6648 | 2.6761 | 2.6875 | 2.6869 | 2.6862 | 2.6856 | 2.6849 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843 | 2.6843
540 | Papakura |  |  | 2052 | 1771.0335 | 1815.5129 | 1861.1093 | 1907.8509 | 1955.7664 | 1964.5057 | 1973.284 | 1982.1016 | 1990.9586 | 1999.8552 | 2008.7653 | 2017.7151 | 2026.7047 | 2035.7344 | 2044.8044 | 2052.9839 | 2061.1962 | 2069.4414 | 2077.7195 | 2086.0308 | 2093.3336 | 2100.6619 | 2108.016 | 2115.3957 | 2122.8013 | 2132.6156 | 2142.4752 | 2152.3803 | 2162.3313 | 2172.3283 | 2181.5375 | 2190.7857 | 2200.0732 | 2209.4 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 | 2218.7664 |  | 4830 | 4950.4212 | 5073.8447 | 5200.3454 | 5330 | 5338.522 | 5347.0576 | 5355.6069 | 5364.1699 | 5372.7465 | 5381.0473 | 5389.361 | 5397.6875 | 5406.0268 | 5414.379 | 5417.4722 | 5420.5672 | 5423.6639 | 5426.7624 | 5429.8627 | 5429.9603 | 5430.0579 | 5430.1555 | 5430.2531 | 5430.3507 | 5436.1495 | 5441.9545 | 5447.7657 | 5453.5831 | 5459.4067 | 5482.3975 | 5505.485 | 5528.6698 | 5551.9522 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | 5575.3327 | [6 empty] | 969 | 981 | 993 | 1005 | 1015.4 | 1030 | 1045 | 1060 | 1075 | 1090 | 1103.9 | 1117 | 1131 | 1145 | 1159 | 1173 | 1187 | 1201 | 1215 | 1229 | 1243 | 1257 | 1271 | 1285 | 1299 | 1313 | 1327 | 1341 | 1355 | 1369 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | 1375.2 | [6 empty] | 2.7272 | 2.7267 | 2.7262 | 2.7258 | 2.7253 | 2.7175 | 2.7097 | 2.702 | 2.6943 | 2.6866 | 2.6788 | 2.671 | 2.6633 | 2.6556 | 2.6479 | 2.6388 | 2.6298 | 2.6208 | 2.6119 | 2.603 | 2.5939 | 2.5849 | 2.576 | 2.567 | 2.5581 | 2.5491 | 2.54 | 2.531 | 2.5221 | 2.5132 | 2.5131 | 2.513 | 2.5129 | 2.5129 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128 | 2.5128
541 | Papakura |  |  | 2052 | 1362.7429 | 1409.218 | 1457.2782 | 1506.9774 | 1558.3715 | 1562.0492 | 1565.7355 | 1569.4306 | 1573.1343 | 1576.8468 | 1580.5961 | 1584.3543 | 1588.1215 | 1591.8976 | 1595.6827 | 1599.1797 | 1602.6845 | 1606.1969 | 1609.717 | 1613.2448 | 1616.3975 | 1619.5564 | 1622.7214 | 1625.8927 | 1629.0701 | 1633.2294 | 1637.3994 | 1641.58 | 1645.7713 | 1649.9733 | 1653.8348 | 1657.7054 | 1661.585 | 1665.4737 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 | 1669.3715 |  | 4150 | 4292.4918 | 4439.8761 | 4592.3209 | 4750 | 4745.9612 | 4741.9259 | 4737.894 | 4733.8656 | 4729.8405 | 4725.6553 | 4721.4738 | 4717.296 | 4713.1219 | 4708.9515 | 4701.8178 | 4694.6949 | 4687.5829 | 4680.4816 | 4673.391 | 4664.8722 | 4656.369 | 4647.8812 | 4639.4089 | 4630.952 | 4624.9548 | 4618.9653 | 4612.9836 | 4607.0096 | 4601.0433 | 4611.8803 | 4622.7428 | 4633.6309 | 4644.5446 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | 4655.484 | [6 empty] | 448 | 451 | 454 | 457 | 460.5 | 467 | 473 | 479 | 485 | 491 | 499.3 | 505 | 511 | 517 | 523 | 529 | 535 | 541 | 547 | 553 | 559 | 565 | 571 | 577 | 583 | 589 | 595 | 601 | 607 | 613 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | 610.7 | [6 empty] | 3.0453 | 3.046 | 3.0467 | 3.0474 | 3.0481 | 3.0383 | 3.0286 | 3.0189 | 3.0092 | 2.9996 | 2.9898 | 2.9801 | 2.9704 | 2.9607 | 2.9511 | 2.9401 | 2.9293 | 2.9184 | 2.9076 | 2.8969 | 2.886 | 2.8751 | 2.8643 | 2.8535 | 2.8427 | 2.8318 | 2.8209 | 2.8101 | 2.7993 | 2.7886 | 2.7886 | 2.7886 | 2.7887 | 2.7887 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888 | 2.7888
542 | Papakura |  |  | 2052 | 1445.0653 | 1472.0446 | 1499.5277 | 1527.5239 | 1556.0427 | 1558.7208 | 1561.4035 | 1564.0908 | 1566.7827 | 1569.4793 | 1572.2096 | 1574.9445 | 1577.6843 | 1580.4288 | 1583.1781 | 1585.6782 | 1588.1822 | 1590.6902 | 1593.2021 | 1595.718 | 1597.9459 | 1600.1769 | 1602.4111 | 1604.6484 | 1606.8888 | 1609.8868 | 1612.8904 | 1615.8996 | 1618.9145 | 1621.9349 | 1624.7467 | 1627.5634 | 1630.3849 | 1633.2114 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 | 1636.0427 |  | 4760 | 4849.9198 | 4941.5382 | 5034.8874 | 5130 | 5109.396 | 5088.8747 | 5068.4358 | 5048.079 | 5027.804 | 5006.8526 | 4985.9884 | 4965.2112 | 4944.5206 | 4923.9162 | 4902.577 | 4881.3302 | 4860.1755 | 4839.1125 | 4818.1407 | 4795.5057 | 4772.9769 | 4750.554 | 4728.2365 | 4706.0238 | 4685.2382 | 4664.5444 | 4643.942 | 4623.4306 | 4603.0098 | 4611.0896 | 4619.1835 | 4627.2916 | 4635.414 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | 4643.5506 | [6 empty] | 236 | 239 | 242 | 245 | 247.2 | 251 | 255 | 259 | 263 | 267 | 268.3 | 272 | 276 | 280 | 284 | 288 | 292 | 296 | 300 | 304 | 308 | 312 | 316 | 320 | 324 | 328 | 332 | 336 | 340 | 344 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | 341.8 | [6 empty] | 3.294 | 3.2947 | 3.2954 | 3.2961 | 3.2968 | 3.2779 | 3.2592 | 3.2405 | 3.2219 | 3.2035 | 3.1846 | 3.1658 | 3.1472 | 3.1286 | 3.1101 | 3.0918 | 3.0735 | 3.0554 | 3.0374 | 3.0194 | 3.001 | 2.9828 | 2.9646 | 2.9466 | 2.9287 | 2.9103 | 2.892 | 2.8739 | 2.8559 | 2.838 | 2.838 | 2.8381 | 2.8382 | 2.8382 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383 | 2.8383
543 | Papakura |  |  | 2052 | 1611.14 | 1644.7898 | 1679.1423 | 1714.2124 | 1750.0149 | 1755.6885 | 1761.3806 | 1767.0911 | 1772.8201 | 1778.5677 | 1784.3519 | 1790.155 | 1795.9769 | 1801.8178 | 1807.6776 | 1812.9759 | 1818.2897 | 1823.6191 | 1828.9642 | 1834.3248 | 1839.048 | 1843.7834 | 1848.531 | 1853.2908 | 1858.0628 | 1864.4138 | 1870.7866 | 1877.1812 | 1883.5976 | 1890.0359 | 1895.994 | 1901.9709 | 1907.9667 | 1913.9813 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 | 1920.0149 |  | 5210 | 5319.0295 | 5430.3407 | 5543.9813 | 5660 | 5654.7922 | 5649.5892 | 5644.391 | 5639.1976 | 5634.0089 | 5628.3847 | 5622.7661 | 5617.1531 | 5611.5458 | 5605.944 | 5597.0653 | 5588.2007 | 5579.3502 | 5570.5136 | 5561.6911 | 5550.3287 | 5538.9895 | 5527.6734 | 5516.3805 | 5505.1107 | 5497.8932 | 5490.6853 | 5483.4867 | 5476.2977 | 5469.118 | 5486.392 | 5503.7206 | 5521.1039 | 5538.5421 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | 5556.0354 | [6 empty] | 335 | 337 | 339 | 341 | 342.9 | 348 | 353 | 358 | 363 | 368 | 373.4 | 377 | 381 | 385 | 389 | 393 | 397 | 401 | 405 | 409 | 413 | 417 | 421 | 425 | 429 | 433 | 437 | 441 | 445 | 449 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | 454.3 | [6 empty] | 3.2337 | 3.2339 | 3.234 | 3.2341 | 3.2343 | 3.2208 | 3.2075 | 3.1942 | 3.1809 | 3.1677 | 3.1543 | 3.1409 | 3.1276 | 3.1144 | 3.1012 | 3.0872 | 3.0733 | 3.0595 | 3.0457 | 3.032 | 3.018 | 3.0041 | 2.9903 | 2.9765 | 2.9628 | 2.9489 | 2.935 | 2.9211 | 2.9074 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937 | 2.8937
544 | Papakura |  |  | 2052 | 416.7385 | 432.0316 | 447.886 | 464.3221 | 481.3615 | 481.3615 | 481.3615 | 481.3615 | 481.3615 | 481.3615 | 481.3615 | 481.3615 | 481.3615 | 481.3615 | 481.3615 | 497.1174 | 513.3889 | 530.1931 | 547.5473 | 565.4696 | 588.0718 | 611.5773 | 636.0224 | 661.4446 | 687.883 | 698.825 | 709.941 | 721.2339 | 732.7065 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 | 744.3615 |  | 1550 | 1602.2936 | 1656.3514 | 1712.233 | 1770 | 1760.4061 | 1750.8642 | 1741.374 | 1731.9353 | 1722.5477 | 1712.9509 | 1703.4076 | 1693.9174 | 1684.4802 | 1675.0954 | 1716.1541 | 1758.2191 | 1801.3152 | 1845.4676 | 1890.7023 | 1949.8831 | 2010.9162 | 2073.8598 | 2138.7735 | 2205.7192 | 2225.1823 | 2244.8171 | 2264.6253 | 2284.6082 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | 2304.7674 | [6 empty] | 2701 | 2710 | 2719 | 2728 | 2736.2 | 2772 | 2808 | 2844 | 2880 | 2916 | 2949.5 | 2965 | 2980 | 2995 | 3010 | 3025 | 3040 | 3055 | 3070 | 3085 | 3100 | 3115 | 3130 | 3145 | 3160 | 3175 | 3190 | 3205 | 3220 | 3235 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | 3254.5 | [6 empty] | 3.7194 | 3.7087 | 3.6982 | 3.6876 | 3.6771 | 3.6571 | 3.6373 | 3.6176 | 3.598 | 3.5785 | 3.5586 | 3.5387 | 3.519 | 3.4994 | 3.4799 | 3.4522 | 3.4247 | 3.3975 | 3.3704 | 3.3436 | 3.3157 | 3.2881 | 3.2607 | 3.2335 | 3.2065 | 3.1842 | 3.162 | 3.1399 | 3.118 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963 | 3.0963
545 | Papakura |  |  | 2052 | 880.0788 | 898.1888 | 916.6715 | 935.5344 | 954.7856 | 957.4579 | 960.1377 | 962.825 | 965.5198 | 968.2222 | 970.9466 | 973.6786 | 976.4183 | 979.1658 | 981.921 | 984.4162 | 986.9178 | 989.4258 | 991.9401 | 994.4608 | 996.685 | 998.9142 | 1001.1483 | 1003.3875 | 1005.6316 | 1008.623 | 1011.6233 | 1014.6325 | 1017.6507 | 1020.6778 | 1023.4839 | 1026.2977 | 1029.1192 | 1031.9485 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 | 1034.7856 |  | 2630 | 2683.3543 | 2737.7911 | 2793.3322 | 2850 | 2847.0307 | 2844.0646 | 2841.1015 | 2838.1415 | 2835.1846 | 2832.0613 | 2828.9415 | 2825.8251 | 2822.7121 | 2819.6025 | 2814.7394 | 2809.8846 | 2805.0382 | 2800.2002 | 2795.3705 | 2789.4551 | 2783.5522 | 2777.6617 | 2771.7838 | 2765.9182 | 2761.8028 | 2757.6934 | 2753.5902 | 2749.4931 | 2745.402 | 2752.8451 | 2760.3083 | 2767.7917 | 2775.2954 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | 2782.8195 | [6 empty] | 354 | 357 | 360 | 363 | 365.3 | 370 | 375 | 380 | 385 | 390 | 393.6 | 398 | 403 | 408 | 413 | 418 | 423 | 428 | 433 | 438 | 443 | 448 | 453 | 458 | 463 | 468 | 473 | 478 | 483 | 488 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | [6 empty] | 2.9884 | 2.9875 | 2.9867 | 2.9858 | 2.985 | 2.9735 | 2.9621 | 2.9508 | 2.9395 | 2.9282 | 2.9168 | 2.9054 | 2.8941 | 2.8828 | 2.8715 | 2.8593 | 2.8471 | 2.835 | 2.823 | 2.8109 | 2.7987 | 2.7866 | 2.7745 | 2.7624 | 2.7504 | 2.7382 | 2.726 | 2.7139 | 2.7018 | 2.6898 | 2.6897 | 2.6896 | 2.6895 | 2.6894 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893 | 2.6893
546 | Papakura |  |  | 2052 | 1372.6646 | 1396.5328 | 1420.8161 | 1445.5216 | 1470.6567 | 1479.3706 | 1488.1361 | 1496.9535 | 1505.8232 | 1514.7455 | 1523.6305 | 1532.5676 | 1541.5571 | 1550.5994 | 1559.6947 | 1567.8541 | 1576.0563 | 1584.3014 | 1592.5895 | 1600.9211 | 1608.2086 | 1615.5292 | 1622.8832 | 1630.2706 | 1637.6917 | 1647.4793 | 1657.3255 | 1667.2306 | 1677.1948 | 1687.2186 | 1696.4056 | 1705.6427 | 1714.93 | 1724.2679 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 | 1733.6567 |  | 4040 | 4108.2509 | 4177.6548 | 4248.2313 | 4320 | 4328.3937 | 4336.8038 | 4345.2302 | 4353.6729 | 4362.1321 | 4370.0263 | 4377.9348 | 4385.8577 | 4393.7948 | 4401.7464 | 4405.5906 | 4409.4381 | 4413.289 | 4417.1433 | 4421.001 | 4421.5406 | 4422.0802 | 4422.62 | 4423.1598 | 4423.6996 | 4429.9166 | 4436.1424 | 4442.3769 | 4448.6202 | 4454.8722 | 4478.4947 | 4502.2424 | 4526.116 | 4550.1163 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | 4574.2437 | [6 empty] | 710 | 714 | 718 | 722 | 725.3 | 736 | 747 | 758 | 769 | 780 | 788.7 | 796 | 804 | 812 | 820 | 828 | 836 | 844 | 852 | 860 | 868 | 876 | 884 | 892 | 900 | 908 | 916 | 924 | 932 | 940 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | 940.3 | [6 empty] | 2.9432 | 2.9418 | 2.9403 | 2.9389 | 2.9375 | 2.9258 | 2.9143 | 2.9027 | 2.8912 | 2.8798 | 2.8682 | 2.8566 | 2.8451 | 2.8336 | 2.8222 | 2.8099 | 2.7978 | 2.7856 | 2.7736 | 2.7615 | 2.7494 | 2.7372 | 2.7252 | 2.7131 | 2.7012 | 2.6889 | 2.6767 | 2.6645 | 2.6524 | 2.6404 | 2.64 | 2.6396 | 2.6392 | 2.6389 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385 | 2.6385
547 | Papakura |  |  | 2052 | 1364.7078 | 1386.3518 | 1408.3391 | 1430.6751 | 1453.3653 | 1458.1209 | 1462.892 | 1467.6787 | 1472.4811 | 1477.2992 | 1482.1475 | 1487.0117 | 1491.8918 | 1496.788 | 1501.7002 | 1506.157 | 1510.627 | 1515.1103 | 1519.6069 | 1524.1168 | 1528.0988 | 1532.0912 | 1536.0941 | 1540.1074 | 1544.1312 | 1549.4855 | 1554.8583 | 1560.2498 | 1565.66 | 1571.0889 | 1576.1119 | 1581.1511 | 1586.2063 | 1591.2777 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 | 1596.3653 |  | 4280 | 4348.3454 | 4417.7822 | 4488.3279 | 4560 | 4561.3096 | 4562.6196 | 4563.93 | 4565.2408 | 4566.5519 | 4567.7006 | 4568.8495 | 4569.9988 | 4571.1484 | 4572.2982 | 4569.8212 | 4567.3455 | 4564.8711 | 4562.3981 | 4559.9264 | 4555.5453 | 4551.1685 | 4546.7958 | 4542.4273 | 4538.063 | 4537.2986 | 4536.5343 | 4535.7701 | 4535.006 | 4534.2421 | 4548.8344 | 4563.4736 | 4578.1599 | 4592.8935 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | 4607.6746 | [6 empty] | 838 | 846 | 854 | 862 | 868.1 | 879 | 890 | 901 | 912 | 923 | 931.3 | 941 | 950 | 959 | 968 | 977 | 986 | 995 | 1004 | 1013 | 1022 | 1031 | 1040 | 1049 | 1058 | 1067 | 1076 | 1085 | 1094 | 1103 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | 1115.4 | [6 empty] | 3.1362 | 3.1365 | 3.1369 | 3.1372 | 3.1375 | 3.1282 | 3.1189 | 3.1096 | 3.1004 | 3.0911 | 3.0818 | 3.0725 | 3.0632 | 3.054 | 3.0447 | 3.0341 | 3.0235 | 3.0129 | 3.0024 | 2.9918 | 2.9812 | 2.9706 | 2.96 | 2.9494 | 2.9389 | 2.9283 | 2.9177 | 2.9071 | 2.8965 | 2.8861 | 2.8861 | 2.8862 | 2.8862 | 2.8863 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864 | 2.8864
548 | Papakura |  |  | 2052 | 864.381 | 895.8876 | 928.5427 | 962.388 | 997.467 | 1030.7094 | 1065.0596 | 1100.5547 | 1137.2327 | 1175.133 | 1209.3127 | 1244.4865 | 1280.6834 | 1317.9331 | 1356.2662 | 1387.8925 | 1420.2563 | 1453.3749 | 1487.2656 | 1521.9467 | 1550.369 | 1579.3221 | 1608.8158 | 1638.8604 | 1669.466 | 1707.4383 | 1746.2742 | 1785.9934 | 1826.616 | 1868.1627 | 1904.0203 | 1940.5663 | 1977.8137 | 2015.776 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 | 2054.467 |  | 2350 | 2435.2481 | 2523.5887 | 2615.1339 | 2710 | 2798.9834 | 2890.8886 | 2985.8115 | 3083.8512 | 3185.1101 | 3276.2361 | 3369.9692 | 3466.3841 | 3565.5574 | 3667.568 | 3747.3073 | 3828.7803 | 3912.0246 | 3997.0788 | 4083.9822 | 4153.8442 | 4224.9013 | 4297.1739 | 4370.6828 | 4445.4492 | 4539.4746 | 4635.4887 | 4733.5336 | 4833.6523 | 4935.8885 | 5030.4234 | 5126.7688 | 5224.9595 | 5325.0309 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | 5427.0188 | [6 empty] | 1006 | 1013 | 1020 | 1027 | 1033.4 | 1046 | 1058 | 1070 | 1082 | 1094 | 1107.5 | 1118 | 1128 | 1138 | 1148 | 1158 | 1168 | 1178 | 1188 | 1198 | 1208 | 1218 | 1228 | 1238 | 1248 | 1258 | 1268 | 1278 | 1288 | 1298 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | 1309.4 | [6 empty] | 2.7187 | 2.7183 | 2.7178 | 2.7173 | 2.7169 | 2.7156 | 2.7143 | 2.713 | 2.7117 | 2.7104 | 2.7092 | 2.7079 | 2.7067 | 2.7054 | 2.7042 | 2.7 | 2.6958 | 2.6917 | 2.6875 | 2.6834 | 2.6793 | 2.6751 | 2.671 | 2.6669 | 2.6628 | 2.6586 | 2.6545 | 2.6504 | 2.6462 | 2.6421 | 2.642 | 2.6419 | 2.6418 | 2.6417 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416 | 2.6416
549 | Papakura |  |  | 2052 | 642.703 | 694.502 | 750.4757 | 810.9607 | 876.3205 | 915.8265 | 957.1136 | 1000.262 | 1045.3555 | 1092.482 | 1133.3792 | 1175.8073 | 1219.8238 | 1265.4881 | 1312.8617 | 1357.3664 | 1403.3796 | 1450.9527 | 1500.1385 | 1550.9916 | 1594.9627 | 1640.1804 | 1686.68 | 1734.4979 | 1783.6715 | 1823.7668 | 1864.7634 | 1906.6817 | 1949.5421 | 1993.3661 | 2021.7378 | 2050.5133 | 2079.6983 | 2109.2987 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 | 2139.3205 |  | 2230 | 2403.6447 | 2590.8107 | 2792.5508 | 3010 | 3128.4056 | 3251.4689 | 3379.3732 | 3512.3089 | 3650.474 | 3766.3498 | 3885.9039 | 4009.253 | 4136.5175 | 4267.8216 | 4384.7782 | 4504.9399 | 4628.3946 | 4755.2324 | 4885.5461 | 4992.0598 | 5100.8957 | 5212.1044 | 5325.7377 | 5441.8484 | 5528.1936 | 5615.9088 | 5705.0158 | 5795.5367 | 5887.4938 | 5970.1105 | 6053.8864 | 6138.838 | 6224.9817 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | 6312.3341 | [6 empty] | 472 | 477 | 482 | 487 | 491.1 | 499 | 506 | 513 | 520 | 527 | 535.5 | 542 | 549 | 556 | 563 | 570 | 577 | 584 | 591 | 598 | 605 | 612 | 619 | 626 | 633 | 640 | 647 | 654 | 661 | 668 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | 673.3 | [6 empty] | 3.4697 | 3.461 | 3.4522 | 3.4435 | 3.4348 | 3.4159 | 3.3972 | 3.3785 | 3.3599 | 3.3415 | 3.3231 | 3.3049 | 3.2867 | 3.2687 | 3.2508 | 3.2304 | 3.2101 | 3.1899 | 3.1699 | 3.15 | 3.1299 | 3.11 | 3.0902 | 3.0705 | 3.0509 | 3.0312 | 3.0116 | 2.9921 | 2.9728 | 2.9535 | 2.953 | 2.9524 | 2.9518 | 2.9512 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506 | 2.9506
550 | Papakura | Drury | Opaheke | 2060 | 490.6564 | 506.6452 | 523.155 | 540.2028 | 557.8061 | 593.4251 | 631.3186 | 671.6318 | 714.5192 | 760.1453 | 800.6667 | 843.3482 | 888.305 | 935.6583 | 985.5358 | 1031.3107 | 1079.2116 | 1129.3374 | 1181.7914 | 1236.6817 | 1285.1756 | 1335.5712 | 1387.9429 | 1442.3682 | 1498.9277 | 1534.2152 | 1570.3334 | 1607.3019 | 1645.1407 | 1683.8703 | 1700.7936 | 1717.8869 | 1735.152 | 1752.5906 | 1770.2045 | 1779.804 | 1789.4034 | 1799.0028 | 1808.6023 | 1818.2017 | 1827.8011 | 1837.4006 | 1847 | 1847 | 1847 | 1847 | 1847 | 1847 | 1847 | 1847 | 1847 | 1847 | 1847 | 1847 | 1847 | 1847 | 1847 | 1847 | 1847 | 1847 | 1847 | 1847 | 1847 |  | 1460 | 1482.256 | 1504.8512 | 1527.7908 | 1551.0802 | 1642.8939 | 1740.1424 | 1843.1473 | 1952.2494 | 2067.8097 | 2168.9862 | 2275.1132 | 2386.4329 | 2503.1994 | 2625.6793 | 2736.87 | 2852.7694 | 2973.5769 | 3099.5002 | 3230.7561 | 3347.4891 | 3468.44 | 3593.761 | 3723.6101 | 3858.1509 | 3939.9995 | 4023.5846 | 4108.9428 | 4196.1119 | 4285.1302 | 4317.7804 | 4350.6794 | 4383.8291 | 4417.2314 | 4450.8882 | 4469.9022 | 4488.9162 | 4507.9301 | 4526.9441 | 4545.9581 | 4564.9721 | 4583.986 | 4603 | 4603 | 4603 | 4603 | 4603 | 4603 | 4603 | 4603 | 4603 | 4603 | 4603 | 4603 | 4603 | 4603 | 4603 | 4603 | 4603 | 4603 | 4603 | 4603 | 4603 | [6 empty] | 1473 | 1478 | 1483 | 1488 | 1493.6 | 1505 | 1516 | 1527 | 1538 | 1549 | 1560.9 | 1554 | 1547 | 1540 | 1533 | 1526 | 1519 | 1512 | 1505 | 1498 | 1491 | 1484 | 1477 | 1470 | 1463 | 1456 | 1449 | 1442 | 1435 | 1428 | 1423.5 | 1442.8125 | 1462.125 | 1481.4375 | 1500.75 | 1520.0625 | 1539.375 | 1558.6875 | 1578 | 1578 | 1578 | 1578 | 1578 | 1578 | 1578 | 1578 | 1578 | 1578 | 1578 | 1578 | 1578 | 1578 | 1578 | 1578 | 1578 | 1578 | 1578 | 1578 | 1578 | [6 empty] | 2.9756 | 2.9256 | 2.8765 | 2.8282 | 2.7807 | 2.7685 | 2.7564 | 2.7443 | 2.7323 | 2.7203 | 2.709 | 2.6977 | 2.6865 | 2.6753 | 2.6642 | 2.6538 | 2.6434 | 2.633 | 2.6227 | 2.6124 | 2.6047 | 2.597 | 2.5893 | 2.5816 | 2.5739 | 2.5681 | 2.5622 | 2.5564 | 2.5506 | 2.5448 | 2.5387 | 2.5326 | 2.5265 | 2.5204 | 2.5143 | 2.5115 | 2.5086 | 2.5058 | 2.503 | 2.5002 | 2.4975 | 2.4948 | 2.4921 | 2.4921 | 2.4921 | 2.4921 | 2.4921 | 2.4921 | 2.4921 | 2.4921 | 2.4921 | 2.4921 | 2.4921 | 2.4921 | 2.4921 | 2.4921 | 2.4921 | 2.4921 | 2.4921 | 2.4921 | 2.4921 | 2.4921 | 2.4921
551 | Franklin | Drury | Opaheke | 2060 | 119.8087 | 115.3868 | 111.1281 | 107.0265 | 103.0763 | 102.5931 | 102.1121 | 101.6333 | 101.1568 | 100.6826 | 116.3239 | 134.3951 | 155.2737 | 179.3959 | 207.2655 | 274.7389 | 364.1778 | 482.7327 | 639.8821 | 848.1901 | 956.9974 | 1079.7627 | 1218.2766 | 1374.5592 | 1550.8901 | 1636.2313 | 1726.2685 | 1821.2602 | 1921.479 | 2027.2126 | 2078.363 | 2130.804 | 2184.5682 | 2239.689 | 2296.2006 | 2311.0505 | 2325.9004 | 2340.7504 | 2355.6003 | 2370.4502 | 2385.3001 | 2400.1501 | 2415 | 2415 | 2415 | 2415 | 2415 | 2415 | 2415 | 2415 | 2415 | 2415 | 2415 | 2415 | 2415 | 2415 | 2415 | 2415 | 2415 | 2415 | 2415 | 2415 | 2415 |  | 350 | 347.7772 | 345.5685 | 343.3738 | 341.193 | 339.6146 | 338.0435 | 336.4797 | 334.9231 | 333.3738 | 376.4087 | 424.9989 | 479.8616 | 541.8065 | 611.7478 | 795.8193 | 1035.2769 | 1346.7859 | 1752.0263 | 2279.2013 | 2569.8736 | 2897.6161 | 3267.1564 | 3683.8252 | 4153.6327 | 4381.9655 | 4622.8503 | 4876.9768 | 5145.0732 | 5427.9074 | 5572.8318 | 5721.6256 | 5874.3923 | 6031.2378 | 6192.271 | 6235.1121 | 6277.9533 | 6320.7944 | 6363.6355 | 6406.4766 | 6449.3178 | 6492.1589 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | [6 empty] | 59 | 59 | 59 | 59 | 58.1 | 58 | 58 | 58 | 58 | 58 | 59.7 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 71.3 | 288.0125 | 504.725 | 721.4375 | 938.15 | 1154.8625 | 1371.575 | 1588.2875 | 1805 | 1805 | 1805 | 1805 | 1805 | 1805 | 1805 | 1805 | 1805 | 1805 | 1805 | 1805 | 1805 | 1805 | 1805 | 1805 | 1805 | 1805 | 1805 | 1805 | 1805 | [6 empty] | 2.9213 | 3.014 | 3.1096 | 3.2083 | 3.3101 | 3.3103 | 3.3105 | 3.3107 | 3.3109 | 3.3111 | 3.2359 | 3.1623 | 3.0904 | 3.0202 | 2.9515 | 2.8966 | 2.8428 | 2.7899 | 2.738 | 2.6871 | 2.6854 | 2.6836 | 2.6818 | 2.68 | 2.6782 | 2.6781 | 2.6779 | 2.6778 | 2.6777 | 2.6775 | 2.6814 | 2.6852 | 2.689 | 2.6929 | 2.6967 | 2.698 | 2.6991 | 2.7003 | 2.7015 | 2.7026 | 2.7038 | 2.7049 | 2.706 | 2.706 | 2.706 | 2.706 | 2.706 | 2.706 | 2.706 | 2.706 | 2.706 | 2.706 | 2.706 | 2.706 | 2.706 | 2.706 | 2.706 | 2.706 | 2.706 | 2.706 | 2.706 | 2.706 | 2.706
552 | Franklin |  |  | 2052 | 371.9429 | 371.1246 | 370.308 | 369.4933 | 368.6803 | 369.013 | 369.3461 | 369.6794 | 370.013 | 370.347 | 370.6797 | 371.0127 | 371.3461 | 371.6797 | 372.0136 | 372.3464 | 372.6794 | 373.0127 | 373.3464 | 373.6803 | 374.013 | 374.3461 | 374.6794 | 375.013 | 375.347 | 375.6797 | 376.0127 | 376.3461 | 376.6797 | 377.0136 | 377.3464 | 377.6794 | 378.0127 | 378.3464 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 | 378.6803 |  | 1140 | 1137.4917 | 1134.989 | 1132.4917 | 1130 | 1125.5238 | 1121.0654 | 1116.6246 | 1112.2015 | 1107.7958 | 1103.2689 | 1098.7606 | 1094.2707 | 1089.7991 | 1085.3458 | 1081.8395 | 1078.3446 | 1074.861 | 1071.3886 | 1067.9275 | 1064.4601 | 1061.004 | 1057.5591 | 1054.1254 | 1050.7028 | 1047.0624 | 1043.4346 | 1039.8193 | 1036.2166 | 1032.6264 | 1033.5378 | 1034.45 | 1035.3629 | 1036.2767 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | 1037.1913 | [6 empty] | 315 | 315 | 315 | 315 | 314.3 | 319 | 324 | 329 | 334 | 339 | 344.9 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | 374.5 | [6 empty] | 3.065 | 3.065 | 3.065 | 3.065 | 3.065 | 3.0501 | 3.0353 | 3.0205 | 3.0058 | 2.9912 | 2.9763 | 2.9615 | 2.9468 | 2.9321 | 2.9175 | 2.9055 | 2.8935 | 2.8816 | 2.8697 | 2.8579 | 2.8461 | 2.8343 | 2.8226 | 2.8109 | 2.7993 | 2.7871 | 2.775 | 2.7629 | 2.7509 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739 | 2.739
553 | Franklin |  |  | 2052 | 239.5097 | 236.1591 | 232.8554 | 229.5978 | 226.3859 | 226.5523 | 226.7188 | 226.8855 | 227.0523 | 227.2192 | 227.3856 | 227.5522 | 227.7188 | 227.8856 | 228.0525 | 228.219 | 228.3855 | 228.5522 | 228.719 | 228.8859 | 229.0523 | 229.2189 | 229.3855 | 229.5523 | 229.7192 | 229.8856 | 230.0522 | 230.2189 | 230.3856 | 230.5525 | 230.719 | 230.8855 | 231.0522 | 231.219 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 | 231.3859 |  | 730 | 719.7877 | 709.7183 | 699.7897 | 690 | 687.712 | 685.4316 | 683.1588 | 680.8935 | 678.6357 | 676.3268 | 674.0257 | 671.7325 | 669.4471 | 667.1694 | 665.3129 | 663.4615 | 661.6153 | 659.7742 | 657.9382 | 656.1059 | 654.2787 | 652.4565 | 650.6394 | 648.8274 | 646.9086 | 644.9955 | 643.088 | 641.1861 | 639.2899 | 639.7514 | 640.2132 | 640.6753 | 641.1378 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | 641.6006 | [6 empty] | 177 | 177 | 177 | 177 | 177.6 | 188 | 198 | 208 | 218 | 228 | 239.6 | 256 | 273 | 290 | 307 | 324 | 341 | 358 | 375 | 392 | 409 | 426 | 443 | 460 | 477 | 494 | 511 | 528 | 545 | 562 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | 577.5 | [6 empty] | 3.0479 | 3.0479 | 3.0479 | 3.0479 | 3.0479 | 3.0356 | 3.0233 | 3.011 | 2.9988 | 2.9867 | 2.9744 | 2.9621 | 2.9498 | 2.9376 | 2.9255 | 2.9152 | 2.905 | 2.8948 | 2.8847 | 2.8745 | 2.8644 | 2.8544 | 2.8444 | 2.8344 | 2.8244 | 2.814 | 2.8037 | 2.7934 | 2.7831 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729 | 2.7729
554 | Franklin | Drury | Drury East | 2060 | 136.4295 | 140.5318 | 144.7575 | 149.1102 | 153.5939 | 158.4036 | 163.3639 | 168.4795 | 173.7553 | 179.1964 | 207.4228 | 240.0952 | 277.9142 | 321.6903 | 372.3618 | 487.8896 | 639.2608 | 837.5959 | 1097.4659 | 1437.9624 | 1629.0418 | 1845.5121 | 2090.7475 | 2368.5702 | 2683.3106 | 2834.7865 | 2994.8134 | 3163.8739 | 3342.4782 | 3531.1648 | 3630.74 | 3733.1231 | 3838.3933 | 3946.632 | 4057.9229 | 4085.9326 | 4113.9422 | 4141.9518 | 4169.9615 | 4197.9711 | 4225.9807 | 4253.9904 | 4282 | 4282 | 4282 | 4282 | 4282 | 4282 | 4282 | 4282 | 4282 | 4282 | 4282 | 4282 | 4282 | 4282 | 4282 | 4282 | 4282 | 4282 | 4282 | 4282 | 4282 |  | 420 | 421.285 | 422.574 | 423.8669 | 425.1637 | 437.662 | 450.5277 | 463.7716 | 477.4048 | 491.4387 | 565.7852 | 651.379 | 749.9217 | 863.3723 | 993.9861 | 1295.4746 | 1688.4084 | 2200.524 | 2867.9707 | 3737.8624 | 4218.0005 | 4759.8136 | 5371.224 | 6061.1717 | 6839.7449 | 7215.7997 | 7612.5303 | 8031.0735 | 8472.6286 | 8938.4607 | 9178.0947 | 9424.153 | 9676.808 | 9936.2366 | 10202.6202 | 10272.5426 | 10342.4651 | 10412.3876 | 10482.3101 | 10552.2326 | 10622.155 | 10692.0775 | 10762 | 10762 | 10762 | 10762 | 10762 | 10762 | 10762 | 10762 | 10762 | 10762 | 10762 | 10762 | 10762 | 10762 | 10762 | 10762 | 10762 | 10762 | 10762 | 10762 | 10762 | [6 empty] | 125 | 162 | 199 | 236 | 273.2 | 334 | 395 | 456 | 517 | 578 | 639.8 | 792 | 944 | 1096 | 1248 | 1400 | 1552 | 1704 | 1856 | 2008 | 2160 | 2312 | 2464 | 2616 | 2768 | 2920 | 3072 | 3224 | 3376 | 3528 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | 3686.6 | [6 empty] | 3.0785 | 2.9978 | 2.9192 | 2.8426 | 2.7681 | 2.763 | 2.7578 | 2.7527 | 2.7476 | 2.7425 | 2.7277 | 2.713 | 2.6984 | 2.6839 | 2.6694 | 2.6553 | 2.6412 | 2.6272 | 2.6133 | 2.5994 | 2.5893 | 2.5791 | 2.569 | 2.559 | 2.549 | 2.5454 | 2.5419 | 2.5384 | 2.5348 | 2.5313 | 2.5279 | 2.5245 | 2.5211 | 2.5176 | 2.5142 | 2.5141 | 2.514 | 2.5139 | 2.5138 | 2.5137 | 2.5135 | 2.5134 | 2.5133 | 2.5133 | 2.5133 | 2.5133 | 2.5133 | 2.5133 | 2.5133 | 2.5133 | 2.5133 | 2.5133 | 2.5133 | 2.5133 | 2.5133 | 2.5133 | 2.5133 | 2.5133 | 2.5133 | 2.5133 | 2.5133 | 2.5133 | 2.5133
555 | Franklin | Drury | Drury East | 2060 | 122.0497 | 124.13 | 126.2458 | 128.3976 | 130.5862 | 134.174 | 137.8603 | 141.648 | 145.5397 | 149.5384 | 167.7304 | 188.1356 | 211.0231 | 236.695 | 265.4901 | 346.0667 | 451.0985 | 588.0076 | 766.4687 | 999.0932 | 1128.3465 | 1274.3214 | 1439.1811 | 1625.3688 | 1835.6438 | 1938.3325 | 2046.7657 | 2161.2648 | 2282.1692 | 2409.8371 | 2475.665 | 2543.291 | 2612.7643 | 2684.1353 | 2757.456 | 2775.899 | 2794.342 | 2812.785 | 2831.228 | 2849.671 | 2868.114 | 2886.557 | 2905 | 2905 | 2905 | 2905 | 2905 | 2905 | 2905 | 2905 | 2905 | 2905 | 2905 | 2905 | 2905 | 2905 | 2905 | 2905 | 2905 | 2905 | 2905 | 2905 | 2905 |  | 370 | 369.1406 | 368.2832 | 367.4278 | 366.5744 | 375.8785 | 385.4187 | 395.2011 | 405.2317 | 415.517 | 463.4472 | 516.9062 | 576.5317 | 643.0351 | 717.2097 | 926.0846 | 1195.7907 | 1544.044 | 1993.7201 | 2574.3566 | 2902.2119 | 3271.8209 | 3688.5013 | 4158.2477 | 4687.8182 | 4944.203 | 5214.61 | 5499.8059 | 5800.5997 | 6117.8444 | 6278.9666 | 6444.3322 | 6614.0529 | 6788.2434 | 6967.0215 | 7013.0188 | 7059.0162 | 7105.0135 | 7151.0108 | 7197.0081 | 7243.0054 | 7289.0027 | 7335 | 7335 | 7335 | 7335 | 7335 | 7335 | 7335 | 7335 | 7335 | 7335 | 7335 | 7335 | 7335 | 7335 | 7335 | 7335 | 7335 | 7335 | 7335 | 7335 | 7335 | [6 empty] | 88 | 88 | 88 | 88 | 88.3 | 89 | 90 | 91 | 92 | 93 | 93.5 | 93 | 92 | 91 | 90 | 89 | 88 | 87 | 86 | 85 | 84 | 83 | 82 | 81 | 80 | 79 | 78 | 77 | 76 | 75 | 83.1 | 164.2125 | 245.325 | 326.4375 | 407.55 | 488.6625 | 569.775 | 650.8875 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | [6 empty] | 3.0316 | 2.9738 | 2.9172 | 2.8616 | 2.8071 | 2.8014 | 2.7957 | 2.79 | 2.7843 | 2.7787 | 2.763 | 2.7475 | 2.7321 | 2.7167 | 2.7015 | 2.676 | 2.6508 | 2.6259 | 2.6012 | 2.5767 | 2.5721 | 2.5675 | 2.5629 | 2.5583 | 2.5538 | 2.5508 | 2.5477 | 2.5447 | 2.5417 | 2.5387 | 2.5363 | 2.5339 | 2.5314 | 2.529 | 2.5266 | 2.5264 | 2.5262 | 2.526 | 2.5258 | 2.5256 | 2.5254 | 2.5252 | 2.525 | 2.525 | 2.525 | 2.525 | 2.525 | 2.525 | 2.525 | 2.525 | 2.525 | 2.525 | 2.525 | 2.525 | 2.525 | 2.525 | 2.525 | 2.525 | 2.525 | 2.525 | 2.525 | 2.525 | 2.525
556 | Franklin |  |  | 2052 | 81.8577 | 94.5264 | 109.1557 | 126.049 | 145.5569 | 145.5569 | 145.5569 | 145.5569 | 145.5569 | 145.5569 | 145.5569 | 145.5569 | 145.5569 | 145.5569 | 145.5569 | 178.0967 | 217.9108 | 266.6255 | 326.2305 | 399.1605 | 455.0089 | 518.6714 | 591.2413 | 673.9647 | 768.2623 | 799.6497 | 832.3193 | 866.3237 | 901.7173 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 | 938.5569 |  | 240 | 274.3812 | 313.6877 | 358.6251 | 410 | 410.0895 | 410.1791 | 410.2686 | 410.3582 | 410.4478 | 410.5373 | 410.6269 | 410.7164 | 410.806 | 410.8956 | 501.4775 | 612.0282 | 746.9498 | 911.6149 | 1112.5803 | 1265.0664 | 1438.4516 | 1635.6003 | 1859.7694 | 2114.6623 | 2197.9914 | 2284.6041 | 2374.6298 | 2468.203 | 2565.4635 | 2565.4636 | 2565.4638 | 2565.4639 | 2565.464 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | 2565.4642 | [6 empty] | 199 | 227 | 255 | 283 | 311.6 | 442 | 572 | 702 | 832 | 962 | 1092.9 | 1371 | 1649 | 1927 | 2205 | 2483 | 2761 | 3039 | 3317 | 3595 | 3873 | 4151 | 4429 | 4707 | 4985 | 5263 | 5541 | 5819 | 6097 | 6375 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | 6649.9 | [6 empty] | 2.9319 | 2.9027 | 2.8738 | 2.8451 | 2.8168 | 2.8174 | 2.818 | 2.8186 | 2.8192 | 2.8198 | 2.8205 | 2.8211 | 2.8217 | 2.8223 | 2.8229 | 2.8158 | 2.8086 | 2.8015 | 2.7944 | 2.7873 | 2.7803 | 2.7733 | 2.7664 | 2.7594 | 2.7525 | 2.7487 | 2.7449 | 2.741 | 2.7372 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334 | 2.7334
557 | Franklin | Drury | Drury West 2 | 2060 | 69.7306 | 72.5402 | 75.463 | 78.5035 | 81.6666 | 81.4106 | 81.1555 | 80.9011 | 80.6476 | 80.3948 | 84.7231 | 89.2843 | 94.0912 | 99.1568 | 104.4952 | 134.5446 | 173.2353 | 223.0522 | 287.1948 | 369.7827 | 412.1165 | 459.2968 | 511.8785 | 570.4798 | 635.79 | 662.0939 | 689.4861 | 718.0115 | 747.7171 | 778.6516 | 781.763 | 784.8868 | 788.0232 | 791.172 | 794.3334 | 795.4168 | 796.5001 | 797.5834 | 798.6667 | 799.75 | 800.8334 | 801.9167 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 |  | 230 | 227.6605 | 225.3449 | 223.0528 | 220.784 | 218.9505 | 217.1323 | 215.3292 | 213.541 | 211.7677 | 222.3695 | 233.502 | 245.1918 | 257.4669 | 270.3565 | 343.7327 | 437.0236 | 555.6341 | 706.4361 | 898.1666 | 989.3641 | 1089.8217 | 1200.4794 | 1322.3731 | 1456.6435 | 1520.6068 | 1587.3789 | 1657.083 | 1729.848 | 1805.8081 | 1811.779 | 1817.7696 | 1823.78 | 1829.8103 | 1835.8605 | 1846.253 | 1856.6454 | 1867.0378 | 1877.4303 | 1887.8227 | 1898.2151 | 1908.6076 | 1919 | 1919 | 1919 | 1919 | 1919 | 1919 | 1919 | 1919 | 1919 | 1919 | 1919 | 1919 | 1919 | 1919 | 1919 | 1919 | 1919 | 1919 | 1919 | 1919 | 1919 | [6 empty] | 37 | 37 | 37 | 37 | 35.6 | 36 | 36 | 36 | 36 | 36 | 37.8 | 59 | 81 | 103 | 125 | 147 | 169 | 191 | 213 | 235 | 257 | 279 | 301 | 323 | 345 | 367 | 389 | 411 | 433 | 455 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | [6 empty] | 3.2984 | 3.1384 | 2.9862 | 2.8413 | 2.7035 | 2.6895 | 2.6755 | 2.6616 | 2.6478 | 2.6341 | 2.6247 | 2.6153 | 2.6059 | 2.5966 | 2.5873 | 2.5548 | 2.5227 | 2.491 | 2.4598 | 2.4289 | 2.4007 | 2.3728 | 2.3452 | 2.318 | 2.2911 | 2.2967 | 2.3023 | 2.3079 | 2.3135 | 2.3191 | 2.3176 | 2.316 | 2.3144 | 2.3128 | 2.3112 | 2.3211 | 2.331 | 2.3409 | 2.3507 | 2.3605 | 2.3703 | 2.3801 | 2.3898 | 2.3898 | 2.3898 | 2.3898 | 2.3898 | 2.3898 | 2.3898 | 2.3898 | 2.3898 | 2.3898 | 2.3898 | 2.3898 | 2.3898 | 2.3898 | 2.3898 | 2.3898 | 2.3898 | 2.3898 | 2.3898 | 2.3898 | 2.3898
558 | Franklin | Drury | Drury West 2 | 2060 | 75.7942 | 75.9005 | 76.0071 | 76.1138 | 76.2206 | 75.9193 | 75.6191 | 75.3202 | 75.0224 | 74.7258 | 74.5288 | 74.3324 | 74.1364 | 73.941 | 73.7461 | 73.5581 | 73.3706 | 73.1835 | 72.9969 | 72.8108 | 72.6052 | 72.4002 | 72.1958 | 71.992 | 71.7887 | 71.5784 | 71.3687 | 71.1596 | 70.9511 | 70.7433 | 70.5719 | 70.4009 | 70.2304 | 70.0603 | 69.8905 | 70.5292 | 71.1679 | 71.8066 | 72.4453 | 73.084 | 73.7226 | 74.3613 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 |  | 140 | 137.169 | 134.3953 | 131.6776 | 129.0149 | 127.8383 | 126.6725 | 125.5173 | 124.3726 | 123.2384 | 122.351 | 121.4699 | 120.5952 | 119.7268 | 118.8646 | 118.0378 | 117.2167 | 116.4014 | 115.5917 | 114.7876 | 113.9507 | 113.1198 | 112.2951 | 111.4763 | 110.6635 | 109.8077 | 108.9585 | 108.1159 | 107.2798 | 106.4502 | 106.1466 | 105.8439 | 105.542 | 105.241 | 104.9409 | 106.0733 | 107.2057 | 108.3381 | 109.4704 | 110.6028 | 111.7352 | 112.8676 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | [6 empty] | 21 | 21 | 21 | 21 | 20.3 | 20 | 20 | 20 | 20 | 20 | 20.9 | 55 | 89 | 123 | 157 | 191 | 225 | 259 | 293 | 327 | 361 | 395 | 429 | 463 | 497 | 531 | 565 | 599 | 633 | 667 | 694.5 | 707.9375 | 721.375 | 734.8125 | 748.25 | 761.6875 | 775.125 | 788.5625 | 802 | 802 | 802 | 802 | 802 | 802 | 802 | 802 | 802 | 802 | 802 | 802 | 802 | 802 | 802 | 802 | 802 | 802 | 802 | 802 | 802 | [6 empty] | 1.8471 | 1.8072 | 1.7682 | 1.73 | 1.6927 | 1.6839 | 1.6751 | 1.6665 | 1.6578 | 1.6492 | 1.6417 | 1.6341 | 1.6267 | 1.6192 | 1.6118 | 1.6047 | 1.5976 | 1.5905 | 1.5835 | 1.5765 | 1.5695 | 1.5624 | 1.5554 | 1.5485 | 1.5415 | 1.5341 | 1.5267 | 1.5193 | 1.512 | 1.5047 | 1.5041 | 1.5034 | 1.5028 | 1.5022 | 1.5015 | 1.504 | 1.5064 | 1.5087 | 1.5111 | 1.5134 | 1.5156 | 1.5178 | 1.52 | 1.52 | 1.52 | 1.52 | 1.52 | 1.52 | 1.52 | 1.52 | 1.52 | 1.52 | 1.52 | 1.52 | 1.52 | 1.52 | 1.52 | 1.52 | 1.52 | 1.52 | 1.52 | 1.52 | 1.52
559 | Franklin | Drury | Drury West 2 | 2060 | 54.5718 | 55.6572 | 56.7643 | 57.8933 | 59.0448 | 58.8505 | 58.6569 | 58.4638 | 58.2714 | 58.0797 | 64.5829 | 71.8142 | 79.8553 | 88.7968 | 98.7394 | 150.7664 | 230.2072 | 351.5063 | 536.7196 | 819.5241 | 924.1324 | 1042.0934 | 1175.1117 | 1325.109 | 1494.2529 | 1581.0903 | 1672.9743 | 1770.1981 | 1873.072 | 1981.9243 | 2027.8193 | 2074.7772 | 2122.8224 | 2171.9803 | 2222.2764 | 2231.7419 | 2241.2073 | 2250.6728 | 2260.1382 | 2269.6037 | 2279.0691 | 2288.5346 | 2298 | 2298 | 2298 | 2298 | 2298 | 2298 | 2298 | 2298 | 2298 | 2298 | 2298 | 2298 | 2298 | 2298 | 2298 | 2298 | 2298 | 2298 | 2298 | 2298 | 2298 |  | 190 | 187.3106 | 184.6592 | 182.0454 | 179.4686 | 177.8057 | 176.1582 | 174.5259 | 172.9088 | 171.3067 | 187.9886 | 206.2949 | 226.3839 | 248.4292 | 272.6213 | 411.5487 | 621.2733 | 937.8732 | 1415.812 | 2137.3077 | 2406.2499 | 2709.0337 | 3049.9174 | 3433.6954 | 3865.7649 | 4091.4482 | 4330.3068 | 4583.11 | 4850.6719 | 5133.8539 | 5248.0523 | 5364.791 | 5484.1264 | 5606.1163 | 5730.8198 | 5752.5923 | 5774.3648 | 5796.1373 | 5817.9099 | 5839.6824 | 5861.4549 | 5883.2275 | 5905 | 5905 | 5905 | 5905 | 5905 | 5905 | 5905 | 5905 | 5905 | 5905 | 5905 | 5905 | 5905 | 5905 | 5905 | 5905 | 5905 | 5905 | 5905 | 5905 | 5905 | [6 empty] | 140 | 140 | 140 | 140 | 139.9 | 141 | 142 | 143 | 144 | 145 | 148.2 | 188 | 228 | 268 | 308 | 348 | 388 | 428 | 468 | 508 | 548 | 588 | 628 | 668 | 708 | 748 | 788 | 828 | 868 | 908 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | 952.9 | [6 empty] | 3.4817 | 3.3654 | 3.2531 | 3.1445 | 3.0395 | 3.0213 | 3.0032 | 2.9852 | 2.9673 | 2.9495 | 2.9108 | 2.8726 | 2.8349 | 2.7977 | 2.761 | 2.7297 | 2.6988 | 2.6682 | 2.6379 | 2.608 | 2.6038 | 2.5996 | 2.5954 | 2.5913 | 2.5871 | 2.5877 | 2.5884 | 2.589 | 2.5897 | 2.5903 | 2.588 | 2.5857 | 2.5834 | 2.5811 | 2.5788 | 2.5776 | 2.5765 | 2.5753 | 2.5741 | 2.573 | 2.5719 | 2.5707 | 2.5696 | 2.5696 | 2.5696 | 2.5696 | 2.5696 | 2.5696 | 2.5696 | 2.5696 | 2.5696 | 2.5696 | 2.5696 | 2.5696 | 2.5696 | 2.5696 | 2.5696 | 2.5696 | 2.5696 | 2.5696 | 2.5696 | 2.5696 | 2.5696
560 | Franklin | Drury | Drury West 2 | 2060 | 6.0635 | 6.7341 | 7.4789 | 8.306 | 9.2246 | 9.1757 | 9.127 | 9.0786 | 9.0304 | 8.9825 | 10.8655 | 13.1433 | 15.8987 | 19.2316 | 23.2632 | 46.8131 | 94.2031 | 189.5672 | 381.4704 | 767.6419 | 887.5433 | 1026.1725 | 1186.4548 | 1371.7723 | 1586.0354 | 1664.8009 | 1747.4781 | 1834.2613 | 1925.3542 | 2020.971 | 2044.0634 | 2067.4197 | 2091.0428 | 2114.9359 | 2139.1019 | 2146.0892 | 2153.0765 | 2160.0637 | 2167.051 | 2174.0382 | 2181.0255 | 2188.0127 | 2195 | 2195 | 2195 | 2195 | 2195 | 2195 | 2195 | 2195 | 2195 | 2195 | 2195 | 2195 | 2195 | 2195 | 2195 | 2195 | 2195 | 2195 | 2195 | 2195 | 2195 |  | 20 | 20.7931 | 21.6177 | 22.475 | 23.3663 | 23.0974 | 22.8316 | 22.5689 | 22.3092 | 22.0524 | 27.0217 | 33.1107 | 40.5719 | 49.7143 | 60.9169 | 122.5777 | 246.6523 | 496.3165 | 998.6936 | 2009.5827 | 2321.8151 | 2682.5595 | 3099.3535 | 3580.9055 | 4137.277 | 4342.1103 | 4557.0846 | 4782.7022 | 5019.49 | 5268.0009 | 5330.7317 | 5394.2095 | 5458.4431 | 5523.4417 | 5589.2142 | 5612.9374 | 5636.6607 | 5660.3839 | 5684.1071 | 5707.8303 | 5731.5536 | 5755.2768 | 5779 | 5779 | 5779 | 5779 | 5779 | 5779 | 5779 | 5779 | 5779 | 5779 | 5779 | 5779 | 5779 | 5779 | 5779 | 5779 | 5779 | 5779 | 5779 | 5779 | 5779 | [6 empty] | 361 | 362 | 363 | 364 | 364.9 | 367 | 369 | 371 | 373 | 375 | 377 | 377 | 377 | 377 | 377 | 377 | 377 | 377 | 377 | 377 | 377 | 377 | 377 | 377 | 377 | 377 | 377 | 377 | 377 | 377 | 369.7 | 395.3625 | 421.025 | 446.6875 | 472.35 | 498.0125 | 523.675 | 549.3375 | 575 | 575 | 575 | 575 | 575 | 575 | 575 | 575 | 575 | 575 | 575 | 575 | 575 | 575 | 575 | 575 | 575 | 575 | 575 | 575 | 575 | [6 empty] | 3.2984 | 3.0877 | 2.8905 | 2.7059 | 2.533 | 2.5172 | 2.5016 | 2.486 | 2.4705 | 2.455 | 2.4869 | 2.5192 | 2.5519 | 2.585 | 2.6186 | 2.6184 | 2.6183 | 2.6182 | 2.618 | 2.6179 | 2.616 | 2.6141 | 2.6123 | 2.6104 | 2.6086 | 2.6082 | 2.6078 | 2.6074 | 2.607 | 2.6067 | 2.6079 | 2.6092 | 2.6104 | 2.6116 | 2.6129 | 2.6154 | 2.618 | 2.6205 | 2.623 | 2.6255 | 2.6279 | 2.6304 | 2.6328 | 2.6328 | 2.6328 | 2.6328 | 2.6328 | 2.6328 | 2.6328 | 2.6328 | 2.6328 | 2.6328 | 2.6328 | 2.6328 | 2.6328 | 2.6328 | 2.6328 | 2.6328 | 2.6328 | 2.6328 | 2.6328 | 2.6328 | 2.6328
561 | Franklin | Drury | Drury West 1 | 2060 | 73.6753 | 117.0277 | 185.8896 | 295.2714 | 469.0161 | 613.8642 | 803.4464 | 1051.578 | 1376.3411 | 1801.4021 | 1938.58 | 2086.2041 | 2245.0698 | 2416.0333 | 2600.0158 | 2704.8654 | 2813.9431 | 2927.4196 | 3045.4722 | 3168.2855 | 3235.1677 | 3303.4617 | 3373.1975 | 3444.4053 | 3517.1164 | 3544.2957 | 3571.6851 | 3599.2861 | 3627.1004 | 3655.1297 | 3670.967 | 3686.873 | 3702.8478 | 3718.8919 | 3735.0055 | 3745.5048 | 3756.0041 | 3766.5034 | 3777.0027 | 3787.502 | 3798.0014 | 3808.5007 | 3819 | 3819 | 3819 | 3819 | 3819 | 3819 | 3819 | 3819 | 3819 | 3819 | 3819 | 3819 | 3819 | 3819 | 3819 | 3819 | 3819 | 3819 | 3819 | 3819 | 3819 |  | 170 | 278.7842 | 457.18 | 749.7326 | 1229.4916 | 1603.5294 | 2091.3576 | 2727.5936 | 3557.3864 | 4639.6199 | 4955.9234 | 5293.7907 | 5654.6919 | 6040.1973 | 6451.9843 | 6709.0109 | 6976.2766 | 7254.1893 | 7543.1731 | 7843.6692 | 8006.3281 | 8172.3601 | 8341.8352 | 8514.8248 | 8691.4018 | 8759.4904 | 8828.1124 | 8897.272 | 8966.9734 | 9037.2208 | 9076.7751 | 9116.5024 | 9156.4037 | 9196.4795 | 9236.7308 | 9262.7645 | 9288.7981 | 9314.8318 | 9340.8654 | 9366.8991 | 9392.9327 | 9418.9664 | 9445 | 9445 | 9445 | 9445 | 9445 | 9445 | 9445 | 9445 | 9445 | 9445 | 9445 | 9445 | 9445 | 9445 | 9445 | 9445 | 9445 | 9445 | 9445 | 9445 | 9445 | [6 empty] | 90 | 91 | 92 | 93 | 94.4 | 105 | 115 | 125 | 135 | 145 | 156.3 | 185 | 213 | 241 | 269 | 297 | 325 | 353 | 381 | 409 | 437 | 465 | 493 | 521 | 549 | 577 | 605 | 633 | 661 | 689 | 723.7 | 747.2375 | 770.775 | 794.3125 | 817.85 | 841.3875 | 864.925 | 888.4625 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | 912 | [6 empty] | 2.3074 | 2.3822 | 2.4594 | 2.5391 | 2.6214 | 2.6122 | 2.603 | 2.5938 | 2.5847 | 2.5756 | 2.5565 | 2.5375 | 2.5187 | 2.5 | 2.4815 | 2.4803 | 2.4792 | 2.478 | 2.4768 | 2.4757 | 2.4748 | 2.4739 | 2.473 | 2.4721 | 2.4712 | 2.4714 | 2.4717 | 2.472 | 2.4722 | 2.4725 | 2.4726 | 2.4727 | 2.4728 | 2.4729 | 2.473 | 2.473 | 2.4731 | 2.4731 | 2.4731 | 2.4731 | 2.4731 | 2.4731 | 2.4732 | 2.4732 | 2.4732 | 2.4732 | 2.4732 | 2.4732 | 2.4732 | 2.4732 | 2.4732 | 2.4732 | 2.4732 | 2.4732 | 2.4732 | 2.4732 | 2.4732 | 2.4732 | 2.4732 | 2.4732 | 2.4732 | 2.4732 | 2.4732
562 | Franklin | Drury | Drury West 1 | 2060 | 57.6036 | 58.5568 | 59.5258 | 60.5108 | 61.5122 | 78.7556 | 100.8328 | 129.0988 | 165.2885 | 211.6231 | 282.4248 | 376.9143 | 503.0166 | 671.3084 | 895.9048 | 1043.284 | 1214.9075 | 1414.7637 | 1647.4969 | 1918.5154 | 2089.7888 | 2276.3525 | 2479.5714 | 2700.9324 | 2942.0552 | 3062.6463 | 3188.1803 | 3318.8597 | 3454.8956 | 3596.5074 | 3646.407 | 3696.9989 | 3748.2928 | 3800.2984 | 3853.0255 | 3870.2723 | 3887.5191 | 3904.7659 | 3922.0128 | 3939.2596 | 3956.5064 | 3973.7532 | 3991 | 3991 | 3991 | 3991 | 3991 | 3991 | 3991 | 3991 | 3991 | 3991 | 3991 | 3991 | 3991 | 3991 | 3991 | 3991 | 3991 | 3991 | 3991 | 3991 | 3991 |  | 180 | 178.6046 | 177.2201 | 175.8463 | 174.4831 | 220.733 | 279.2424 | 353.2607 | 446.8989 | 565.3576 | 752.4528 | 1001.4639 | 1332.8808 | 1773.9744 | 2361.0402 | 2730.9268 | 3158.7607 | 3653.6203 | 4226.0058 | 4888.0627 | 5309.1102 | 5766.4258 | 6263.1337 | 6802.6269 | 7388.5909 | 7673.7704 | 7969.957 | 8277.5756 | 8597.0674 | 8928.8907 | 9044.2434 | 9161.0863 | 9279.4387 | 9399.3201 | 9520.7503 | 9564.1565 | 9607.5627 | 9650.9689 | 9694.3751 | 9737.7814 | 9781.1876 | 9824.5938 | 9868 | 9868 | 9868 | 9868 | 9868 | 9868 | 9868 | 9868 | 9868 | 9868 | 9868 | 9868 | 9868 | 9868 | 9868 | 9868 | 9868 | 9868 | 9868 | 9868 | 9868 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124.75 | 249.5 | 374.25 | 499 | 623.75 | 748.5 | 873.25 | 998 | 998 | 998 | 998 | 998 | 998 | 998 | 998 | 998 | 998 | 998 | 998 | 998 | 998 | 998 | 998 | 998 | 998 | 998 | 998 | 998 | [6 empty] | 3.1248 | 3.0501 | 2.9772 | 2.906 | 2.8366 | 2.8028 | 2.7694 | 2.7364 | 2.7038 | 2.6715 | 2.6643 | 2.657 | 2.6498 | 2.6426 | 2.6354 | 2.6176 | 2.6 | 2.5825 | 2.5651 | 2.5478 | 2.5405 | 2.5332 | 2.5259 | 2.5186 | 2.5114 | 2.5056 | 2.4998 | 2.4941 | 2.4884 | 2.4827 | 2.4803 | 2.478 | 2.4756 | 2.4733 | 2.471 | 2.4712 | 2.4714 | 2.4716 | 2.4718 | 2.472 | 2.4722 | 2.4724 | 2.4726 | 2.4726 | 2.4726 | 2.4726 | 2.4726 | 2.4726 | 2.4726 | 2.4726 | 2.4726 | 2.4726 | 2.4726 | 2.4726 | 2.4726 | 2.4726 | 2.4726 | 2.4726 | 2.4726 | 2.4726 | 2.4726 | 2.4726 | 2.4726
563 | Franklin |  |  | 2052 | 75.7942 | 78.133 | 80.5439 | 83.0292 | 85.5912 | 86.0855 | 86.5826 | 87.0826 | 87.5854 | 88.0912 | 88.5856 | 89.0828 | 89.5828 | 90.0856 | 90.5912 | 91.0858 | 91.5831 | 92.083 | 92.5858 | 93.0912 | 93.5859 | 94.0833 | 94.5833 | 95.0859 | 95.5912 | 96.0861 | 96.5835 | 97.0835 | 97.586 | 98.0912 | 98.5862 | 99.0837 | 99.5837 | 100.0862 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 | 100.5912 |  | 250 | 257.1843 | 264.5751 | 272.1783 | 280 | 280.3455 | 280.6914 | 281.0377 | 281.3845 | 281.7317 | 282.0043 | 282.2772 | 282.5504 | 282.8238 | 283.0975 | 283.5553 | 284.0138 | 284.4731 | 284.9332 | 285.3939 | 285.8126 | 286.2319 | 286.6518 | 287.0723 | 287.4934 | 287.8204 | 288.1477 | 288.4755 | 288.8036 | 289.132 | 290.591 | 292.0574 | 293.5311 | 295.0123 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | 296.501 | [6 empty] | 96 | 96 | 96 | 96 | 96.9 | 98 | 99 | 100 | 101 | 102 | 101.5 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | 95.1 | [6 empty] | 3.2984 | 3.2916 | 3.2849 | 3.2781 | 3.2714 | 3.2566 | 3.2419 | 3.2273 | 3.2127 | 3.1982 | 3.1834 | 3.1687 | 3.1541 | 3.1395 | 3.125 | 3.1131 | 3.1012 | 3.0893 | 3.0775 | 3.0657 | 3.054 | 3.0423 | 3.0307 | 3.0191 | 3.0075 | 2.9954 | 2.9834 | 2.9714 | 2.9595 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476 | 2.9476
564 | Franklin |  |  | 2052 | 199.2567 | 200.9551 | 202.6679 | 204.3953 | 206.1374 | 207.1836 | 208.2351 | 209.292 | 210.3542 | 211.4218 | 212.4884 | 213.5605 | 214.638 | 215.7208 | 216.8092 | 217.6297 | 218.4533 | 219.28 | 220.1099 | 220.9429 | 221.5855 | 222.23 | 222.8763 | 223.5246 | 224.1747 | 224.7561 | 225.3389 | 225.9233 | 226.5093 | 227.0967 | 227.5034 | 227.9108 | 228.319 | 228.7278 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 | 229.1374 |  | 560 | 564.9344 | 569.9123 | 574.934 | 580 | 580.5182 | 581.0368 | 581.556 | 582.0755 | 582.5956 | 583.0269 | 583.4586 | 583.8906 | 584.3229 | 584.7556 | 584.8185 | 584.8814 | 584.9443 | 585.0072 | 585.0701 | 584.5833 | 584.097 | 583.611 | 583.1254 | 582.6403 | 581.8454 | 581.0517 | 580.259 | 579.4674 | 578.6769 | 579.7754 | 580.876 | 581.9787 | 583.0835 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | 584.1904 | [6 empty] | 138 | 138 | 138 | 138 | 139.2 | 142 | 145 | 148 | 151 | 154 | 158.2 | 158 | 157 | 156 | 155 | 154 | 153 | 152 | 151 | 150 | 149 | 148 | 147 | 146 | 145 | 144 | 143 | 142 | 141 | 140 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | 145.7 | [6 empty] | 2.8104 | 2.8112 | 2.8121 | 2.8129 | 2.8137 | 2.8019 | 2.7903 | 2.7787 | 2.7671 | 2.7556 | 2.7438 | 2.7321 | 2.7204 | 2.7087 | 2.6971 | 2.6872 | 2.6774 | 2.6676 | 2.6578 | 2.6481 | 2.6382 | 2.6283 | 2.6185 | 2.6088 | 2.599 | 2.5888 | 2.5786 | 2.5684 | 2.5583 | 2.5482 | 2.5484 | 2.5487 | 2.549 | 2.5492 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495 | 2.5495
565 | Franklin |  |  | 2052 | 72.7623 | 72.7623 | 72.7623 | 72.7623 | 72.7623 | 89.696 | 110.5706 | 136.3033 | 168.0246 | 207.1283 | 229.2622 | 253.7615 | 280.8787 | 310.8938 | 344.1162 | 370.0859 | 398.0155 | 428.0529 | 460.3571 | 495.0992 | 521.8393 | 550.0236 | 579.7302 | 611.0411 | 644.0432 | 668.9709 | 694.8634 | 721.7581 | 749.6937 | 778.7106 | 796.6729 | 815.0496 | 833.8502 | 853.0844 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 | 872.7623 |  | 250 | 250 | 250 | 250 | 250 | 306.7304 | 376.334 | 461.7323 | 566.5093 | 695.0624 | 765.7167 | 843.5532 | 929.3019 | 1023.7671 | 1127.8349 | 1207.7127 | 1293.2478 | 1384.8408 | 1482.9207 | 1587.9471 | 1666.6007 | 1749.1501 | 1835.7884 | 1926.7179 | 2022.1513 | 2091.2675 | 2162.746 | 2236.6676 | 2313.1158 | 2392.177 | 2446.8516 | 2502.7758 | 2559.9782 | 2618.4879 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | 2678.335 | [6 empty] | 112 | 111 | 110 | 109 | 109.9 | 111 | 112 | 113 | 114 | 115 | 115.3 | 120 | 125 | 130 | 135 | 140 | 145 | 150 | 155 | 160 | 165 | 170 | 175 | 180 | 185 | 190 | 195 | 200 | 205 | 210 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | 209 | [6 empty] | 3.4358 | 3.4358 | 3.4358 | 3.4358 | 3.4358 | 3.4197 | 3.4036 | 3.3875 | 3.3716 | 3.3557 | 3.3399 | 3.3242 | 3.3086 | 3.293 | 3.2775 | 3.2633 | 3.2492 | 3.2352 | 3.2212 | 3.2073 | 3.1937 | 3.1801 | 3.1666 | 3.1532 | 3.1398 | 3.1261 | 3.1125 | 3.0989 | 3.0854 | 3.072 | 3.0713 | 3.0707 | 3.0701 | 3.0694 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688 | 3.0688
566 | Franklin |  |  | 2052 | 48.5082 | 49.4165 | 50.3417 | 51.2843 | 52.2445 | 53.2398 | 54.2541 | 55.2877 | 56.3409 | 57.4143 | 58.4317 | 59.4671 | 60.5209 | 61.5934 | 62.6849 | 63.6347 | 64.5989 | 65.5777 | 66.5713 | 67.5799 | 68.4379 | 69.3068 | 70.1868 | 71.0779 | 71.9803 | 73.1114 | 74.2603 | 75.4273 | 76.6126 | 77.8165 | 78.873 | 79.9439 | 81.0293 | 82.1294 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 | 83.2445 |  | 140 | 142.4357 | 144.9138 | 147.435 | 150 | 151.6766 | 153.372 | 155.0863 | 156.8198 | 158.5726 | 160.424 | 162.297 | 164.1919 | 166.1089 | 168.0482 | 169.8107 | 171.5917 | 173.3914 | 175.21 | 177.0476 | 178.5583 | 180.0819 | 181.6185 | 183.1681 | 184.7311 | 186.835 | 188.9629 | 191.1151 | 193.2918 | 195.4932 | 198.0257 | 200.591 | 203.1895 | 205.8217 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | 208.4879 | [6 empty] | 133 | 133 | 133 | 133 | 134.7 | 135 | 136 | 137 | 138 | 139 | 139.3 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | 130.7 | [6 empty] | 2.8861 | 2.8824 | 2.8786 | 2.8749 | 2.8711 | 2.8489 | 2.8269 | 2.8051 | 2.7834 | 2.7619 | 2.7455 | 2.7292 | 2.713 | 2.6969 | 2.6808 | 2.6685 | 2.6563 | 2.6441 | 2.6319 | 2.6198 | 2.6091 | 2.5983 | 2.5876 | 2.577 | 2.5664 | 2.5555 | 2.5446 | 2.5338 | 2.523 | 2.5122 | 2.5107 | 2.5091 | 2.5076 | 2.5061 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045 | 2.5045
567 | Franklin |  |  | 2052 | 54.5718 | 53.0753 | 51.6198 | 50.2042 | 48.8274 | 50.6278 | 52.4945 | 54.43 | 56.437 | 58.5179 | 60.0588 | 61.6403 | 63.2634 | 64.9292 | 66.639 | 73.8987 | 81.9494 | 90.8771 | 100.7774 | 111.7562 | 130.9769 | 153.5033 | 179.904 | 210.8453 | 247.108 | 273.3799 | 302.445 | 334.6003 | 370.1741 | 409.5301 | 426.169 | 443.4838 | 461.5021 | 480.2525 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 | 499.7647 |  | 190 | 184.7896 | 179.722 | 174.7934 | 170 | 174.467 | 179.0514 | 183.7562 | 188.5847 | 193.5401 | 197.3987 | 201.3343 | 205.3484 | 209.4425 | 213.6182 | 233.8009 | 255.8904 | 280.067 | 306.5277 | 335.4885 | 391.018 | 455.7387 | 531.1719 | 619.0907 | 721.5617 | 794.5303 | 874.878 | 963.3508 | 1060.7706 | 1168.0421 | 1215.4985 | 1264.883 | 1316.2739 | 1369.7529 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | 1425.4046 | [6 empty] | 17 | 17 | 17 | 17 | 16.5 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | 17.9 | [6 empty] | 3.4817 | 3.4817 | 3.4817 | 3.4817 | 3.4817 | 3.4461 | 3.4109 | 3.376 | 3.3415 | 3.3074 | 3.2868 | 3.2663 | 3.2459 | 3.2257 | 3.2056 | 3.1638 | 3.1225 | 3.0818 | 3.0416 | 3.002 | 2.9854 | 2.9689 | 2.9525 | 2.9362 | 2.92 | 2.9063 | 2.8927 | 2.8791 | 2.8656 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522 | 2.8522
568 | Franklin |  |  | 2052 | 39.413 | 58.5072 | 86.852 | 128.9289 | 191.3906 | 275.5221 | 396.636 | 570.9891 | 821.9843 | 1183.312 | 1338.906 | 1514.9592 | 1714.1616 | 1939.5572 | 2194.5901 | 2263.6931 | 2334.9721 | 2408.4955 | 2484.334 | 2562.5604 | 2565.1323 | 2567.7068 | 2570.2838 | 2572.8635 | 2575.4457 | 2576.6336 | 2577.822 | 2579.011 | 2580.2005 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 | 2581.3906 |  | 150 | 206.6174 | 284.605 | 392.0289 | 540 | 773.6393 | 1108.3662 | 1587.9178 | 2274.9548 | 3259.2489 | 3722.4177 | 4251.407 | 4855.5704 | 5545.5909 | 6333.6696 | 6502.9394 | 6676.733 | 6855.1713 | 7038.3784 | 7226.4818 | 7201.6057 | 7176.8152 | 7152.11 | 7127.4899 | 7102.9545 | 7071.7346 | 7040.6518 | 7009.7057 | 6978.8956 | 6948.221 | 6948.2351 | 6948.2493 | 6948.2634 | 6948.2776 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | 6948.2917 | [6 empty] | 309 | 313 | 317 | 321 | 324.8 | 342 | 359 | 376 | 393 | 410 | 426.3 | 459 | 492 | 525 | 558 | 591 | 624 | 657 | 690 | 723 | 756 | 789 | 822 | 855 | 888 | 921 | 954 | 987 | 1020 | 1053 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | 1080.4 | [6 empty] | 3.8059 | 3.5315 | 3.2769 | 3.0407 | 2.8215 | 2.8079 | 2.7944 | 2.781 | 2.7676 | 2.7543 | 2.7802 | 2.8063 | 2.8326 | 2.8592 | 2.886 | 2.8727 | 2.8594 | 2.8462 | 2.8331 | 2.82 | 2.8075 | 2.795 | 2.7826 | 2.7703 | 2.758 | 2.7446 | 2.7312 | 2.718 | 2.7048 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917 | 2.6917
569 | Franklin |  |  | 2052 | 78.826 | 75.1495 | 71.6444 | 68.3028 | 65.1171 | 77.279 | 91.7124 | 108.8415 | 129.1698 | 153.2948 | 168.1172 | 184.3728 | 202.2003 | 221.7515 | 243.1931 | 257.8162 | 273.3185 | 289.753 | 307.1757 | 325.646 | 339.1812 | 353.2791 | 367.963 | 383.2572 | 399.187 | 417.2814 | 436.196 | 455.9679 | 476.636 | 498.241 | 515.5684 | 533.4984 | 552.0519 | 571.2507 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 | 591.1171 |  | 230 | 219.2726 | 209.0454 | 199.2953 | 190 | 223.7039 | 263.3864 | 310.1082 | 365.1179 | 429.8857 | 470.3793 | 514.6872 | 563.1688 | 616.2172 | 674.2625 | 713.2286 | 754.4465 | 798.0465 | 844.1661 | 892.9511 | 928.3989 | 965.2539 | 1003.572 | 1043.4112 | 1084.8319 | 1131.8742 | 1180.9565 | 1232.1671 | 1285.5984 | 1341.3466 | 1387.5817 | 1435.4104 | 1484.8877 | 1536.0705 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | 1589.0175 | [6 empty] | 115 | 115 | 115 | 115 | 115.1 | 116 | 117 | 118 | 119 | 120 | 119.3 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | [6 empty] | 2.9178 | 2.9178 | 2.9178 | 2.9178 | 2.9178 | 2.8948 | 2.8719 | 2.8492 | 2.8267 | 2.8043 | 2.7979 | 2.7916 | 2.7852 | 2.7789 | 2.7725 | 2.7664 | 2.7603 | 2.7542 | 2.7482 | 2.7421 | 2.7372 | 2.7323 | 2.7274 | 2.7225 | 2.7176 | 2.7125 | 2.7074 | 2.7023 | 2.6972 | 2.6922 | 2.6914 | 2.6906 | 2.6898 | 2.689 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882 | 2.6882
570 | Franklin |  |  | 2052 | 54.5718 | 52.1402 | 49.817 | 47.5973 | 45.4765 | 45.4765 | 45.4765 | 45.4765 | 45.4765 | 45.4765 | 45.4765 | 45.4765 | 45.4765 | 45.4765 | 45.4765 | 47.1963 | 48.9811 | 50.8334 | 52.7557 | 54.7508 | 57.2178 | 59.796 | 62.4904 | 65.3062 | 68.2488 | 69.4512 | 70.6748 | 71.92 | 73.1871 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 | 74.4765 |  | 180 | 171.9797 | 164.3168 | 156.9953 | 150 | 149.5019 | 149.0054 | 148.5106 | 148.0174 | 147.5259 | 147.0277 | 146.5312 | 146.0364 | 145.5432 | 145.0517 | 149.1729 | 153.4111 | 157.7698 | 162.2522 | 166.8621 | 173 | 179.3637 | 185.9614 | 192.8019 | 199.894 | 202.4216 | 204.981 | 207.5729 | 210.1975 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | 212.8553 | [6 empty] | 22 | 22 | 22 | 22 | 22.3 | 23 | 23 | 23 | 23 | 23 | 23.9 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | [6 empty] | 3.2984 | 3.2984 | 3.2984 | 3.2984 | 3.2984 | 3.2875 | 3.2765 | 3.2657 | 3.2548 | 3.244 | 3.233 | 3.2221 | 3.2112 | 3.2004 | 3.1896 | 3.1607 | 3.132 | 3.1037 | 3.0755 | 3.0477 | 3.0235 | 2.9996 | 2.9758 | 2.9523 | 2.9289 | 2.9146 | 2.9003 | 2.8862 | 2.8721 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858 | 2.858
571 | Franklin |  |  | 2052 | 42.4447 | 46.4236 | 50.7755 | 55.5353 | 60.7413 | 64.1808 | 67.8151 | 71.6552 | 75.7127 | 80 | 83.6512 | 87.469 | 91.461 | 95.6352 | 100 | 130.6233 | 170.6245 | 222.8755 | 291.1273 | 380.2802 | 430.3786 | 487.077 | 551.2448 | 623.8662 | 706.0548 | 768.3988 | 836.2477 | 910.0876 | 990.4476 | 1077.9032 | 1143.8816 | 1213.8984 | 1288.201 | 1367.0516 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 | 1450.7287 |  | 140 | 151.1069 | 163.0951 | 176.0343 | 190 | 198.5122 | 207.4058 | 216.6978 | 226.4061 | 236.5493 | 249.5128 | 263.1867 | 277.6099 | 292.8236 | 308.871 | 401.0788 | 520.8136 | 676.293 | 878.1879 | 1140.3549 | 1282.8205 | 1443.0844 | 1623.3703 | 1826.1794 | 2054.3256 | 2222.1663 | 2403.7197 | 2600.1063 | 2812.5379 | 3042.3254 | 3228.5644 | 3426.2042 | 3635.9427 | 3858.5206 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | 4094.7239 | [6 empty] | 193 | 193 | 193 | 193 | 194.4 | 197 | 199 | 201 | 203 | 205 | 207.8 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | 204.7 | [6 empty] | 3.2984 | 3.255 | 3.2121 | 3.1698 | 3.128 | 3.093 | 3.0584 | 3.0242 | 2.9903 | 2.9569 | 2.9828 | 3.0089 | 3.0353 | 3.0619 | 3.0887 | 3.0705 | 3.0524 | 3.0344 | 3.0165 | 2.9987 | 2.9807 | 2.9627 | 2.9449 | 2.9272 | 2.9096 | 2.8919 | 2.8744 | 2.857 | 2.8397 | 2.8224 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225 | 2.8225
572 | Franklin |  |  | 2052 | 93.9848 | 102.0626 | 110.8346 | 120.3605 | 130.7052 | 132.3309 | 133.9769 | 135.6433 | 137.3304 | 139.0386 | 140.6667 | 142.3138 | 143.9802 | 145.6662 | 147.3719 | 149.0021 | 150.6503 | 152.3168 | 154.0017 | 155.7052 | 157.3373 | 158.9865 | 160.653 | 162.337 | 164.0386 | 165.6724 | 167.3224 | 168.9889 | 170.672 | 172.3719 | 174.0072 | 175.6581 | 177.3246 | 179.0069 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 | 180.7052 |  | 260 | 282.0367 | 305.9412 | 331.8717 | 360 | 362.7843 | 365.5902 | 368.4178 | 371.2672 | 374.1387 | 376.7193 | 379.3176 | 381.9339 | 384.5683 | 387.2208 | 389.9355 | 392.6691 | 395.4219 | 398.1941 | 400.9856 | 403.5612 | 406.1534 | 408.7622 | 411.3878 | 414.0302 | 416.3885 | 418.7603 | 421.1455 | 423.5444 | 425.9569 | 429.998 | 434.0775 | 438.1958 | 442.3531 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | 446.5498 | [6 empty] | 92 | 92 | 92 | 92 | 92.7 | 93 | 93 | 93 | 93 | 93 | 95.4 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | 88.2 | [6 empty] | 2.7664 | 2.7634 | 2.7603 | 2.7573 | 2.7543 | 2.7415 | 2.7288 | 2.7161 | 2.7035 | 2.6909 | 2.6781 | 2.6654 | 2.6527 | 2.6401 | 2.6275 | 2.617 | 2.6065 | 2.596 | 2.5856 | 2.5753 | 2.5649 | 2.5546 | 2.5444 | 2.5342 | 2.524 | 2.5133 | 2.5027 | 2.4921 | 2.4816 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712 | 2.4712
573 | Franklin |  |  | 2052 | 421.444 | 411.605 | 401.9957 | 392.6108 | 383.445 | 385.0973 | 386.7568 | 388.4234 | 390.0973 | 391.7783 | 393.431 | 395.0906 | 396.7572 | 398.4309 | 400.1116 | 401.7646 | 403.4244 | 405.091 | 406.7645 | 408.445 | 410.0982 | 411.7581 | 413.4247 | 415.0981 | 416.7783 | 418.4318 | 420.0918 | 421.7585 | 423.4317 | 425.1116 | 426.7654 | 428.4256 | 430.0922 | 431.7653 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 | 433.445 |  | 1220 | 1191.518 | 1163.701 | 1136.5334 | 1110 | 1110.1699 | 1110.3398 | 1110.5097 | 1110.6796 | 1110.8496 | 1110.8215 | 1110.7934 | 1110.7653 | 1110.7372 | 1110.7091 | 1111.2555 | 1111.8021 | 1112.3491 | 1112.8963 | 1113.4437 | 1113.9323 | 1114.421 | 1114.91 | 1115.3992 | 1115.8886 | 1116.0986 | 1116.3087 | 1116.5188 | 1116.7289 | 1116.9391 | 1121.2862 | 1125.6502 | 1130.0313 | 1134.4293 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | 1138.8445 | [6 empty] | 772 | 773 | 774 | 775 | 776.7 | 782 | 787 | 792 | 797 | 802 | 809.2 | 806 | 803 | 800 | 797 | 794 | 791 | 788 | 785 | 782 | 779 | 776 | 773 | 770 | 767 | 764 | 761 | 758 | 755 | 752 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | 739.9 | [6 empty] | 2.8948 | 2.8948 | 2.8948 | 2.8948 | 2.8948 | 2.8828 | 2.8709 | 2.859 | 2.8472 | 2.8354 | 2.8234 | 2.8115 | 2.7996 | 2.7878 | 2.776 | 2.7659 | 2.7559 | 2.7459 | 2.736 | 2.7261 | 2.7163 | 2.7065 | 2.6968 | 2.6871 | 2.6774 | 2.6673 | 2.6573 | 2.6473 | 2.6373 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274 | 2.6274
574 | Franklin |  |  | 2052 | 1273.2196 | 1273.2196 | 1273.2196 | 1273.2196 | 1273.2196 | 1274.7479 | 1276.278 | 1277.81 | 1279.3439 | 1280.8796 | 1283.1694 | 1285.4633 | 1287.7612 | 1290.0633 | 1292.3696 | 1298.4403 | 1304.5395 | 1310.6673 | 1316.824 | 1323.0096 | 1356.8835 | 1391.6246 | 1427.2553 | 1463.7983 | 1501.2769 | 1517.3775 | 1533.6507 | 1550.0985 | 1566.7227 | 1583.5251 | 1597.8187 | 1612.2414 | 1626.7942 | 1641.4784 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 | 1656.2951 |  | 3750 | 3750 | 3750 | 3750 | 3750 | 3745.2557 | 3740.5174 | 3735.785 | 3731.0587 | 3726.3383 | 3723.6925 | 3721.0485 | 3718.4064 | 3715.7662 | 3713.1279 | 3709.0174 | 3704.9114 | 3700.81 | 3696.7132 | 3692.6209 | 3768.4388 | 3845.8134 | 3924.7767 | 4005.3613 | 4087.6004 | 4116.8543 | 4146.3176 | 4175.9917 | 4205.8782 | 4235.9786 | 4274.1468 | 4312.659 | 4351.5182 | 4390.7276 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | 4430.2902 | [6 empty] | 649 | 654 | 659 | 664 | 667.1 | 673 | 678 | 683 | 688 | 693 | 699.6 | 697 | 695 | 693 | 691 | 689 | 687 | 685 | 683 | 681 | 679 | 677 | 675 | 673 | 671 | 669 | 667 | 665 | 663 | 661 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | 654.4 | [6 empty] | 2.9453 | 2.9453 | 2.9453 | 2.9453 | 2.9453 | 2.938 | 2.9308 | 2.9236 | 2.9164 | 2.9092 | 2.9019 | 2.8947 | 2.8875 | 2.8803 | 2.8731 | 2.8565 | 2.84 | 2.8236 | 2.8073 | 2.7911 | 2.7773 | 2.7635 | 2.7499 | 2.7363 | 2.7227 | 2.7131 | 2.7036 | 2.694 | 2.6845 | 2.675 | 2.675 | 2.6749 | 2.6749 | 2.6749 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748 | 2.6748
575 | Franklin |  |  | 2052 | 1566.095 | 1576.1304 | 1586.2301 | 1596.3945 | 1606.6241 | 1608.0336 | 1609.4443 | 1610.8563 | 1612.2696 | 1613.6841 | 1615.7965 | 1617.9117 | 1620.0297 | 1622.1505 | 1624.2741 | 1629.8832 | 1635.5117 | 1641.1596 | 1646.827 | 1652.5141 | 1684.1408 | 1716.3729 | 1749.2219 | 1782.6995 | 1816.8179 | 1831.7322 | 1846.7689 | 1861.929 | 1877.2136 | 1892.6237 | 1905.8515 | 1919.1717 | 1932.5851 | 1946.0922 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 | 1959.6937 |  | 4280 | 4307.2389 | 4334.6511 | 4362.2378 | 4390 | 4384.9492 | 4379.9041 | 4374.8649 | 4369.8315 | 4364.8038 | 4361.5722 | 4358.3429 | 4355.1159 | 4351.8914 | 4348.6693 | 4353.6925 | 4358.7216 | 4363.7564 | 4368.7971 | 4373.8436 | 4447.2931 | 4521.976 | 4597.913 | 4675.1252 | 4753.6341 | 4781.4859 | 4809.5009 | 4837.6801 | 4866.0243 | 4894.5346 | 4928.8093 | 4963.3239 | 4998.0803 | 5033.08 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | 5068.3248 | [6 empty] | 1331 | 1334 | 1337 | 1340 | 1343.5 | 1353 | 1363 | 1373 | 1383 | 1393 | 1403.4 | 1408 | 1412 | 1416 | 1420 | 1424 | 1428 | 1432 | 1436 | 1440 | 1444 | 1448 | 1452 | 1456 | 1460 | 1464 | 1468 | 1472 | 1476 | 1480 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | 1487.5 | [6 empty] | 2.7329 | 2.7328 | 2.7327 | 2.7326 | 2.7324 | 2.7269 | 2.7214 | 2.7159 | 2.7104 | 2.7049 | 2.6993 | 2.6938 | 2.6883 | 2.6828 | 2.6773 | 2.6712 | 2.6651 | 2.6589 | 2.6529 | 2.6468 | 2.6407 | 2.6346 | 2.6285 | 2.6225 | 2.6165 | 2.6104 | 2.6043 | 2.5982 | 2.5922 | 2.5861 | 2.5861 | 2.5862 | 2.5862 | 2.5862 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863 | 2.5863
576 | Franklin |  |  | 2052 | 1518.7324 | 1630.1712 | 1749.787 | 1878.1797 | 2015.9934 | 2015.9934 | 2015.9934 | 2015.9934 | 2015.9934 | 2015.9934 | 2015.9934 | 2015.9934 | 2015.9934 | 2015.9934 | 2015.9934 | 2039.4885 | 2063.2574 | 2087.3033 | 2111.6295 | 2136.2392 | 2170.1474 | 2204.5938 | 2239.5869 | 2275.1355 | 2311.2484 | 2327.1763 | 2343.214 | 2359.3623 | 2375.6218 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 | 2391.9934 |  | 4540 | 4865.7366 | 5214.8442 | 5588.9996 | 5990 | 5968.2214 | 5946.5219 | 5924.9014 | 5903.3594 | 5881.8958 | 5860.1143 | 5838.4134 | 5816.7928 | 5795.2524 | 5773.7917 | 5821.856 | 5870.3204 | 5919.1883 | 5968.463 | 6018.1478 | 6093.4942 | 6169.7839 | 6247.0288 | 6325.2407 | 6404.4318 | 6429.1471 | 6453.9577 | 6478.864 | 6503.8665 | 6528.9654 | 6528.5671 | 6528.1689 | 6527.7706 | 6527.3724 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | 6526.9742 | [6 empty] | 425 | 427 | 429 | 431 | 434.5 | 438 | 441 | 444 | 447 | 450 | 454.1 | 452 | 450 | 448 | 446 | 444 | 442 | 440 | 438 | 436 | 434 | 432 | 430 | 428 | 426 | 424 | 422 | 420 | 418 | 416 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | 420.6 | [6 empty] | 2.9893 | 2.9848 | 2.9803 | 2.9758 | 2.9712 | 2.9604 | 2.9497 | 2.9389 | 2.9283 | 2.9176 | 2.9068 | 2.896 | 2.8853 | 2.8746 | 2.864 | 2.8546 | 2.8452 | 2.8358 | 2.8265 | 2.8172 | 2.8079 | 2.7986 | 2.7894 | 2.7802 | 2.771 | 2.7626 | 2.7543 | 2.746 | 2.7378 | 2.7295 | 2.7293 | 2.7292 | 2.729 | 2.7288 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287 | 2.7287
577 | Franklin |  |  | 2052 | 358.9731 | 357.817 | 356.6645 | 355.5159 | 354.3709 | 366.7227 | 379.505 | 392.7329 | 406.4218 | 420.5879 | 433.298 | 446.3922 | 459.8821 | 473.7796 | 488.0971 | 499.8963 | 511.9807 | 524.3573 | 537.033 | 550.0151 | 560.6417 | 571.4735 | 582.5146 | 593.769 | 605.2409 | 619.4361 | 633.9643 | 648.8332 | 664.0509 | 679.6255 | 693.0349 | 706.7088 | 720.6526 | 734.8714 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 | 749.3709 |  | 780 | 777.4879 | 774.9839 | 772.4879 | 770 | 795.8242 | 822.5144 | 850.0998 | 878.6104 | 908.0771 | 934.6639 | 962.0292 | 990.1956 | 1019.1866 | 1049.0265 | 1072.7772 | 1097.0656 | 1121.904 | 1147.3047 | 1173.2804 | 1194.5161 | 1216.1362 | 1238.1476 | 1260.5573 | 1283.3727 | 1311.6879 | 1340.6278 | 1370.2062 | 1400.4371 | 1431.3351 | 1458.327 | 1485.8278 | 1513.8473 | 1542.3951 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | 1571.4813 | [6 empty] | 3534 | 3567 | 3600 | 3633 | 3664.7 | 3692 | 3719 | 3746 | 3773 | 3800 | 3826.6 | 3815 | 3804 | 3793 | 3782 | 3771 | 3760 | 3749 | 3738 | 3727 | 3716 | 3705 | 3694 | 3683 | 3672 | 3661 | 3650 | 3639 | 3628 | 3617 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | 3597.3 | [6 empty] | 2.1729 | 2.1729 | 2.1729 | 2.1729 | 2.1729 | 2.1701 | 2.1673 | 2.1646 | 2.1618 | 2.1591 | 2.1571 | 2.1551 | 2.1532 | 2.1512 | 2.1492 | 2.146 | 2.1428 | 2.1396 | 2.1364 | 2.1332 | 2.1306 | 2.1281 | 2.1255 | 2.123 | 2.1204 | 2.1176 | 2.1147 | 2.1118 | 2.1089 | 2.1061 | 2.1043 | 2.1025 | 2.1007 | 2.0989 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971 | 2.0971
578 | Franklin |  |  | 2052 | 1100.8077 | 1114.9807 | 1129.3361 | 1143.8764 | 1158.6038 | 1158.6038 | 1158.6038 | 1158.6038 | 1158.6038 | 1158.6038 | 1158.6038 | 1158.6038 | 1158.6038 | 1158.6038 | 1158.6038 | 1180.2261 | 1202.2519 | 1224.6887 | 1247.5443 | 1270.8264 | 1301.9323 | 1333.7996 | 1366.4469 | 1399.8933 | 1434.1583 | 1475.6216 | 1518.2836 | 1562.179 | 1607.3435 | 1653.8138 | 1693.064 | 1733.2457 | 1774.3811 | 1816.4927 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 | 1859.6038 |  | 3070 | 3109.2412 | 3148.984 | 3189.2347 | 3230 | 3217.2383 | 3204.5271 | 3191.8661 | 3179.2551 | 3166.6939 | 3153.9302 | 3141.218 | 3128.557 | 3115.947 | 3103.3879 | 3148.963 | 3195.2075 | 3242.1311 | 3289.7437 | 3338.0556 | 3406.2319 | 3475.8006 | 3546.7901 | 3619.2295 | 3693.1484 | 3783.4716 | 3876.0037 | 3970.799 | 4067.9126 | 4167.4013 | 4265.794 | 4366.5097 | 4469.6033 | 4575.1309 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | 4683.15 | [6 empty] | 839 | 845 | 851 | 857 | 864.3 | 872 | 879 | 886 | 893 | 900 | 908.4 | 906 | 903 | 900 | 897 | 894 | 891 | 888 | 885 | 882 | 879 | 876 | 873 | 870 | 867 | 864 | 861 | 858 | 855 | 852 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | 855.7 | [6 empty] | 2.7889 | 2.7886 | 2.7883 | 2.7881 | 2.7878 | 2.7768 | 2.7659 | 2.7549 | 2.744 | 2.7332 | 2.7222 | 2.7112 | 2.7003 | 2.6894 | 2.6786 | 2.6681 | 2.6577 | 2.6473 | 2.637 | 2.6267 | 2.6163 | 2.6059 | 2.5956 | 2.5854 | 2.5751 | 2.564 | 2.5529 | 2.5418 | 2.5308 | 2.5199 | 2.5196 | 2.5193 | 2.519 | 2.5187 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184 | 2.5184
579 | Franklin |  |  | 2052 | 230.4144 | 230.4144 | 230.4144 | 230.4144 | 230.4144 | 237.9633 | 245.7595 | 253.8111 | 262.1265 | 270.7144 | 278.4054 | 286.3149 | 294.4491 | 302.8144 | 311.4174 | 325.4152 | 340.0422 | 355.3266 | 371.2981 | 387.9874 | 403.6045 | 419.8503 | 436.75 | 454.3299 | 472.6174 | 486.8971 | 501.6082 | 516.7639 | 532.3774 | 548.4627 | 564.4314 | 580.865 | 597.777 | 615.1815 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 | 633.0927 |  | 690 | 690 | 690 | 690 | 690 | 707.9409 | 726.3484 | 745.2344 | 764.6115 | 784.4925 | 801.7565 | 819.4004 | 837.4326 | 855.8616 | 874.6962 | 909.8202 | 946.3547 | 984.3562 | 1023.8837 | 1064.9984 | 1103.0447 | 1142.4503 | 1183.2635 | 1225.5347 | 1269.3161 | 1302.1798 | 1335.8943 | 1370.4817 | 1405.9645 | 1442.3661 | 1484.0247 | 1526.8864 | 1570.9861 | 1616.3594 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | 1663.0432 | [6 empty] | 269 | 306 | 343 | 380 | 416.9 | 420 | 424 | 428 | 432 | 436 | 437.9 | 475 | 512 | 549 | 586 | 623 | 660 | 697 | 734 | 771 | 808 | 845 | 882 | 919 | 956 | 993 | 1030 | 1067 | 1104 | 1141 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | 1171.6 | [6 empty] | 2.9946 | 2.9946 | 2.9946 | 2.9946 | 2.9946 | 2.975 | 2.9555 | 2.9362 | 2.917 | 2.8979 | 2.8798 | 2.8619 | 2.8441 | 2.8264 | 2.8088 | 2.7959 | 2.7831 | 2.7703 | 2.7576 | 2.7449 | 2.733 | 2.7211 | 2.7092 | 2.6975 | 2.6857 | 2.6744 | 2.6632 | 2.652 | 2.6409 | 2.6298 | 2.6292 | 2.6286 | 2.628 | 2.6275 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269 | 2.6269
580 | Franklin |  |  | 2052 | 60.6353 | 59.8212 | 59.0181 | 58.2257 | 57.444 | 57.444 | 57.444 | 57.444 | 57.444 | 57.444 | 57.444 | 57.444 | 57.444 | 57.444 | 57.444 | 83.4852 | 121.3316 | 176.335 | 256.2731 | 372.4497 | 437.2861 | 513.4094 | 602.7843 | 707.7176 | 830.9179 | 869.4749 | 909.821 | 952.0393 | 996.2167 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 | 1042.444 |  | 190 | 187.4491 | 184.9324 | 182.4495 | 180 | 179.7411 | 179.4826 | 179.2244 | 178.9667 | 178.7093 | 178.4504 | 178.1918 | 177.9337 | 177.6759 | 177.4185 | 253.6675 | 362.6859 | 518.5569 | 741.4166 | 1060.0543 | 1238.4607 | 1446.8927 | 1690.4037 | 1974.8973 | 2307.2711 | 2403.4078 | 2503.5501 | 2607.8651 | 2716.5266 | 2829.7156 | 2829.7298 | 2829.7439 | 2829.7581 | 2829.7723 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | 2829.7864 | [6 empty] | 78 | 79 | 80 | 81 | 80.2 | 81 | 82 | 83 | 84 | 85 | 85.8 | 108 | 130 | 152 | 174 | 196 | 218 | 240 | 262 | 284 | 306 | 328 | 350 | 372 | 394 | 416 | 438 | 460 | 482 | 504 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | 520.2 | [6 empty] | 3.1335 | 3.1335 | 3.1335 | 3.1335 | 3.1335 | 3.129 | 3.1245 | 3.12 | 3.1155 | 3.111 | 3.1065 | 3.102 | 3.0975 | 3.093 | 3.0885 | 3.0385 | 2.9892 | 2.9407 | 2.8931 | 2.8462 | 2.8322 | 2.8182 | 2.8043 | 2.7905 | 2.7768 | 2.7642 | 2.7517 | 2.7392 | 2.7268 | 2.7145 | 2.7145 | 2.7145 | 2.7145 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146 | 2.7146
581 | Franklin |  |  | 2052 | 2693.8856 | 2710.4548 | 2727.1259 | 2743.8995 | 2760.7763 | 2766.2198 | 2771.6741 | 2777.139 | 2782.6148 | 2788.1014 | 2793.6509 | 2799.2114 | 2804.7831 | 2810.3658 | 2815.9596 | 2821.0513 | 2826.1523 | 2831.2625 | 2836.3819 | 2841.5106 | 2846.0539 | 2850.6045 | 2855.1623 | 2859.7275 | 2864.2999 | 2870.4129 | 2876.5388 | 2882.6779 | 2888.8301 | 2894.9953 | 2900.7288 | 2906.4736 | 2912.2298 | 2917.9973 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 | 2923.7763 |  | 6990 | 7032.1178 | 7074.4894 | 7117.1163 | 7160 | 7206.1874 | 7252.6728 | 7299.458 | 7346.5451 | 7393.9358 | 7441.0527 | 7488.4698 | 7536.189 | 7584.2123 | 7632.5417 | 7669.2714 | 7706.1778 | 7743.2618 | 7780.5242 | 7817.966 | 7853.1356 | 7888.4634 | 7923.9502 | 7959.5965 | 7995.4033 | 8035.7058 | 8076.2114 | 8116.9212 | 8157.8362 | 8198.9575 | 8214.3598 | 8229.791 | 8245.2512 | 8260.7405 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | 8276.2588 | [6 empty] | 3972 | 3959 | 3946 | 3933 | 3919.3 | 3948 | 3976 | 4004 | 4032 | 4060 | 4089 | 4084 | 4079 | 4074 | 4069 | 4064 | 4059 | 4054 | 4049 | 4044 | 4039 | 4034 | 4029 | 4024 | 4019 | 4014 | 4009 | 4004 | 3999 | 3994 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | 3986.1 | [6 empty] | 2.5948 | 2.5944 | 2.5941 | 2.5938 | 2.5935 | 2.6051 | 2.6167 | 2.6284 | 2.6402 | 2.652 | 2.6636 | 2.6752 | 2.6869 | 2.6987 | 2.7105 | 2.7186 | 2.7267 | 2.7349 | 2.7431 | 2.7513 | 2.7593 | 2.7673 | 2.7753 | 2.7833 | 2.7914 | 2.7995 | 2.8076 | 2.8158 | 2.8239 | 2.8321 | 2.8318 | 2.8315 | 2.8313 | 2.831 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307 | 2.8307
582 | Franklin |  |  | 2052 | 42.4447 | 44.7729 | 47.2288 | 49.8194 | 52.5521 | 53.2024 | 53.8608 | 54.5274 | 55.2022 | 55.8854 | 56.5367 | 57.1956 | 57.8622 | 58.5365 | 59.2187 | 59.8709 | 60.5302 | 61.1968 | 61.8707 | 62.5521 | 63.205 | 63.8647 | 64.5313 | 65.2048 | 65.8854 | 66.539 | 67.199 | 67.8656 | 68.5388 | 69.2187 | 69.8729 | 70.5333 | 71.1999 | 71.8728 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 | 72.5521 |  | 130 | 136.9265 | 144.2221 | 151.9063 | 160 | 161.1599 | 162.3282 | 163.505 | 164.6903 | 165.8842 | 166.9456 | 168.0138 | 169.0889 | 170.1708 | 171.2596 | 172.4109 | 173.5699 | 174.7367 | 175.9114 | 177.094 | 178.1803 | 179.2734 | 180.3731 | 181.4796 | 182.5929 | 183.5778 | 184.5679 | 185.5634 | 186.5642 | 187.5705 | 189.3432 | 191.1326 | 192.939 | 194.7625 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | 196.6032 | [6 empty] | 31 | 31 | 31 | 31 | 31.3 | 32 | 32 | 32 | 32 | 32 | 33.9 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | 30.9 | [6 empty] | 3.0628 | 3.0582 | 3.0537 | 3.0491 | 3.0446 | 3.0292 | 3.0138 | 2.9986 | 2.9834 | 2.9683 | 2.9529 | 2.9375 | 2.9223 | 2.9071 | 2.892 | 2.8797 | 2.8675 | 2.8553 | 2.8432 | 2.8311 | 2.8191 | 2.8071 | 2.7951 | 2.7832 | 2.7714 | 2.759 | 2.7466 | 2.7343 | 2.722 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098 | 2.7098
583 | Franklin |  |  | 2052 | 51.54 | 50.8088 | 50.0879 | 49.3773 | 48.6767 | 48.6767 | 48.6767 | 48.6767 | 48.6767 | 48.6767 | 48.6767 | 48.6767 | 48.6767 | 48.6767 | 48.6767 | 72.6755 | 108.5064 | 162.0027 | 241.874 | 361.124 | 425.0589 | 500.3131 | 588.8906 | 693.1503 | 815.8686 | 854.0795 | 894.0799 | 935.9537 | 979.7887 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 | 1025.6767 |  | 180 | 177.4462 | 174.9286 | 172.4467 | 170 | 169.3426 | 168.6877 | 168.0354 | 167.3856 | 166.7383 | 166.0808 | 165.4259 | 164.7736 | 164.1238 | 163.4766 | 235.5855 | 339.5012 | 489.2536 | 705.0612 | 1016.0606 | 1187.1592 | 1387.0697 | 1620.6441 | 1893.5509 | 2212.4137 | 2304.3008 | 2400.0043 | 2499.6825 | 2603.5007 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | 2711.6307 | [6 empty] | 377 | 378 | 379 | 380 | 381.9 | 385 | 388 | 391 | 394 | 397 | 397.9 | 405 | 412 | 419 | 426 | 433 | 440 | 447 | 454 | 461 | 468 | 475 | 482 | 489 | 496 | 503 | 510 | 517 | 524 | 531 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | [6 empty] | 3.4924 | 3.4924 | 3.4924 | 3.4924 | 3.4924 | 3.4789 | 3.4655 | 3.4521 | 3.4387 | 3.4254 | 3.4119 | 3.3985 | 3.3851 | 3.3717 | 3.3584 | 3.2416 | 3.1289 | 3.02 | 2.915 | 2.8136 | 2.7929 | 2.7724 | 2.752 | 2.7318 | 2.7117 | 2.698 | 2.6843 | 2.6707 | 2.6572 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437 | 2.6437
584 | Franklin |  |  | 2052 | 709.7467 | 719.7984 | 729.9926 | 740.331 | 750.8159 | 750.8159 | 750.8159 | 750.8159 | 750.8159 | 750.8159 | 750.8159 | 750.8159 | 750.8159 | 750.8159 | 750.8159 | 753.8613 | 756.9189 | 759.989 | 763.0715 | 766.1665 | 770.5836 | 775.0261 | 779.4943 | 783.9882 | 788.5081 | 790.559 | 792.6152 | 794.6767 | 796.7436 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 | 798.8159 |  | 2060 | 2089.3661 | 2119.1508 | 2149.3601 | 2180 | 2172.4612 | 2164.9486 | 2157.4618 | 2150.001 | 2142.566 | 2135.0263 | 2127.5132 | 2120.0265 | 2112.5661 | 2105.132 | 2107.1209 | 2109.1117 | 2111.1044 | 2113.0989 | 2115.0954 | 2120.7508 | 2126.4213 | 2132.107 | 2137.8079 | 2143.524 | 2142.0957 | 2140.6684 | 2139.242 | 2137.8165 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | 2136.392 | [6 empty] | 489 | 489 | 489 | 489 | 488.6 | 492 | 496 | 500 | 504 | 508 | 511 | 512 | 513 | 514 | 515 | 516 | 517 | 518 | 519 | 520 | 521 | 522 | 523 | 524 | 525 | 526 | 527 | 528 | 529 | 530 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | 540.7 | [6 empty] | 2.9024 | 2.9027 | 2.903 | 2.9032 | 2.9035 | 2.8935 | 2.8835 | 2.8735 | 2.8636 | 2.8537 | 2.8436 | 2.8336 | 2.8236 | 2.8137 | 2.8038 | 2.7951 | 2.7864 | 2.7778 | 2.7692 | 2.7606 | 2.7521 | 2.7437 | 2.7352 | 2.7268 | 2.7185 | 2.7096 | 2.7008 | 2.692 | 2.6832 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744 | 2.6744
585 | Franklin |  |  | 2052 | 312.6602 | 316.2784 | 319.9385 | 323.6409 | 327.3861 | 333.7049 | 340.1456 | 346.7106 | 353.4023 | 360.2231 | 366.6828 | 373.2583 | 379.9518 | 386.7652 | 393.7009 | 399.6629 | 405.7152 | 411.8592 | 418.0962 | 424.4276 | 429.7748 | 435.1893 | 440.672 | 446.2238 | 451.8456 | 458.9226 | 466.1105 | 473.4109 | 480.8257 | 488.3567 | 494.9804 | 501.694 | 508.4987 | 515.3956 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 | 522.3861 |  | 860 | 869.8302 | 879.7727 | 889.8289 | 900 | 914.794 | 929.8311 | 945.1154 | 960.651 | 976.4419 | 991.1533 | 1006.0863 | 1021.2443 | 1036.6307 | 1052.2488 | 1065.2908 | 1078.4944 | 1091.8616 | 1105.3946 | 1119.0952 | 1130.1725 | 1141.3595 | 1152.6571 | 1164.0666 | 1175.5891 | 1190.6603 | 1205.9247 | 1221.3848 | 1237.0431 | 1252.9021 | 1269.7547 | 1286.834 | 1304.1431 | 1321.6849 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | 1339.4628 | [6 empty] | 392 | 394 | 396 | 398 | 398.8 | 401 | 403 | 405 | 407 | 409 | 412.8 | 411 | 410 | 409 | 408 | 407 | 406 | 405 | 404 | 403 | 402 | 401 | 400 | 399 | 398 | 397 | 396 | 395 | 394 | 393 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | 385.9 | [6 empty] | 2.7506 | 2.7502 | 2.7498 | 2.7494 | 2.749 | 2.7413 | 2.7336 | 2.7259 | 2.7183 | 2.7107 | 2.703 | 2.6954 | 2.6878 | 2.6803 | 2.6727 | 2.6655 | 2.6583 | 2.6511 | 2.6439 | 2.6367 | 2.6297 | 2.6227 | 2.6157 | 2.6087 | 2.6017 | 2.5945 | 2.5872 | 2.58 | 2.5727 | 2.5655 | 2.5653 | 2.565 | 2.5647 | 2.5644 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641 | 2.5641
586 | Franklin |  |  | 2052 | 106.1119 | 108.5754 | 111.096 | 113.6751 | 116.3141 | 116.4139 | 116.5138 | 116.6138 | 116.7139 | 116.8141 | 116.9139 | 117.0138 | 117.1138 | 117.2139 | 117.3141 | 117.4139 | 117.5138 | 117.6138 | 117.7139 | 117.8141 | 117.9139 | 118.0138 | 118.1138 | 118.2139 | 118.3141 | 118.4139 | 118.5138 | 118.6138 | 118.7139 | 118.8141 | 118.9139 | 119.0138 | 119.1138 | 119.2139 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 | 119.3141 |  | 350 | 357.2703 | 364.6917 | 372.2671 | 380 | 378.6212 | 377.2475 | 375.8787 | 374.5149 | 373.156 | 371.7623 | 370.3738 | 368.9905 | 367.6124 | 366.2394 | 365.1703 | 364.1044 | 363.0415 | 361.9818 | 360.9251 | 359.8686 | 358.8152 | 357.7649 | 356.7177 | 355.6735 | 354.5643 | 353.4586 | 352.3563 | 351.2575 | 350.1621 | 350.4563 | 350.7508 | 351.0455 | 351.3405 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | 351.6357 | [6 empty] | 347 | 348 | 349 | 350 | 350.8 | 353 | 355 | 357 | 359 | 361 | 365 | 364 | 363 | 362 | 361 | 360 | 359 | 358 | 357 | 356 | 355 | 354 | 353 | 352 | 351 | 350 | 349 | 348 | 347 | 346 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | [6 empty] | 3.2984 | 3.2905 | 3.2827 | 3.2748 | 3.267 | 3.2524 | 3.2378 | 3.2233 | 3.2088 | 3.1944 | 3.1798 | 3.1652 | 3.1507 | 3.1363 | 3.1219 | 3.1101 | 3.0984 | 3.0867 | 3.0751 | 3.0635 | 3.052 | 3.0405 | 3.029 | 3.0176 | 3.0062 | 2.9943 | 2.9824 | 2.9706 | 2.9589 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471 | 2.9471
587 | Franklin |  |  | 2052 | 180.5569 | 183.0113 | 185.4991 | 188.0207 | 190.5765 | 204.3186 | 219.0515 | 234.8468 | 251.781 | 269.9364 | 284.4672 | 299.7802 | 315.9175 | 332.9235 | 350.8449 | 376.7228 | 404.5093 | 434.3453 | 466.3821 | 500.7817 | 531.9374 | 565.0314 | 600.1844 | 637.5243 | 677.1873 | 719.1698 | 763.7551 | 811.1044 | 861.3892 | 914.7914 | 955.5508 | 998.1263 | 1042.5987 | 1089.0527 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 | 1137.5765 |  | 600 | 607.3633 | 614.817 | 622.3622 | 630 | 670.9587 | 714.5802 | 761.0378 | 810.5157 | 863.2104 | 905.8303 | 950.5546 | 997.4871 | 1046.7368 | 1098.4181 | 1169.7611 | 1245.7379 | 1326.6494 | 1412.8162 | 1504.5795 | 1585.847 | 1671.5041 | 1761.7877 | 1856.9479 | 1957.2481 | 2062.4268 | 2173.2577 | 2290.0444 | 2413.1071 | 2542.7828 | 2653.6627 | 2769.3776 | 2890.1383 | 3016.1649 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | 3147.6869 | [6 empty] | 199 | 201 | 203 | 205 | 207.8 | 218 | 228 | 238 | 248 | 258 | 268.9 | 289 | 309 | 329 | 349 | 369 | 389 | 409 | 429 | 449 | 469 | 489 | 509 | 529 | 549 | 569 | 589 | 609 | 629 | 649 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | 661.5 | [6 empty] | 3.3231 | 3.3187 | 3.3144 | 3.3101 | 3.3058 | 3.2839 | 3.2622 | 3.2406 | 3.2191 | 3.1978 | 3.1843 | 3.1708 | 3.1574 | 3.1441 | 3.1308 | 3.1051 | 3.0796 | 3.0544 | 3.0293 | 3.0045 | 2.9813 | 2.9582 | 2.9354 | 2.9127 | 2.8903 | 2.8678 | 2.8455 | 2.8234 | 2.8014 | 2.7796 | 2.7771 | 2.7746 | 2.7721 | 2.7695 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767 | 2.767
588 | Franklin |  |  | 2052 | 306.2084 | 309.6558 | 313.142 | 316.6674 | 320.2326 | 320.9139 | 321.5967 | 322.281 | 322.9667 | 323.6539 | 324.3486 | 325.0447 | 325.7423 | 326.4414 | 327.142 | 327.7758 | 328.4108 | 329.047 | 329.6845 | 330.3232 | 330.8867 | 331.4512 | 332.0166 | 332.583 | 333.1504 | 333.8843 | 334.6199 | 335.357 | 336.0958 | 336.8362 | 337.5128 | 338.1907 | 338.8699 | 339.5506 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 | 340.2326 |  | 910 | 919.8393 | 929.7849 | 939.8381 | 950 | 946.8631 | 943.7367 | 940.6205 | 937.5146 | 934.419 | 931.2657 | 928.123 | 924.9909 | 921.8694 | 918.7585 | 916.3257 | 913.8993 | 911.4794 | 909.0659 | 906.6588 | 904.0949 | 901.5383 | 898.9889 | 896.4468 | 893.9118 | 891.5654 | 889.2251 | 886.891 | 884.5631 | 882.2412 | 883.725 | 885.2113 | 886.7001 | 888.1914 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | 889.6853 | [6 empty] | 264 | 265 | 266 | 267 | 267.2 | 269 | 271 | 273 | 275 | 277 | 276.6 | 276 | 275 | 274 | 273 | 272 | 271 | 270 | 269 | 268 | 267 | 266 | 265 | 264 | 263 | 262 | 261 | 260 | 259 | 258 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | 257.8 | [6 empty] | 2.9718 | 2.9705 | 2.9692 | 2.9679 | 2.9666 | 2.9505 | 2.9345 | 2.9186 | 2.9028 | 2.8871 | 2.8712 | 2.8554 | 2.8396 | 2.824 | 2.8084 | 2.7956 | 2.7828 | 2.7701 | 2.7574 | 2.7448 | 2.7323 | 2.72 | 2.7077 | 2.6954 | 2.6832 | 2.6703 | 2.6574 | 2.6446 | 2.6319 | 2.6192 | 2.6183 | 2.6175 | 2.6166 | 2.6158 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149 | 2.6149
589 | Franklin |  |  | 2052 | 820.9984 | 834.8489 | 848.9329 | 863.2546 | 877.8179 | 881.9773 | 886.1563 | 890.3552 | 894.5739 | 898.8126 | 903.0533 | 907.314 | 911.5947 | 915.8957 | 920.217 | 923.3784 | 926.5506 | 929.7337 | 932.9278 | 936.1328 | 938.5407 | 940.9548 | 943.3752 | 945.8017 | 948.2345 | 951.3096 | 954.3947 | 957.4898 | 960.595 | 963.7102 | 966.5153 | 969.3287 | 972.1502 | 974.98 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 | 977.8179 |  | 2160 | 2196.5612 | 2233.7413 | 2271.5506 | 2310 | 2309.791 | 2309.582 | 2309.373 | 2309.164 | 2308.955 | 2308.4251 | 2307.8953 | 2307.3656 | 2306.8361 | 2306.3067 | 2304.7746 | 2303.2436 | 2301.7136 | 2300.1846 | 2298.6566 | 2295.1237 | 2291.5962 | 2288.0742 | 2284.5576 | 2281.0463 | 2278.5834 | 2276.1232 | 2273.6656 | 2271.2107 | 2268.7584 | 2275.3741 | 2282.0091 | 2288.6635 | 2295.3372 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | 2302.0304 | [6 empty] | 324 | 325 | 326 | 327 | 327.6 | 331 | 334 | 337 | 340 | 343 | 348.3 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | 348.9 | [6 empty] | 2.6309 | 2.6311 | 2.6312 | 2.6314 | 2.6315 | 2.6189 | 2.6063 | 2.5938 | 2.5813 | 2.5689 | 2.5562 | 2.5437 | 2.5311 | 2.5187 | 2.5063 | 2.496 | 2.4858 | 2.4757 | 2.4656 | 2.4555 | 2.4454 | 2.4354 | 2.4254 | 2.4155 | 2.4056 | 2.3952 | 2.3849 | 2.3746 | 2.3644 | 2.3542 | 2.3542 | 2.3542 | 2.3542 | 2.3542 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543 | 2.3543
590 | Franklin |  |  | 2052 | 1335.1285 | 1378.2996 | 1422.8666 | 1468.8747 | 1516.3704 | 1544.7018 | 1573.5626 | 1602.9625 | 1632.9118 | 1663.4206 | 1692.3786 | 1721.8407 | 1751.8157 | 1782.3125 | 1813.3403 | 1834.7151 | 1856.342 | 1878.2237 | 1900.3634 | 1922.764 | 1938.8475 | 1955.0655 | 1971.4191 | 1987.9095 | 2004.5379 | 2026.0516 | 2047.7961 | 2069.7741 | 2091.9879 | 2114.4401 | 2134.6367 | 2155.0261 | 2175.6103 | 2196.3911 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 | 2217.3704 |  | 3930 | 4056.2819 | 4186.6215 | 4321.1494 | 4460 | 4520.0885 | 4580.9866 | 4642.7052 | 4705.2552 | 4768.648 | 4826.3923 | 4884.8358 | 4943.987 | 5003.8544 | 5064.4468 | 5101.7063 | 5139.2399 | 5177.0497 | 5215.1376 | 5253.5058 | 5274.2974 | 5295.1713 | 5316.1279 | 5337.1674 | 5358.2901 | 5390.8331 | 5423.5737 | 5456.5132 | 5489.6528 | 5522.9936 | 5575.4671 | 5628.4392 | 5681.9146 | 5735.898 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | 5790.3943 | [6 empty] | 1884 | 1883 | 1882 | 1881 | 1881.9 | 1896 | 1910 | 1924 | 1938 | 1952 | 1968.5 | 1964 | 1960 | 1956 | 1952 | 1948 | 1944 | 1940 | 1936 | 1932 | 1928 | 1924 | 1920 | 1916 | 1912 | 1908 | 1904 | 1900 | 1896 | 1892 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | 1879.7 | [6 empty] | 2.9435 | 2.943 | 2.9424 | 2.9418 | 2.9412 | 2.9262 | 2.9112 | 2.8963 | 2.8815 | 2.8668 | 2.8518 | 2.837 | 2.8222 | 2.8075 | 2.7929 | 2.7807 | 2.7685 | 2.7564 | 2.7443 | 2.7323 | 2.7203 | 2.7084 | 2.6966 | 2.6848 | 2.6731 | 2.6608 | 2.6485 | 2.6363 | 2.6241 | 2.612 | 2.6119 | 2.6118 | 2.6116 | 2.6115 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114 | 2.6114
591 | Franklin |  |  | 2052 | 3844.9093 | 3868.7134 | 3892.6648 | 3916.7645 | 3941.0134 | 3960.4713 | 3980.0253 | 3999.6759 | 4019.4234 | 4039.2685 | 4059.1071 | 4079.0432 | 4099.0773 | 4119.2097 | 4139.441 | 4157.5887 | 4175.816 | 4194.1233 | 4212.5108 | 4230.9789 | 4247.1456 | 4263.3741 | 4279.6646 | 4296.0174 | 4312.4326 | 4334.155 | 4355.9868 | 4377.9286 | 4399.9809 | 4422.1443 | 4442.5293 | 4463.0083 | 4483.5817 | 4504.2499 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 | 4525.0134 |  | 9950 | 10011.9196 | 10074.2245 | 10136.9172 | 10200 | 10204.5859 | 10209.1739 | 10213.7639 | 10218.356 | 10222.9502 | 10226.2279 | 10229.5066 | 10232.7864 | 10236.0673 | 10239.3492 | 10244.5301 | 10249.7136 | 10254.8998 | 10260.0886 | 10265.28 | 10264.6197 | 10263.9594 | 10263.2991 | 10262.6389 | 10261.9787 | 10271.7953 | 10281.6212 | 10291.4566 | 10301.3013 | 10311.1555 | 10358.9246 | 10406.9151 | 10455.1279 | 10503.5641 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | 10552.2246 | [6 empty] | 3833 | 3844 | 3855 | 3866 | 3877.9 | 3906 | 3934 | 3962 | 3990 | 4018 | 4046.2 | 4024 | 4001 | 3978 | 3955 | 3932 | 3909 | 3886 | 3863 | 3840 | 3817 | 3794 | 3771 | 3748 | 3725 | 3702 | 3679 | 3656 | 3633 | 3610 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | 3592.2 | [6 empty] | 2.5878 | 2.5879 | 2.588 | 2.5881 | 2.5882 | 2.5766 | 2.5651 | 2.5536 | 2.5422 | 2.5309 | 2.5193 | 2.5078 | 2.4964 | 2.485 | 2.4736 | 2.4641 | 2.4545 | 2.4451 | 2.4356 | 2.4262 | 2.4168 | 2.4075 | 2.3982 | 2.3889 | 2.3796 | 2.37 | 2.3603 | 2.3508 | 2.3412 | 2.3317 | 2.3318 | 2.3318 | 2.3319 | 2.3319 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332 | 2.332
592 | Franklin |  |  | 2052 | 1176.3321 | 1193.9413 | 1211.814 | 1229.9543 | 1248.3662 | 1249.0321 | 1249.6985 | 1250.3651 | 1251.0321 | 1251.6995 | 1252.3655 | 1253.0318 | 1253.6985 | 1254.3655 | 1255.0329 | 1255.6988 | 1256.3651 | 1257.0318 | 1257.6988 | 1258.3662 | 1259.0321 | 1259.6985 | 1260.3651 | 1261.0321 | 1261.6995 | 1262.3655 | 1263.0318 | 1263.6985 | 1264.3655 | 1265.0329 | 1265.6988 | 1266.3651 | 1267.0318 | 1267.6988 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 | 1268.3662 |  | 2990 | 3034.0184 | 3078.6848 | 3124.0088 | 3170 | 3155.5658 | 3141.1973 | 3126.8942 | 3112.6562 | 3098.4831 | 3083.959 | 3069.503 | 3055.1147 | 3040.7939 | 3026.5402 | 3015.2279 | 3003.9578 | 2992.7299 | 2981.5439 | 2970.3998 | 2959.2458 | 2948.1338 | 2937.0634 | 2926.0347 | 2915.0473 | 2903.4412 | 2891.8812 | 2880.3673 | 2868.8992 | 2857.4768 | 2858.9811 | 2860.4862 | 2861.9921 | 2863.4987 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | 2865.0062 | [6 empty] | 535 | 535 | 535 | 535 | 533.2 | 537 | 541 | 545 | 549 | 553 | 554.2 | 553 | 551 | 549 | 547 | 545 | 543 | 541 | 539 | 537 | 535 | 533 | 531 | 529 | 527 | 525 | 523 | 521 | 519 | 517 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | 523.9 | [6 empty] | 2.5418 | 2.5412 | 2.5406 | 2.5399 | 2.5393 | 2.5264 | 2.5136 | 2.5008 | 2.4881 | 2.4754 | 2.4625 | 2.4497 | 2.4369 | 2.4242 | 2.4115 | 2.4012 | 2.391 | 2.3808 | 2.3706 | 2.3605 | 2.3504 | 2.3403 | 2.3303 | 2.3203 | 2.3104 | 2.3 | 2.2896 | 2.2793 | 2.269 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588 | 2.2588
593 | Franklin |  |  | 2052 | 1892.6915 | 1924.0178 | 1955.8626 | 1988.2345 | 2021.1422 | 2021.8084 | 2022.4748 | 2023.1415 | 2023.8084 | 2024.4755 | 2025.1417 | 2025.8082 | 2026.4748 | 2027.1417 | 2027.8088 | 2028.4751 | 2029.1415 | 2029.8082 | 2030.4751 | 2031.1422 | 2031.8084 | 2032.4748 | 2033.1415 | 2033.8084 | 2034.4755 | 2035.1417 | 2035.8082 | 2036.4748 | 2037.1417 | 2037.8088 | 2038.4751 | 2039.1415 | 2039.8082 | 2040.4751 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 | 2041.1422 |  | 5530 | 5620.2658 | 5712.0049 | 5805.2415 | 5900 | 5871.4982 | 5843.1341 | 5814.9071 | 5786.8164 | 5758.8614 | 5730.2514 | 5701.7836 | 5673.4572 | 5645.2715 | 5617.2259 | 5594.7887 | 5572.4411 | 5550.1827 | 5528.0133 | 5505.9324 | 5483.8412 | 5461.8387 | 5439.9245 | 5418.0982 | 5396.3595 | 5373.4675 | 5350.6727 | 5327.9746 | 5305.3728 | 5282.8669 | 5284.594 | 5286.3217 | 5288.05 | 5289.7789 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | 5291.5083 | [6 empty] | 1784 | 1777 | 1770 | 1763 | 1754.9 | 1766 | 1778 | 1790 | 1802 | 1814 | 1824 | 1815 | 1806 | 1797 | 1788 | 1779 | 1770 | 1761 | 1752 | 1743 | 1734 | 1725 | 1716 | 1707 | 1698 | 1689 | 1680 | 1671 | 1662 | 1653 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | 1647.5 | [6 empty] | 2.9218 | 2.9211 | 2.9205 | 2.9198 | 2.9191 | 2.9041 | 2.8891 | 2.8742 | 2.8594 | 2.8446 | 2.8296 | 2.8146 | 2.7997 | 2.7848 | 2.7701 | 2.7581 | 2.7462 | 2.7343 | 2.7225 | 2.7108 | 2.699 | 2.6873 | 2.6756 | 2.664 | 2.6525 | 2.6403 | 2.6283 | 2.6163 | 2.6043 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924 | 2.5924
594 | Tuakau-Pokeno |  |  | 2052 | 1160.2997 | 1310.0368 | 1479.0977 | 1669.9759 | 1885.487 | 1975.425 | 2069.6531 | 2168.3759 | 2271.8077 | 2380.1733 | 2437.914 | 2497.0553 | 2557.6314 | 2619.677 | 2683.2278 | 2733.967 | 2785.6657 | 2838.342 | 2892.0144 | 2946.7017 | 2994.9677 | 3044.0242 | 3093.8843 | 3144.5611 | 3196.0679 | 3229.5646 | 3263.4124 | 3297.6149 | 3332.1759 | 3367.0991 | 3365.1551 | 3363.2122 | 3361.2704 | 3359.3297 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 | 3357.3902 |  | 3360 | 3793.6095 | 4283.1764 | 4835.9222 | 5460 | 5702.5666 | 5955.9095 | 6220.5075 | 6496.8605 | 6785.4908 | 6940.7415 | 7099.5443 | 7261.9805 | 7428.1331 | 7598.0874 | 7730.2808 | 7864.7741 | 8001.6074 | 8140.8214 | 8282.4574 | 8408.3192 | 8536.0936 | 8665.8097 | 8797.497 | 8931.1854 | 9001.5392 | 9072.4471 | 9143.9136 | 9215.9431 | 9288.5399 | 9282.8606 | 9277.1846 | 9271.5122 | 9265.8432 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | 9260.1777 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2.8958 | 2.8958 | 2.8958 | 2.8958 | 2.8958 | 2.8868 | 2.8777 | 2.8687 | 2.8598 | 2.8508 | 2.847 | 2.8432 | 2.8393 | 2.8355 | 2.8317 | 2.8275 | 2.8233 | 2.8191 | 2.8149 | 2.8108 | 2.8075 | 2.8042 | 2.8009 | 2.7977 | 2.7944 | 2.7872 | 2.78 | 2.7729 | 2.7657 | 2.7586 | 2.7585 | 2.7584 | 2.7583 | 2.7582 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581 | 2.7581
595 | Tuakau-Pokeno |  |  | 2052 | 2253.5593 | 2316.8573 | 2381.9333 | 2448.8371 | 2517.6201 | 2583.5337 | 2651.1731 | 2720.5833 | 2791.8108 | 2864.903 | 2934.5037 | 3005.7952 | 3078.8187 | 3153.6163 | 3230.231 | 3297.2996 | 3365.7607 | 3435.6432 | 3506.9768 | 3579.7913 | 3648.357 | 3718.2359 | 3789.4532 | 3862.0346 | 3936.0061 | 3983.4767 | 4031.5198 | 4080.1424 | 4129.3513 | 4179.1538 | 4176.4511 | 4173.7502 | 4171.051 | 4168.3536 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 | 4165.6579 |  | 6230 | 6404.9884 | 6584.8918 | 6769.8484 | 6960 | 7086.156 | 7214.5987 | 7345.3695 | 7478.5107 | 7614.0651 | 7748.4072 | 7885.1195 | 8024.244 | 8165.8232 | 8309.9004 | 8450.0442 | 8592.5516 | 8737.4623 | 8884.8168 | 9034.6565 | 9177.9521 | 9323.5204 | 9471.3975 | 9621.6201 | 9774.2253 | 9852.817 | 9932.0407 | 10011.9013 | 10092.4041 | 10173.5542 | 10167.1777 | 10160.8052 | 10154.4367 | 10148.0722 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | 10141.7116 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2.7645 | 2.7645 | 2.7645 | 2.7645 | 2.7645 | 2.7428 | 2.7213 | 2.6999 | 2.6787 | 2.6577 | 2.6404 | 2.6233 | 2.6063 | 2.5894 | 2.5725 | 2.5627 | 2.5529 | 2.5432 | 2.5335 | 2.5238 | 2.5156 | 2.5075 | 2.4994 | 2.4913 | 2.4833 | 2.4734 | 2.4636 | 2.4538 | 2.4441 | 2.4344 | 2.4344 | 2.4345 | 2.4345 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346 | 2.4346
596 | Waiheke - Great Barrier |  |  | 2052 | 4971.3872 | 4983.3696 | 4995.3809 | 5007.4211 | 5019.4903 | 5030.0273 | 5040.5864 | 5051.1677 | 5061.7712 | 5072.3969 | 5083.1391 | 5093.9041 | 5104.6918 | 5115.5024 | 5126.3359 | 5136.205 | 5146.093 | 5156.0001 | 5165.9263 | 5175.8716 | 5184.6851 | 5193.5136 | 5202.3571 | 5211.2157 | 5220.0893 | 5231.9469 | 5243.8314 | 5255.7429 | 5267.6814 | 5279.6471 | 5290.7688 | 5301.9139 | 5313.0825 | 5324.2746 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 | 5335.4903 |  | 10400 | 10424.9104 | 10449.8804 | 10474.9102 | 10500 | 10552.633 | 10605.5299 | 10658.692 | 10712.1205 | 10765.8168 | 10819.5336 | 10873.5183 | 10927.7724 | 10982.2972 | 11037.0941 | 11071.8946 | 11106.8049 | 11141.8253 | 11176.956 | 11212.1976 | 11244.9856 | 11277.8695 | 11310.8496 | 11343.9261 | 11377.0994 | 11416.7281 | 11456.4948 | 11496.4001 | 11536.4443 | 11576.6281 | 11600.8778 | 11625.1784 | 11649.5299 | 11673.9323 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | 11698.3859 | [6 empty] | 4268 | 4285 | 4302 | 4319 | 4337.9 | 4383 | 4428 | 4473 | 4518 | 4563 | 4606.4 | 4634 | 4662 | 4690 | 4718 | 4746 | 4774 | 4802 | 4830 | 4858 | 4886 | 4914 | 4942 | 4970 | 4998 | 5026 | 5054 | 5082 | 5110 | 5138 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | 5160.2 | [6 empty] | 2.092 | 2.0919 | 2.0919 | 2.0919 | 2.0918 | 2.0979 | 2.104 | 2.1101 | 2.1163 | 2.1224 | 2.1285 | 2.1346 | 2.1407 | 2.1469 | 2.153 | 2.1557 | 2.1583 | 2.1609 | 2.1636 | 2.1662 | 2.1689 | 2.1715 | 2.1742 | 2.1768 | 2.1795 | 2.1821 | 2.1848 | 2.1874 | 2.19 | 2.1927 | 2.1927 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926 | 2.1926
TOTAL |  |  |  |  | 563560.8877 | 566096.8715 | 569171.0837 | 572944.4165 | 577683.5956 | 584188.1237 | 591192.9069 | 598907.4154 | 607716.8541 | 618370.1849 | 625878.3456 | 633765.467 | 642075.1999 | 650859.7868 | 660182.6489 | 667862.5807 | 676006.6624 | 684729.1047 | 694199.2923 | 704679.0077 | 712384.1911 | 720474.8823 | 728991.953 | 737981.9881 | 747498.1969 | 755327.102 | 763395.7021 | 771732.643 | 780379.0915 | 789396.692 | 795628.3508 | 802009.3949 | 808548.5268 | 815255.4541 | 822141.0448 | 823582.0191 | 825157.741 | 826863.6371 | 828696.271 | 830653.2257 | 832733.0064 | 834934.961 | 837259.2144 | 838238.0445 | 839216.8747 | 840195.7048 | 841174.535 | 842153.3651 | 842904.7641 | 843656.163 | 844407.562 | 845158.9609 | 845910.3598 | 846661.7588 | 847413.1577 | 848164.5567 | 848915.9556 | 849667.3546 | 850418.7535 | 851170.1525 | 851921.5514 | 852672.9503 | 853424.3493 |  | 1664140 | 1672184.7679 | 1681820.477 | 1693538.3113 | 1708160.6197 | 1724818.4735 | 1742946.9954 | 1762958.5265 | 1785858.4239 | 1813198.2915 | 1832621.792 | 1853125.0481 | 1874835.524 | 1897906.8733 | 1922527.3789 | 1940810.926 | 1960309.9571 | 1981313.2343 | 2004246.6103 | 2029765.9377 | 2047831.1782 | 2066915.0287 | 2087121.9826 | 2108570.777 | 2131396.6466 | 2148934.1524 | 2167089.0159 | 2185930.3056 | 2205553.8049 | 2226097.2891 | 2242630.108 | 2259552.0222 | 2276885.267 | 2294654.5437 | 2312887.3854 | 2316397.4258 | 2320362.1371 | 2324735.384 | 2329506.8918 | 2334669.5442 | 2340219.0731 | 2346153.8038 | 2268933.086 | 2271120.3992 | 2273307.7125 | 2275495.0257 | 2277682.3389 | 2279869.6522 | 2281632.9911 | 2283396.3301 | 2285159.669 | 2286923.008 | 2288686.347 | 2290449.6859 | 2292213.0249 | 2293976.3638 | 2295739.7028 | 2297503.0417 | 2299266.3807 | 2301029.7197 | 2302793.0586 | 2304556.3976 | 2306319.7365 | [6 empty] | 934212 | 948538 | 962864 | 977190 | 991496.8 | 1002321 | 1013152 | 1023983 | 1034814 | 1045645 | 1056383.7 | 1068027 | 1079693 | 1091359 | 1103025 | 1114691 | 1126357 | 1138023 | 1149689 | 1161355 | 1173021 | 1184687 | 1196353 | 1208019 | 1219685 | 1231351 | 1243017 | 1254683 | 1266349 | 1278015 | 1289232.7 | 1290517.5371 | 1292111.7355 | 1293999.4297 | 1296169.4211 | 1298614.9223 | 1301333.3075 | 1286623.9804 | 1289896.1112 | 1290444.4925 | 1290992.8738 | 1291541.2551 | 1292089.6364 | 1292638.0177 | 1292948.2606 | 1293258.5035 | 1293568.7463 | 1293878.9892 | 1294189.232 | 1294499.4749 | 1294809.7177 | 1295119.9606 | 1295430.2035 | 1295740.4463 | 1296050.6892 | 1296360.932 | 1296671.1749 | 1296981.4177 | 1297291.6606 | [6 empty] | 2.9529 | 2.9539 | 2.9549 | 2.9559 | 2.9569 | 2.9525 | 2.9482 | 2.9436 | 2.9386 | 2.9322 | 2.9281 | 2.924 | 2.92 | 2.916 | 2.9121 | 2.906 | 2.8998 | 2.8936 | 2.8871 | 2.8804 | 2.8746 | 2.8688 | 2.863 | 2.8572 | 2.8514 | 2.845 | 2.8387 | 2.8325 | 2.8263 | 2.82 | 2.8187 | 2.8174 | 2.816 | 2.8146 | 2.8132 | 2.8126 | 2.812 | 2.8115 | 2.8111 | 2.8106 | 2.8103 | 2.81 | 2.71 | 2.7094 | 2.7088 | 2.7083 | 2.7077 | 2.7072 | 2.7069 | 2.7065 | 2.7062 | 2.7059 | 2.7056 | 2.7053 | 2.705 | 2.7046 | 2.7043 | 2.704 | 2.7037 | 2.7034 | 2.7031 | 2.7027 | 2.7024
Annual change | [5 empty] | 2535.9837 | 3074.2123 | 3773.3328 | 4739.1791 | 6504.5281 | 7004.7832 | 7714.5085 | 8809.4387 | 10653.3309 | 7508.1607 | 7887.1214 | 8309.7329 | 8784.5869 | 9322.8621 | 7679.9318 | 8144.0817 | 8722.4422 | 9470.1876 | 10479.7154 | 7705.1833 | 8090.6912 | 8517.0707 | 8990.0351 | 9516.2088 | 7828.9051 | 8068.6001 | 8336.9409 | 8646.4485 | 9017.6005 | 6231.6588 | 6381.0442 | 6539.1319 | 6706.9273 | 6885.5907 | 1440.9743 | 1575.7219 | 1705.8962 | 1832.6339 | 1956.9547 | 2079.7807 | 2201.9546 | 2324.2534 | 978.8302 | 978.8302 | 978.8302 | 978.8302 | 978.8302 | 751.3989 | 751.3989 | 751.3989 | 751.3989 | 751.3989 | 751.3989 | 751.3989 | 751.3989 | 751.3989 | 751.3989 | 751.3989 | 751.3989 | 751.3989 | 751.3989 | 751.3989 |  |  | 8044.7679 | 9635.709 | 11717.8343 | 14622.3085 | 16657.8537 | 18128.5219 | 20011.5311 | 22899.8974 | 27339.8676 | 19423.5005 | 20503.2561 | 21710.4759 | 23071.3493 | 24620.5057 | 18283.547 | 19499.0311 | 21003.2772 | 22933.376 | 25519.3273 | 18065.2405 | 19083.8505 | 20206.9539 | 21448.7943 | 22825.8696 | 17537.5058 | 18154.8636 | 18841.2897 | 19623.4993 | 20543.4842 | 16532.8189 | 16921.9142 | 17333.2448 | 17769.2767 | 18232.8417 | 3510.0404 | 3964.7112 | 4373.2469 | 4771.5078 | 5162.6525 | 5549.5288 | 5934.7307 | -77220.7178 | 2187.3132 | 2187.3132 | 2187.3132 | 2187.3132 | 2187.3132 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | [7 empty] | 14326 | 14326 | 14326 | 14306.8 | 10824.2 | 10831 | 10831 | 10831 | 10831 | 10738.7 | 11643.3 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11217.7 | 1284.8371 | 1594.1985 | 1887.6941 | 2169.9915 | 2445.5011 | 2718.3852 | -14709.327 | 3272.1307 | 548.3813 | 548.3813 | 548.3813 | 548.3813 | 548.3813 | 310.2429 | 310.2429 | 310.2429 | 310.2429 | 310.2429 | 310.2429 | 310.2429 | 310.2429 | 310.2429 | 310.2429 | 310.2429 | 310.2429 | 310.2429 | 310.2429 | 310.2429
Auckland Region total (excludes Tuakau-Pokeno) |  |  |  |  | 560147.0287 | 562469.9773 | 565310.0528 | 568825.6035 | 573280.4885 | 579629.165 | 586472.0808 | 594018.4562 | 602653.2356 | 613125.1086 | 620505.928 | 628262.6165 | 636438.7497 | 645086.4935 | 654269.1901 | 661831.3142 | 669855.2361 | 678455.1194 | 687800.3012 | 698152.5147 | 705740.8664 | 713712.6222 | 722108.6155 | 730975.3924 | 740366.1228 | 748114.0606 | 756100.7699 | 764354.8857 | 772917.5642 | 781850.4391 | 788086.7446 | 794472.4326 | 801016.2054 | 807727.7708 | 814617.9967 | 816058.971 | 817634.6929 | 819340.589 | 821173.223 | 823130.1776 | 825209.9583 | 827411.9129 | 829736.1663 | 830714.9964 | 831693.8266 | 832672.6567 | 833651.4869 | 834630.317 | 835381.716 | 836133.1149 | 836884.5139 | 837635.9128 | 838387.3118 | 839138.7107 | 839890.1097 | 840641.5086 | 841392.9075 | 842144.3065 | 842895.7054 | 843647.1044 | 844398.5033 | 845149.9023 | 845901.3012 |  | 1654550 | 1661986.1701 | 1670952.4088 | 1681932.5407 | 1695740.6197 | 1712029.7508 | 1729776.4871 | 1749392.6495 | 1771883.0527 | 1798798.7355 | 1817932.6433 | 1838140.3843 | 1859549.2995 | 1882312.917 | 1906619.3912 | 1924630.601 | 1943852.6314 | 1964574.1647 | 1987220.9721 | 2012448.8238 | 2030244.9069 | 2049055.4147 | 2068984.7753 | 2090151.6598 | 2112691.2358 | 2130079.7961 | 2148084.5281 | 2166774.4907 | 2186245.4577 | 2206635.195 | 2223180.0698 | 2240114.0324 | 2257459.3181 | 2275240.6283 | 2293485.4961 | 2296995.5365 | 2300960.2477 | 2305333.4946 | 2310105.0024 | 2315267.6549 | 2320817.1837 | 2326751.9145 | 2249531.1967 | 2251718.5099 | 2253905.8231 | 2256093.1364 | 2258280.4496 | 2260467.7628 | 2262231.1018 | 2263994.4407 | 2265757.7797 | 2267521.1186 | 2269284.4576 | 2271047.7966 | 2272811.1355 | 2274574.4745 | 2276337.8134 | 2278101.1524 | 2279864.4914 | 2281627.8303 | 2283391.1693 | 2285154.5082 | 2286917.8472 | [6 empty] | 934212 | 948538 | 962864 | 977190 | 991496.8 | 1002321 | 1013152 | 1023983 | 1034814 | 1045645 | 1056383.7 | 1068027 | 1079693 | 1091359 | 1103025 | 1114691 | 1126357 | 1138023 | 1149689 | 1161355 | 1173021 | 1184687 | 1196353 | 1208019 | 1219685 | 1231351 | 1243017 | 1254683 | 1266349 | 1278015 | 1289232.7 | 1290517.5371 | 1292111.7355 | 1293999.4297 | 1296169.4211 | 1298614.9223 | 1301333.3075 | 1286623.9804 | 1289896.1112 | 1290444.4925 | 1290992.8738 | 1291541.2551 | 1292089.6364 | 1292638.0177 | 1292948.2606 | 1293258.5035 | 1293568.7463 | 1293878.9892 | 1294189.232 | 1294499.4749 | 1294809.7177 | 1295119.9606 | 1295430.2035 | 1295740.4463 | 1296050.6892 | 1296360.932 | 1296671.1749 | 1296981.4177 | 1297291.6606
Annual change | [5 empty] | 2322.9485 | 2840.0755 | 3515.5508 | 4454.885 | 6348.6764 | 6842.9158 | 7546.3755 | 8634.7794 | 10471.873 | 7380.8194 | 7756.6885 | 8176.1333 | 8647.7438 | 9182.6966 | 7562.124 | 8023.9219 | 8599.8834 | 9345.1817 | 10352.2135 | 7588.3517 | 7971.7558 | 8395.9933 | 8866.777 | 9390.7304 | 7747.9378 | 7986.7093 | 8254.1158 | 8562.6785 | 8932.8749 | 6236.3055 | 6385.688 | 6543.7728 | 6711.5654 | 6890.226 | 1440.9743 | 1575.7219 | 1705.8962 | 1832.6339 | 1956.9547 | 2079.7807 | 2201.9546 | 2324.2534 | 978.8302 | 978.8302 | 978.8302 | 978.8302 | 978.8302 | 751.3989 | 751.3989 | 751.3989 | 751.3989 | 751.3989 | 751.3989 | 751.3989 | 751.3989 | 751.3989 | 751.3989 | 751.3989 | 751.3989 | 751.3989 | 751.3989 | 751.3989 |  |  | 7436.1701 | 8966.2387 | 10980.132 | 13808.079 | 16289.1311 | 17746.7363 | 19616.1623 | 22490.4032 | 26915.6829 | 19133.9078 | 20207.741 | 21408.9152 | 22763.6174 | 24306.4743 | 18011.2097 | 19222.0304 | 20721.5332 | 22646.8074 | 25227.8517 | 17796.0831 | 18810.5078 | 19929.3607 | 21166.8845 | 22539.576 | 17388.5604 | 18004.732 | 18689.9625 | 19470.9671 | 20389.7373 | 16544.8748 | 16933.9626 | 17345.2857 | 17781.3102 | 18244.8678 | 3510.0404 | 3964.7112 | 4373.2469 | 4771.5078 | 5162.6525 | 5549.5288 | 5934.7307 | -77220.7178 | 2187.3132 | 2187.3132 | 2187.3132 | 2187.3132 | 2187.3132 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | 1763.339 | [7 empty] | 14326 | 14326 | 14326 | 14306.8 | 10824.2 | 10831 | 10831 | 10831 | 10831 | 10738.7 | 11643.3 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11666 | 11217.7 | 1284.8371 | 1594.1985 | 1887.6941 | 2169.9915 | 2445.5011 | 2718.3852 | -14709.327 | 3272.1307 | 548.3813 | 548.3813 | 548.3813 | 548.3813 | 548.3813 | 310.2429 | 310.2429 | 310.2429 | 310.2429 | 310.2429 | 310.2429 | 310.2429 | 310.2429 | 310.2429 | 310.2429 | 310.2429 | 310.2429 | 310.2429 | 310.2429 | 310.2429
Filter Total |  |  |  |  | 563560.8877 | 566096.8715 | 569171.0837 | 572944.4165 | 577683.5956 | 584188.1237 | 591192.9069 | 598907.4154 | 607716.8541 | 618370.1849 | 625878.3456 | 633765.467 | 642075.1999 | 650859.7868 | 660182.6489 | 667862.5807 | 676006.6624 | 684729.1047 | 694199.2923 | 704679.0077 | 712384.1911 | 720474.8823 | 728991.953 | 737981.9881 | 747498.1969 | 755327.102 | 763395.7021 | 771732.643 | 780379.0915 | 789396.692 | 795628.3508 | 802009.3949 | 808548.5268 | 815255.4541 | 822141.0448 | 823582.0191 | 825157.741 | 826863.6371 | 828696.271 | 830653.2257 | 832733.0064 | 834934.961 | 837259.2144 | 838238.0445 | 839216.8747 | 840195.7048 | 841174.535 | 842153.3651 | 842904.7641 | 843656.163 | 844407.562 | 845158.9609 | 845910.3598 | 846661.7588 | 847413.1577 | 848164.5567 | 848915.9556 | 849667.3546 | 850418.7535 | 851170.1525 | 851921.5514 | 852672.9503 | 853424.3493 |  | 1664140 | 1672184.7679 | 1681820.477 | 1693538.3113 | 1708160.6197 | 1724818.4735 | 1742946.9954 | 1762958.5265 | 1785858.4239 | 1813198.2915 | 1832621.792 | 1853125.0481 | 1874835.524 | 1897906.8733 | 1922527.3789 | 1940810.926 | 1960309.9571 | 1981313.2343 | 2004246.6103 | 2029765.9377 | 2047831.1782 | 2066915.0287 | 2087121.9826 | 2108570.777 | 2131396.6466 | 2148934.1524 | 2167089.0159 | 2185930.3056 | 2205553.8049 | 2226097.2891 | 2242630.108 | 2259552.0222 | 2276885.267 | 2294654.5437 | 2312887.3854 | 2316397.4258 | 2320362.1371 | 2324735.384 | 2329506.8918 | 2334669.5442 | 2340219.0731 | 2346153.8038 | 2268933.086 | 2271120.3992 | 2273307.7125 | 2275495.0257 | 2277682.3389 | 2279869.6522 | 2281632.9911 | 2283396.3301 | 2285159.669 | 2286923.008 | 2288686.347 | 2290449.6859 | 2292213.0249 | 2293976.3638 | 2295739.7028 | 2297503.0417 | 2299266.3807 | 2301029.7197 | 2302793.0586 | 2304556.3976 | 2306319.7365 | [6 empty] | 934212 | 948538 | 962864 | 977190 | 991496.8 | 1002321 | 1013152 | 1023983 | 1034814 | 1045645 | 1056383.7 | 1068027 | 1079693 | 1091359 | 1103025 | 1114691 | 1126357 | 1138023 | 1149689 | 1161355 | 1173021 | 1184687 | 1196353 | 1208019 | 1219685 | 1231351 | 1243017 | 1254683 | 1266349 | 1278015 | 1289232.7 | 1290517.5371 | 1292111.7355 | 1293999.4297 | 1296169.4211 | 1298614.9223 | 1301333.3075 | 1286623.9804 | 1289896.1112 | 1290444.4925 | 1290992.8738 | 1291541.2551 | 1292089.6364 | 1292638.0177 | 1292948.2606 | 1293258.5035 | 1293568.7463 | 1293878.9892 | 1294189.232 | 1294499.4749 | 1294809.7177 | 1295119.9606 | 1295430.2035 | 1295740.4463 | 1296050.6892 | 1296360.932 | 1296671.1749 | 1296981.4177 | 1297291.6606
[5 empty] | 2018 | [5 empty] | 40%
[5 empty] | 2023 Est HH | 2023 Est Emp | 2060 HH | 2060 EMP | HH Growth | Emp Growth | 2023 HH+0.4EMP | 2060 HH+0.4EMP | HH+0.4EMP Growth | Growth % of 2060
554 | Drury East |  |  |  | 2018: 158.4036; 2019: 162; 2020: 4282; 2021: 3686.6; 2022: 4123.5964; 2023: 3524.6; 2024: 223.2036; 2025: 3686.6; 2026: 3463.3964; 2027: 93.95%
555 | Drury East |  |  |  | 2018: 134.174; 2019: 88; 2020: 2905; 2021: 732; 2022: 2770.826; 2023: 644; 2024: 169.374; 2025: 732; 2026: 562.626; 2027: 76.86%
561 | Drury West 1 |  |  |  | 2018: 613.8642; 2019: 91; 2020: 3819; 2021: 912; 2022: 3205.1358; 2023: 821; 2024: 650.2642; 2025: 912; 2026: 261.7358; 2027: 28.7%
562 | Drury West 1 |  |  |  | 2018: 78.7556; 2019: 0; 2020: 3991; 2021: 998; 2022: 3912.2444; 2023: 998; 2024: 78.7556; 2025: 998; 2026: 919.2444; 2027: 92.11%
557 | Drury West 2 |  |  |  | 2018: 81.4106; 2019: 37; 2020: 803; 2021: 470.4; 2022: 721.5894; 2023: 433.4; 2024: 96.2106; 2025: 470.4; 2026: 374.1894; 2027: 79.55%
558 | Drury West 2 |  |  |  | 2018: 75.9193; 2019: 21; 2020: 75; 2021: 802; 2022: -0.91928; 2023: 781; 2024: 84.3193; 2025: 802; 2026: 717.6807; 2027: 89.49%
559 | Drury West 2 |  |  |  | 2018: 58.8505; 2019: 140; 2020: 2298; 2021: 952.9; 2022: 2239.1495; 2023: 812.9; 2024: 114.8505; 2025: 952.9; 2026: 838.0495; 2027: 87.95%
560 | Drury West 2 |  |  |  | 2018: 9.1757; 2019: 362; 2020: 2195; 2021: 575; 2022: 2185.8243; 2023: 213; 2024: 153.9757; 2025: 575; 2026: 421.0243; 2027: 73.22%
550 | Opaheke |  |  |  | 2018: 593.4251; 2019: 1478; 2020: 1847; 2021: 1578; 2022: 1253.5749; 2023: 100; 2024: 1184.6251; 2025: 1578; 2026: 393.3749; 2027: 24.93%
551 | Opaheke |  |  |  | 2018: 102.5931; 2019: 59; 2020: 2415; 2021: 1805; 2022: 2312.4069; 2023: 1746; 2024: 126.1931; 2025: 1805; 2026: 1678.8069; 2027: 93.01%
556 | Southern growth area 3 | Drury South |  |  | 2018: 145.5569; 2019: 227; 2020: 938.5569; 2021: 6649.9; 2022: 793; 2023: 6422.9; 2024: 236.3569; 2025: 6649.9; 2026: 6413.5431; 2027: 96.45%
567 | Southern growth area 2 | Paerata / Pukekoehoe |  |  | 2018: 50.6278; 2019: 17; 2020: 499.7647; 2021: 17.9; 2022: 449.1369; 2023: 0.9; 2024: 57.4278; 2025: 17.9; 2026: -39.5278; 2027: -220.8%
568 | Southern growth area 2 | Paerata / Pukekoehoe |  |  | 2018: 275.5221; 2019: 313; 2020: 2581.3906; 2021: 1080.4; 2022: 2305.8686; 2023: 767.4; 2024: 400.7221; 2025: 1080.4; 2026: 679.6779; 2027: 62.91%
571 | Southern growth area 2 | Paerata / Pukekoehoe |  |  | 2018: 64.1808; 2019: 193; 2020: 1450.7287; 2021: 204.7; 2022: 1386.5479; 2023: 11.7; 2024: 141.3808; 2025: 204.7; 2026: 63.3192; 2027: 30.93%
574 | Southern growth area 2 | Paerata / Pukekoehoe |  |  | 2018: 1274.7479; 2019: 654; 2020: 1656.2951; 2021: 654.4; 2022: 381.5472; 2023: 0.4; 2024: 1536.3479; 2025: 654.4; 2026: -881.9479; 2027: -134.8%
575 | Southern growth area 2 | Paerata / Pukekoehoe |  |  | 2018: 1608.0336; 2019: 1334; 2020: 1959.6937; 2021: 1487.5; 2022: 351.6601; 2023: 153.5; 2024: 2141.6336; 2025: 1487.5; 2026: -654.1336; 2027: -43.98%
576 | Southern growth area 2 | Paerata / Pukekoehoe |  |  | 2018: 2015.9934; 2019: 427; 2020: 2391.9934; 2021: 420.6; 2022: 376; 2023: -6.4; 2024: 2186.7934; 2025: 420.6; 2026: -1766.1934; 2027: -419.9%
577 | Southern growth area 2 | Paerata / Pukekoehoe |  |  | 2018: 366.7227; 2019: 3567; 2020: 749.3709; 2021: 3597.3; 2022: 382.6482; 2023: 30.3; 2024: 1793.5227; 2025: 3597.3; 2026: 1803.7773; 2027: 50.14%
578 | Southern growth area 2 | Paerata / Pukekoehoe |  |  | 2018: 1158.6038; 2019: 845; 2020: 1859.6038; 2021: 855.7; 2022: 701; 2023: 10.7; 2024: 1496.6038; 2025: 855.7; 2026: -640.9038; 2027: -74.9%
579 | Southern growth area 2 | Paerata / Pukekoehoe |  |  | 2018: 237.9633; 2019: 306; 2020: 633.0927; 2021: 1171.6; 2022: 395.1294; 2023: 865.6; 2024: 360.3633; 2025: 1171.6; 2026: 811.2367; 2027: 69.24%
580 | Southern growth area 2 | Paerata / Pukekoehoe |  |  | 2018: 57.444; 2019: 79; 2020: 1042.444; 2021: 520.2; 2022: 985; 2023: 441.2; 2024: 89.044; 2025: 520.2; 2026: 431.156; 2027: 82.88%
581 | Southern growth area 2 | Paerata / Pukekoehoe |  |  | 2018: 2766.2198; 2019: 3959; 2020: 2923.7763; 2021: 3986.1; 2022: 157.5565; 2023: 27.1; 2024: 4349.8198; 2025: 3986.1; 2026: -363.7198; 2027: -9.125%
582 | Southern growth area 2 | Paerata / Pukekoehoe |  |  | 2018: 53.2024; 2019: 31; 2020: 72.5521; 2021: 30.9; 2022: 19.3496; 2023: -0.1; 2024: 65.6024; 2025: 30.9; 2026: -34.7024; 2027: -112.3%
510 | Southern growth area 1 | Papakura / Takanini |  |  | 2018: 1241.4287; 2019: 775; 2020: 1314.9836; 2021: 944.2; 2022: 73.5549; 2023: 169.2; 2024: 1551.4287; 2025: 944.2; 2026: -607.2287; 2027: -64.31%
531 | Southern growth area 1 | Papakura / Takanini |  |  | 2018: 2351.5151; 2019: 964; 2020: 2448.1655; 2021: 1307.7; 2022: 96.6504; 2023: 343.7; 2024: 2737.1151; 2025: 1307.7; 2026: -1429.4151; 2027: -109.3%
534 | Southern growth area 1 | Papakura / Takanini |  |  | 2018: 79.9615; 2019: 98; 2020: 79.9615; 2021: 119.8; 2022: 0; 2023: 21.8; 2024: 119.1615; 2025: 119.8; 2026: 0.63849; 2027: 0.533%
535 | Southern growth area 1 | Papakura / Takanini |  |  | 2018: 274.4595; 2019: 144; 2020: 274.4595; 2021: 175.3; 2022: 0; 2023: 31.3; 2024: 332.0595; 2025: 175.3; 2026: -156.7595; 2027: -89.42%
536 | Southern growth area 1 | Papakura / Takanini |  |  | 2018: 537.9419; 2019: 232; 2020: 572.5814; 2021: 290.9; 2022: 34.6395; 2023: 58.9; 2024: 630.7419; 2025: 290.9; 2026: -339.8419; 2027: -116.8%
537 | Southern growth area 1 | Papakura / Takanini |  |  | 2018: 1081.2109; 2019: 607; 2020: 1933.1824; 2021: 843.1; 2022: 851.9716; 2023: 236.1; 2024: 1324.0109; 2025: 843.1; 2026: -480.9109; 2027: -57.04%
539 | Southern growth area 1 | Papakura / Takanini |  |  | 2018: 1657.4254; 2019: 3694; 2020: 2166.1573; 2021: 5096.5; 2022: 508.7319; 2023: 1402.5; 2024: 3135.0254; 2025: 5096.5; 2026: 1961.4746; 2027: 38.49%
540 | Southern growth area 1 | Papakura / Takanini |  |  | 2018: 1964.5057; 2019: 981; 2020: 2218.7664; 2021: 1375.2; 2022: 254.2607; 2023: 394.2; 2024: 2356.9057; 2025: 1375.2; 2026: -981.7057; 2027: -71.39%
541 | Southern growth area 1 | Papakura / Takanini |  |  | 2018: 1562.0492; 2019: 451; 2020: 1669.3715; 2021: 610.7; 2022: 107.3223; 2023: 159.7; 2024: 1742.4492; 2025: 610.7; 2026: -1131.7492; 2027: -185.3%
542 | Southern growth area 1 | Papakura / Takanini |  |  | 2018: 1558.7208; 2019: 239; 2020: 1636.0427; 2021: 341.8; 2022: 77.3219; 2023: 102.8; 2024: 1654.3208; 2025: 341.8; 2026: -1312.5208; 2027: -384%
543 | Southern growth area 1 | Papakura / Takanini |  |  | 2018: 1755.6885; 2019: 337; 2020: 1920.0149; 2021: 454.3; 2022: 164.3264; 2023: 117.3; 2024: 1890.4885; 2025: 454.3; 2026: -1436.1885; 2027: -316.1%
544 | Southern growth area 1 | Papakura / Takanini |  |  | 2018: 481.3615; 2019: 2710; 2020: 744.3615; 2021: 3254.5; 2022: 263; 2023: 544.5; 2024: 1565.3615; 2025: 3254.5; 2026: 1689.1385; 2027: 51.9%
545 | Southern growth area 1 | Papakura / Takanini |  |  | 2018: 957.4579; 2019: 357; 2020: 1034.7856; 2021: 487.5; 2022: 77.3277; 2023: 130.5; 2024: 1100.2579; 2025: 487.5; 2026: -612.7579; 2027: -125.7%
546 | Southern growth area 1 | Papakura / Takanini |  |  | 2018: 1479.3706; 2019: 714; 2020: 1733.6567; 2021: 940.3; 2022: 254.2861; 2023: 226.3; 2024: 1764.9706; 2025: 940.3; 2026: -824.6706; 2027: -87.7%
547 | Southern growth area 1 | Papakura / Takanini |  |  | 2018: 1458.1209; 2019: 846; 2020: 1596.3653; 2021: 1115.4; 2022: 138.2444; 2023: 269.4; 2024: 1796.5209; 2025: 1115.4; 2026: -681.1209; 2027: -61.07%
548 | Southern growth area 1 | Papakura / Takanini |  |  | 2018: 1030.7094; 2019: 1013; 2020: 2054.467; 2021: 1309.4; 2022: 1023.7576; 2023: 296.4; 2024: 1435.9094; 2025: 1309.4; 2026: -126.5094; 2027: -9.662%
549 | Southern growth area 1 | Papakura / Takanini |  |  | 2018: 915.8265; 2019: 477; 2020: 2139.3205; 2021: 673.3; 2022: 1223.4939; 2023: 196.3; 2024: 1106.6265; 2025: 673.3; 2026: -433.3265; 2027: -64.36%
[5 empty] | 2023 Est HH | 2023 Est Emp | 2060 HH | 2060 EMP | HH Growth | Emp Growth | 2023 HH+0.4EMP | 2060 HH+0.4EMP | HH+0.4EMP Growth | Growth % of 2060
Transport - Drury East IPA | Drury East |  |  |  | 2018: 292.5775; 2019: 250; 2020: 7187; 2021: 4418.6; 2022: 6894.4225; 2023: 4168.6; 2024: 392.5775; 2025: 8954.44; 2026: 8561.8625; 2027: 95.62%
Transport - Drury West 1 IPA | Drury West 1 |  |  |  | 2018: 692.6199; 2019: 91; 2020: 7810; 2021: 1910; 2022: 7117.3801; 2023: 1819; 2024: 729.0199; 2025: 1910; 2026: 1180.9801; 2027: 61.83%
Transport - Drury West 2 IPA | Drury West 2 |  |  |  | 2018: 225.3561; 2019: 560; 2020: 5371; 2021: 2800.3; 2022: 5145.6439; 2023: 2240.3; 2024: 449.3561; 2025: 2800.3; 2026: 2350.9439; 2027: 83.95%
Transport - Opaheke IPA | Opaheke |  |  |  | 2018: 696.0182; 2019: 1537; 2020: 4262; 2021: 3383; 2022: 3565.9818; 2023: 1846; 2024: 1310.8182; 2025: 3383; 2026: 2072.1818; 2027: 61.25%
Transport - Southern Growth Area 3 | Southern growth area 3 | Drury South |  |  | 2018: 145.5569; 2019: 227; 2020: 938.5569; 2021: 6649.9; 2022: 793; 2023: 6422.9; 2024: 236.3569; 2025: 6649.9; 2026: 6413.5431; 2027: 96.45%
Transport - Southern Growth Area 1 | Southern growth area 2 | Paerata / Pukekoehoe |  |  | 2018: 9929.2615; 2019: 11725; 2020: 17820.7059; 2021: 14027.3; 2022: 7891.4445; 2023: 2302.3; 2024: 14619.2615; 2025: 14027.3; 2026: -591.9615; 2027: 61.05%
Transport - Southern Growth Area 2 | Southern growth area 1 | Papakura / Takanini |  |  | 2018: 20387.754; 2019: 14639; 2020: 25536.6433; 2021: 19339.9; 2022: 5148.8894; 2023: 4700.9; 2024: 26243.354; 2025: 19339.9; 2026: -6903.454; 2027: 36.35%
Transport - Auckland Wide | Auckland wide |  |  |  | 2018: 579629.165; 2019: 948538; 2020: 829736.1663; 2021: 1289896.1112; 2022: 250107.0013; 2023: 341358.1112; 2024: 959044.365; 2025: 1345694.6107; 2026: 386650.2458; 2027: 28.73%
Transport - Drury IPA | Drury IPA |  |  |  | 2018: 1906.5717; 2019: 2438; 2020: 24630; 2021: 12511.9; 2022: 22723.4283; 2023: 10073.9; 2024: 2881.7717; 2025: 29634.76; 2026: 26752.9883; 2027: 90.28%

## Drury_beneficiary_allocation
| Drury West | Drury East | Drury West2 | Opaheke | Drury South | Paerata/Pukekohe | Papaukura/Takaanini | Auckland | SUM
Project number | Drury West 1 | Drury East | Drury West 2 | Opaheke | Southern Growth Area 3 | Southern Growth Area 2 | Southern Growth Area 1 | Auckland wide | SUM
1a | 15% | 62.5% | 0% | 20% | 0% | 0% | 2.5% | 0% | 100%
1b | 7.5% | 57.5% | 7.5% | 17.5% | 0% | 2.5% | 5% | 2.5% | 100%
2a | 15% | 57.5% | 0% | 17.5% | 0% | 2.5% | 5% | 2.5% | 100%
2b | 7.5% | 57.5% | 7.5% | 17.5% | 0% | 2.5% | 5% | 2.5% | 100%
3 | 25% | 2.5% | 27.5% | 0% | 35% | 10% | 0% | 0% | 100%
4b | 0% | 90% | 0% | 7.5% | 0% | 0% | 2.5% | 0% | 100%
5 | 12.5% | 52.5% | 0% | 15% | 12.5% | 2.5% | 2.5% | 2.5% | 100%
6 | 12.5% | 52.5% | 0% | 15% | 12.5% | 2.5% | 2.5% | 2.5% | 100%
7 | 0% | 97.5% | 0% | 0% | 2.5% | 0% | 0% | 0% | 100%
8 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
9a | 12.5% | 62.5% | 2.5% | 20% | 0% | 2.5% | 0% | 0% | 100%
9b | 7.5% | 62.5% | 7.5% | 20% | 0% | 2.5% | 0% | 0% | 100%
10a | 0% | 87.5% | 0% | 10% | 0% | 0% | 2.5% | 0% | 100%
10b | 0% | 70% | 0% | 27.5% | 0% | 0% | 2.5% | 0% | 100%
11 | 0% | 90% | 0% | 7.5% | 0% | 0% | 2.5% | 0% | 100%
12 | 47.5% | 52.5% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
13a | 0% | 97.5% | 0% | 0% | 0% | 0% | 2.5% | 0% | 100%
13b | 5% | 50% | 5% | 32.5% | 0% | 0% | 5% | 2.5% | 100%
14a | 5% | 80% | 12.5% | 0% | 0% | 0% | 0% | 2.5% | 100%
14b | 5% | 80% | 12.5% | 0% | 0% | 0% | 0% | 2.5% | 100%
15 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
16a | 77.5% | 20% | 0% | 0% | 0% | 0% | 0% | 2.5% | 100%
16b | 52.5% | 17.5% | 20% | 7.5% | 0% | 0% | 0% | 2.5% | 100%
19-1 | 5% | 10% | 5% | 0% | 5% | 17.5% | 5% | 52.5% | 100%
19-2 | 5% | 10% | 5% | 0% | 5% | 17.5% | 5% | 52.5% | 100%
19-3 | 0% | 10% | 10% | 0% | 5% | 17.5% | 5% | 52.5% | 100%
20a | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
21 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
22 | 0% | 20% | 50% | 0% | 30% | 0% | 0% | 0% | 100%
23a | 0% | 97.5% | 0% | 0% | 0% | 0% | 0% | 2.5% | 100%
23b | 2.5% | 67.5% | 2.5% | 17.5% | 0% | 5% | 5% | 0% | 100%
23c | 2.5% | 97.5% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
23d | 2.5% | 67.5% | 2.5% | 17.5% | 0% | 5% | 5% | 0% | 100%
24 | 0% | 90% | 0% | 7.5% | 0% | 0% | 2.5% | 0% | 100%
25 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
27a | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
27b | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
28 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
28a | 0% | 97.5% | 0% | 0% | 0% | 0% | 0% | 2.5% | 100%
29 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
30.1 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
30.2 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
31 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
32 | 0% | 90% | 0% | 7.5% | 0% | 0% | 2.5% | 0% | 100%
33 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
34 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
35a | 0% | 15% | 0% | 5% | 0% | 5% | 5% | 70% | 100%
35b | 0% | 10% | 5% | 5% | 0% | 5% | 5% | 70% | 100%
36a | 47.5% | 45% | 2.5% | 2.5% | 0% | 0% | 0% | 2.5% | 100%
36b | 37.5% | 45% | 5% | 10% | 0% | 0% | 0% | 2.5% | 100%
36c | 37.5% | 45% | 5% | 10% | 0% | 0% | 0% | 2.5% | 100%
37a(i) | 2.5% | 30% | 2.5% | 55% | 0% | 0% | 5% | 5% | 100%
37a(ii) | 2.5% | 30% | 2.5% | 55% | 0% | 0% | 5% | 5% | 100%
37b(i) | 5% | 27.5% | 5% | 55% | 0% | 2.5% | 5% | 0% | 100%
37b(ii) | 5% | 27.5% | 5% | 55% | 0% | 2.5% | 5% | 0% | 100%
38a | 0% | 15% | 0% | 5% | 0% | 5% | 5% | 70% | 100%
38b | 0% | 10% | 5% | 5% | 0% | 5% | 5% | 70% | 100%
18a | 0% | 17.5% | 2.5% | 5% | 0% | 5% | 5% | 65% | 100%
18b | 0% | 10% | 5% | 5% | 0% | 2.5% | 5% | 72.5% | 100%
39a | 82.5% | 0% | 15% | 0% | 0% | 2.5% | 0% | 0% | 100%
39b | 62.5% | 2.5% | 22.5% | 2.5% | 0% | 2.5% | 2.5% | 5% | 100%
39c | 62.5% | 2.5% | 22.5% | 2.5% | 0% | 2.5% | 2.5% | 5% | 100%
40a | 90% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100%
40b | 75% | 0% | 22.5% | 0% | 0% | 0% | 0% | 2.5% | 100%
41a | 90% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100%
41b | 75% | 0% | 22.5% | 0% | 0% | 0% | 0% | 2.5% | 100%
42a | 90% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100%
42b | 90% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100%
42c | 75% | 0% | 22.5% | 0% | 0% | 0% | 0% | 2.5% | 100%
43b | 40% | 0% | 40% | 0% | 0% | 2.5% | 0% | 17.5% | 100%
44 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
45 | 55% | 0% | 0% | 0% | 0% | 0% | 0% | 45% | 100%
46 | 47.5% | 52.5% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
47 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
17 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
48 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
49 | 27.5% | 0% | 27.5% | 0% | 0% | 45% | 0% | 0% | 100%
50a | 60% | 0% | 30% | 0% | 0% | 10% | 0% | 0% | 100%
50b | 42.5% | 0% | 27.5% | 0% | 0% | 25% | 0% | 5% | 100%
51 | 47.5% | 0% | 32.5% | 0% | 0% | 20% | 0% | 0% | 100%
52 | 90% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 100%
53 | 90% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100%
54 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
55a | 97.5% | 0% | 0% | 0% | 0% | 0% | 0% | 2.5% | 100%
56 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
57 | 27.5% | 0% | 62.5% | 0% | 0% | 0% | 0% | 10% | 100%
58 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
59 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
60a | 80% | 0% | 0% | 0% | 0% | 10% | 0% | 10% | 100%
60b | 27.5% | 0% | 52.5% | 0% | 0% | 10% | 0% | 10% | 100%
63 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
65a(i) | 80% | 0% | 15% | 2.5% | 0% | 2.5% | 0% | 0% | 100%
65a(ii) | 80% | 0% | 15% | 2.5% | 0% | 2.5% | 0% | 0% | 100%
65b(i) | 60% | 2.5% | 22.5% | 5% | 0% | 10% | 0% | 0% | 100%
65b(ii) | 60% | 2.5% | 22.5% | 5% | 0% | 10% | 0% | 0% | 100%
66 | 22.5% | 5% | 25% | 2.5% | 5% | 32.5% | 0% | 7.5% | 100%
67 | 15% | 30% | 10% | 0% | 0% | 45% | 0% | 0% | 100%
68 | 10% | 0% | 45% | 0% | 0% | 45% | 0% | 0% | 100%
69 | 5% | 80% | 15% | 0% | 0% | 0% | 0% | 0% | 100%
70 | 27.5% | 15% | 55% | 0% | 2.5% | 0% | 0% | 0% | 100%

## DC_growth (hidden)
Weigthed Measure of Growth (HH+Emp)
|  | HH Weight |  | 1
|  | EMP Weight |  | 0.5
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
|  | Area | 2023 Est HH | 2023 Est Emp | 2060 HH | 2060 EMP | HH Growth | Emp Growth | 2023 HH+0.5EMP | 2060 HH+0.5EMP | HH+0.5EMP Growth | Growth % of 2060 | Previous 2022 Growth
Transport - Drury / Opaheke | DE/DW | Drury / Opaheke | 1791.4552 | 2343.834 | 24629.8693 | 11270.7763 | 22838.4142 | 8926.9423 | 2963.3722 | 30265.2575 | 27301.8853 | 90.21% | 90.56%
Transport - Combined Drury West | DW | Combined Drury West | 801.644 | 709.6975 | 13180.8971 | 4321.9726 | 12379.2531 | 3612.275 | 1156.4927 | 15341.8834 | 14185.3907 | 92.46% | 92.86%
Transport - Drury East / Opaheke | DE | Drury East / Opaheke | 989.8112 | 1634.1365 | 11448.9722 | 6948.8037 | 10459.161 | 5314.6672 | 1806.8794 | 14923.3741 | 13116.4947 | 87.89% | 88.2%
Transport - Drury East IPA |  | Drury East IPA | 293.652 | 197.2958 | 7186.91 | 3839.8202 | 6893.258 | 3642.5244 | 392.2999 | 9106.8201 | 8714.5202 | 95.69% | 95.81%
Transport - Drury West 1 IPA |  | Drury West 1 IPA | 575.8252 | 312.948 | 7809.4796 | 1828.371 | 7233.6544 | 1515.4229 | 732.2993 | 8723.6651 | 7991.3658 | 91.61% | 92.3%
Transport - Drury West 2 IPA |  | Drury West 2 IPA | 225.8187 | 396.7495 | 5371.4175 | 2493.6016 | 5145.5988 | 2096.8521 | 424.1935 | 6618.2183 | 6194.0248 | 93.59% | 93.59%
Transport - Opaheke IPA |  | Opaheke IPA | 696.1592 | 1436.8407 | 4262.0622 | 3108.9836 | 3565.903 | 1672.1428 | 1414.5796 | 5816.554 | 4401.9744 | 75.68% | 76.29%
Transport - Southern Growth Area 3 | Drury South | Southern Growth Area 3 | 379.9563 | 615.5999 | 1000.4913 | 6295.9324 | 620.5349 | 5680.3324 | 687.7563 | 4148.4575 | 3460.7012 | 83.42% | 88.18%
Transport - Southern Growth Area 1 | Papakura/Takanini | Southern Growth Area 1 | 20363.2795 | 11081.6615 | 32162.5216 | 17069.5739 | 11799.2421 | 5987.9124 | 25904.1102 | 40697.3086 | 14793.1983 | 36.35% | 39.54%
Transport - Southern Growth Area 2 | Paerata/Pukekohoe | Southern Growth Area 2 | 9566.4584 | 6557.0611 | 26514.2951 | 12923.2763 | 16947.8366 | 6366.2152 | 12844.989 | 32975.9332 | 20130.9442 | 61.05% | 55.04%
Transport - Auckland Wide | Auckland Wide | Auckland Wide | 582640.4255 | 724705.0304 | 926524.6336 | 962446.206 | 343884.2082 | 237741.1757 | 944992.9406 | 1407747.7366 | 462754.796 | 32.87% | 35.66%